| Sl | Additional NIT requirements |
| --- | --- |
|  | Petty civil works like making opening in the walls & making it good after erection is included in bidder’s scope |
|  | Material of Construction (MOC) Of Major Equipment Shall Be as Per Table-1 Below |
|  | PQC Requirement: In addition to the PQC requirement furnished in the NIT, the following shall be met by bidder: Bidder shall be a ISO Certified company |
|  | All Input drawings shall be governed by per clause no 18.6 of BHEL’s specification. |
|  | Bidders is advised to quote strictly as per BHEL’s specification requirements. In case bidder excludes some components of scope of supply or some features of specification requirements, the bidder will be required to include the same in the scope during offer evaluation stage /contract execution stage without any additional commercial and price implications on account of the same. Bidder to note that they won’t be entitled for any price impact on account of Withdrawal of deviation taken from BHEL spec during technical scrutiny stage. |
|  | 1 Transportation of material inside India up to Bhutan Border and transportation from Bhutan Border to site shall be vendor’s responsibility at its costs. Border clearance formalities like appointment of clearing agent, obtaining clearance from Indian and Bhutanese Authorities, transhipment of material on Bhutan registered vehicle at the border including unloading and re-loading, storage of material during transhipment etc. shall be vendor’s responsibility at its costs. PESD to consult IO and decide about taxation in Bhutan on Plant material and mode of payment. 2. Unloading of material at site, storage and preservation, cleaning, painting/ re-painting, final painting of material till completion of erection, testing and commissioning shall be vendor’s responsibility. Land for storage shall be arranged by the vendor on lease. Covered storage area, if required, shall be arranged by the vendor at its costs. The material at site shall remain in the custody of the vendor till the system is handed over to Customer (MHPA). Vendor shall arrange for security of the materials and its T & Ps at site and any item found missing during storage, erection, testing, commissioning till handing over to MHPA shall be replenished promptly without any costs to BHEL. Insurance for plant materials, vendors manpower and T & Ps shall be arranged by the vendor as per the terms of contract between BHEL and MHPA from Bhutanese Underwriters only (mandatory requirement). Transportation of materials from Storage yard to Power House/ place of erection, including loading/ unloading and arranging for vehicles, shall be vendor’s responsibility. 3. Construction power shall be provided at 415 Volt at one point on chargeable basis as per the prevailing rate. Further distribution of Construction Power shall be vendor’s responsibility. The contractor shall arrange for back-up power, in case of any disruption. No compensation/ time extension shall be granted to the Contractor in case of such eventualities. 4. The Contractor shall make adequate arrangement of lighting at the storage and Work Area. All decision of BHEL’s Construction Manager in this regard shall be final and binding on the Contractor. 5. The contractor at his costs shall arrange for entry of his manpower/ T&Ps and other items required for execution of work under this contract, inside Bhutan. T & Ps etc. shall be taken back by the contractor after the work is completed. BHEL shall provide assistance, wherever necessary, in this regard. Any taxes/ fees required to be paid in India/ Bhutan shall be to Contractor’s account. 6. Contractor, at its costs, shall arrange for accommodation for its workmen and supervisors at site. Domestic power and water shall be arranged by the contractor at its costs. 7. The contractor shall arrange necessary first aid for all his employees and workman working under him. Sufficient nos. of person shall be trained in administering first aid. 8. The contractor shall mobilize adequate trained/ skilled manpower numbers to the satisfaction of BHEL. The supervisory staff employed by the contractor will be qualified and experienced in the area of work. They will ensure proper out turn of work and discipline on the part of labour put on the job by the contractor. They will ensure that the work is carried out in a safe and proper manner and in co-ordination with other labour and staff employed directly by BHEL or other contractors of BHEL or other contractors of BHEL’s client. The contractor shall employ the necessary number of qualified and approved full time electricians at his cost to maintain his temporary electrical installations till the completion of work. It is responsibility of the contractor to engage his workmen in shifts or in overtime basis for achieving the target set by BHEL and also during erection, commissioning and testing period. The contractor’s quoted rate shall include all these contingencies. It is important that the Contractor familiarize himself with the Bhutan Laws for import of labours. 9. All consumables, T & Ps and IMTEs, required for qualitative and timely completion of the work and as demanded by BHEL at site, shall be arranged by the contractor at his costs. 10. Contractor to note Bhutan has a stringent HSE Law and Contractor at its costs shall ensure compliance. The Contractor shall be responsible for any action by the statutory authority for any infringement of law. 11. Contractor to note that Mangdechhu HEP is an underground power station and shall take all precautions in respect of fire hazard, fumes etc. 12. PESD to incorporate suitable warranty clause in line with BHEL’s contract with MHPA. 13. The entire scope of work of engineering, procurement, supply, transportation, erection, testing, commissioning and handing over shall be completed within a period of six months to be reckoned from the date of notification of BHEL’s Construction Manager for commencement of work. In case of delay on account of the Contractor, LD @ 0.05% of Contract Price per day subject to a maximum of 10% of Contract Price shall be levied. 14. No PVC applicable for this contract. No ORC/ Rate Revision applicable for this contract. No interest bearing advance payment applicable for this contract. 15. TERMS OF PAYMENT : Supply : 20% of supply price shall be payable after handing over of the system to MHPA. Service : Stage payments as RA Payment shall be as per notional Billing Breakup (BBU) to be agreed by BHEL. For this purpose, the contractor, within 15 days of LOI, shall submit to BHEL proposed (BBU) for approval. The BBU shall be for payment purpose only and cannot be referred as exhaustive list of activities. The total work under this scope as detailed in the tender specification shall be completed by the contractor within the accepted price. Out of Hundred (100%) percent Value of the RA bill , payable as per billing break up, Ninety (85%) payment of RA bill shall be released on pro-rata basis for the work completed as per BBU as progressive payment on submission of protocols duly signed by BHEL site official(s) / Owner. Out of balance 15% of RA bill, 10% of contract price, retained from each RA bill, shall be paid against successful handing over of the system to MHPA. Balance 5 % of contract price retained from each RA Bill will be released on completion of. However, this 5% payment can be released against the Bank Guarantee for an equivalent amount valid till warranty period in the prescribed format subject to receipt of certificate from BHEL-Site that all works are completed. The BG shall be valid for 12 months initially to be extended unconditionally as and when desired by BHEL. The submission of Bank Guarantee towards above is separate and the bank guarantee towards security deposit cannot be utilized for this purpose. The security deposit will be refunded as per certificate of site on completion of final bill formalities as per relevant clauses of GCC. 16. Site visit by the vendor before submission of bid is must. 17. Bidder to include Service Tax in his quoted prices. Bidder has to raise Tax Invoice. Bidder has to obtain TPN no. at Bhutan. Contractor’s Tax in Bhutan shall be deducted at Source and TDS Certificate shall be issued. It is requested that PESD Finance should interact with PSER Finance and finalise the Tax Clause. 18. Total erection & commissioning charges, excluding service tax and insurance, should be minimum 20% of the total quoted package price (excluding mandatory spares but including all taxes and freight), failing which the break-up of prices shall be adjusted accordingly for ordering. This is standard clause of Power Sector for turnkey BoP Packages. 19. PESD shall incorporate suitable clause so that for any variation in quantity during detail/ final design, no additional erection price is payable. It may kindly be noted that Contract with MHPA is on Cost (L1 Price) + 18% basis. 20. PESD to incorporate standard GCC and SCC for Power Sector (attached) 21. Supply and application of final paint on all the equipment to be erected is under the scope of the vendor. Supply and application of final paint on all the equipment to be erected is under the scope of the vendor. 22. After completion of the commissioning activity of equipment/ systems, the vendor shall prepare the test reports which shall include all the relevant information related to various commissioning checks, tests carried out, any deviations/ commissioning noticed wrt the intended design requirements, sequence of various commissioning activities as actually adopted vis-à-vis as recommended in the procedures, programme schedule achieved and any other such information as required. These test reports shall be submitted in requisite number of copies to BHEL/ owner/ vendor involved during the commissioning activities. After completion of the commissioning activity of equipment/ systems, the vendor shall prepare the test reports which shall include all the relevant information related to various commissioning checks, tests carried out, any deviations/ commissioning noticed wrt the intended design requirements, sequence of various commissioning activities as actually adopted vis-à-vis as recommended in the procedures, programme schedule achieved and any other such information as required. These test reports shall be submitted in requisite number of copies to BHEL/ owner/ vendor involved during the commissioning activities. 23. Maintaining proper documentation of all the site activities undertaken by the vendor as per the proforma mutually agreed with BHEL, submitting monthly progress reports as also any such document as & when desired by BHEL/ owner, taking approval of all statutory authorities (Fire Safety, Factory Inspector, Labour Commissioner, etc) as applicable for respective portions of work under the jurisdiction of such statutes of laws shall be Contractor’s responsibility. 24. The vendor shall be responsible for arranging all communication facilities for himself at site. The vendor has to establish independent internet/e-mail facilities with mobile connection for all key site personnel. The vendor shall be responsible for arranging all communication facilities for himself at site. The vendor has to establish independent internet/e-mail facilities with mobile connection for all key site personnel. 25. The vendor shall prepare and maintain the detailed master schedule (L2 network) during the course of the work. The vendor shall prepare and maintain the detailed master schedule (L2 network) during the course of the work. 26. Any other service, although not specifically called for but required for a contract of the size and nature indicated in the specification. Any other service, although not specifically called for but required for a contract of the size and nature indicated in the specification. 27. The vendor shall prepare the Field Quality Plan and submit for approval by BHEL/ MHPA within 1 month of receipt of LOI. |

TABLE-1

The major items of FPS system and their MOC is listed in the table below: -

| SL. NO. | ITEM | MOC |
| --- | --- | --- |
|  | Tank filling Pumps (Electric Motor Driven) | - Impeller : High grade duplex stainless steel ( AISI 329 or better) - Casing : Cast steel ( ASTM A 216 WCB or better) - Shaft, sleeve and key: stainless steel( AISI 410 or better) |
|  | Fire Water Pipes | A106 Gr-B |
|  | Fire Water Pipes (Over ground pipes normally empty but periodically charge with water & foam system applications) | A106 Gr-B Galvanized to IS:1239, Part- 1, Galvanized as per IS: 4736 |
|  | Valve |  |
| 4A | Valves DN 50 NB and below | Body : SS (ASTM A276 Type 316 / A182 Gr F 316) Spindle shaft & Pin : SS (AISI 410) Disc / Ball / Wedge : SS (ASTM A 351 Gr CF8) Gland seal / Seat : PTFE Seat / Body lining : PTFE |
| 4B | Valves Above DN 50 NB | Body : ASTM A216 WCB Spindle shaft & Pin : SS (AISI 410) Disc / Ball / Wedge : SS (ASTM A 351 Gr CF8) Gland seal / Seat : PTFE Seat / Body lining : PTFE |
|  | HVWS Nozzle | S.S 304 |
|  | MVWS Nozzle | S.S 304 |
|  | Hydrant Valve | S.S 304 |
|  | Basket/Y Strainer | Body is ASTM A 106(R-04) and internal is S.S (AISI 316), 30 mesh |
|  | Branch Pipe | S.S 304 |
|  | Air Release Valve | Gun Metal as per IS 318 |
|  | Deluge Valve | Carbon steel |
|  | Flanges | Up to 150 NB: 105. Note: Mitered/Fabricated bends flanges shall be provided for sizes 200 NB and above. |
|  | Fittings | a) Up to 32 NB: 105. b) 32 NB & Above : ASTM 234(R-04) Note: - All fittings and flanges for galvanized pipes shall be galvanized as per IS 4736. - Mitered/Fabricated bends shall be provided for sizes 200 NB and above. |
|  | Hose Pipe | Reinforced Rubber Lined Fire Hose as per IS 636, Type – A |
|  | Bolts, Screws and Nuts | As per IS 1363 (Part I and II) |