## Excel sheet
Excel sheet- BILL OF QUANTITIES AND % WEIGHTAGE OF INDIVIDUAL ITEMS
Estimated value (EV) for Balance work of Handling of materials at BHEL / Client's Stores / Storage Yard and transportation to site Erection, Testing, Assistance for commissioning & Trial Operation including supply & application of final painting and Handing Over of Flue Gas Desulphurization System (FGD) Erection and Commissioning of Unit 1, Unit 2 & Common Systems AT 2X500 MW NTPC Mauda, Stage- I, Maharashtra
Estimate :Balance Mechanical works of (FGD) Erection and Commissioning of Unit 1, Unit 2 & Common Systems AT 2X500 MW NTPC Mauda
SN | Description of work |  | Balance Mechanical works of (FGD) Erection and Commissioning of Unit 1, Unit 2 & Common Systems AT 2X500 MW NTPC Mauda
|  | UOM | Balance quantity to execute-BOQ | Weightage | Unit rate (Rs.) | Total Amount (Rs.)
1 | Structure
1.1 | Pre Assembly | MT | 4917.88 | 0.087085 | 0 | 0
1.2 | Placement in Position | MT | 4944.39 | 0.087554 | 0 | 0
1.3 | Alignment | MT | 6074.41 | 0.10756 | 0 | 0
1.4 | Welding /Bolting/Fixing | MT | 6131.4 | 0.10857 | 0 | 0
1.5 | Completion of NDE & SR/Heat treatment | MT | 6147.66 | 0.027215 | 0 | 0
1.6 | Milestones | MT | 4944.39 | 0.065666 | 0 | 0
2 | Non Pressure Parts Including Tanks
2.1 | Pre Assembly | MT | 3435.16 | 0.060672 | 0 | 0
2.2 | Placement in Position | MT | 3482.93 | 0.061516 | 0 | 0
2.3 | Alignment | MT | 3801.97 | 0.067151 | 0 | 0
2.4 | Welding /Bolting/Fixing | MT | 3882.55 | 0.068574 | 0 | 0
2.5 | Completion of NDE & SR/Heat treatment | MT | 3975.88 | 0.017556 | 0 | 0
2.6 | Milestones | MT | 3485.13 | 0.046166 | 0 | 0
3 | Rotating Machines
3.1 | Pre Assembly | MT | 894.95 | 0.011668 | 0 | 0
3.2 | Placement in Position | MT | 902.67 | 0.011769 | 0 | 0
3.3 | Alignment | MT | 929.98 | 0.012125 | 0 | 0
3.4 | Welding /Bolting/Fixing | MT | 929.98 | 0.012125 | 0 | 0
3.5 | Completion of NDE & SR/Heat treatment | MT | 929.98 | 0.0030312 | 0 | 0
3.6 | Milestones | MT | 902.67 | 0.0088266 | 0 | 0
4 | Mineral Wool
4.1 | Placement in Position | MT | 100 | 0.0042118 | 0 | 0
4.2 | Alignment | MT | 100 | 0.0016847 | 0 | 0
4.3 | Welding /Bolting/Fixing | MT | 100 | 0.0012635 | 0 | 0
4.4 | Milestones | MT | 100 | 0.0012635 | 0 | 0
5 | Fixing Components
5.1 | Placement in Position | MT | 110 | 0.0059993 | 0 | 0
5.2 | Alignment | MT | 110 | 0.0023997 | 0 | 0
5.3 | Welding /Bolting/Fixing | MT | 110 | 0.0017998 | 0 | 0
5.4 | Milestones | MT | 110 | 0.0017998 | 0 | 0
6 | Aluminium Sheeting
6.1 | Placement in Position | MT | 114 | 0.0067095 | 0 | 0
6.2 | Alignment | MT | 114 | 0.0026838 | 0 | 0
6.3 | Welding /Bolting/Fixing | MT | 114 | 0.0020128 | 0 | 0
6.4 | Milestones | MT | 114 | 0.0020128 | 0 | 0
7 | CS Piping
7.1 | Pre Assembly | MT | 534.45 | 0.014838 | 0 | 0
7.2 | Placement in Position | MT | 534.45 | 0.019784 | 0 | 0
7.3 | Alignment | MT | 534.45 | 0.014838 | 0 | 0
7.4 | Welding /Bolting/Fixing | MT | 534.45 | 0.019784 | 0 | 0
7.5 | Completion of NDE & SR/Heat treatment | MT | 534.45 | 0.004946 | 0 | 0
7.6 | Hangers & Supports | MT | 534.45 | 0.004946 | 0 | 0
7.7 | Hydraulic Test or Pneumatic Test | MT | 534.45 | 0.004946 | 0 | 0
7.8 | Milestones | MT | 534.45 | 0.014838 | 0 | 0
8 | SS Piping
8.1 | Pre Assembly | MT | 8 | 0.0003605 | 0 | 0
8.2 | Placement in Position | MT | 8 | 0.0004807 | 0 | 0
8.3 | Alignment | MT | 8 | 0.0003605 | 0 | 0
8.4 | Welding /Bolting/Fixing | MT | 8 | 0.0004807 | 0 | 0
8.5 | Completion of NDE & SR/Heat treatment | MT | 8 | 0.0001202 | 0 | 0
8.6 | Hangers & Supports | MT | 8 | 0.0001202 | 0 | 0
8.7 | Hydraulic Test or Pneumatic Test | MT | 8 | 0.0001202 | 0 | 0
8.8 | Milestones | MT | 8 | 0.0003605 | 0 | 0
Total amount to be quoted by bidder

## SUMMARY (hidden)
| ERECTABLE ANALYSIS OF U#03, PATRATU | [9 empty] | 2024-03-01
AREA | SL. NO. | DESCRIPTIONS | Designed Billable Weight U#3 in MT (A) | AVAILABLE WT (B) | PENDING WT (C=A-B) | ERECTED WT UP TO 29.02.2024 (D) | BALANCE WT (E=B-D) | ERECTABLE WT (F) |  | NON ERECTABLE WT (G=E-F) | Remarks (Reason for Non Erectable)
[8 empty] | 2024-02-01 | SEQUENTIAL ERECTION
STR | 1 | STRUCTURE | 33587.834 | #REF! | #REF! | #REF! | #REF! | 66.9078 | #REF! | #REF! | MATERIAL REQUIRED: STR 35 GROUP HELDUP FOR SEQUENTIAL ERECTION ( MIDDLE STRUCTURE). 36 GROUP SEQUENTIAL PLATFORM MATERIALS ARE EITHER PENDING OR NOT TRACEABLE. MILL MAINTENANCE & INTER CONNECTION PLATFORMS ARE HELDUP DUE TO NON-AVAILABILITY /NON-TRACEABILITY OF STRUCTURAL MEMBERS. | 167.3497 | 300
PP | 2 | PRESSURE PARTS | #REF! | #REF! | #REF! | #REF! | #REF! | 310 | #REF! | #REF! | MATERIAL REQUIRED: BP SIDE WALL SUSPENSION MATERIALS ARE NOT TRACEABLE. 1ST PASS SUPPORT MATERIALS & TENSION BARS ARE NOT AVAILABLE FURNACE ROOF SUSPENSION MATERIALS ARE NOT-TRACEABLE. HANGER TUBE 15 NOS. PENDING FROM MU ( PGMA 19802, DU 002, 004, 008) FURNACE REAR SCREEN, REAR ARCH & REAR PANEL ASSY TOTALLY HELDUP DUE TO SUSPENSION MATERIALS NOT AVAILABLE/ NOT TRACEABLE. | 601.1653 | 28
NPPT | 3 | NON PRESSUTE PARTS | #REF! | #REF! | #REF! | #REF! | #REF! | 48 | #REF! | #REF! | MATERIAL REQUIRED SEQUENTIAL DUCT MATERIALS, EXPANSION & SUPPORTS ARE STILL PENDING ESP O/L AREA SEQUENTIAL SUPPORTING STR & FRONTS ARE NOT AVAILABLE. GATES & DAMPERS ARE NOT AVAILABLE. ESP I/L AREA ALSO SEQUENTIAL DUCT SUPPORTING STRUCTURE MATERIALS & FRONTS NOT AVAILABLE. | 54.9176
RMT | 4 | ROTATING MACHINE | #REF! | #REF! | #REF! | #REF! | #REF! | 52 | #REF! | #REF! | MATERIAL REQUIRED: FOR MILL, DRIVE ASSEMBLY PENDING 04 NOS ( PGMA 61314, DU 002).WORK HELDUP FROM LAST 6 MONTHS FOR ID FAN, DELIVERY FLANGE NON TRACEABLE ( PGMA 55628 DU 125 PGMA 55328 DU 016) FOR PA AND FD FAN, WORK HOLD DUE TO FAN HANDING STRUCTURE MATERIALS PENDING
APHT | 5 | AIR PREHEATER (APH) | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF! | APH A HELDUP DUE TO BOILER CAVITY APPROACH | 7
WOOLT | 6 | INSULATION WOOL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | SEQUENTIAL HELDUP
PCT | 7 | INSULATION POURABLE & CASTABLE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | SEQUENTIAL HELDUP
IPT | 8 | INSULATION IRON PARTS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | SEQUENTIAL HELDUP
ALT | 9 | INSULATION AL CLADDING SHEET | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | SEQUENTIAL HELDUP
ESP | 10 | ESP & ITS AUXILIARIES | #REF! | #REF! | #REF! | #REF! | #REF! | 215 | #REF! | #REF! | MATERIAL REQUIRED: PASS A, B, C, D, E, F Inlet funnel pre assembly and erection work held up due to non-traceability / non-availability of splitters and guide vanes. PASS A, B, D Outer roof erection, HVR transformers, roof sheeting work, emitting rapping mechanism and alignment of emitting & collecting system work held up due to non-traceability / non-availability of suspension rod.. PASS B, F Pent house and outer roof work affected due to the area of crane placement is in excavated condition for civil work. PASS A Inlet GD screen sheet work held up due to excavated area for Civil work. | 150
FGDT | 11 | FGD & ITS AUXILIARIES (STR,DUCT,DAMPER) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | MATERIALS & FOUNDATIONS NOT AVAILABLE.
P91T | 12 | POWER CYCLE PIPING P-91/92 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | SEQUENTIAL ERECTION HELDUP
P11T | 13 | PIPING INCLUDING P-11,P-12,P-22 (HP PIPING) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | FRONTS NOT AVAILABLE
LPT | 14 | LP PIPING | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | FRONTS NOT AVAILABLE
SST | 15 | SS PIPING | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | FRONTS NOT AVAILABLE
HGRT | 16 | HANGERS/PUMPS & TANKS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | SEQUENTIAL HELDUP
| 17 | BUNKER & ALLIED WORKS | 2870 | 110 | 2760 | #REF! | #REF! | 94 | 0 | #REF! | BUNKER MATERIALS PENDING, ESP CONTROL ROOM MATERIALS & FRONTS NOT AVAILABLE, FEEDER FLOOR TRIPPER FLOOR MATERIALS PENDING | 48
|  | G.TOTAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## SUMMARY (2) (hidden)
| ERECTABLE MATERIAL DETAILS : - | [8 empty] | 2023-04-01
AREA | SL. NO. | DESCRIPTIONS | Designed Billable Weight U#3 in MT (A) | AVAILABLE WT (B) | ERECTED WT UP TO 31.03.2023 (D) | PENDNG WT TO BE RECEIVED (C=A-B) | BALANCE WT (E=B-D) | ERECTABLE WT (F) | NON ERECTABLE WT (G=E-F) | REMARK
STR | 1 | STRUCTURE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Sequential erection heldup due to non availablity of materials.
PPT | 2 | PRESSURE PARTS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NPPT | 3 | NON PRESSUTE PARTS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RMT | 4 | ROTATING MACHINE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
APHT | 5 | AIR PREHEATER (APH) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
WOOLT | 6 | INSULATION WOOL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PCT | 7 | INSULATION POURABLE & CASTABLE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IPT | 8 | INSULATION IRON PARTS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ALT | 9 | INSULATION AL CLADDING SHEET | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ESP | 10 | ESP & ITS AUXILIARIES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FGDT | 11 | FGD & ITS AUXILIARIES (STR,DUCT,DAMPER) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
P91T | 12 | POWER CYCLE PIPING P-91/92 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
P11T | 13 | PIPING INCLUDING P-11,P-12,P-22 (HP PIPING) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LPT | 14 | LP PIPING | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
SST | 15 | SS PIPING | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
HGRT | 16 | HANGERS/PUMPS & TANKS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | G.TOTAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!