## AUGUST '09
DOC. NO. PSER:SCT:MIR(AWARD):45 | [9 empty] | DT: 04-09-09
DETAILS OF CONTRACTS CONCLUDED DURING THE MONTH
PERIOD:AUGUST '09
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TENDER NO. | ITEM/ NATURE OF WORK | MODE OF TENDER ENQUIRY | DATE OF PUBLICATION OF NIT | TYPE OF BIDDING (SINGLE /TWO BID SYSTEM) | LAST DATE OF RECEIPT OF TENDER | NO.OF TNDRS RECD. | NOS. AND NAMES OF PARTIES QUALIFIED AFTER TECHNICAL EVALUATION | NOS. AND NAMES OF PARTIES NOT QUALIFIED AFTER TECHNICAL EVALUATION | WHETHER CONTRACT AWARDED TO LOWEST TENDERER / EVALUATED L1 | CONTRACT NO. & DATE | NAME OF CONTRACTOR | VALUE OF CONTRACT (RS. LACS) | SCHEDULE DATE OF COMPLETION OF SUPPLIES
PSER:SCT-MJA-I 999:09 | ETC OF CONTROL & INSTRUMENTATION (C&I) PACKAGE FOR 2X500 MW FOR MEJIA-B UNIT # 1 & 2 | OT | 2009-03-31 | TWO | 2009-04-28 | 5 | 3 NOS (I) CHEMIN C&I PVT LTD (II) POWERTRONIX (III) SIGMA CONSTRUCTION | 2 NO (I) PACE PROCESS CONTROLS PVT LTD (II) MIRAJ INSTRUMENTATION SERVICES (I) PVT LTD | YES | LOI-165-09 29/7/2009 | CHEMIN C&I PVT LTD | 301.93 | 18 M
PSER:SCT:MTN-T 1019:09 | TESTING, COMMISSIONING & HANDING OVER OF STEAM TURBINE & AUX OF 2X525 MW FOR MAITHON RIGHT BANK, JHARKHAND UNIT # 1 & 2 | OT | 2009-05-18 | TWO | 2009-06-08 | 3 | 3 NOS (I) M/S POWER MECH PROJECTS LTD (II) M/S P.E ERECTORS PVT. LTD (III) M/S INDWELL CONSTRUCTION PVT. LTD. | NIL | YES | LOI-166-09 29/7/2009 | INDWELL CONSTRUCTION PVT. LTD. | 1092.5442 | 20 M
PSER:SCT:MJA-E 973:09 | ETC OF TG & AUX, OTHER MISC. TRANSFORMERS, HT/LT BUS DUCTS, DG SETS AND ASSOCIATED PIPING, PANELS ETC FOR 2X500 MW FOR MEJIA-B UNIT # 1 & 2 | OT | 2009-02-25 | TWO | 2009-03-30 | 3 | 3 NOS 01. M/S P. R. V. CONSTRUCTION PVT. LTD. 02. M/S SIGMA CONSTRUCTION 03. M/S TECHNO ELECTRIC AND ENGINEERING CO. LTD. | NIL | YES | LOI-167-09 30/7/2009 | SIGMA CONSTRUCTION | 210.75 | 15 M
PSER:SCT:PAL-C 987:09 | CIVIL, STRUCTURAL, ARCHITECTURAL WORK OF MAIN CIVIL PKG FOR PALATONA UNIT # 1 & 2 | OT | 2009-03-24 | TWO | 2009-05-04 | 12 | 6 NOS. (I) NAVAYUGA ENGINEERING CO LTD (IN CONSORTIUM WITH SRI AVANTKA CONTRACTORS); (II) SEW INFRASTRUCTURE LTD; (III) PRASAD & CO (PROJECT WORKS) LTD; (IV) BRIDGE & ROOF CO (I) LTD; (V) SIMPLEX INFRASTRUCTURES LTD (VI) SNC POWER CORPORATION (P) LTD. | 6 NOS. (I) IVRCL INFRASTRUCTURE & PROJECT LTD (II) NBCC LTD (III) TANTIA CONSTRUCTION LTD; (IV) RAMKY INFRASTRUCTURE LTD; (V) NAGARJUNA CONSTRUCTION COMPANY LTD; (VI) ABCI INFRASTRUCTURES PVT LTD | YES | LOI-171-09 3/8/2009 | SNC POWER CORPORATION (P) LTD | 19414.2134 | 38 M
0 | FOR UNIT # | 0 | 0 | TWO | 0 | 0 | 0 | 0 | YES | LOI-182-09 7/8/2009 | 0 | 0 | 0
PSER:SCT:DGP-T 1005:09 | ERECTION, TESTING, COMMISSIONING & HANDING OVER OF TG & AUX FOR 2x500 MW FOR DURGAPUR STEEL THERMAL POWER STATION UNIT # I,II | OT | 2009-04-13 | TWO | 2009-05-11 | 3 | 3 NOS (I) M/S POWER MECH PROJECTS LTD.(II)M/S INDWELL CONSTRUCTION PVT. LTD. AND (III) M/S P. E. ERECTORS PVT. LTD. | NIL | YES | LOI-188-09 22/8/2009 | POWER MECH PROJECTS LTD | 1080 | 20 M
PSER:SCT:DGP-M 990:09 | ERECTION, TESTING, COMMISSIONING ETC OF CW PIPING, ACW PIPING & DM WATER PIPING SYSTEMS AND VARIOUS BALANCE PIPING SYSTEMS FOR 2X500 MW FOR DURGAPUR STEEL THERMAL POWER STATION UNIT # I,II | OT | 2009-03-16 | TWO | 2009-04-15 | 6 | 5 NOS (I) BRIDGE & ROOF CO (I) LTD; (II) GILLANDER ARBUTHNOT & CO LTD (UNIT – MICCO); (III) POWER MECH PROJECTS LTD; (IV) RAUNAQ INTERNATIONAL LTD AND (V) RUKMANI INFRA PROJECTS PVT LTD. | 1 NO 1) DINESH ENGINEERING & CO. | YES | LOI-189-09 22/8/2009 | RUKMANI INFRA PROJECTS PVT LTD | 759.458 | 19 M
PSER:SCT:KBA-C 981:09 | SITE LEVELING & GRADING, CIVIL, STRUCTURAL AND ARCHITECTURAL JOB OF POWER BLOCK WITH AUXILIARY BUILDING AND OTHER MISC FOUNDATIONS & STRUCTURES FOR 1X500 MW FOR KORBA (W) UNIT # I | OT | 2009-02-27 | TWO | 2009-04-10 | 16 | 6 NOS (I) SIMPLEX INFRASTRUCTURES LTD. (II) LARSEN & TOUBRO LTD. (III) BRIDGE & ROOF CO (I) LTD. (IV) PRASAD & CO (PROJECTS WORKS) LTD IN CONSORTIUM WITH M/S POWER MECH PROJECTS LTD. (V) SNC POWER CORPORATION (P) LTD. (VI) M/S SEW IN CONSORTIUM WITH P&R | 10 NOS I) SHAPOORJI PALLONJI & CO LTD (II) LANCO INSFASTRUCTURE LTD. (III) JMC PROJECTS (I) LTD (IV) NAGARJUNA CONSTRUCTION CO LTD IN CONSORTIUM WITH M/S SANGHA ERECTORS PVT. LTD. (V) NBCC LTD. (VI) METCON INDIA IN CONSORTIUM WITH M/S R. S. AVTAR SINGH & CO (VII) ERA INFRA ENGINEERING LTD (VIII) SUNIL HITECH ENGINERS LTD (IX) INDU PROJECTS LTD. IN CONSORTIUM WITH M/S SUNIL HITECH ENGINEERS LTD (X) GANNON DUNKERLEY & CO LTD. | YES | LOI-190-09 24/8/2009 | BRIDGE & ROOF CO (I) LTD | 10140.8995 | 39 M
PSER:SCT:MRW-C 982:09 | SITE LEVELING & GRADING, CIVIL, STRUCTURAL AND ARCHITECTURAL JOB OF POWER BLOCK – 1 AND POWER BLOCK -2 WITH ALL AUXILIARY BUILDING AND OTHER MISC FOUNDATIONS & STRUCTURES FOR 2X500 MW FOR MARWA TPS UNIT # I,II | OT | 2009-02-27 | TWO | 2009-04-13 | 15 | 6 NOS (I) SIMPLEX INFRASTRUCTURES LTD. (II) LARSEN & TOUBRO LTD. (III) BRIDGE & ROOF CO (I) LTD. (IV) PRASAD & CO (PROJECTS WORKS) LTD IN CONSORTIUM WITH M/S POWER MECH PROJECTS LTD. (V) SNC POWER CORPORATION (P) LTD. (VI) M/S SEW IN CONSORTIUM WITH P&R | 9 NOS (I) SHAPOORJI PALLONJI & CO LTD (II) LANCO INSFASTRUCTURE LTD. (III) JMC PROJECTS (I) LTD (IV) NAGARJUNA CONSTRUCTION CO LTD IN CONSORTIUM WITH M/S SANGHA ERECTORS PVT. LTD. (V) NBCC LTD. (VI) GANNON DUNKERLEY & CO LTD (VII) METCON INDIA in consortium with M/s R. S. AVTAR SINGH & CO (VIII) ERA INFRA ENGINEERING LTD (IX) INDU PROJECTS LTD. | YES | LOI-191-09 24/8/2009 | BRIDGE & ROOF CO (I) LTD | 15618.6235 | 42 M
DETAILS OF PURCHASE ORDER PLACED DURING THE MONTH OF AUGUST
PERIOD: 25/07/2009 - 24/08/2009
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TENDER NO. | ITEM/ NATURE OF WORK | MODE OF TENDER ENQUIRY | DATE OF PUBLICATION OF NIT | TYPE OF BIDDING (SINGLE /TWO BID SYSTEM) | LAST DATE OF RECEIPT OF TENDER | NO.OF TNDRS RECD. | NOS. AND NAMES OF PARTIES QUALIFIED AFTER TECHNICAL EVALUATION | NOS. AND NAMES OF PARTIES NOT QUALIFIED AFTER TECHNICAL EVALUATION | WHETHER CONTRACT AWARDED TO LOWEST TENDERER / EVALUATED L1 | CONTRACT NO. & DATE | NAME OF CONTRACTOR | VALUE OF CONTRACT (RS. LACS) | SCHEDULE DATE OF COMPLETION OF SUPPLIES
PSER:PUR:PMX:102:151 | SUPPLY OF CEMENT FOR CHANDRAPURA | LT | 2009-04-03 | TWO | 2009-04-10 | TWO | 1. Grasim Industries Ltd. 2.Ultratech Cement Ltd | NA | YES | PSER : PUR : PMX:102:151 R-:066:PPR001778 Date :27/07/2009 | Grasim Industries Ltd. | 178.91 | IMMEDIATE
PSER:PUR:PMX:102:151 | SUPPLY OF CEMENT FOR CHANDRAPURA | LT | 2009-04-03 | TWO | 2009-04-10 | TWO | 1. Grasim Industries Ltd. 2.Ultratech Cement Ltd | NA | YES | PSER : PUR : PMX:102:151 R-:067:PPR001779 Date :27/07/2009 | Ultratech Cement Ltd | 178.91 | IMMEDIATE
PSER:PUR:PMX:104:147 | SUPPLY OF CEMENT FOR SANTALDIH | LT | 2009-03-25 | TWO | 2009-04-08 | TWO | 1. Grasim Industries Ltd. 2.Ultratech Cement Ltd | NA | YES | PSER : PUR : PMX:104:147 R-:068:PPR001780 Date :28/07/2009 | Ultratech Cement Ltd | 250.98 | IMMEDIATE
PSER:PUR:PMX:144 | SUPPLY OF STEEL FOR MEJIA | NOU | NA | MOU | NA | NA | NA | NA | YES | PSER : PUR : PMX:144 R-069:PPR001781 Date :28/07/2009 | SAIL/DURGAPUR | 268.95 | IMMEDIATE
PSER:PUR:PMX:159 | SUPPLY OF STEEL FOR ANDAL | MOU | NA | MOU | NA | NA | NA | NA | YES | PSER:PUR:PMX:159 R-071 PPR001786 Date : 01/08/2009 | SAIL/DURGAPUR | 270.4 | IMMEDIATE
PSER:PUR:PMX:159 | SUPPLY OF STEEL FOR ANDAL | MOU | NA | MOU | NA | NA | NA | NA | YES | PSER:PUR:PMX:159 R-072 PPR001787 Date : 07/08/2009 | SAIL/DURGAPUR | 1121.23 | IMMEDIATE
PSER:PUR:PMX:186 | SUPPLY OF STEEL FOR BOKARO | MOU | NA | MOU | NA | NA | NA | NA | YES | PSER:PUR:PMX:186 R-075 PPR001790 Date : 12/08/2009 | SAIL/BOKARO | 557.19 | IMMEDIATE
PSER:PUR:PMX:100 | SUPPLY OF STEEL FOR BAKRESWAR | MOU | NA | MOU | NA | NA | NA | NA | YES | PSER:PUR:PMX:100 R-076 PPR001794 Date : 18/08/2009 | SAIL/KOLKATA | 121.63 | IMMEDIATE
PSER:PUR:PMX:186 | SUPPLY OF STEEL FOR BOKARO | MOU | NA | MOU | NA | NA | NA | NA | YES | PSER:PUR:PMX:186 R-079 PPR001799 Date : 19/08/2009 | SAIL/BOKARO | 186.71 | IMMEDIATE
PSER:PUR:FEX:157 | SUPPLY OF CRANE SPARES FOR ANDAL | ST | 2009-06-23 | TWO | 2009-07-07 | ONE | M/s VOLTAS LIMITED, | NA | YES | PSER:PUR:FEX:157:40:041 C-041 PPR001784 Date : 01/08/2009 | VOLTAS LTD. | 219.75 | IMMEDIATE