## Master List of Drawings
"PANKI - Conveyor Pkg" "MASTER LIST OF DRAWINGS" |  |  |  | 43190
S.NO. | BHEL_DRG_NO | NTPC_DRG_NO | DRG_TITLE | SCHEDULED FIRST 2D AUTOICAD SUBMISSION (NO. OF DAYS FROM LOA DATE | SCHEDULED FIRST 3D PDMS SUBMISSION (NO. OF DAYS FROM LOA DATE
A | MECHANICAL
1 | IS-1-FL-713-100-M001 | 9962-001-IS-155-PVM-L-001 | COAL FLOW / LIMESTONE FLOW/ GYPSUM FLOWDIAGRAM | 180
2 | IS-0-PL-713-100-M002 | 9962-001-IS-155-PVM-F-002 | LAYOUT OF COAL HANDLING PLANT | 150 | 280
3 | IS-1-GA-713-101-M004 | 9962-001-IS-155-PVM-B-004 | CONV. PROFILE FOR ALL CONV. | 20
4 | IS-4-DM-713-100-M005 | 9962-001-IS-155-PVM-Z-005 | DESIGN MEMORANDUM FOR CHP/ LHP/ GHP | 30
5 | IS-1-GA-713-101-M006 | 9962-001-IS-155-PVM-B-006 | G.A. & LOAD DATA OF CONV. BC-1A/B | 50 | 230
6 | IS-1-GA-713-101-M007 | 9962-001-IS-155-PVM-B-007 | G.A. & LOAD DATA OF CONV. BC-2A/B | 40 | 220
7 | IS-1-GA-713-101-M008 | 9962-001-IS-155-PVM-B-008 | G.A. & LOAD DATA OF CONV. BC-3A/B | 40 | 220
8 | IS-1-GA-713-101-M009 | 9962-001-IS-155-PVM-B-009 | G.A. & LOAD DATA OF CONV. BC-3C/D | 42 | 222
9 | IS-1-GA-713-101-M010 | 9962-001-IS-155-PVM-B-010 | G.A. & LOAD DATA OF CONV. BC-4A/B | 45 | 225
10 | IS-1-GA-713-101-M011 | 9962-001-IS-155-PVM-B-011 | G.A. & LOAD DATA OF CONV. BC-4C/D | 45 | 225
11 | IS-1-GA-713-101-M012 | 9962-001-IS-155-PVM-B-012 | G.A. & LOAD DATA OF CONV. BC-5A/B | 30 | 210
12 | IS-1-GA-713-101-M013 | 9962-001-IS-155-PVM-B-013 | G.A. & LOAD DATA OF CONV. BC-6A/B | 22 | 202
13 | IS-1-GA-713-101-M014 | 9962-001-IS-155-PVM-B-014 | G.A. & LOAD DATA OF CONV. BC-7A/B | 47 | 227
14 | IS-1-GA-713-101-M015 | 9962-001-IS-155-PVM-B-015 | G.A. & LOAD DATA OF CONV. BC-8A/B | 27 | 207
15 | IS-1-GA-713-101-M016 | 9962-001-IS-155-PVM-B-016 | G.A. & LOAD DATA OF CONV. RC-1A/B | 45 | 225
16 | IS-1-GA-713-101-M017 | 9962-001-IS-155-PVM-B-017 | G.A. & LOAD DATA OF YARD CONV. YBC-1A | 50 | 230
17 | IS-1-GA-713-101-M018 | 9962-001-IS-155-PVM-B-018 | G.A. & LOAD DATA OF YARD CONV. YBC-1B | 50 | 230
18 | IS-1-GA-713-101-M019 | 9962-001-IS-155-PVM-B-019 | G.A. & LOAD DATA OF BUNKER CONV. TBC-1A/B | 20 | 200
19 | IS-1-GA-715-101-M020 | 9962-001-IS-155-PVM-B-020 | G.A. & LOAD DATA OF BUNKER CONV. TBC-2A/B | 20 | 200
20 | IS-1-GA-715-101-M021 | 9962-001-IS-155-PVM-B-023 | G.A. & LOAD DATA OF REVERSIBLE BELT FEEDER RBF-1 & 2 AT CRH | 30 | 210
21 | IS-1-GA-715-116-M022 | 9962-001-IS-155-PVM-B-024 | G.A. OF TRAVELLING TRIPPER | 70 | 250
22 | IS-1-GA-713-104-M025 | 9962-001-IS-155-PVM-B-025 | G.A. & LOAD DATA OF JUNCTION TOWER JT-1 | 32 | 212
23 | IS-1-GA-713-104-M026 | 9962-001-IS-155-PVM-B-026 | G.A. & LOAD DATA OF JUNCTION TOWER JT-2 | 35 | 215
24 | IS-1-GA-713-107-M027 | 9962-001-IS-155-PVM-B-027 | G.A. & LOAD DATA OF CRUSHER HOUSE CRH | 32 | 212
25 | IS-1-GA-713-104-M028 | 9962-001-IS-155-PVM-B-028 | G.A. & LOAD DATA OF JUNCTION TOWER JT-3 | 30 | 210
26 | IS-1-GA-713-104-M029 | 9962-001-IS-155-PVM-B-029 | G.A. & LOAD DATA OF JUNCTION TOWER JT-4 | 32 | 212
27 | IS-1-GA-713-104-M030 | 9962-001-IS-155-PVM-B-030 | G.A. & LOAD DATA OF JUNCTION TOWER JT-5 | 27 | 207
28 | IS-1-GA-713-104-M031 | 9962-001-IS-155-PVM-B-031 | G.A. & LOAD DATA OF JUNCTION TOWER JT-6 | 12 | 192
29 | IS-1-GA-713-104-M032 | 9962-001-IS-155-PVM-B-032 | G.A. & LOAD DATA OF JUNCTION TOWER JT-7 | 10 | 190
30 | IS-1-GA-713-104-M033 | 9962-001-IS-155-PVM-B-033 | G.A. & LOAD DATA OF JUNCTION TOWER JT-8 | 35 | 215
31 | IS-1-GA-713-104-M034 | 9962-001-IS-155-PVM-B-034 | G.A. & LOAD DATA OF JUNCTION TOWER JT-9 | 35 | 215
32 | IS-1-GA-713-104-M035 | 9962-001-IS-155-PVM-B-035 | G.A. & LOAD DATA OF JUNCTION TOWER JT-10 | 37 | 217
33 | IS-1-GA-713-104-M036 | 9962-001-IS-155-PVM-B-036 | G.A. & LOAD DATA OF JUNCTION TOWER JT-11 | 40 | 220
34 | IS-1-GA-713-104-M037 | 9962-001-IS-155-PVM-B-037 | G.A. & LOAD DATA OF JUNCTION TOWER JT-12 | 42 | 222
35 | IS-1-GA-713-109-M038 | 9962-001-IS-155-PVM-B-038 | G.A. OF EMERGENCY RECLAIM HOPPER #ERHC | 27 | 207
36 | IS-1-GA-713-112-M039 | 9962-001-IS-155-PVM-B-039 | GA OF DS PUMP HOUSE-1 |  | 255
37 | IS-1-GA-713-112-M040 | 9962-001-IS-155-PVM-B-040 | GA OF DS PUMP HOUSE-2 |  | 255
38 | IS-1-GA-713-113-M041 | 9962-001-IS-155-PVM-B-041 | GA OF BULLDOZER SHED | 53 | 260
39 | IS-1-GA-713-113-M042 | 9962-001-IS-155-PVM-B-042 | GA OF SAMPLING TOWER#ST | 25 | 205
40 | IS-1-GA-713-113-M043 | 9962-001-IS-155-PVM-B-043 | GA OF COAL SETTLING POND
41 | IS-4-DC-713-101-M044 | 9962-001-IS-155-PVM-U-044 | POWER & BELT TENSION CALC. FOR CONVEYORS | 30
42 | IS-4-DC-713-101-M045 | 9962-001-IS-155-PVM-U-045 | POWER & BELT TENSION CALC. FOR BELT FEEDER BF-1&2 | 30
43 | IS-4-DC-713-116-M046 | 9962-001-IS-155-PVM-U-046 | MOTOR RATING & WHEEL LOAD CALC. FOR TRAVELLING TRIPPER | 70
44 | IS-4-DC-713-111-M047 | 9962-001-IS-155-PVM-U-047 | MOTOR RATING CALC. FOR R.P.GATE | 40
45 | IS-4-DC-713-111-M048 | 9962-001-IS-155-PVM-U-048 | MOTOR RATING CALC. FOR DIVERTER GATE | 50
46 | IS-4-DC-713-111-M049 | 9962-001-IS-155-PVM-U-049 | MOTOR RATING CALC. FOR FLAP GATE | 55
47 | IS-4-DC-713-110-M050 | 9962-001-IS-155-PVM-U-050 | DESIGN BASIS REPORT FOR VENTILATION SYSTEM | 200
48 | IS-4-DC-713-111-M051 | 9962-001-IS-155-PVM-U-051 | DESIGN BASIS FOR A/C SYSTEM IN CHP CONTROL ROOM | 200
49 | IS-4-DC-713-110-M052 | 9962-001-IS-155-PVM-U-052 | DESIGN BASIS REPORT FOR SA, SW & PW SYSTEMS
50 | IS-4-DC-713-110-M053 | 9962-001-IS-155-PVM-U-053 | DESIGN BASIS REPORT FOR DFDS & DS SYSTEMS
51 | IS-4-DC-713-110-M054 | 9962-001-IS-155-PVM-U-054 | DESIGN BASIS REPORT OF DE SYSTEM | 80
52 | IS-4-DC-713-111-M055 | 9962-001-IS-155-PVM-U-055 | DESIGN CALCULATION FOR COAL SAMPLING SYSTEM | 130
53 | IS-3-GA-713-111-M056 | 9962-001-IS-155-PVM-B-056 | G.A. OF R.P GATE | 40
54 | IS-3-GA-713-111-M057 | 9962-001-IS-155-PVM-B-057 | G.A. OF DIVERTER GATE | 50
55 | IS-3-GA-713-111-M058 | 9962-001-IS-155-PVM-B-058 | G.A. OF FLAP GATE | 55
56 | IS-3-GA-713-111-M059 | 9962-001-IS-155-PVM-B-059 | G.A. OF ROD GATE | 40
57 | IS-3-GA-713-111-M060 | 9962-001-IS-155-PVM-B-060 | TYPICAL GA OF CHUTE WORK | 35
58 | IS-3-GA-713-111-M061 | 9962-001-IS-155-PVM-B-061 | TYP. GA OF SKIRT BOARD | 60
59 | IS-3-GA-713-111-M062 | 9962-001-IS-155-PVM-B-062 | GA OF GEAR BOX FOR CONVEYORS & BELT FEEDER | 86
60 | IS-3-GA-713-111-M063 | 9962-001-IS-155-PVM-B-063 | GA OF SCOOP TYPE FLUID COUPLING FOR CONVEYORS | 91
61 | IS-3-GA-713-111-M064 | 9962-001-IS-155-PVM-B-064 | GA OF TRACTION TYPE FLUID COUPLING FOR CONVEYORS & BELT FEEDER | 96
62 | IS-3-GA-713-111-M065 | 9962-001-IS-155-PVM-B-065 | GA OF GEAR COUPLING FOR CONVEYORS & BELT FEEDER | 106
63 | IS-3-GA-713-111-M066 | 9962-001-IS-155-PVM-B-066 | ELECTRO HYDRAULIC THRUSTER BRAKE FOR CONVEYORS & BELT FEEDER AND TRIPPER | 111
64 | IS-3-GA-713-111-M067 | 9962-001-IS-155-PVM-B-067 | GA OF DRIVE ARRANGMENT FOR TRIPPER | 70
65 | IS-3-GA-713-111-M068 | 9962-001-IS-155-PVM-B-068 | AUTOMATIC RAIL CLAMP FOR TRIPPER | 70
66 | IS-3-GA-713-116-M069 | 9962-001-IS-155-PVM-Y-069 | GA & DATASHEET FOR ELEVATOR FOR CRH | 99
67 | IS-3-GA-713-116-M070 | 9962-001-IS-155-PVM-Y-070 | GA & DATASHEET FOR ELEVATOR FOR JT-6 | 99
68 | IS-3-GA-713-116-M071 | 9962-001-IS-155-PVM-Y-071 | GA & DATASHEET FOR ELEVATOR FOR JT-7 | 99
69 | IS-4-DS-713-111-M072 | 9962-001-IS-155-PVM-Y-072 | DATASHEET FOR CONVEYOR BELT | 40
70 | IS-3-GA-713-111-M073 | 9962-001-IS-155-PVM-B-073 | GA OF RESILIENT COUPLING FOR TRIPPER | 70
71 | IS-3-GA-713-111-M074 | 9962-001-IS-155-PVM-B-074 | G.A. OF ACTUATOR FOR DIVERTER GATE, FLAPGATE & RP GATE | 112
72 | IS-3-GA-713-111-M075 | 9962-001-IS-155-PVM-B-075 | G.A. OF BELT WEIGHER | 77
73 | IS-3-GA-713-111-M076 | 9962-001-IS-155-PVM-B-076 | G.A. OF METAL DETECTOR | 83
74 | IS-3-GA-713-111-M077 | 9962-001-IS-155-PVM-B-077 | G.A. OF ILMS | 90
75 | IS-3-GA-713-111-M078 | 9962-001-IS-155-PVM-B-078 | G.A. OF SUSPENDED MAGNET | 90
76 | IS-3-GA-713-111-M079 | 9962-001-IS-155-PVM-B-079 | G.A. OF COAL SCOOPER | 127
77 | IS-3-GA-713-111-M080 | 9962-001-IS-155-PVM-B-080 | G.A. OF COAL SAMPLING SYSTEM AT ST | 135
78 | IS-3-GA-713-111-M081 | 9962-001-IS-155-PVM-B-081 | G.A. OF ELECTRICAL HOIST | 130
79 | IS-3-GA-713-111-M082 | 9962-001-IS-155-PVM-B-082 | GA OF MANUAL HOIST & CHAIN PULLEY BLOCK | 130
80 | IS-3-GA-713-111-M083 | 9962-001-IS-155-PVM-B-083 | G.A. OF EOT CRANE
81 | IS-3-GA-713-111-M084 | 9962-001-IS-155-PVM-B-084 | GA OF EXTERNAL BELT SCRAPPER FOR CONVEYORS (PRIMARY) | 82
82 | IS-3-GA-713-111-M085 | 9962-001-IS-155-PVM-B-085 | GA OF EXTERNAL BELT SCRAPPER FOR CONVEYORS (SECONDARY) | 76
83 | IS-3-GA-713-111-M086 | 9962-001-IS-155-PVM-B-086 | G.A. OF INTERNAL SCRAPPER | 76
84 | IS-3-GA-713-111-M087 | 9962-001-IS-155-PVM-B-087 | GA OF SKIRT SEALING SYSTEM FOR CONVEYORS | 65
85 | IS-3-GA-713-111-M088 | 9962-001-IS-155-PVM-Y-088 | G.A. & DATA SHEET FOR BELT VULCANISING MACHINE | 146
86 | IS-3-GA-713-111-M089 | 9962-001-IS-155-PVM-B-089 | GA OF VIBRATING FEEDER | 95
87 | IS-4-DS-713-101-M090 | 9962-001-IS-155-PVM-Y-090 | TECHNICAL DATA SHEET - CONVEYOR BELTING | 216
88 | IS-3-GA-713-111-M084 | 9962-001-IS-155-PVM-B-084 | GA OF EXTERNAL BELT SCRAPPER FOR CONVEYORS (PRIMARY)
89 | IS-3-GA-713-111-M085 | 9962-001-IS-155-PVM-B-085 | GA OF EXTERNAL BELT SCRAPPER FOR CONVEYORS (SECONDARY)
90 | IS-3-GA-713-111-M086 | 9962-001-IS-155-PVM-B-086 | G.A. OF INTERNAL SCRAPPER
91 | IS-3-GA-713-111-M087 | 9962-001-IS-155-PVM-B-087 | GA OF SKIRT SEALING SYSTEM FOR CONVEYORS
92 | IS-3-GA-713-111-M088 | 9962-001-IS-155-PVM-Y-088 | G.A. & DATA SHEET FOR BELT VULCANISING MACHINE
93 | IS-3-GA-713-111-M089 | 9962-001-IS-155-PVM-B-089 | GA OF VIBRATING FEEDER
94 | IS-4-DS-713-101-M090 | 9962-001-IS-155-PVM-Y-090 | TECHNICAL DATA SHEET - CONVEYOR BELTING
95 | IS-1-PI-713-110-M091 | 9962-001-IS-155-PVM-L-091 | SCHEMATIC DIAGRAM FOR DFDS & DS SYSTEMS
96 | IS-1-PI-713-110-M092 | 9962-001-IS-155-PVM-L-092 | SCHEMATIC FOR SA, SW & PW SYSTEMS
97 | IS-3-GA-713-110-M093 | 9962-001-IS-155-PVM-Y-093 | GA, DATASHEET & CURVE OF PUMPS FOR DS,DFDS,SW,PW,CW & MW SYSTEM
98 | IS-3-GA-713-110-M094 | 9962-001-IS-155-PVM-Y-094 | GA & DATA SHEET OF SCREW COMPRESSOR FOR DFDS SYSTEM
99 | IS-3-GA-713-110-M095 | 9962-001-IS-155-PVM-Y-095 | GA AND DATA SHEET OF SPRINKLER FOR STOCKPILE DS SYSTEM
100 | IS-3-GA-713-110-M096 | 9962-001-IS-155-PVM-Y-096 | G.A. AND DATA SHEET OF COAL SETTLING POND PUMP
101 | IS-3-GA-713-110-M097 | 9962-001-IS-155-PVM-Y-097 | G.A. & DATA SHEET OF GATE VALVE
102 | IS-3-GA-713-110-M098 | 9962-001-IS-155-PVM-B-098 | GA OF DUPLEX STRAINER FOR DFDS, DS, SW & PW SYSTEM
103 | IS-3-GA-713-110-M099 | 9962-001-IS-155-PVM-B-099 | GA OF CI, FS & SS VALVES FOR DFDS, DS, PW & SW SYSTEM
104 | IS-3-GA-713-110-M100 | 9962-001-IS-155-PVM-B-100 | GA OF QRC, HOSE, HOSE REELING DRUM FOR SW & DS SYSTEM
105 | IS-3-GA-713-110-M101 | 9962-001-IS-155-PVM-Y-101 | GA & DATA SHEET FOR PVC TANK FOR PW & SW SYSTEM
106 | IS-3-GA-713-110-M102 | 9962-001-IS-155-PVM-B-102 | GA OF VERTICAL AIR RECEIVER FOR CHP
107 | IS-4-DS-713-110-M103 | 9962-001-IS-155-PVM-Y-103 | DATA SHEET FOR PIPE & PIPE FITTINGS FOR DFDS,DS,PW & SW SYSTEM
108 | IS-4-DS-713-110-M104 | 9962-001-IS-155-PVM-B-104 | GA OF SPRAY NOZZLE FOR DS & DFDS SYSTEM
109 | IS-3-GA-713-110-M105 | 9962-001-IS-155-PVM-Y-105 | GA & DATA SHEET FOR SOLENOID VALVE FOR DS & DFDS SYSTEM
110 | IS-3-GA-713-110-M106 | 9962-001-IS-155-PVM-B-106 | GA DRG OF FCU, FCU_D, CCU, PRU FOR DFDS & SB BOX FOR DS SYSTEM
111 | IS-1-PI-713-110-M107 | 9962-001-IS-155-PVM-P-107 | PIPING LAYOUT FOR WATER SYSTEM AT JT-1
112 | IS-1-PI-713-110-M108 | 9962-001-IS-155-PVM-P-108 | PIPING LAYOUT FOR WATER SYSTEM AT JT-2
113 | IS-1-PI-713-110-M109 | 9962-001-IS-155-PVM-P-109 | PIPING LAYOUT FOR WATER SYSTEM AT JT-3
114 | IS-1-PI-713-110-M110 | 9962-001-IS-155-PVM-P-110 | PIPING LAYOUT FOR WATER SYSTEM AT JT-4
115 | IS-1-PI-713-110-M111 | 9962-001-IS-155-PVM-P-111 | PIPING LAYOUT FOR WATER SYSTEM AT JT-5
116 | IS-1-PI-713-110-M112 | 9962-001-IS-155-PVM-P-112 | PIPING LAYOUT FOR SWATER SYSTEM AT JT-6
117 | IS-1-PI-713-110-M113 | 9962-001-IS-155-PVM-P-113 | PIPING LAYOUT FOR WATER SYSTEM AT JT-7
118 | IS-1-PI-713-110-M114 | 9962-001-IS-155-PVM-P-114 | PIPING LAYOUT FOR WATER SYSTEM AT JT-8
119 | IS-1-PI-713-110-M115 | 9962-001-IS-155-PVM-P-115 | PIPING LAYOUT FOR WATER SYSTEM AT JT-9
120 | IS-1-PI-713-110-M116 | 9962-001-IS-155-PVM-P-116 | PIPING LAYOUT FOR WATER SYSTEM AT JT-10
121 | IS-1-PI-713-110-M117 | 9962-001-IS-155-PVM-P-117 | PIPING LAYOUT FOR WATER SYSTEM AT JT-11
122 | IS-1-PI-713-110-M118 | 9962-001-IS-155-PVM-P-118 | PIPING LAYOUT FOR WATER SYSTEM AT JT-12
123 | IS-1-PI-713-110-M119 | 9962-001-IS-155-PVM-P-119 | PIPING LAYOUT FOR WATER SYSTEM AT EMERGENCY RECLAIM HOPPER COMPLEX
124 | IS-1-PI-713-110-M120 | 9962-001-IS-155-PVM-P-120 | PIPING LAYOUT FOR WATER SYSTEM AT CRUSHER HOUSE
125 | IS-1-PI-713-110-M121 | 9962-001-IS-155-PVM-P-121 | PIPING LAYOUT FOR WATER SYSTEM AT WAGON TIPPLER COMPLEX
126 | IS-1-PI-713-110-M122 | 9962-001-IS-155-PVM-P-122 | PIPING LAYOUT FOR DS SYSTEM AT STOCK PILE AREA
127 | IS-1-PI-713-110-M123 | 9962-001-IS-155-PVM-P-123 | PIPING LAYOUT FOR WATER SYSTEM AT MCC-1
128 | IS-1-PI-713-110-M124 | 9962-001-IS-155-PVM-P-124 | PIPING LAYOUT FOR WATER SYSTEM AT MCC-2
129 | IS-1-PI-713-110-M125 | 9962-001-IS-155-PVM-P-125 | PIPING LAYOUT FOR WATER SYSTEM AT MCC-3
130 | IS-1-PI-713-110-M126 | 9962-001-IS-155-PVM-P-126 | PIPING LAYOUT FOR WATER SYSTEM AT MCC-4
131 | IS-1-PI-713-110-M127 | 9962-001-IS-155-PVM-P-127 | PIPING LAYOUT FOR PRE-WETTING OF WAGON
132 | IS-1-PI-713-110-M128 | 9962-001-IS-155-PVM-P-128 | GENERAL PLOT PLAN PIPING LAYOUT FOR DFDS, DS, CW, SW, PW SYSTEM
133 | IS-3-GA-713-110-M129 | 9962-001-IS-155-PVM-B-129 | GA OF Y STRAINER FOR DS & DFDS SYSTEM
134 | IS-3-GA-713-110-M130 | 9962-001-IS-155-PVM-B-130 | GA OF SPRAY HEADER FOR DS SYSTEM
135 | IS-3-GA-713-110-M131 | 9962-001-IS-155-PVM-Y-131 | GA & DATA SHEET OF MOTORISED BUTTERFLY VALVES FOR DFDS,DS,PW & SW SYSTEM
136 | IS-4-SC-713-110-M132 | 9962-001-IS-155-PVM-H-132 | VALVE SCHEDULE FOR CHP WATER SYSTEM
137 | IS-1-GA-713-110-M133 | 9962-001-IS-155-PVM-F-133 | DUCTING LAYOUT FOR TUNNEL VENTILATION SYSTEM FOR WAGAON TIPPLER AREA AND CONV 1A/B | 224
138 | IS-1-GA-713-110-M134 | 9962-001-IS-155-PVM-F-134 | DUCTING LAYOUT FOR TUNNEL VENTILATION SYSTEM FOR JT-1 AND CONV 2A/B | 229 | 275
139 | IS-1-GA-713-110-M135 | 9962-001-IS-155-PVM-F-135 | DUCT LAYOUT OF PRESSURIZED VENTILATION SYSTEM & AIR CONDITIONING FOR CHP MCC-1 NEAR WT | 235 | 275
140 | IS-1-GA-713-110-M136 | 9962-001-IS-155-PVM-F-136 | DUCT LAYOUT OF PRESSURIZED VENTILATION SYSTEM & AIR CONDITIONING FOR CHP MCC-2 NEAR CH | 239 | 270
141 | IS-1-GA-713-110-M137 | 9962-001-IS-155-PVM-B-137 | DUCT LAYOUT OF PRESSURIZED VENTILATION SYSTEM & AIR CONDITIONING FOR CHP MCC-3 NEAR JT-10 | 245 | 270
142 | IS-1-GA-713-110-M138 | 9962-001-IS-155-PVM-B-138 | DUCT LAYOUT OF PRESSURIZED VENTILATION SYSTEM & AIR CONDITIONING FOR CHP MCC-4 NEAR JT-5 | 249 | 265
143 | IS-1-GA-713-110-M139 | 9962-001-IS-155-PVM-B-139 | LAYOUT OF BUNKER BAY VENTILATION | 60 | 260
144 | IS-3-GA-713-110-M140 | 9962-001-IS-155-PVM-B-140 | GA OF FAN FOR VENTILATION | 56
145 | IS-3-GA-713-110-M141 | 9962-001-IS-155-PVM-B-141 | GA OF CENTRIFUGAL FANS FOR DE SYSTEM | 56
146 | IS-3-GA-713-110-M142 | 9962-001-IS-155-PVM-B-142 | GA OF BAG FILTER FOR DE SYSTEM | 60
147 | IS-3-GA-713-110-M143 | 9962-001-IS-155-PVM-B-143 | GA OF AIR RECEIVER FOR DE SYSTEMS | 46
148 | IS-3-GA-713-110-M144 | 9962-001-IS-155-PVM-B-144 | GA OF AIR COMPRESSOR FOR DE SYSTEM | 56
149 | IS-1-GA-713-110-M145 | 9962-001-IS-155-PVM-B-145 | DUCTING LAYOUT FOR DE SYSTEM AT CRH | 85 | 212
150 | IS-1-GA-713-110-M146 | 9962-001-IS-155-PVM-B-146 | DUCTING LAYOUT FOR DE SYSTEM AT BUNKERS | 90 | 200
151 | IS-3-GA-713-110-M147 | 9962-001-IS-155-PVM-B-147 | GA & DATA SHEET OF ROTARY AIR LOCK VALVE FOR DE SYSTEM | 85
152 | IS-3-GA-713-110-M148 | 9962-001-IS-155-PVM-B-148 | GA OF AIR DRIER FOR DE SYSTEM | 81
153 | IS-4-SC-713-110-M149 | 9962-001-IS-155-PVM-B-149 | GA, DATASHEET & CURVE OF AXIAL FAN WITH MOTOR FOR DS PUMP HOUSE-1 & 2 | 56
154 | IS-4-SC-713-110-M150 | 9962-001-IS-155-PVM-W-150 | PAINT SCHEME FOR CHP WATER SYSTEMS
155 | IS-3-SC-713-100-M151 | 9962-001-IS-155-PVM-H-151 | DRAWING DOCUMENT SCHEDULE
156 | IS-3-SC-713-101-M152 | 9962-001-IS-155-PVM-H-152 | BELT SCHEDULE | 225
157 | IS-3-SC-713-101-M153 | 9962-001-IS-155-PVM-H-153 | PULLEY SCHEDULE | 46
158 | IS-3-SC-713-101-M154 | 9962-001-IS-155-PVM-H-154 | IDLER SCHEDULE | 56
159 | IS-3-SC-713-111-M155 | 9962-001-IS-155-PVM-H-155 | HOIST SCHEDULE | 70
160 | IS-4-SC-713-101-M156 | 9962-001-IS-155-PVM-H-156 | PAINTING SCHEDULE (SPECIFICATIONS) | 36
161 | IS-4-OM-713-101-M157 | 9962-001-IS-155-PVM-X-157 | O & M MANUALS | 300
162 | IS-4-CM-713-000-M158 | 9962-001-IS-155-PVM-W-158 | INDICATIVE SUB VENDOR LIST OF CHP MECHNICAL
163 | IS-1-GA-713-108-M159 | 9962-001-IS-155-PVM-B-159 | G.A. OF STACKER CUM RECLAIMER WITH TECHNICAL DATA SHEET
164 | IS-4-GA-713-108-M160 | 9962-001-IS-155-PVM-B-160 | PERMISSIBLE RAIL LAYING TOLERANCE FOR SCR
165 | IS-1-GA--108-M161 | 9962-001-IS-155-PVM-B-161 | G.A OF RAIL & RAIL FIXING ACCESSORIES FOR SCR
166 | IS-1-GA-713-108-M162 | 9962-001-IS-155-PVM-B-162 | G.A. OF STOCK YARD LAYOUT OF SCR
167 | IS-1-DS-713-108-M163 | 9962-001-IS-155-PVM-B-163 | WHEEL LOAD DATA FOR SCR
168 | IS-1-GA-713-108-M164 | 9962-001-IS-155-PVM-B-164 | GA OF RAIL TRAVEL MECHANISM FOR SCR
169 | IS-1-GA-713-108-M165 | 9962-001-IS-155-PVM-B-165 | ARRGT. OF STORM ANCHOR FOR SCR
170 | IS-4-DS-713-108-M166 | 9962-001-IS-155-PVM-B-166 | DATASHEET FOR CONVEYOR BELT FOR SCR
171 | IS-4-DC-713-108-M167 | 9962-001-IS-155-PVM-B-167 | DESIGN CALCULATION FOR STOCKPILE CAPACITY FOR STACKER CUM RECLAIMER
172 | IS-3-GA-713-108-M168 | 9962-001-IS-155-PVM-B-168 | G.A. OF DRIVE, NON-DRIVE & TAKE-UP PULLEYS FOR SCR
173 | IS-3-GA-713-108-M169 | 9962-001-IS-155-PVM-B-169 | ARRGT. OF PARALLEL CRD POWER FOR SCR
174 | IS-3-GA-713-108-M170 | 9962-001-IS-155-PVM-B-170 | ARRGT. OF PARALLEL CRD CONTROL FOR SCR
175 | IS-3-GA-713-108-M171 | 9962-001-IS-155-PVM-B-171 | GA OF ALL TYPES OF IDLERS FOR SCR
176 | IS-3-GA-713-108-M172 | 9962-001-IS-155-PVM-B-172 | BELT WEIGHER DRGS. FOR SCR.
177 | IS-3-GA--108-M173 | 9962-001-IS-155-PVM-B-173 | LUB.SYSTEM FOR STACKER RECLAIMER
178 | IS-3-GA-713-108-M174 | 9962-001-IS-155-PVM-B-174 | HYD. CIRCUIT PLAN FOR BOOM LUFFING, CABIN LEVELLING & OTHER CYLINDER FOR SCR
179 | IS-3-GA-713-108-M175 | 9962-001-IS-155-PVM-B-175 | DS SYSTEM FOR SCR
180 | IS-3-GA-713-108-M176 | 9962-001-IS-155-PVM-B-176 | HYD. CIRCUIT PLAN FOR BUCKET WHEEL DRIVE STACKER CUM RECLAIMER
181 | IS-3-GA-713-108-M177 | 9962-001-IS-155-PVM-B-177 | GA OF GEAR BOX FOR STACKER CUM RECLAIMER
182 | IS-3-GA-713-108-M178 | 9962-001-IS-155-PVM-B-178 | GA OF SLEWING DRIVE ASSEMBLY FOR SCR
183 | IS-3-GA--108-M179 | 9962-001-IS-155-PVM-B-179 | GA OF BRAKES FOR SCR
184 | IS-3-GA-713-108-M180 | 9962-001-IS-155-PVM-B-180 | GA OF BOOM CONV FOR SCR
185 | IS-3-GA-713-108-M181 | 9962-001-IS-155-PVM-B-181 | GA OF GEAR COUPLING FOR SCR
186 | IS-3-GA-713-108-M182 | 9962-001-IS-155-PVM-B-182 | GA OF OPERATORS CABIN FOR STACKER RECLAIMER
187 | IS-4-DC-713-108-M183 | 9962-001-IS-155-PVM-B-183 | POWER CALCULATIONS FOR BOOM LUFFING DRIVE
188 | IS-4-DC-713-108-M184 | 9962-001-IS-155-PVM-B-184 | POWER CALCULATIONS FOR BOOM CONV
189 | IS-4-DC--108-M185 | 9962-001-IS-155-PVM-B-185 | POWER CALCULATIONS FOR SLEWING DRIVE
190 | IS-4-DC-713-108-M186 | 9962-001-IS-155-PVM-B-186 | POWER CALCULATIONS FOR TRAVEL DRIVE
191 | IS-4-DC-713-108-M187 | 9962-001-IS-155-PVM-B-187 | SIZING & POWER CALCULATIONS FOR BUCKET WHEEL DRIVE
192 | IS-3-GA-713-108-M188 | 9962-001-IS-155-PVM-B-188 | BELT SCRAPPER FOR SCR
193 | IS-3-GA--108-M189 | 9962-001-IS-155-PVM-B-189 | AUTOMATIC RAIL CLAMP FOR SCR
194 | IS-3-GA-713-108-M190 | 9962-001-IS-155-PVM-B-190 | GA OF FLUID COUPLING FOR SCR
195 | IS-1-GA-713-103-M191 | 9962-001-IS-155-PVM-B-191 | GA OF WAGON TIPPLER COMPLEX
196 | IS-1-GA-713-103-M192 | 9962-001-IS-155-PVM-B-192 | GA DRAWING OF WAGON TIPPLER
197 | IS-1-DS--103-M193 | 9962-001-IS-155-PVM-B-193 | LOAD DATA & FOUNDATION DETAILS OF WAGON TIPPLER
198 | IS-1-GA-713-103-M194 | 9962-001-IS-155-PVM-B-194 | WAGON TIPPLER AND SAC TIMING
199 | IS-4-OP-713-103-M195 | 9962-001-IS-155-PVM-B-195 | OPERATIONAL WRITE UP FOR SIDE DISCHARGE WAGON TIPPLER WITH SIDE ARM CHARGER
200 | IS-4-DC-713-103-M196 | 9962-001-IS-155-PVM-B-196 | POWER CALCULATION OF WT, WT CLAMPING & SAC
201 | IS-1-GA-713-103-M197 | 9962-001-IS-155-PVM-B-197 | GA DRAWING OF SIDE ARM CHARGER
202 | IS-1-DS--103-M198 | 9962-001-IS-155-PVM-B-198 | LOAD DATA & FOUNDATION DETAILS OF SIDE ARM CHARGER
203 | IS-1-GA-713-103-M199 | 9962-001-IS-155-PVM-B-199 | GA OF APRON & DRIBBLE FEEDER
204 | IS-4-DC-713-103-M200 | 9962-001-IS-155-PVM-B-200 | DESIGN CALCULATION OF APRON FEEDER
205 | IS-4-DC-713-103-M201 | 9962-001-IS-155-PVM-B-201 | DESIGN CALCULATION OF DRIBBLE FEEDER
206 | IS-4-DC-713-103-M202 | 9962-001-IS-155-PVM-B-202 | DATASHEET FOR DRIBBLE CONVEYOR BELT
207 | IS-3-GA--103-M203 | 9962-001-IS-155-PVM-B-203 | GA & DATASHEET OF INTEGRATED WEIGH BRIDGE FOR WAGON TIPPLERS
208 | IS-1-PI-713-103-M204 | 9962-001-IS-155-PVM-B-204 | HYDRAULIC SYSTEM DRAWINGS FOR WAGON TIPPLER
209 | IS-4-GA-713-103-M205 | 9962-001-IS-155-PVM-B-205 | GA & DATASHEET OF LINEAR ACTUATOR FOR WAGON TIPPLER
210 | IS-1-PI-713-103-M206 | 9962-001-IS-155-PVM-B-206 | HYDRAULIC SYSTEM DRAWINGS FOR SIDE ARM CHARGER
211 | IS-4-DC-713-111-M207 | 9962-001-IS-155-PVM-B-207 | SIZING CALCULATION AIR CONDITIONING SYSTEM WT CONTROL ROOM
212 | IS-3-GA-713-103-M208 | 9962-001-IS-155-PVM-B-208 | ARRANGEMENT & FOUNDATION DETAILS OF MECHANICAL STOPPER (TRACK STOP)
213 | IS-3-GA-713-103-M209 | 9962-001-IS-155-PVM-B-209 | GA OF GEARBOX FOR APRON FEEDER
214 | IS-1-GA--103-M210 | 9962-001-IS-155-PVM-B-210 | GEN. ARRGT. OF TRANSFER SHIFTER & PUSHER
215 | IS-1-GA-713-103-M211 | 9962-001-IS-155-PVM-B-211 | FOUNDATION DETAILS OF TRANSFER WAGON SHIFTER & PUSHER
216 | IS-1-GA-713-107-M215 | 9962-001-IS-155-PVM-B-215 | GA OF CRUSHER (RING GRANULATOR) | 90
217 | IS-1-GA-713-107-M216 | 9962-001-IS-155-PVM-B-216 | GA OF VIBRATING GRIZZLY FEEDER (INCLUDING TECH. DATA SHEET) | 90
218 | IS-1-GA-713-107-M217 | 9962-001-IS-155-PVM-B-217 | GA OF SCOOP TYPE COUPLING FOR RING GRANULATOR | 95
219 | IS-1-GA-713-107-M218 | 9962-001-IS-155-PVM-B-218 | G.A. OF VIBRATION ISOLATION SYSTEM FOR CRUSHERS | 90
220 | IS-4-QP-713-101-Q001 | 9962-001-IS-155-QVM-Q-001 | INSPECTION PLAN FOR CONVEYOR PACKAGE | 25
221 | IS-4-QP-713-101-Q002 | 9962-001-IS-155-QVM-Q-002 | PG TEST PROCEDURE FOR CHP | 266
222 | IS-4-QP-713-101-Q003 | 9962-001-IS-155-QVM-G-003 | FIELD QUALITY PLAN FOR CHP MECHANICAL | 245
223 | IS-4-QP-713-103-Q004 | 9962-001-IS-155-QVM-Q-004 | QAP FOR WAGON TIPPLER
224 | IS-4-QP-713-103-Q005 | 9962-001-IS-155-QVM-Q-005 | QAP FOR SIDE ARM CHARGER
225 | IS-4-QP-713-103-Q006 | 9962-001-IS-155-QVM-Q-006 | QAP FOR APRON FEEDER
226 | IS-4-QP-713-103-Q007 | 9962-001-IS-155-QVM-Q-007 | QAP OF DRIBBLE CONVEYOR BELT
227 | IS-4-QP-713-103-Q008 | 9962-001-IS-155-QVM-Q-008 | QAP OF GRID OVER WAGON TIPPLER HOPPER
228 | IS-4-QP-713-103-Q009 | 9962-001-IS-155-QVM-Q-009 | QAP OF LUBRICATION SYSTEM FOR APRON FEEDER
229 | IS-4-QP-713-103-Q010 | 9962-001-IS-155-QVM-Q-010 | QAP OF WEIGH BRIDGE FOR WAGON TIPPLER
230 | IS-4-QP-713-103-Q011 | 9962-001-IS-155-QVM-Q-011 | QAP OF HYDRAULIC POWER PACK FOR WAGON TIPPLER & SAC
231 | IS-4-QP-713-103-Q012 | 9962-001-IS-155-QVM-Q-012 | QAP OF HYDRAULIC CYLINDER FOR WAGON TIPPLER, SAC, WAGON SHIFTER AND PUSHER
232 | IS-5-QP-713-103-Q013 | 9962-001-IS-155-QVM-Q-013 | QAP OF WAGON SHIFTER & PUSHER
233 | IS-4-QP-713-107-Q014 | 9962-001-IS-155-QVM-Q-014 | QAP- RING GRANULATOR CRUSHER | 100
234 | IS-4-QP-713-107-Q015 | 9962-001-IS-155-QVM-Q-015 | QAP-VIBRATING GRIZZLY FEEDER | 100
235 | IS-4-QP-713-108-Q016 | 9962-001-IS-155-QVM-Q-016 | QAP OF STACKER RECLAIMER
236 | IS-4-QP-713-108-Q017 | 9962-001-IS-155-QVM-Q-017 | QAP OF CABLE REELING DRUM FOR SCR
237 | IS-4-QP-713-108-Q018 | 9962-001-IS-155-QVM-Q-018 | QAP OF FLAP GATE | 65
238 | IS-4-QP-713-108-Q019 | 9962-001-IS-155-QVM-Q-019 | QAP FOR LUBRICATION SYSTEM FOR STACKER CUM RECLAIMER
239 | IS-4-QP-713-108-Q020 | 9962-001-IS-155-QVM-Q-020 | QAP OF BRAKE FOR SCR
240 | IS-4-QP-713-108-Q021 | 9962-001-IS-155-QVM-Q-021 | QAP OF CONVEYOR BELT FOR SCR
241 | IS-4-QP-713-108-Q022 | 9962-001-IS-155-QVM-Q-022 | QAP OF AUTOMATIC RAIL CLAMP FOR SCR
242 | IS-4-QP-713-108-Q023 | 9962-001-IS-155-QVM-Q-023 | QAP OF GEARBOX FOR SCR
243 | IS-4-QP-713-108-Q024 | 9962-001-IS-155-QVM-Q-024 | QAP OF HYD EQUIPMENT FOR LUFFING SYSTEM, CABIN LEVELLING & OTHER CYLINDER FOR SCR
244 | IS-4-QP-713-108-Q025 | 9962-001-IS-155-QVM-Q-025 | QAP OF SLEW GEAR
245 | IS-4-QP-713-108-Q026 | 9962-001-IS-155-QVM-Q-026 | QAP OF FLUID COUPLING FOR SCR
246 | IS-4-QP-713-108-Q027 | 9962-001-IS-155-QVM-Q-027 | QAP OF DS SYSTEM FOR SCR
247 | IS-4-QP-713-108-Q028 | 9962-001-IS-155-QVM-Q-028 | QAP OF E-HOUSE FOR SCR
248 | IS-4-QP-713-108-Q029 | 9962-001-IS-155-QVM-Q-029 | QAP OF OPERATOR'S CABIN FOR SCR
249 | IS-4-QP-713-110-Q030 | 9962-001-IS-155-QVM-Q-030 | QAP OF DS, SW, PW & SA SYSTEM FOR CHP
250 | IS-4-QP-713-110-Q031 | 9962-001-IS-155-QVM-Q-031 | QAP OF SUMP PUMP | 125
251 | IS-4-QP-713-111-Q032 | 9962-001-IS-155-QVM-Q-032 | QAP FOR EOT CRANE
252 | IS-4-QP-713-111-Q033 | 9962-001-IS-155-QVM-Q-033 | QAP OF IDLERS | 60
253 | IS-4-QP-713-111-Q034 | 9962-001-IS-155-QVM-Q-034 | QAP OF PULLEY | 65
254 | IS-4-QP-713-111-Q035 | 9962-001-IS-155-QVM-Q-035 | QAP OF TECHNOLOGICAL STRUCTURE | 46
255 | IS-4-QP-713-111-Q036 | 9962-001-IS-155-QVM-Q-036 | QAP OF TRAVELLING TRIPPER | 81
256 | IS-4-QP-713-111-Q037 | 9962-001-IS-155-QVM-Q-037 | QAP OF VIBRATING FEEDER IN ERH | 105
257 | IS-4-QP-713-111-Q038 | 9962-001-IS-155-QVM-Q-038 | QAP OF RPG & ROD GATES | 65
258 | IS-4-QP-713-111-Q039 | 9962-001-IS-155-QVM-Q-039 | QAP OF GEAR BOX | 116
259 | IS-4-QP-713-111-Q040 | 9962-001-IS-155-QVM-Q-040 | QAP OF FLUID COUPLING | 120
260 | IS-4-QP-713-111-Q041 | 9962-001-IS-155-QVM-Q-041 | QAP OF GEAR COUPLING | 120
261 | IS-4-QP-713-111-Q042 | 9962-001-IS-155-QVM-Q-042 | QAP OF SCOOP TYPE COUPLING FOR RING GRANULATOR | 125
262 | IS-4-QP-713-111-Q043 | 9962-001-IS-155-QVM-Q-043 | QAP OF VIBRATION ISOLATION SYSTEM | 116
263 | IS-4-QP-713-111-Q044 | 9962-001-IS-155-QVM-Q-044 | QAP OF METAL DETECTOR | 96
264 | IS-4-QP-713-111-Q045 | 9962-001-IS-155-QVM-Q-045 | QAP OF BELT WEIGHERS | 123
265 | IS-4-QP-713-111-Q046 | 9962-001-IS-155-QVM-Q-046 | QAP OF COAL SCOOPER | 130
266 | IS-4-QP-713-111-Q047 | 9962-001-IS-155-QVM-Q-047 | QAP OF BELT VULCANIZING MACHINE | 151
267 | IS-4-QP-713-111-Q048 | 9962-001-IS-155-QVM-Q-048 | QAP OF MAGNETIC SEPARATORS | 116
268 | IS-4-QP-713-111-Q049 | 9962-001-IS-155-QVM-Q-049 | QAP OF SUSPENDED MAGNET | 116
269 | IS-4-QP-713-111-Q052 | 9962-001-IS-155-QVM-Q-052 | QAP OF ELEVATOR FOR CHP | 125
270 | IS-4-QP-713-111-Q053 | 9962-001-IS-155-QVM-Q-053 | QAP OF COAL SAMPLING UNIT | 145
271 | IS-4-QP-713-111-Q054 | 9962-001-IS-155-QVM-Q-054 | QAP OF RESILIENT COUPLING | 120
272 | IS-4-QP-713-101-Q055 | 9962-001-IS-155-QVM-Q-055 | QAP OF CONVEYOR BELTING | 245
273 | IS-4-QP-713-111-Q056 | 9962-001-IS-155-QVM-Q-056 | QAP OF DE SYSTEM EQUIPMENTS | 130
274 | IS-4-QP--111-Q057 | 9962-001-IS-155-QVM-Q-057 | QAP OF BRAKE FOR BELT FEEDER AND TRIPPER | 110
275 | IS-4-QP-713-111-Q058 | 9962-001-IS-155-QVM-Q-058 | QAP OF ELECTRIC HOIST | 155
276 | IS-4-QP-713-111-Q059 | 9962-001-IS-155-QVM-Q-059 | QAP OF MANUAL HOIST & CHAIN PULLEY BLOCK | 155
277 | IS-4-QP-713-111-Q060 | 9962-001-IS-155-QVM-Q-060 | QAP OF ACTUATOR FOR FLAPGATE, DIVERTER GATER & RP GATE | 135
278 | IS-4-QP-713-111-Q061 | 9962-001-IS-155-QVM-Q-061 | QAP OF RAIL CLAMP FOR TRIPPER | 112
279 | IS-4-QP-713-111-Q062 | 9962-001-IS-155-QVM-Q-062 | QAP OF EXTERNAL SCRAPPERS & SKIRT SEALING | 128
280 | IS-4-QP-713-111-Q063 | 9962-001-IS-155-QVM-Q-063 | QAP OF BELT FOR BELT FEEDER & BUNKER SEALING | 225
281 | IS-1-GA-713-101-M221 | 9962-001-IS-109-PVM-B-221 | G.A. & LOAD DATA OF LIMESTONE CONV. BCN-1A/B | 30 | 265
282 | IS-1-GA-713-101-M222 | 9962-001-IS-109-PVM-B-222 | G.A. & LOAD DATA OF LIMESTONE CONV. BCN-2A/B | 32 | 268
283 | IS-1-GA-713-101-M223 | 9962-001-IS-109-PVM-B-223 | G.A. & LOAD DATA OF LIMESTONE BELT FEEDER-1 | 35 | 270
284 | IS-1-GA-713-101-M224 | 9962-001-IS-109-PVM-B-224 | G.A. & LOAD DATA OF LIMESTONE BELT FEEDER-2A/B | 40 | 272
285 | IS-1-GA-713-101-M225 | 9962-001-IS-109-PVM-B-225 | G.A. & LOAD DATA OF GYPSUM CONV. BCN-1A/B | 42 | 275
286 | IS-1-GA-713-104-M226 | 9962-001-IS-109-PVM-B-226 | G.A. & LOAD DATA OF TRANSFER TOWER TP-1 | 35 | 270
287 | IS-1-GA-713-104-M227 | 9962-001-IS-109-PVM-B-227 | G.A. & LOAD DATA OF LHP CRUSHER HOUSE#LHP CRH | 40 | 272
288 | IS-1-GA-713-104-M228 | 9962-001-IS-109-PVM-B-228 | G.A. OF LHP RECLAIME HOPPER COMPLEX | 25
289 | IS-1-GA-713-107-M229 | 9962-001-IS-109-PVM-B-229 | GA OF CRUSHER (HAMMEL MILL) | 90
290 | IS-1-GA-713-107-M230 | 9962-001-IS-109-PVM-B-230 | GA OF VIBRATING SCREEN | 95
291 | IS-1-GA-713-107-M231 | 9962-001-IS-109-PVM-B-231 | GA OF VIBRATING FEEDER | 95
292 | IS-1-GA-713-107-M232 | 9962-001-IS-109-PVM-B-232 | GA OF BUCKET ELEVATOR | 120
293 | IS-4-QP-713-107-Q064 | 9962-001-IS-109-QVM-Q-064 | QAP FOR HAMMER MILL CRUSHER | 120
294 | IS-5-QP-713-107-Q065 | 9962-001-IS-109-QVM-Q-065 | QAP FOR BUCKE ELEVATOR | 130
B | ELECTRICAL AND C&I
1 | IS-4-GA-713-100-E146 | 9962-001-IS-155-PVE-B-146 | GA & DATASHEET OF LT TRANSFORMER (STACKER RECLAIMER)
2 | IS-4-QP-713-100-E147 | 9962-001-IS-155-QVE-P-147 | QAP OF LT TRANSFORMER FOR SCR MACHINE
3 | IS-4-LL-713-108-E148 | 9962-001-IS-155-PVE-P-148 | SCR MACHINE ELCTRICAL LOAD LIST
4 | IS-4-GA-713-108-E149 | 9962-001-IS-155-PVE-B-149 | GA, BOM OF SCR MACHINE LT MCC
5 | IS-4-SL-713-108-E150 | 9962-001-IS-155-PVE-P-150 | SLD OF SCR MACHINE LT MCC
6 | IS-4-CI-713-108-E151 | 9962-001-IS-155-PVE-S-151 | CONTROL SCHEME OF SCR MACHINE LT MCC
7 | IS-4-DC-713-108-E152 | 9962-001-IS-155-PVE-P-152 | SCR MACHINE TRANSFORMER SIZING CALCULATION
8 | IS-4-GA-713-108-E153 | 9962-001-IS-155-PVE-B-153 | GA, DATASHEET, TB DWGS, CHAR. CURVES OF LT MOTOR FOR SCR MACHINE
9 | IS-4-QP-713-101-E154 | 9962-001-IS-155-QVE-P-154 | QAP OF LT MOTORS FOR SCR MACHINE
10 | IS-4-GA-713-100-E155 | 9962-001-IS-155-PVE-B-155 | GA OF E-HOUSE WITH EQUIPMENT LOCATION FOR SCR MACHINE
11 | IS-4-EE-713-100-E156 | 9962-001-IS-155-PVE-F-156 | ELECTRICAL EQUIPMENT LAYOUT IN OPERATOR CABIN FOR SCR MACHINE
12 | IS-4-GA-713-100-E157 | 9962-001-IS-155-PVE-B-157 | GA, DATA SHEET AND CATALOGUES OF FIELD DEVICES FOR SCR MACHINE
13 | IS-4-GA-713-100-E158 | 9962-001-IS-155-PVE-B-158 | GA, DATASHEET & BOM OF RECEPTACLES FOR SCR MACHINE
14 | IS-4-QP-713-100-E160 | 9962-001-IS-155-QVE-P-160 | QAP OF PLC FOR SCR MACHINE
15 | IS-4-IO-713-100-E161 | 9962-001-IS-155-PVE-G-161 | PLC I/O LIST SCR MACHINE
16 | IS-4-CF-713-100-E162 | 9962-001-IS-155-PVE-P-162 | PLC CONFIGURATION SCR MACHINE
17 | IS-4-GA-713-100-E163 | 9962-001-IS-155-PVE-B-163 | GA, BOM, SCHEMES OF PLC FOR SCR MACHINE
18 | IS-4-GA-713-100-E164 | 9962-001-IS-155-PVE-B-164 | GA, DATASHEET OF UPS FOR SCR MACHINE PLC
19 | IS-4-QP-713-100-E165 | 9962-001-IS-155-QVE-P-165 | QAP OF UPS FOR SCR MACHINE PLC
20 | IS-4-GA-713-100-E166 | 9962-001-IS-155-PVE-B-166 | GA, SCHEMES OF CONTROL DESK FOR SCR MACHINE
21 | IS-4-QP-713-100-E167 | 9962-001-IS-155-QVE-P-167 | QAP OF CONTROL DESK FOR SCR MACHINE
22 | IS-4-CS-713-100-E168 | 9962-001-IS-155-PVE-H-168 | POWER CABLE SCHEDULE SCR MACHINE
23 | IS-4-CS-713-100-E169 | 9962-001-IS-155-PVE-H-169 | CONTROL & INSTRUMENTATION CABLE SCHEDULE FOR SCR MACHINE
24 |  |  | TRAILING CABLE SIZING CALCULATIONS FOR SCR MACHINE
25 |  |  | DATA SHEET OF HT TRAILING CABLE FOR SCR MACHINE
26 |  |  | QAP OF HT TRAILING CABLE FOR SCR MACHINE
27 |  |  | DATA SHEET OF CONTROL TRAILING CABLE FOR SCR MACHINE
28 |  |  | QAP OF CONTROL TRAILING CABLE FOR SCR MACHINE
29 |  |  | GA DRAWINGS, SCHEMES OF HT LOAD BREAK SWITCH FOR SCR MACHINE
30 |  |  | EQUIPMENT LOCATION ,CABLE TRAY ROUTING,EARTHING &LIGHTING LAYOUT OF SCR MACHINE
31 |  |  | GA DRAWING OF CONTROL JUNCTION BOX AT CENTER OF TRAVEL OR LAND MOUNTED CONTROL JUNCTION BOX
32 |  |  | GA DRAWINGS, SCHEMES OF VFD PANEL FOR SCR MACHINE
33 |  |  | OPERATIONAL CONTROL PHILOSOPHY FOR SCR MACHINE
34 |  |  | DATA SHEET / CATALOGUES OF LIGHTING FIXTURES FOR SCR MACHINE
35 |  |  | GA DRAWINGS, SCHEMES OF LIGHTING DISTRIBUTION BOARD FOR SCR MACHINE
36 |  |  | LIST OF FIELD DEVICES FOR SCR MACHINE
37 |  |  | QAP OF FIELD DEVICES FOR SCR MACHINE
38 |  |  | GA DRAWINGS, SCHEMES OF 3-D STOCKPILE VOLUME/QTY MEASUREMENT SYSTEM
39 | IS-4-LL-713-103-E173 | 9962-155-PVE-P-173 | WT & SAC MACHINE ELCTRICAL LOAD LIST
40 | IS-4-GA-713-103-E174 | 9962-155-PVE-B-174 | GA, DATASHEET, TB DWGS, CHAR. CURVES OF LT MOTOR FOR WT & SAC MACHINE
41 | IS-4-EE-713-100-E175 | 9962-155-PVE-F-175 | ELECTRICAL EQUIPMENT LAYOUT FOR WT & SAC CONTROL ROOM
42 | IS-4-GA-713-100-E176 | 9962-155-PVE-B-176 | GA, DATASHEET AND CATALOGUES OF FIELD DEVICES FOR WT & SAC MACHINE
43 | IS-4-QP-713-100-E177 | 9962-155-QVE-P-177 | QAP OF PLC FOR WT & SAC MACHINE
44 | IS-4-IO-713-100-E178 | 9962-155-PVE-P-178 | PLC I/O LIST WT & SAC MACHINE
45 | IS-4-CF-713-100-E179 | 9962-155-PVE-P-179 | PLC CONFIGURATION WT & SAC MACHINE
46 | IS-4-GA-713-100-E180 | 9962-155-PVE-B-180 | GA, BOM, SCHEMES OF PLC FOR WT & SAC MACHINE
47 | IS-4-GA-713-100-E181 | 9962-155-PVE-B-181 | GA, DATASHEET OF UPS FOR WT & SAC MACHINE PLC
48 | IS-4-QP-713-100-E182 | 9962-155-QVE-P-182 | QAP OF UPS FOR WT & SAC MACHINE PLC
49 | IS-4-GA-713-100-E183 | 9962-155-PVE-B-183 | GA, SCHEMES OF CONTROL DESK FOR WT & SAC MACHINE
50 | IS-4-QP-713-100-E184 | 9962-155-QVE-P-184 | QAP OF CONTROL DESK FOR WT & SAC MACHINE
51 | IS-4-CS-713-100-E187 | 9962-155-PVE-H-187 | POWER CABLE SCHEDULE WT & SAC MACHINE
52 | IS-4-CS-713-100-E188 | 9962-155-PVE-H-188 | CONTROL & INSTRUMENTATION CABLE SCHEDULE FOR WT & SAC MACHINE
53 | IS-4-QP-713-100-E189 | 9962-155-QVE-P-189 | QAP OF LT MOTORS FOR WT & SAC MACHINE
54 |  |  | GA DRAWINGS, SCHEMES OF VFD PANEL FOR APRON FEEDER
55 |  |  | OPERATIONAL CONTROL PHILOSOPHY FOR WT & SAC MACHINE
56 |  |  | LIST OF FIELD DEVICES FOR WT & SAC MACHINE
57 |  |  | QAP OF FIELD DEVICES FOR WT & SAC MACHINE
58 |  |  | CABLE TRAY AND EARTHING LAYOUT OF WT COMPLEX
59 |  |  | CABLE TRAY AND EARTHING LAYOUT FOR WT & SAC CONTROL ROOM
60 |  |  | PLC LOGIC AND HMI SCREEN DIAGRAMS FOR WT & SAC MACHINE
61 | IS-4-GA-713-100-E044 | 9962-155-PVE-B-044 | GA, DATASHEET, WIRING DIAGRAM OF LPBS FOR CHP AND LHP & AHP
62 | IS-4-QP-713-100-E045 | 9962-155-QVE-P-045 | QAP OF LPBS FOR CHP AND LHP & AHP
63 | IS-4-GA-713-101-E046 | 9962-155-PVE-B-046 | GA, DATASHEET, TB DWGS, CHAR. CURVES OF LT MOTOR FOR CONVEYORS
64 | IS-4-GA-713-100-E047 | 9962-155-PVE-B-047 | GA, BOQ, WIRING DIAGRAM OF BELT MONITORING SYSTEM PANEL
65 | IS-4-QP-713-100-E048 | 9962-155-QVE-P-048 | QAP OF BELT MONITORING SYSTEM PANEL
66 | IS-4-GA-713-100-E049 | 9962-155-PVE-B-049 | GA, BOQ, WIRING DIAGRAM OF DUST EXTRACTION SYSTEM PANEL
67 | IS-4-QP-713-100-E050 | 9962-155-QVE-P-050 | QAP OF DUST EXTRACTION SYSTEM PANEL
68 | IS-4-GA-713-100-E051 | 9962-155-PVE-B-051 | GA, BOQ, WIRING DIAGRAM OF TRAVELLING TRIPPER PANEL
69 | IS-4-QP-713-100-E052 | 9962-155-QVE-P-052 | QAP OF TRAVELLING TRIPPER PANEL
70 | IS-4-GA-713-100-E053 | 9962-155-PVE-B-053 | GA, BOQ, WIRING DIAGRAM OF METAL DETECTOR PANEL
71 | IS-4-GA-713-100-E054 | 9962-155-PVE-B-054 | GA, BOQ, WIRING DIAGRAM OF ILMS AND SM PANEL
72 | IS-4-GA-713-100-E055 | 9962-155-PVE-B-055 | GA, BOQ, WIRING DIAGRAM OF SCOOP COUPLING PANEL FOR CONVEYORS
73 | IS-4-GA-713-100-E056 | 9962-155-PVE-B-056 | GA, BOQ, WIRING DIAGRAM OF COAL SAMPLING UNIT CONTROL PANEL
74 | IS-4-QP-713-100-E057 | 9962-155-QVE-P-057 | QAP OF COAL SAMPLING UNIT CONTROL PANEL
75 | IS-4-OP-713-100-E058 | 9962-155-PVE-P-058 | CONTROL WRITE UP -CHP, LHP and GHP
76 | IS-4-GA-713-100-E059 | 9962-155-PVE-B-059 | GA, DATASHEET OF ZSS, PCS, CBS & BSS FOR CHP AND LHP & AHP
77 | IS-4-QP-713-100-E060 | 9962-155-QVE-P-060 | QAP OF ZSS, PCS, CBS & BSS FOR CHP AND LHP & AHP
78 | IS-4-SC-713-100-E061 | 9962-155-PVE-H-061 | SAFETY SWITCHES SCHEDULE (ZSS,BSS,PCS,CBS) FOR CHP AND LHP & AHP
79 | IS-4-QP-713-100-E062 | 9962-155-QVE-P-062 | QAP OF LT MOTORS FOR CONVEYORS
80 | IS-4-GA-713-100-E042 | 9962-109-PVE-B-042 | GA, DATASHEET, TB DWGS, CHAR. CURVES OF LT MOTOR FOR LHP-GHP
81 | IS-4-QP-713-100-E043 | 9962-109-QVE-P-043 | QAP OF LT MOTORS FOR LHP-GHP
82 |  |  | LOAD LIST FOR CHP AND LHP & AHP
83 |  |  | GA OF POWER JUNCTION BOX FOR CHP AND LHP & AHP
84 |  |  | GA OF CONTROL JUNCTION BOX FOR CHP AND LHP & AHP
85 |  |  | GA, BOQ, WIRING DIAGRAM OF SCOOP COUPLING PANEL FOR CRUSHERS
86 |  |  | GA, BOQ, WIRING DIAGRAM OF LIME SAMPLING UNIT CONTROL PANEL
87 |  |  | QAP OF LIME SAMPLING UNIT CONTROL PANEL
88 |  |  | GA, BOQ, WIRING DIAGRAM OF VENTILATION SYSTEM PANEL
89 |  |  | QAP OF VENTILATION SYSTEM PANEL
90 |  |  | GA, BOQ, WIRING DIAGRAM OF AIR CONDITIONING SYSTEM PANEL
91 |  |  | QAP OF AIR CONDITIONING SYSTEM PANEL
92 |  |  | GA, DATASHEET, TB DWGS, CHAR. CURVES OF LT MOTOR FOR COMPRESSORS
93 |  |  | DCS INPUT OUTPUT LIST -FOR CHP AND LHP & AHP.
94 |  |  | INTERCONNECTION CABLE TERMINATION CHARTS-FOR CONVEYOR PACKAGE
95 |  |  | CABLE SCHEDULE FOR FOR CONVEYOR PACKAGE - POWER CABLES -LT
96 |  |  | CABLE SCHEDULE FOR FOR CONVEYOR PACKAGE- CONTROL
97 |  |  | CABLE SCHEDULE FOR FOR CONVEYOR PACKAGE - INSTRUMENTATION
98 |  |  | GA, TECHNICAL DETAILS & WIRING SCHEME OF ACDB/PDB FOR CHP AND LHP & AHP
99 |  |  | ELECTRICAL AND C&I MANDATORY SPARES LIST FOR FOR CHP AND LHP & AHP
100 |  |  | G.A & DATA SHEET OF HOOTER/SIREN FOR CHP AND LHP & AHP
101 |  |  | DATA SHEET FOR TEMP TRANSMITTER WITH JB FOR FOR CHP AND LHP & AHP.
102 |  |  | HMI DETAILS ( GRAPHICS,LOG,REPORT,ALARM ETC ) INPUT FOR CHP AND LHP & AHP.
103 |  |  | GA, TECHNICAL DETAILS & WIRING SCHEME OF BELT WEIGHER
104 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-1
105 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-2
106 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CRUSHER HOUSE CRH
107 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-3
108 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-4
109 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-5
110 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-6
111 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-7
112 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-8
113 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-9
114 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-10
115 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-11
116 |  |  | CABLE TRAY AND EARTHING LAYOUT OF JUNCTION TOWER JT-12
117 |  |  | CABLE TRAY AND EARTHING LAYOUT OF EMERGENCY RECLAIM HOPPER
118 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CRUSHER HOUSE
119 |  |  | CABLE TRAY AND EARTHING LAYOUT OF DS PUMP HOUSE-1
120 |  |  | CABLE TRAY AND EARTHING LAYOUT OF DS PUMP HOUSE-2
121 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-1A/B
122 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-2A/B
123 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-3A/B
124 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-3C/D
125 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-4A/B
126 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-4C/D
127 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-5A/B
128 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-6A/B
129 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-7A/B
130 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. BC-8A/B
131 |  |  | CABLE TRAY AND EARTHING LAYOUT OF CONV. RC-1A/B
132 |  |  | CABLE TRAY AND EARTHING LAYOUT OF YARD CONV. YBC-1A
133 |  |  | CABLE TRAY AND EARTHING LAYOUT OF YARD CONV. YBC-1B
134 |  |  | CABLE TRAY AND EARTHING LAYOUT OF BUNKER CONV. TBC-1A/B
135 |  |  | CABLE TRAY AND EARTHING LAYOUT OF BUNKER CONV. TBC-2A/B
136 |  |  | CABLE TRAY AND EARTHING LAYOUT OF LIMESTONE CONV. BCN-1A/B
137 |  |  | CABLE TRAY AND EARTHING LAYOUT OF LIMESTONE CONV. BCN-2A/B
138 |  |  | CABLE TRAY AND EARTHING LAYOUT OF GYPSUM CONV. BCN-1A/B
139 |  |  | CABLE TRAY AND EARTHING LAYOUT OF TRANSFER TOWER TP-1
140 |  |  | CABLE TRAY AND EARTHING LAYOUT OF LHP CRUSHER HOUSE#LHP CRH
141 |  |  | CABLE TRAY AND EARTHING LAYOUT OF LHP RECLAIME HOPPER COMPLEX
142 | IS-4-GA-713-100-E190 | 9962-001-IS-155-PVE-B-190 | GA, DATASHEET, TB DWGS, CHAR. CURVES OF LT MOTOR FOR DS SYSTEM
143 | IS-4-GA-713-100-E191 | 9962-001-IS-155-PVE-B-191 | GA, BOQ, WIRING DIAGRAM OF DUST SUPRESSION SYSTEM PANEL
144 | IS-4-QP-713-100-E192 | 9962-001-IS-155-QVE-P-192 | QAP OF DUST SUPRESSION SYSTEM PANEL
145 | IS-4-CS-713-100-E193 | 9962-001-IS-155-PVE-H-193 | POWER, CONTROL & INSTRUMENTATION CABLE SCHEDULE FOR DUST SUPRESSION SYSTEM
146 | IS-4-QP-713-100-E194 | 9962-001-IS-155-QVE-P-194 | QAP OF LT MOTORS FOR DS SYSTEM