## Sheet1
Details of contracts concluded during the Period (25.03.2007 TO 24.03.2008) by SAS Nagpur
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Tender No. | Items/ Nature of work | Mode of Tender Enqriry | Date of Publication of NIT | Type of bidding (Single/ Two Bid System | Last Date of receipt of tender | Nos. of tender recd. | Nos. and Names of Parties Qualified after technical evaluation | Nos. and Names of Parties Qualified not Qualified after technical evaluation | Whether contract awarded to lowest tenderer/Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contractor | Scheduled date of completion of supplies
PUR/SER/NGP/07/001 30.04.2007 | Bearing inspection alignment and casing centering ,Roll chech and Bump check of HP/IP ,CRH,NRV of 210 KMW Unit # 3,Khaperkheda.TPS | Limited | 30.04.2007 | Two Bid | 02.05.2007 | 5 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. . | 1 parties not responded | Yes | PUR/SER/NGP/07/01 30.04.2007 | M/s.Indwell construction Pvt. Ltd. | 2,96,550 | 03.05.2007 to 04.05.2007
PUR/SER/NGP/07/003 31.05.2007 | AOH of TG set of 210 MW of U # 3 ,SGTPS,Birsinghpur | Limited | 31.05.2007 | Two Bid | 07.06.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. | 1 parties not responded | Yes | PUR/SER/NGP/06/42 31.05.2007 | M/s.Power Mech Projects Pvt. Ltd | 20,60,000 | 22.06.2007 to 22.07.2007
PUR/SER/NGP/07/004 15.06.2007 | AOH of HP,LP,IP ,Generator ,Exiter, Valve at Unit # 2,250 MW, REL,Dahanu | Limited | 15.06.2007 | Two Bid | 25.06.07 | 6 | 1.Vasvi Power Servising Pvt.Ltd. 2.M/s.Power Mech Projects Pvt. Ltd. | 3 parties not responded | Yes | PUR/SER/NGP/07/04 15.06.2007 | Vasvi Power Servising Pvt.Ltd. | 32,50,000 | 07.07.2007 to 15.07.2007
PUR/SER/NGP/07/05 08.06.2007 | Minor OH of 540 MW ,Inspecion of Brg.,Strs and COH of generator in Unit # 4 | Limited | 08.06.2207 | Two Bid | 19.06.2007 | 6 | 1.Vasvi Power Servising Pvt.Ltd. 2.M/s.Power Mech Projects Pvt. Ltd. | 4 parties not responded | Yes | PUR/SER/NGP/07/05 08.06.2007 | M/s.Power Mech Projects Pvt. Ltd | 21,58,000 | 01.07.2007 to 23.08.2007
PUR/SER/NGP/07/006 21.06.2007 | AOH of TG set of Unit # 1at CSEB Korba West | Limited | 21.06.2007 | Two Bid | 25.06.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. | 2 parties not responded | Yes | PUR/SER/NGP/07/06 21.06.2007 | Alpha Power Engg.Ser.Pvt Ltd | 10,32,000 | 29.06.2007 to 11.07.2007
PUR/SER/NGP/07/007 26.06.2007 | E&C of HP Heater of 3x200 MW at NTPC Korba | Limited | 26.06.2007 | Two Bid | 05.07.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. | 3 parties not responded | Yes | PUR/SER/NGP/07/007 26.06.2007 | M/s.Indwell construction Pvt. Ltd. | 24,00,000 | 19.09.2007 to
PUR/SER/NGP/07/008 28.06.2007 | OH of all valves,MS/HRH Strainers in TG set of Unit # 8 & COH of Generator,Exciter,Gen.OH of Turbine & Replt.of Brgs.(OPT) in Unit # 9. | Limited | 28.06.2007 | Two Bid | 05.07.2207 | 6 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. | 2 parties not responded | Yes | PUR/SER/NGP/07/008 28.06.2007 | M/s.Power Mech Projects Pvt. Ltd | 25,90,000 | 11.07.2007 to 24.07.2007
PUR/SER/NGP/07/009 12.07.2007 | AOH of TG set of Unit # 3 at CSEB,Korba West | Limited | 12.07.2007 | Two Bid | 19.07.2207 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. |  | Yes | PUR/SER/NGP/07/009 12.07.2007 | Alpha Power Engg.Ser.Pvt Ltd | 12,00,000 | 25.07.2007 to 19.08.2007
PUR/SER/NGP/07/010 07.07.2007 | Brg.Inspection (No.1 to 7),Brg Replt.and Reaming & Honing in Unit-4,210 Mw at KKT. | Limited | 07.07.2007 | Two Bid | 11.07.2007 | 5 | 1.Vasvi Power Servising Pvt.Ltd. 2.M/s.Power Mech Projects Pvt. Ltd. | 3 parties not responded | Yes | PUR/SER/NGP/07/010 07.07.2007 | M/s.Power Mech Projects Pvt. Ltd | 9,40,000 | 14.07.2007 to
PUR/SER/NGP/07/011 10.07.2007 | Work of cleaning & Hydraulic Test of H2 Exciter coolers,Air leak test of Generator & Replacement of MOP coupling,unit-7,500 MW at Chandrapur STPS | Limited | 10.07.2007 | Two Bid | 16.07.2007 | 7 | 1.Vasvi Power Servising Pvt.Ltd. 2.M/s.Power Mech Projects Pvt. Ltd. | 4 parties not responded | Yes | PUR/SER/NGP/07/011 10.07.2007 | Vasvi Power Servising Pvt.Ltd. | 6,75,000 | 27.07.2007 to 10.08.2007
PUR/SER/NGP/07/012 10.09.2007 | AOH of TG set of Unit # 2 at CSEB,Korba West | Limited | 10.09.2007 | Two Bid | 11.09.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2.Alpha Power Engg.Ser.Pvt Ltd. | 2 parties not responded | Yes | PUR/SER/NGP/07/012 10.09.2007 | M/s.Indwell construction Pvt. Ltd. | 22,00,000 | 28.09.2007 to 18.10.2007
PUR/SER/NGP/07/013 26.07.2007 | AOH of TG set of Unit # 3,120 Mw at MPPGCL,AMK | Limited | 26.07.2007 | Two Bid | 01.08.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Vasvi Power Servising Pvt.Ltd | 4 parties not responded | Yes | PUR/SER/NGP/07/013 26.07.2007 | Vasvi Power Servising Pvt.Ltd. | 9,36,000 | 12.08.2007 to 12.09.2007
PUR/SER/NGP/07/014 13.08.2007 | AOH of TG set of Unit # 4 at CSEB,Korba West | Limited | 13.08.2007 | Two Bid | 22.08.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. | 4 parties not responded | Yes | PUR/SER/NGP/07/014 13.08.2007 | Alpha Power Engg.Ser.Pvt Ltd | 23,00,000 | 30.08.2007 to 17.09.2007
PUR/SER/NGP/07/015 07.08.2007 | COH of TG set of Unit # 1,210 MW at MSPGCL,Birsunghpur | Limited | 07.08.2007 | Two Bid | 13.08.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. 4.Vasvi Power Servising Pvt.Ltd. 5.P.E.Erector Pvt.Ltd. | 1 parties not responded | Yes | PUR/SER/NGP/07/015 07.08.2007 | M/s.Indwell construction Pvt. Ltd. | 24,00,000 | 17.08.2007 to 18.09.2007
PUR/SER/NGP/07/016 14.08.2007 | 1.OH of HP,IP Turbine,CRHNRVs valves & MS HRH Strs. In Unit-1,200 MW 2.OH of Generator and core repaire | Limited | 14.08.2007 | Two Bid | 23.08.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. 4.P.E.Erector Pvt.Ltd. | 1 parties not responded | Yes | PUR/SER/NGP/07/016 14.08.2007 | P.E.Erector Pvt.Ltd | 27,00,000 | 23.09.2007 to 12.10.2007
PUR/SER/NGP/07/017 05.09.2007 | OH of HPT module at VSTPP (SINGLE TENDER BASIS) ,NTPC Vindhyachal , U-7 | Single | 05.09.2007 | Single | 07.09.02007 | 1 | 1.M/s.Power Mech Projects Pvt. Ltd. | Single | Yes | PUR/SER/NGP/07/017 05.09.2007 | M/s.Power Mech Projects Pvt. Ltd | 16,00,000 | 04.09.2007 to 28.09.2007
PUR/SER/NGP/07/018 26.09.2007 | OH of HP/IP/LP Turbine and Gen..valves & Str. In Unit-3 , 210 MW at KKT | Limited | 26.09.2007 | Two Bid | 01.10.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. | 4 parties not responded | Yes | PUR/SER/NGP/07/018 26.09.2007 | M/s.Power Mech Projects Pvt. Ltd | 23,00,000 | 09.10.2007 to 02.11.2007
PUR/SER/NGP/07/019 14.11.2007 | OH of HP/IP/LP Turbine and Gen..valves & Str.RLA Study in Unit-4,210 MW at Parli TPS | Limited | 14.11.2007 | Two Bid | 23.11.2007 | 7 | 1.Vasvi Power Servising Pvt.Ltd. 2.M/s.Power Mech Projects Pvt. Ltd 3.Eco Project Pvt. Ltd. | nil | Yes | PUR/SER/NGP/07/019 14.11.2007 | Vasvi Power Servising Pvt.Ltd. | 43,20,000 | 30.11.2007 to
PUR/SER/NGP/07/020 14.12.2007 | Chemical cleaning of Boiler Unit-4 at Parli TPs | Limited | 14.12.2007 | Two Bid | 20.12.2007 | 2 | 1.Aru Chemical Pvt.Ltd. 2.M/s Vallabha India Chemical Pvt Ltd. | 2 Parties not responded | Yes | PUR/SER/NGP/07/020 14.12.2007 | Aru Chemical Pvt.Ltd | 34,11,900 | 02.12.2007 to 21.01.2008
PUR/SER/NGP/07/021 12.12.2007 | E&C of Economiser structure & Hoists in Brg. No.5,Unit-5 at NTPC,KORBA | Limited | 12.12.2007 | Two Bid | 16.01.2008 | 11 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Sunil Hi-tech Energy Pvt.Ltd. | 7 parties not responded | Yes | PUR/SER/NGP/07/021 12.12.2007 | M/s.Power Mech Projects Pvt. Ltd | 33,99,900
PUR/SER/NGP/07/022 01.12.2007 | Taxt matter Typing,Tabular formating Drgs/Graphs&submi in soft/CD | Limited | 0 | Two Bid | 27.11.07 | 3 | 1SynergySolutions.2.Sricomp.3.V&T Computers | nil | Yes | PUR/SER/NGP/07/22 Dt01.12.07 | Ms Synergy Solutions | 14375 | 24 Months
PUR/SER/NGP/07/023 08.12.2007 | Gen.OH of Turbine,HPT,LPT valves,Strs.Oil sys.Modification in Unit-1 at MSPGCL,KKT | Limited | 08.12.2007 | Two Bid | 13.12.2007 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. 4.Vasvi Power Servi | 2 parties not responded | Yes | PUR/SER/NGP/07/023 08.12.2007 | Alpha Power Engg.Ser.Pvt Ltd | 18,85,000 | 15 days
PUR/SER/NGP/07/024 18.01.2008 | Gen.OH of LPT,Valves & Strs. Etc in Unit-2 at MSPGCL,KKT | Limited | 18.01.2008 | Two Bid | 21.01.2008 | 7 | 1.M/s.Indwell Constructions Pvt. Ltd. 2. M/s.Power Mech Projects Pvt. Ltd. 3.Alpha Power Engg.Ser.Pvt Ltd. | 1 parties not responded | Yes | PUR/SER/NGP/07/024 18.01.2008 | M/s.Power Mech Projects Pvt. Ltd | 15,04,100 | 15 days