ANNEXURE ‘B’

# COMMERCIAL TERMS AND CONDITIONS FOR INDIGENOUS ITMES

- PAYMENT TERMS: 80% payment of supplies shall be made with in 90 days from the date receipt of material and balance 20% after successful installation and commissioning of the equipment at our works and against submission of performance bank guarantee for 10% value valid till the guarantee period. Erection and commissioning charges (if any) shall be released only after satisfactory commissioning against certificate from competent authority.

2.	Vendor to quote price FOR BHEL, Bhopal basis. Transit insurance will be by BHEL for which vendor to fax dispatch documents immediately after despatch.

3.	Delivery shall be counted from the date of letter of intent. Quoted delivery period should include transit time from vendor’s works to BHEL, Bhopal.

- Penalty for late delivery shall be imposed @ ½% (half percent) per week subject to a maximum 10% of the contract value.

- Entire material should be despatched in one lot.  Part despatches not permissible/acceptable.

- Prices quoted shall be FIRM with validity up to 120 days and prices should remain Firm till execution of the contract.

- 5% of contract value bank guarantee is to be submitted for contract execution immediately after the placement of LOI (letter of intent) before the issue of confirmed Purchase Order and shall be valid till erection and commissioning.

- Machine will be inspected and proved at supplier’s work prior to despatch however, final inspection and acceptance of machine will be carried after installation of the machine at BHEL, Bhopal.

- Applicable service tax shall be paid extra by BHEL against invoice.

- Income tax deduction as per Govt. Guide line shall be deducted at source for which TDS certificate will be issued.

*****************