
Project:  TANGEDCO UDANGUDI SS 
Item :      N2 INJECTION FPS system [Supply + Services]
Subject:  Bid specific Additional Terms and Conditions

1. For any technical clarification, please contact Mr. Ayushi Jindal, Sr. Manager (TBEM); Contact No. 0120-6748459; e-mail: ayushi@bhel.in

2. For any commercial clarification, please contact Mr. Prateek Kumar, Dy. Manager (TBMM); Contact No. 0120- 6748480; e-mail: pkp@bhel.in 

3. Technical PQR – As per technical specification No. TB-400-552-126 Rev 00

4. Destination / Delivery Location: TANGEDCO Udangudi- Switchyard. Consignee details as per GEM contract.

5. Vendor Approval- For non-approved vendors “Bidder is required to submit Credentials like Registration Certificates, PAN/GSTIN, Financial soundness (ITRs, Audited Results), Work experience related documents (experience list, Performance /Completion Certificates from customers) along with bid. 

Bidder’s offer will be acceptable subject to final acceptance of vendor by ultimate customer as approved supplier.

6. Vendor to furnish “Quoted/Not Quoted” in unpriced bid given in Annexure-1.

7. Delivery Requirement: 31-Dec-2021. However, vendor to dispatch the material as per delivery plan mentioned in ACTIVITY SCHEDULE to meet the project requirement. In case, BHEL’s delivery requirement is not met by vendor(s), then a chance may be given to all such vendors to review their quoted delivery schedule in line with BHEL’s delivery requirement. However, if vendor fails to meet the requisite delivery plan, then BHEL reserves the right not to consider the offer of such vendor(s).

Tentatively Break up of delivery period: (Delay analysis for cases of delivery extension if required, shall be governed as per below schedule)-
	SL.
NO.
	ACTIVITY
	ACTIVITY TIME IN WEEKS

	1.
	Submission of documents necessary for getting manufacturing clearance like Drawings, data sheet etc. (In scope of vendor)
	02

	2.
	Review and Approval of documents and issue of manufacturing clearance (In scope of BHEL)
	03

	3.
	Manufacturing Time (In scope of vendor)
	10

	4.
	Inspection (In scope of BHEL)
	02

	5.
	Issue of MICC (In scope of BHEL)
	02

	6.
	Dispatch (In scope of vendor)
	01

	7
	ETC Work (Starting from clearance from site)
	12


Note – 1 - Supplier to ensure every revised submission incorporating comments within 1 weeks from the date of comments by BHEL.
	
	
	Vendor to mention as NIL deviation
	Remarks if any

	1.
	Schedule of Commercial Deviation, if any
(All terms and conditions shall be as per GeM except as mentioned above)
	
	

	2.
	Schedule of Technical Deviation, if any
(Against Technical Specification)
	
	



8. Reverse Auction – Bid to RA.

9. Prices: The quoted prices shall be on Firm basis. Price to be quoted as inclusive of GST. i.e. Ex-Works (Supply+ Spare+ ETC) + F&I + GST on FOR destination basis. Unloading at site is not in the scope of bidder. Bidders to quote price accordingly. Bidder to ensure that, minimum 20% of total Supply value shall be quoted under ETC. 

10. Payment Terms – Payment due date shall be as per GEM. 
(a) Supply Payment -  80% of payment of total contractual value shall be made upon submission of complete billing documents. Supplier has to provide the following documents for processing of bills:
[bookmark: _GoBack]•	Original GST Compliant Tax Invoice 
•	LR
•	original Packing List
•	original Guarantee Certificate
•	Copy of Transit Insurance Certificate from underwriters
•	CRAC (consignee receipt-cum-acceptance certificate)
•	Performance Bank Guarantee (PBG) 

(b) Balance 20% of payment shall be made upon submission of complete invoice along with Certificate of successful completion of successful Erection, Testing & Commissioning and Certificate of completion of final documentation as per Technical Specification issued by BHEL Engineering Management. 

(c) For Charges of Erection Testing and Commissioning – 100% of payment along with applicable GST from the date of receipt of complete GST compliant Tax invoice along with certificate of successful completion of Erection, Testing & Commissioning at Site issued by BHEL Site Official / Construction Management.

11. Local content - For this procurement, the local content to categorize a supplier as class-I local supplier / class-II local supplier / Non-Local supplier and purchase preference to class-I local supplier, is as defined in Public Procurement (Preference to Make in India), Order 2017 dated 04.06.2020, issued by DPIIT. In case of subsequent orders issued by the nodal ministry, changing the definition of local content for the items of the NIT, the same shall be applicable even if issued after issue of this NIT but before opening of part-II bids against this NIT. 
  
“This tender is not a global tender and only class-I and Class II suppliers as defined under the DPIIT order no. P-45021/2/2017-PP (BE-II) dated 04.06.2020 are eligible to bid in this tender. Bids received from Class-II & Non-Local supplier shall be rejected.”

12. Bidder to comply the below clause and submit the certification in their letter head. Non-compliance/ Non-submission of certification will lead to rejection of Offer.

i. Compliance to GOI Order for restrictions under Rule 144 (xi) of General Financial Rules (GFRs), 2017 (enclosed in Annexure-II)
ii. MOP circular dated 02-07-2020 (Annexure-III)
iii. Make In India Format as Annexure-IV

13. Performance Bank Guarantee: Supplier shall arrange to submit Performance BG along with first invoice. Performance BG shall be valid for 18 months from the date of last delivery with claim period of 3 months extra over and above 18 months. 

“Bidder agrees to submit performance security required for execution of the contract within the time period mentioned. In case of delay in submission of performance security, enhanced performance security which would include interest (SBI rate + 6%) for the delayed period, shall be submitted by the bidder. Further, if performance security is not submitted till such time the first bill becomes due, the amount of performance security due shall be recovered as per terms and conditions defined in NIT / Contract, from the bills along with due interest.”	

14. Liquidation Damage- Applicable as per GEM GTC.  However, calculation of LD for Main, Spares and Services shall be done separately, if the delay is not attributable to supplier.

All other terms & conditions shall be applicable as per GEM GTC.

· Bidder to mention their works address below from where material will be supplied to Site.

Works Address-      -------------------------------------------------
			------------------------------------------------
			-------------------------------------------------

Communication Address-      -------------------------------------------------
			                ------------------------------------------------
			                -------------------------------------------------
Person Name - -------------------------------------------------
Email ID – -------------------------------------------------
Contact no. - -------------------------------------------------







Annexure-1
	Item Title
	Item Description
	Item Quantity
	Unit of Measure
	Bidder to confirm (Quoted/Not Quoted*)

	Supply-1
	SUPPLY- NITROGEN INJECTION SYSTEM : NITROGEN INJECTION FIRE PROTECTION SYSTEM [NIFPS] FOR 125MVAR REACTOR (COMPLTE WITH FIRE EXTINGUISHING CUBICLE WITH NITROGEN GAS CYLINDER, FIRE DETECTORS, FIRE SURVIVAL CABLE, CONTROL BOX, SIGNAL BOX, PNRV AND ALL OTHER FITTINGS AND ACCESSORIES)
	2
	Set
	

	Supply-2
	SUPPLY- NITROGEN INJECTION SYSTEM : FIRE RETARDANT LOW SMOKE(FRLS), 4CORE X 1.5 SQ .MM, ARMOURED COPPER CABLE
	150
	Meter
	

	Supply-3
	SUPPLY- NITROGEN INJECTION SYSTEM : FIRE RETARDANT LOW SMOKE(FRLS), 12CORE X 1.5 SQ .MM, ARMOURED COPPER CABLE
	600
	Meter
	

	Supply-4
	SUPPLY- NITROGEN INJECTION SYSTEM : PIPES & CONNECTION FITTINGS WITH SUPPORT (REACTOR-FEC- OIL PIT)
	2
	Set
	

	Mandatory Spare 1
	SUPPLY- NITROGEN INJECTION SYSTEM : FILLED NITROGEN CYLINDER
	1
	Nos
	

	Mandatory Spare 2
	SUPPLY- NITROGEN INJECTION SYSTEM : FIRE DETECTOR
	2
	Nos
	

	Mandatory Spare 3
	SUPPLY- NITROGEN INJECTION SYSTEM : HOSE PIPE WITH FITTING
	1
	Set
	

	ETC -1
	NITROGEN INJECTION FIRE PROTECTION SYSTEM [NIFPS] FOR 125MVAR REACTOR
	2
	Nos
	

	ETC -2
	FIRE RETARDANT LOW SMOKE(FRLS), 4CORE X 1.5 SQ .MM, ARMOURED COPPER CABLE
	150
	Meter
	

	ETC -3
	FIRE RETARDANT LOW SMOKE(FRLS), 12CORE X 1.5 SQ .MM, ARMOURED COPPER CABLE
	600
	Meter
	

	ETC -4
	PIPES AND CONNECTION FITTING WITH SUPPORT
	2
	Set
	


*If Bidder mention “Not quoted” it means bidder shall supply the item free of cost to BHEL.








Annexure-II
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Annexure-III
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Annexure-IV

	Item/Package Name : 
	N2 Injection Fire Protection system 

	Enquiry No.: 
	 GEM/2021/B/1459072

	Project: 
	 TANGEDCO UDANGUDI

	Type of project 
	 

	Percentage of Local Content 
	 (Bidder to enter the applicable % of local content) 



Format of Self certification regarding Local Content in line with PPP-MII order, 2017 & its revision dated 04.06.2020. 
Date:……………… 
 
I ______________________________S/o, D/o, W/o, _____________________Resident of _________________________________________________________ hereby solemnly affirm and declare as under:  
That I will agree to abide by the terms and conditions of the Public Procurement (Preference to Make in India) Order, 2017 (hereinafter PPP-MII order) of Government of India issued vide Notification No: P-45021/2/2017-BE-II dated 15/06/2017, its revision dated 04/06/2020 and any subsequent modifications/Amendments, if any.  
That the information furnished hereinafter is correct to the best of my knowledge and belief and I undertake to produce relevant records before the procuring entity/BHEL or any other Government authority for the purpose of assessing the local content of goods/services/works supplied by me for ……………………………………. (Enter the name of the Equipment/Item for Project).  
 
That the local content for all inputs which constitute the said goods/services/works has been verified by me and I am responsible for the correctness of the claims made therein. 
That the goods/services/works supplied by me for ………………………………… (Enter the name of the Equipment/Item for Project) contains….........% (mention the Local content in %age) Local Content.

That the value addition for the purpose of meeting the ‘Minimum Local Content ‘has been made by me at ……………………… (Enter the details of the location(s) at which value addition is made). 
That in the event of the local content of the goods/services/works mentioned herein is found to be incorrect and not meeting the prescribed supplier class categorization criteria as per said order, based on the assessment of procuring agency (ies)/BHEL/Government Authorities for the purpose of assessing the local content, action shall be taken against me in line with the PPP-MII order and provisions of the Integrity pact/ Bidding Documents.  
I agree to maintain the following information in the Company's record for a period of 8 years and shall make this available for verification to any statutory authority.  
i. Name and   details of the Local Supplier   
(Registered Office, Manufacturing unit location, nature of legal entity)  
ii. Date on which this certificate is issued  

iii. Goods/services/works for which the certificate is produced  
iv. Procuring entity to whom the certificate is furnished  
v. Percentage of local content claimed and whether it meets the Minimum Local Content prescribed  
vi. Name and contact details of the unit of the Local Supplier (s)  
vii. Sale Price of the product  
viii. Ex-Factory Price of the product  
ix. Freight, insurance and handling  
x.    Total Bill of Material 
xi    List and total cost value of input used to manufacture the Goods/to provide services/in construction of works 
xii. List and total cost of input which are domestically sourced. Value addition certificates from suppliers, if the input is not in-house to be attached 
xiii. List and cost of inputs which are imported, directly or indirectly  
 
For and on behalf of……………………………………………… (Name of firm/entity)  
 
Authorized signatory (To be duly authorized by the Board of Directors)  
<Insert Name,  Designation and Contact No.>  
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