## SCC
SPECIAL CONDITIONS OF THE CONTRACT [SCC]
(This sheet is a mandatory & vendor shall submit/attach filled-in sheet of the same along with the technical bid)
Enquiry No.: C7A1Y36051, Date: 30.07.2025 |  | Vendor Offer Ref. No.
Item: PRESSURE COMPENSATOR WITH LEVEL SENSOR FOR SEAL CAVITY OF ELECTRIC MOTOR IN SUB-SEA APPLICATIONS - 1 No |  | Dt:
Vendor contact details:
Email ID:
Mobile Nimber:
SL.NO. | DESCRIPTION |  | RESPONSE /CONFIRMATION | DEVIATION / COMMENTS
1 | BID SUBMISSION METHOD:
For technical offer email id: technicalbid_hyd@bhel.in For Price offer email id: pricebid_hyd@bhel.in https://eprocurebhel.co.in/nicgep/app against enquiry.
2 | TECHNICAL PQR
The filled-in, sign & stamped Technical Pre-Qualification Requirement [PQR] shall be submitted along with technical bid. Note: The Technical PQR is enclosed.
3 | FIRM'S OFFER ACCEPTANCE CRITERIA:
The quotation/offer submitted by vendor shall be considered only after scrutiny of technical bid, PQR and bid acceptance by BHEL/Customer.
4 | SCOPE OF SUPPLY
PRESSURE COMPENSATOR WITH LEVEL SENSOR FOR SEAL CAVITY OF ELECTRIC MOTOR IN SUB-SEA APPLICATIONS - 1 No shall be as per BHEL specification TG66647 Rev.00 (inclusive of packing & forwarding and Freight & Insurance upto CIP Hyderabad Airport).
5 | Taxes, HSN code and Vendor works place
Applicable Taxes in percentage
HSN code for subject item
Vendor works place from where material is being dispatched
6 | TERMS OF DELIVERY / INCOTERMS:
Vendor offer shall be on "CIP Hyderabad Airport" basis
7 | VALIDITY OF OFFER:
Offer validity shall be 90 days from date of technical bid opening
8 | Documents to be submitted/attached by vendor with Technical Bid[Part-I]:
Vendor shall submit / attach the filled-in signed & stamped the following documents along with the technical offer/bid [Part-I]: 1. Technical offer
2. Special Conditions of the Contract (SCC)
3. Technical Pre-Qualification Requirement (PQR)
4. ITB 17
9 | DELIVERY PROGRAMME:
Manufacturing & delivery shall be within 16 weeks from the date of LOI/PO.
Delivery Milestones:
Delivery shall be within 112 days (16 Weeks) days from the PO date. The breakup is given below.
(a) | Submission of Drawings: Within 2 weeks (14 days) from the date of PO/Inputs. |  | Vendor
(d) | Approval of Documents by BHEL: Within 1 week (7 days) from the date of drawing submission by vendor. |  | BHEL/Customer
© | Manufacturing, Raising of Inspection, Inspection completion, Submission of all test certificates, final inspection report and compliance (if any) : Within 63 days (9 Weeks) from the date of of approved drawings. |  | Vendor
(d) | Dispatch clearance: Within 3 days from the date of submission of final inspection report subject to submission of all test certificates and compliance (if any) by vendor. |  | BHEL/Customer
(e) | Delivery up to BHEL works: Within 25 days from the date of issue of Dispatch instructions / Dispatch clearance up to CIP Hyderabad Airport. |  | Vendor
| Subsequent submission of revised drawings (if any): Within 1 week (7 days) days from the date of issue of comments by BHEL / Customer |  | Vendor
| Subsequent issue of comments (if any): Within 1 week (7 days) from the date of drawings submission by vendor |  | BHEL/Customer
10 | PRICE TO BE QUOTED: (As per Annexure-A of Price format)
The VENDOR shall quote price for supply of PRESSURE COMPENSATOR WITH LEVEL SENSOR FOR SEAL CAVITY OF ELECTRIC MOTOR IN SUB-SEA APPLICATIONS - 1 No shall be as per BHEL specification TG66647 Rev.00 (inclusive of packing & forwarding and Freight & Insurance upto CIP Hyderabad Airport and applicable taxes (if any).
11 | EVALUATION:
Evaluation shall be on overall L1 Basis.
12 | GUARANTEE CLAUSE:
The equipment shall be guaranteed for a period of 12 months from the date of commissioning or 18 months from date of dispatch whichever is earlier against any defect in design manufacture , materials or workmanship
13 | PAYMENT TERMS:
i) 100% payment (less Indian Agency Commission, if any) shall be through Wire Transfer with a credit period of 45 days - Cash Against Documents (CAD) ii) In case Bidder opts for Letter of Credit payment, the LC Usance period shall be 90 days with respective bank charges to respective accounts and loading of 0.50% iii) Indian Agency commission if payable and so specified in the Purchase order shall be paid in Indian Rupees, considering the SBI TT selling exchange rate, as on the date of payment after successful completion of the contract. Conditions for LC: a. LC validity period will be 90 days and for any extension, applicable charges will be to bidder's account. b. LC will be opened after successful completion of pre dispatch inspection prior to the scheduled / agreed delivery date. LC will be opened within 15 bank working days from the date of request.
14 | PENALTY CLAUSE
In the event of delay in supply of goods, penalty of 0.5% per week or part there of shall be levied on the undelivered portion subject to a maximum of 10% of the order value. Penalty amount so determined along with applicable Taxes thereon shall be recovered. The date of AWB shall be considered the date of delivery for Penalty calculation.
15 | QUALITY PLAN
Quality Plan shall be submitted after placement of PO for BHEL approval in BHEL standard format
6 | INSPECTION:
Material shall be Remotely Inspected by BHEL as per approved quality plan and specification.
15 | TERMS & CONDITIONS
Vendor shall confirm to all terms & conditions of ITB-17, SCC, PQR
For any clarifications/ details for the subject tender, seller may contact under signed through email
Mr. Srinivasa Rao K, Manager/EM Purchase 4th Floor, Admn Building, BHEL-R.C.Puram,Hyderabad, Telangana (State), INDIA. PIN 502032. e-mail ID: srinivasark@bhel.in/rameshmanne@bhel.in Ph No.: +91 9276609755
SIGNED & STAMPED BY THE VENDOR