## Summary
1x660MW, Bhusawal EPC Project
Digitalization of quality protocols as per Field Quality Plan
System: |  | Civil and Structural Steel Works
Sub-systems: |  | Topographical Survey and Soil Investigation
Civil Works
Structural Steel Works
Potocol formats sub-systemwise as given below;
Topographical Survey and Soil Investigation
SN | Format / Logsheet No. | Activity | Remarks
A |  | TOPOGRAPHICAL SURVEY:
1 | L01 | BENCHMARKING (LEVEL & CO-ORDINATES)
2 |  | AREA LEVELLING
B |  | SOIL INVESTIGATION:
B.1 |  | FIELD TESTS/INVESTIGATIONS:
1 |  | GENERALISED SURAFACE & SUB-SURFACE CONDITIONS
2 |  | SOIL BORING
3 |  | STANDARD PENETRATION TESTS (SPT)
4 |  | ROCK DRILLING
5 |  | GROUNDWATER
6 |  | TRIAL PITS
7 |  | FIELD PERMEABILITY TEST
8 |  | DYNAMIC CONE PENETRATION TEST
9 |  | ELECTRICAL RESISTIVITY TEST
10 |  | FIELD CALIFORNIA BEARING RATIO TEST
11 |  | STATIC & CYCLIC PLATE LOAD TEST
12 |  | SEISMIC REFRACTION TEST
13 |  | CROSS-HOLE SEISMIC TEST
14 |  | PRESSUREMETER TEST
B.2 |  | LAB TEST:
1 |  | BULK DENSITY AND MOISTURE CONTENT
2 | L05 | SIEVE ANALYSIS
3 |  | HYDROMETER ANALYSIS
4 |  | LIQUID LIMIT AND PLASTIC LIMIT
5 |  | SHRINKAGE LIMIT
6 |  | SPECIFIC GRAVITY
7 |  | SWELL PRESSURE
8 |  | FREE SWELL INDEX
9 |  | RELATIVE DENSITY
10 | L08 | UNCONFINED COMPRESSIVE STRENGTH
11 |  | DIRECT SHEAR TEST
12 |  | TRIAXIAL SHEAR TEST I) UNCONSOLIDATED UNDRAINED TEST
13 |  | ONE DIMENSIONAL CONSOLIDATION TEST
14 | L02 | STANDARD PROCTOR COMPACTION TEST
15 |  | CBR TEST
16 |  | CHEMICAL ANALYSIS
17 |  | CHEMICAL TEST OF WATER
Civil Works
SN | Format No. / Logsheet No. | Activity | Sheet no.
1 | P-01 | PROTOCOL FOR SITE GRADING | 01 & 02
2 | P-02 | PROTOCOL FOR PILING WORKS | 03 & 04
3 | L-05, Levelbook, Test reports | EXCAVATION | 05
| L12 | BACK FILLING AND COMPACTION | 06
L13
4 | L15
5 | L16, Logbook | UNDER GROUND PIPING (RCC/CI) | 07 & 08
6 | L12 | WBM ROADS | 09
L13
L14
7 | L14 | BLACK TOPPING (PREMIX CARPETING) ROADS | 10
L17
8 | L06 | TANK PADS | 11
L15
9 | P-03 | MICRO GRADING | 12
10 | L04, Test report | COARSE AGGREGATE | 13
11 | L03, Test report | FINE AGGREGATE | 14
12 | L03 Level book, Logbook | PLANE CEMENT CONCRETE | 15
L04, Level book, Logbook
13 | L05, L07, Level book, Logbook, Protocol | RCC-SUBSTRUCTURES | 16,17 & 18
14 | L05, L07, Level book, Logbook, Protocol | RCC-SUPERSTRUCTURES | 19,20 & 21
15 | L05, L07, Level book, Logbook, Protocol | RCC-CRITICAL STRUCTURES | 22,23 & 24
16 | Logbook & Test report | RCC FLOORING / PAVEMENT | 25 & 26
17 | P-04 | BRICK MASONRY WORK | 27 & 28
L10
L11
18 | P-05 | ANTI-TERMITE TREATMENT | 29
19 | P-06 | PLASTERING | 30
20 | P-07 | DOORS, WINDOWS AND VENTILATORS | 31
21 | P-08 | PAINTING | 32
22 | P-09 | SANITARY FITTINGS | 33
23 | P-10 | WATER ROOFING | 34
24 | P-11 | FALSE FOORING | 35
25 | P-11 | FALSE CEILING | 35
26 | P-12 | UNDER DECK INSULATION | 36
27 |  | PILING DATA SHEET
28 |  | POUR CARD FOR RCC
29 |  | CUBE TEST REPORTS FOR RCC WORKS
30 |  | NDCT & Chimney record Verticality/ Dia / Thickness
31 | L6 | PROTOCOL FOR FIXING OF EMBEDDED PARTS
32 | L7 | TEST REPORT FOR BRICKS
33 | L10 | PROTOCOL FOR SAMPLING OF MATERIAL FOR TESTING
34 |  | BAR BENDING SCHEDULE
35 |  | CHECK LIST FOR T.G DECK SLAB CONCRETING
36 |  | Field Core cutter test (OVEN METHOD)
37 |  | Field Core cutter test (RAPID MOISTURE METHOD)

## L02
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
PROTOCOL FOR DEGREE OF COMPACTION ( By Core Cutter Method)
Test Report No : COMP- Date Of Testing :
Area : Elevation :
Sub-Structure : Layer No :
Reference of Source Test :
Results Of Source Test :
Max. Dry Density ( Max) :
Optimum Moiture Content (OMC) :
Swell Index :
Sl.No | Description | Unit | Test 1 | Test 2 | Test 3 | Test 4 | Test 5 | Test 6
1 | Wt of Core Cutter (Wc) | gm
2 | Wt of Core Cutter + Wt of Soil (W) | gm
3 | Wt of Soil (Ws) (W-Wc) | gm
4 | Volume of Core Cutter (V) | cc
5 | Bulk Density ( b) (Ws/V) | gm/cc
6 | If Rapid Moiture Meter Used
| Water Content (w) (Observed in meter) | %
7 | If Oven Dried
| Wt of Crucible (Wcr) | gm
| Wt of Crucible + Wet Soil (Wcw) | gm
| Wt of Wet Soil (Wws) (Wcr)-( Wcw) | gm
| Wt of Dry Soil (Wds) | gm
| Wt of Water (Ww) (Wws-Wds) | gm
| Water Content (w) (Ww/Wds)x100 | %
8 | Dry Density ( d) ( b/ (1+ w/100)) | gm/cc
9 | Degree of compaction ( d / max)x100 | %
Doc.No:QPE-CL-035
Rev. No: R 00
Log Sheet No: L-02
Contractor BHEL NLC Consultant |  |  | Test 5: Sheet 1/1 sheet

## L2
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
PROTOCOL FOR STANDARD PROCTOR TEST
Test Report No : PROCT- Date Of Testing :
Place of Sample collected |  | :
Soil Sample No |  | :
a) Diameter of Mould (mm) |  | : |  | e) Weight of sample | :
b) Height of Mould (mm) |  | :
c) Volume of Mould , V ( cc) |  | : | CC
d) Weight of the Mould ( gm) |  | :
Sl.No | Description | Unit | Increment of Water content (%)
1 | Wt of mould + Compacted Soil (W) | gm
2 | Wt of Compacted Soil (Wc) (W-d) | gm
3 | Bulk Density (γb) (Wc/V) | gm/cc
4 | Crucible No.
5 | Wt of Crucible (Wcr) | gm
6 | Wt of Crucible + Wet Soil (Wcw) | gm
7 | Wt of Crucible + Dry Soil (Wcd) | gm
8 | Wt of Water (Ww) (Wcw-Wcd) | gm
9 | Wt of Dry Soil (Ws) (Wcd-Wcr) | gm
10 | Water Content (w) (Ww/Ws)x100 | %
11 | Dry Density (γd) ( γb / (1+ (w/100))) | gm/cc
| Maximum Dry Density (MDD) (gm/cc) |  |  | :
| Optimum Moisture Content (OMC) ( % ) |  |  | :
Doc.No:QPE-CL-035
Rev. No: R 00
Log Sheet No: L-15
Contractor BHEL NLC Consultant |  |  |  |  | Sheet 1/1 sheet

## L01 Benchmark
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
Protocol for Transfering the Temporary Bench Marks /Levels
Area of Work: |  |  |  |  | Date:
Chainage | BS | IS | FS | HI | RL | Remarks
Doc.No: QPE-CL-035
Rev. No: R 00
Log Sheet No: L-01
Contractor BHEL NLC Consultant | [5 empty] | Sheet 1/1 sheet
Doc.No: QPE-CL-
Rev. No: R 00
Log Sheet No: L-
Sheet 1/11 sheet

## L05
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
SIEVE ANALYSIS - Determining the Grading of Coarse Aggregate
Date of Testing :
Area of Conreteing Planned |  |  |  | Qty | Grade | Area of Concreteing Planned |  |  |  | Qty | Grade
1) | [5 empty] | 6)
2) | [5 empty] | 7)
3) | [5 empty] | 8)
4) | [5 empty] | 9)
5) | [5 empty] | 10)
Total Concrete Qty Planned for the Day |  |  |  |  | : | Cum
Required Qty of Aggregate to be Tested |  |  |  |  | : 1) | 20mm : |  | Cum 2) | 12.5mm : |  | Cum
Sample No: CA - Name of the Source:
Weight of Sample : |  |  |  |  | : 1) | 20mm : |  | Cum 2) | 12.5mm : |  | Cum
Sl.No | IS Sieves | 20mm Aggregate |  |  |  | 12.5mm Aggregate |  |  |  | Requirement as per IS 383 - 1970
|  | Weight Retained | % Weight Retained | Cumm. % Wt. Retained | % Passing | Weight Retained | % Weight Retained | Cumm. % Wt. Retained | % Passing
[10 empty] | 20mm (%) | 12.5mm (%)
1 | 40mm | [8 empty] | 100
2 | 20mm | [8 empty] | 85 - 100
3 | 16mm | [9 empty] | 100
4 | 12.5mm | [9 empty] | 85 - 100
5 | 10mm | [8 empty] | 0 - 20 | 0 - 45
6 | 4.75mm | [8 empty] | 0 - 5 | 0 - 10
7 | 2.36mm
8 | PAN
Occational Test on Combined Material | [5 empty] | Regular tests
1) Flakiness Index (%) |  |  | : |  |  | 1) Moiture Content (%) |  |  | :
2) Elongation (%) |  |  | : |  |  | 2) Water Absorption (%) |  |  | :
3) Passing in 75micron (%) |  |  | :
4) Clay Lumps (%) |  |  | :
Wheather the Material is Accepted or Rejected
=
Doc.No: QPE-CL-035
Rev. No: R 00
Log Sheet No: L- 05
Contractor BHEL NLC Consultant | [8 empty] | Sheet 1/1 sheet

## L06
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
PROTOCOL FOR FIXING OF EMBEDDED PARTS
DATE:
AREA:
Type of EP: Steel Insert plate/Bolt / Water stopper/ Bitumen board/If any :
Drg/ Documents referred:
Sl.No | Sub Structure | EP Mark | EP Size (ax bx thk) mm | Spacing of EP's (mm) | Total number of EP's | Details of Lugs | Location of EP (RL) | Remarks
Doc.No: QPE-CL-035
Rev. No: R 00
Log Sheet No: L- 06
Contractor BHEL NLC Consultant | [6 empty] | Sheet 1/1 sheet

## L07
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
TEST REPORT FOR BRICKS
Bicks Test Report No. : BRI - Date of Testing :
Brand Name : |  | Quantity Received :
Source name : |  | Class of Brick | :
COMPRESSIVE STRENGTH TEST
Sl.No | Dimension of brick | Wt of Brick (kg) | Comp.Load | Comp. Strength (Kg/sqm)
1
2
3
4
5
Average Strength of Brick =
WATER ABSORPTION TEST
Sl.No | Dimension of brick | Dry Wt of Brick, M1 (kg) | Wet Wt of Brick , M2 (kg) | Water Absorption ((M2-M1)/M1)X100 (%)
1
2
3
4
5
Average Water Absorption of Bricks =
Doc.No:QPE-CL-35
Rev. No: R 00
Log Sheet No: L-07
Contractor BHEL NLC Consultant |  |  |  | Sheet 1/1 sheet

## L08
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
PROTOCOL FOR COMPRESSIVE STRENGTH OF CONCRETE CUBES
Sl. No | Location | Cube Mark | Date of Casting | Grade of Concrete | W/C Ratio | Slump Observed (mm) | Compressive Strength ( N/mm2)
[7 empty] | 7 days Strength |  |  |  | 28 days Strength
[7 empty] | Weight of Cube (kg) | Failure Load (KN) | Strength (N/mm2) | Avg. Strength (N/mm2) | Weight of Cube (kg) | Failure Load (KN) | Strength (N/mm2) | Avg. Strength (N/mm2)
Doc.No:QPE-CL-035
Rev. No: R 00
Log Sheet No: L- 08
Contractor BHEL NLC Consultant | [12 empty] | Sheet 1/11 sheet

## L10
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
PROTOCOL FOR SAMPLING OF MATERIAL FOR TESTING
Date:
1 | Type Of Sample | :
2 | Location of sample | :
3 | Area for which the sample to to be used | :
4 | Purpose of the Sample at Site | :
5 | No. of Samples Collected | :
6 | DB No/Invoice Reference | :
7 | Quantity Received | :
8 | Ref. Of Drawing /Tech.Spec/ IS Code | :
9 | Name of Tests Recommended | :
| 1) | 6)
| 2) | 7)
| 3) | 8)
| 4) | 9)
| 5) | 10)
10 | Weather Sample sent for In House / Third Party testing | :
11 | If Third Party testing: Name of the Testing Agency | :
Doc.No: QPE-CL-035
Rev. No: R 00
Log Sheet No: L- 10
Contractor BHEL NLC Consultant |  |  |  | Sheet 1/1 sheet

## BAR BENDING
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
REINFORCEMENT STEEL MEASUREMENT SHEET (BAR BENDING SCHEDULE)
AREA: STRUCTURE : DRG.NO:
Sl. No | Bar Mark | Description & Shape of Bar | Dia | Cutting Length | Nos | Total Cut Length ( m) | [9 empty] | Remarks
1 | [5 empty] | 6 mm Ø | 8 mm Ø | 10 mm Ø | 12 mm Ø | 16 mm Ø | 20 mm Ø | 25 mm Ø | 28 mm Ø | 32 mm Ø | 36 mm Ø
1
2
3
4
5
6
7
8
9
10
11
12
13
14
Contractor BHEL NLC Consultant

## POUR CARD
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
POUR CARD FOR CONCRETE
Pour Card No |  | : |  | Date:
Structure |  | : | Coordinate checked | :
Location |  | : | Reinforcement checked | :
Concrete Grade |  | : | Embeddments/pockets/ checked | :
Mix Proportion |  | : | Water stopper checked | :
Volume of Concrete : |  |  | Drawing No:
MEASUREMENT FOR CONCRETE
SL.No | Description of Measurement |  | Quantity ( Cum) | Remarks / Extra Reinforcement provided
Shuttering Measurement
SL.No | Measurement of Shuttering |  | Quantity ( Sq.m) | Remarks
Contractor BHEL Consultant NLC

## TG DECK
BHARAT HEAVY ELECTRICALS LIMITED
BELLARY THERMAL POWER PROJECT (1X500MW)
CHECK LIST FOR T.G DECK SLAB CONCRETING
Structure : TURBINE GENERATOR DECK SLAB
Quantity : 850 cum
Sl.No | Description | Requirement | Protocol Requirment as per FQP
1 | Cement | 6300Bags | Test reports of cemet for the batches identified for concreting
2 | Coarse Aggregate | 500Cum | 1) Report of Source test
20mm Aggregates
2) Reports of Sieve analysis, Elongation, Flakiness Index
a) For Stack No: 1 (100 cum)
b) For Stack No: 2 (100 cum)
c) For Stack No: 3 (100 cum)
d) For Stack No: 4 (100 cum)
e) For Stack No: 5 (100 cum)
|  | 200 cum | 10mm Aggregates
Reports of Sieve analysis, Elongation, Flakiness Index
a) For Stack No: 1 (100 cum)
b) For Stack No: 2 (100 cum)
3 | Sand | 300Cum | 1) Reports of Sourse test
2) Reports of Sieve analysis, Silt & Clay content
a) For Stack No: 1 (100 cum)
b) For Stack No: 2 (100 cum)
c) For Stack No: 3 (100 cum)
4 | Admixture | 2000 litres | Manufacturers Test Certificates
5 | Construction Water | 1,63,000 litres | Test report of the water
6 | Ice | 100 MT | Test report of the water for Ice | NA
7 | Reinforcement Steel | 275 MT | Test report of the Reinforcement
8 | Batching Plant | 2 Nos | Report of Calibration of Batching Plant
a) Batching Plant - I
b) Batching Plant - II
Sl.No | Description | Requirement | Protocol Requirment as per FQP
9 | TransitMixer | 3 Nos | Confirmation of Readiness
10 | Concrete Pump | 2 Nos | Confirmation of Readiness
11 | Vibrators
| 1) Electrical Operated | 5 Nos | Confirmation of Readiness
| 2) Petrol Operated | 3 Nos | Confirmation of Readiness
12 | Vibrator Needles
| 60mm dia | 6 Nos | Confirmation of Readiness
| 40mm dia | 3 Nos | Confirmation of Readiness
13 | Cube Moulds with Tamping rod | 114 Nos | Confirmation of Readiness
14 | Thermometers | 5 Nos | Confirmation of Readiness | NA
15 | Slump Cone with tamping rod | 5 Nos | Confirmation of Readiness
16 | Tarpaulin | 3 Nos | Confirmation of Readiness
17 | Surveying |  | Total station required
18 | Reinforcement check
19 | Location of raft and pedestal at site

## CORE CUTTER TEST(OVEN)
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
Results of Field Core cutter test (Oven dry method)
Area of Work: LAYER NO. Date :
Sl. No | Wt of core (gm) | Volume of cutter (cc) | Bulk density (gm/cc) | Wt of crucible gm | Wt of cru.+ wet soil gm | wt of cru.+ dry soil gm | Wt of water gm | Wt of dry soil gm | Water content based on wet mass (Observed in the Rapid moisture meter) ( m' ) % | Water content based on dry mass m = ( m'/(100-m') )x 100 % | Dry Density (gm/cc) | Max dry density from lab test (gm/cc) | % of compaction
Results of Core cutter test (Repeat Test - if any)
Area of Work: Layer No - Date :
Contractor BHEL NLC TCE

## CORE CUTTER TEST(MOISTURE)
BHARAT HEAVY ELECTRICALS LTD
Project : 2 X 250MW - Neyveli Thermal Power Project (TS-II Expn)
Customer : Neyveli Lignite Corporation Ltd
Results of Field Core cutter test (Using Rapid moisture meter)
Test Report No : COMP-
Area of Work: LAYER NO. Date :
Sl. No | Wt of core (gm) | Volume of cutter (cc) | Bulk density (gm/cc) | Wt of crucible gm | Wt of cru.+ wet soil gm | wt of cru.+ dry soil gm | Wt of water gm | Wt of dry soil gm | Water content based on wet mass (Observed in the Rapid moisture meter) ( m' ) % | Water content based on dry mass m = ( m'/(100-m') )x 100 % | Dry Density gm/cc | Max dry density from lab test (gm/cc) | % of compaction
Results of Core cutter test (Repeat Test - if any)
Area of Work: Layer No - Date :
Contractor BHEL NLC TCE

## CLS no. 1
PSWR-NAGPUR | Instrument Reg. No.
| Date Of Inspection |  |  |  |  | Only Check-points (Y/N) | No. of digital data points to be entered | Can be calculated by the system | Textual fields
| Drawing/Doc. Reference |  |  |  |  | 0 | 6 | 1 | 0
DETERMINATION OF CONSISTENCY OF CEMENT
This method is for determining the quantity of water required for preparing a cement paste of standard consistency, using VICAT apparatus.
Weight of sample: ____________ Grams.
Note: 500 GMS for 80 mm diameter VICAT mould.
Quantity of water: _____________ ML
Time of gauging: _____________ Minutes.
Note: 3 to 5 minutes.
Plunger Penetration: ___________ mm
Note: 5 to 7 MM from bottom of the mould of 10 mm diameter.
Consistency: Water added X 100 %
Weight of cement
|  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  | REV NO.: 00
UNIT NO. |  | ACCEPTED BY |  |  | LOG SHEET NO. L-01
RATING |  | CUSTOMER |  |  | SHEET: 01 Of 01

## CLS no.2
PSWR-NAGPUR | Instrument Reg. No.
Date Of Inspection
| Drawing/Doc. Reference |  |  |  |  | No. of digital Data points to be entered | Can be calculated by the system | Textual fields
[6 empty] | 4 | 0 | 1
INITIAL & FINAL SETTING TIMES OF CEMENT
(VICAT APPARATUS)
1. Weight of sample __________ Grams (500 Grams for 80 mm diameter VICAT mould).
2. Quantity of water ___________ ml (85% of standard consistency).
3. Initial Setting Time:
Penetration of VICAT needle of 1 mm2: 5 + 0.5 mm from the bottom of the mould
Initial Setting Time: ______ Minutes/Seconds
(Total time from water addition to proper penetration of the needle.
4. Final Setting Time: ______ Minutes/Seconds
(Total time from water addition to failure of making outer impression of the surface of the cement specimen.)
5. Specification:
Initial Minimum 30 minutes.
Final Maximum 600 minutes.
6. Remarks (if any):
|  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  | REV NO.: 00
UNIT NO. |  | ACCEPTED BY |  |  | LOG SHEET NO. L-02
RATING |  | CUSTOMER |  |  | SHEET: 01 Of 01

## CLS no.3
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
[14 empty] | Only Check-points (Y/N) | No. of digital data points to be entered | Can be calculated by the system | Textual fields
GRADING OF THE SAND (FINE AGGREGATE) | [13 empty] | 0 | 6 | 1 | 0
Weight of sample: _________________ Grams.
Type of Aggregate: _________________
Sr. No. | Retained on |  |  | Weight Retained |  |  | Percentage Weight Retained |  |  | Cumulative % Weight Retained |  |  | Percentage Passing
IS Sieve No.
1. | 10 mm
2. | 4.74 mm
3. | 2.36 mm
4. | 1.18 mm
5. | 600 microns
6. | 300 microns
7. | 150 microns
8. | 75 microns
GRADING ZONES OF FINE AGGREGATE (IS 383)
IS Sieve Designation |  |  | Percentage Passing for
|  |  | Grading Zone I |  |  | Grading Zone II |  |  | Grading Zone III |  |  | Grading Zone IV
10 mm |  |  | 100 |  |  | 100 |  |  | 100 |  |  | 100
4.75 mm |  |  | 90 - 100 |  |  | 90 - 100 |  |  | 90 - 100 |  |  | 95 - 100
2.36 mm |  |  | 60 - 95 |  |  | 75 - 100 |  |  | 85 - 100 |  |  | 95 - 100
1.18 mm |  |  | 30 - 70 |  |  | 55 - 90 |  |  | 75 - 100 |  |  | 90 - 100
600 microns |  |  | 15 - 34 |  |  | 35 - 59 |  |  | 60 - 79 |  |  | 80 - 100
300 microns |  |  | 2020-05-01 |  |  | 1930-08-01 |  |  | 1940-12-01 |  |  | 15 - 50
150 microns |  |  | 0 - 10 |  |  | 0 - 10 |  |  | 0 - 10 |  |  | 0 - 15
Note: Graphical Plot of Grading Curve to include during execution of work
[5 empty] | NAME |  |  | SIG. / DATE |  |  | DOC. NO. QPE - CL - 001
PROJECT |  |  |  | CHECKED BY | [6 empty] | REV NO.: 00
UNIT NO. |  |  |  | ACCEPTED BY | [6 empty] | LOG SHEET NO. L-03
RATING |  |  |  | CUSTOMER | [6 empty] | SHEET: 01 Of 01

## CLS no.4
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
SIEVE ANALYSIS (GRADING OF COARSE AGGREGATE)
Weight of sample: _________________ Grams.
Type of Aggregate: _________________
Sr. No. | Retained on |  |  | Weight Retained |  |  | Percentage Weight Retained |  |  | Cumulative % Weight Retained |  |  | Percentage Passing
IS Sieve No.
1 | 10 mm
2 | 20 mm
3 | 16 mm
4 | 12.5 mm
5 | 10 mm
6 | 4.75 mm
7 | 2.36 mm
GRADING ZONES OF FINE AGGREGATE (IS 383):
IS Sieve Designation |  |  | Percentage Passing for Graded Aggregate of Nominal size
|  |  | 40 mm |  | 20 mm |  |  |  | 16 mm |  |  | 12.5 mm
10 mm |  |  | 95 - 100 |  | 100 |  |  |  | - |  |  | -
20 mm |  |  | 30 - 70 |  | 95 - 100 |  |  |  | 100 |  |  | 100
16 mm |  |  | - |  | - |  |  |  | 90 - 100 |  |  | -
12.5 mm |  |  | - |  | - |  |  |  | - |  |  | 90 - 100
10 mm |  |  | 1935-10-01 |  | 25 - 55 |  |  |  | 30 - 70 |  |  | 40 - 85
4.75 mm |  |  | 0 - 5 |  | 0 - 10 |  |  |  | 0 - 10 |  |  | 0 - 10
2.36 mm |  |  | - |  | - |  |  |  | - |  |  | -
Note: Graphical Plot of Grading Curve to be included during execution of work.
Remarks (if any):
[6 empty] | NAME |  | SIG. / DATE |  |  | DOC. NO. QPE - CL - 001
PROJECT |  |  |  | CHECKED BY | [6 empty] | REV NO.: 00
UNIT NO. |  |  |  | ACCEPTED BY | [6 empty] | LOG SHEET NO. L-04
RATING |  |  |  | CUSTOMER | [6 empty] | SHEET: 01 Of 01

## CLS no.5
PSWR-NAGPUR |  |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
COMPRESSIVE STRENGTH TESTING OF CEMENT CONCRETE
[15 empty] | Only Check-points (Y/N) | No. of digital data points to be entered | Can be calculated by the system | Textual fields | Only Check-points (Y/N) | No. of digital data points to be entered | Can be calculated by the system | Textual fields
Name of Agency: | [14 empty] | 0 | 6 | 2 | 6 | 7 | 8.4 | 9.8 | 11.2
Location / Structure:
Grade of Concrete Mix Proportion:
Sr. No. | Date of Cube Casting | Cube Identification Mark |  | Slump | Concrete Quantity sampling method |  | Date of Cube Testing | Age of Cube | Weight of Cube |  | Compression Strength / mm2 |  |  | Remarks
|  |  |  | (MM) | [6 empty] | Individual |  | Average
[6 empty] | NAME |  |  |  | SIGNATURE / DATE |  | DOC. NO. QPE - CL - 001
PROJECT |  |  |  | CHECKED BY | [7 empty] | REV NO.: 00
UNIT NO. |  |  |  | ACCEPTED BY | [7 empty] | LOG SHEET NO. L-05
RATING |  |  |  | CUSTOMER | [7 empty] | SHEET: 01 Of 01

## CLS no. 6
PSWR-NAGPUR | Instrument Reg No.
Date of inseption
Drawing Doc. Reference
PCC FOR FOUNDATION
SR NO. | ACTUAL DIMENSION | DIMENSION AS PER DRAWING | TOP LEVEL PCC | EXCAVATION LEVEL | REMARK
Acceptable /released for further work
|  |  | NAME | SIG/DATE
QP NO.:QPE:CL:001
PROJECT |  | CHECKED BY |  |  | REV NO:01
UNIT NO. |  | ACCEPTED BY |  |  | LOG SHEET NO.:L-06
RATING |  | CUSTOMER |  |  | SHEET 1 OF 1

## CLS no.7
PSWR-NAGPUR | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
POUR CLEARANCE FORM
AREA / LOCATION:
Name of work: Date:
1. Grade of concrete:
2. Water cement ratio of concrete:
3 Quantity of concrete to be poured:
4. Type Of Cement used:
5. Quality of aggregate:
6. Quality & Source of water:
7. Checking completion of alignment (as applicable):
8. Checking completion of formwork/shuttering and supports (as applicable):
9. Reinforcement Completion (as applicable):
10. Staging and scaffolding Completion (as applicable):
11. Embedded parts / Anchor bolts/ Pockets / opening etc. (as applicable):
12. Machineries proposed to be used
a) Concrete Mixers
b) Vibrators
c) Pumps
d) Hoists
13. Intending to pour from ________ Hrs. to _________ Hrs. on date ____
The above structure work has been checked and found ready for concreting.
Remarks (If any):
|  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  | REV NO.: 01
UNIT NO. |  | ACCEPTED BY |  |  | LOG SHEET NO. L-07
RATING |  | CUSTOMER |  |  | SHEET: 01 Of 01

## CLS no.8
PSWR-NAGPUR | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
OBSERVATION DURING/AFTER CONCRETING
AREA / LOCATION:
Name of work: Date:
1. Compaction of concrete:
2. Slump:
3. Correctness of anchor bolts:
4. Correctness of pockets / openings:
5. Rigidity of shuttering / strutting
6. Any other defect observed during concreting
7. Quality of concrete
8. Total cement consumption
9. Actual time of pouring
a) Starting Time
b) Completion Time
10. Date of de-shuttering
11. De-shuttering Observations
12. Cubes taken
a) Nos.
b) Identification Mark
|  |  | NAME |  | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  |  | REV NO.: 00
UNIT NO. |  | ACCEPTED BY |  |  |  | LOGSHEETNO. L-08
RATING |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CLS no.9
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
FOUNDATION AS BUILT SCHEME
AREA / LOCATION:
Sl. No. | Description of Dimension & Top of Foundation |  |  | As Per Drawing |  | Measured/Concrete |  |  | Remarks
|  |  |  | (Top Level) |  | (Top Level)
Acceptable / Released for further work.
[5 empty] | NAME |  | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  |  | REV NO.: 00
UNIT NO. |  |  | ACCEPTED BY |  |  |  |  | LOGSHEETNO. L-09
RATING |  |  | CUSTOMER |  |  |  |  | SHEET: 01 Of 01

## CLS no.10
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
COMPRESSIVE STRENGTH OF BRICKS
AREA / LOCATION:
Sl. No. | Sample No. |  | Brick Mark |  | Dimensions |  | Area of Cross Section Loaded |  | Load In Kg | Compression Strength Kg/Cm2 | Remarks
L x B x D
Cm x Cm x Cm
[6 empty] | NAME |  | SIG. / DATE |  | DOC. NO. QPE - CL - 001
PROJECT |  |  |  | CHECKED BY | [5 empty] | REV NO.: 00
UNIT NO. |  |  |  | ACCEPTED BY | [5 empty] | LOGSHEETNO. L-10
RATING |  |  |  | CUSTOMER | [5 empty] | SHEET: 01 Of 01

## CLS no.11
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
COMPUTING WATER ABSORPTION TEST OF BRICK
Sample No. | Brick Mark |  | Dimension |  | Weight of Dry Brick (W1) | Duration of Soaking Water |  |  |  | Weight of Soaked Brick (W2) In Kg |  | Weight of Water Absorbed | % Of Individual Absorption
|  |  | (L x B x D) |  | In Kg | [6 empty] | (W2 - W1)
|  |  | (Cm x Cm x Cm) | [8 empty] | In Kg | (W2 - W1) x100
[6 empty] | From | To | Period |  |  |  |  | W
Remarks (If any):
[6 empty] | NAME |  |  | SIG. / DATE |  | DOC. NO. QPE - CL - 001
PROJECT |  |  |  | CHECKED BY | [6 empty] | REV NO.: 00
UNIT NO. |  |  |  | ACCEPTED BY | [6 empty] | LOGSHEETNO. L-11
RATING |  |  |  | CUSTOMER | [6 empty] | SHEET: 01 Of 01

## CLS no. 12
PSWR-NAGPUR | Instrument Reg. No.
Date Of Inspection
| Drawing/Doc. Reference |  |  |  |  | No. of Data points to be entered | Can be calculated by the system | Textual fields
[6 empty] | 6 | 1 | 0
BACK FILLING
AREA / LOCATION:
1. Type of Soil: Soil / Sand / Moorum
2. No. Of Layers: ______ Per CNS Soil
3. Mode of Compaction: Watering / Ramming / Plate Vibrator
4. Final Level of Filling:
5. Field Compaction Test:
Remarks (If any):
|  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  | REV NO.: 00
UNIT NO. |  | ACCEPTED BY |  |  | LOGSHEETNO. L-12
RATING |  | CUSTOMER |  |  | SHEET: 01 Of 01

## CLS no.13
PSWR-NAGPUR | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
DETERMINATION BULK DENSITY, MOISTURE CONTENT & DRY DENSITY
AREA / LOCATION:
PART-I: CALCULATION OF BULK DENSITY
1. Weight of Core Cutter=Wc In Grams:
2. Inner Volume of Core Cutter {πd2h/4} In Cm3 = Vc :
3. Weight of {Core Cutter + Wet Soil Sample} = Ws Grams:
4. Weight of Wet Soil sample in Cutter = (Ws – Wc) In Grams:
5. Bulk Density (γ) in Grams /Cm3 = (Ws – Wc) / Vc :
PART-II: CALCULATION OF MOISTURE CONTENT & DRY DENSITY
1. Weight of container + Wet soil sample in Grams = W1:
2. Weight container + Weight of Dry soil sample in Grams = W2:
3. Weight of container in Grams = Wc:
4. Weight of water in Grams (Ww) in Grams = W1 - W2:
5. Weight of dry soil (Ws) in Grams = W2 - Wc:
6. Moisture content (ω) in Grams = Ww x 100/ Ws:
7. Dry Density (γd) = γ x100/(1+ω):
8. Laboratory control density in Grams/ Cm3 = γd (Lab):
9. Optimum moisture content in % =
10. Degree of Compaction ={γd / γd / ab} x 100:
Remarks:
|  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  | REV NO.: 00
UNIT NO. |  | ACCEPTED BY |  |  | LOGSHEETNO. L-13
RATING |  | CUSTOMER |  |  | SHEET: 01 Of 01

## CLS no. 14
Instrument Reg. No.
Date Of Inspection
PSWR-NAGPUR
Drawing/Doc. Reference
ROAD WORKS
AREA / LOCATION:
ROAD (W.B.M)
(a) SPREADING OF AGGREGATE AND MOORUM
(b) WATERING
(c) ROLLING OF W B M FIRST LAYER
(d) ROLLING OF W B M SECOND LAYER
(e) CHECK FOR CAMBER
BACK TOPPING
(a) CHECK FOR CAMBER AND LEVELS/COMPACTION
(b) CHECK FOR SURFACE PREPARATION
(c) CHECK FOR TACK COAT
(d) CHECK FOR PROPORTION / THICKNESS / ROLLING
(e) CHECK FOR SEAL COAT
(f) CHECK FOR SAND SPRAY
ACCEPTABLE / RELEASED FOR FURTHER WORK.
|  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  | REV NO.: 00
UNIT NO. |  | ACCEPTED BY |  |  | LOGSHEETNO. L-14
RATING |  | CUSTOMER |  |  | SHEET: 01 Of 01

## CLS no. 15
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
MAX. DRY DENSITY OF SOIL FOR BACK FILLING
&
CNS SOIL OPTIMUM MOISTURE CONTENT
AREA / LOCATION:
Sl. No. | Location of Soil Selected for Filling (Sample) |  | Date of Sample Collection |  |  | Date of Testing | Test Results |  |  | Reference & Date of Lab Test Report |  | Remarks
As per Lab Report
[7 empty] | O.M.C |  | M.D.D
[5 empty] | NAME |  |  | SIG. /DATE |  |  | DOC. NO. QPE - CL - 001
PROJECT |  |  |  | CHECKED BY | [6 empty] | REV NO.: 00
UNIT NO. |  |  |  | ACCEPTED BY | [6 empty] | LOGSHEETNO. L-15
RATING |  |  |  | CUSTOMER | [6 empty] | SHEET: 01 Of 01

## CLS no. 16
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
UNDERGROUND PIPING (RCC) HYDRO TEST
AREA / LOCATION:
Sl. No. | Drawing/Document |  |  | Size Of Pipe | LOCATION OF PIPE |  |  |  | Initial Head Reading | Final Head Reading | Head Loss | Remarks
| Reference No. |  |  |  | FROM |  | TO
[6 empty] | NAME |  | SIG. / DATE |  | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY | [6 empty] | REV NO.: 00
UNIT NO. |  |  | ACCEPTED BY | [6 empty] | LOGSHEETNO. L-16
RATING |  |  | CUSTOMER | [6 empty] | SHEET: 01 Of 01

## CLS no.17
Instrument Reg. No.
Date Of Inspection
PSWR-NAGPUR
Drawing/Doc. Reference
BITUMEN TEMPERATURE AND CONSUMPTION
AREA/LOCATION:
BITUMEN GRADE:
Date | Opening | Receipt |  | Cumulative |  |  | Consumption |  |  | Cumulative | Closing | Location | Bitumen |  | Remarks
| Balance | Quantity |  | Quantity | [5 empty] | Consumption | Balance |  | temperature
[6 empty] | Tack |  | Carpet | Sealing
Coat
[10 empty] | NAME |  | SIGNATURE / DATE |  | DOC. NO. QPE - CL - 001
PROJECT |  |  |  |  | CHECKED BY | [8 empty] | REV NO.: 00
UNIT NO. |  |  |  |  | ACCEPTED BY | [8 empty] | LOG SHEETNO. L-17
RATING |  |  |  |  | CUSTOMER | [8 empty] | SHEET: 01 Of 01

## CP no.1
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR SITE GRADING
AREA/ LOCATION |  |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK |  | REMARK
1 | Cleaning and stripping of soil including disposal of unsuitable material
2 | Taking and plotting of initial joint level at specified intervals for cutting as well as filling areas
3 | Classification and testing of filling soil for suitability including preparation of lead charts to filling/disposal area
4 | Proper warning of explosions, misfires and storage of explosive material (as applicable)
5 | Breaking up colds, lump etc at the time of filling and compaction
6 | Identification and suitability of borrowed areas for filling soil/murrum including verification of payment for royalty etc.
REMARK(IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 00
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-01
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.2
PSWR-NAGPUR | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR PILING WORKS
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  | OK/NOT OK | REMARK
1 | BORING AND CONCRETING OF PILE
a. | diameter of bore hole
b. | check for pile layout
c. | check and record ground level
d. | cleaning/flushing of pile after completion of bore, after lowering of reinforcement cage and just before placing concrete
e. | During boring record size of bore commencement of SPT/core recovery, ensure socket length equivalent in items of the diameter of pile below the socket horizon
f. | Check for pile casting, reinforcement and pouring of sound concrete of required strength
g. | Check for pile termination level and record soil data
h. | Check for pile cap line level, shape, size, reinforcement, concreting, and curing etc.
2.2 | TESTING OF PILE
a. | Bentonite liquid limit, sand content density of fresh prepared bentonite suspension, marsh viscosity, differential free swell, PH value
b. | Density of mud sample collected from pile
c. | slump test & cube test for concrete
d. | Initial pile load test: vertical load(compression),lateral load(horizontal),and pull out load ( tension)
e. | Routine pile test compression and horizontal
f. | Pile integrity test(NDT)
REMARK(IF ANY)
|  |  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-02
RATING |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.3
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR MASONARY BRICK WORK
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | Review of calibration certificate of instrument testing equipment
2 | Check for field calibration of instruments/testing equipment in case of doubt or out of calibration
3 | Ensure that incoming material(cement, sand, brick and water) are as per specification/approve brand
4 | Ensure that brick have uniform colour and are free from crack and efflorescence. NOTE: Efflorescence check on each source of supply
5 | Ensure that clear ringing sound is heard of being struck
6 | Check for compressive strength test wrap age curing and water absorption test on brick
7 | Check for cement mortar proportion and mixing
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-03
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.4
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR ANTITERMITE TREATMENT
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | Testing of material & spraying device including personal protective equipment like face mask gloves ,shoes, etc
2 | Check for preparation of surface for taking dosage of emulsion by ramming of each layer of soil by roding the earth at specified intervals
3 | Ensure backfilling and compaction in specified layers along with application of emulsifier along sides of masonry & RCC structure
4 | Ensure compaction of top surface for taking dosage of emulsifier by roding the earth at specified intervals for the entire floor area before concreting
5 | Check for consumption of emulsifier utilized
6 | Review of test and inspection documents
REMARK(IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-04
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.5
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR PLASTERING
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | Check for completeness of hidden jobs like piping work, conduit work etc
2 | Check for grading of sand mix proportion
3 | Ensure for sample preparation for finish and its approval
4 | Check for neeru application on plaster
5 | Hacking and cleaning of surface removing loose particles and wetting of plastering surfaces
6 | Ensure fixing of chicken mesh at RCC/brick masonry connection
7 | Check for plaster thickness line ,level, plumbness and finishing of surface
8 | Check for grooves, opening, rounding of corners hollow in plaster
9 | Ensure that curing of plastered surface is carried out for seven days minimum
10 | Review of test and inspection documents
REMARK(IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-05
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no. 6
PSWR-NAGPUR | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR DOORS , WINDOWS & VENTILATION INSTALLATION
AREA/ LOCATION |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  | OK/NOT OK | REMARK
1 | Check for material as per specifications
2 | Check for section, dimension
3 | Check for levels, line & plumb
4 | Check for section joinery details
5 | Check for grouting with lugs/fasteners
6 | Check for fixture and fittings
7 | Check for thickness and type of glazing
8 | Check for brand/shade of paints surface preparation and number of coats
9 | Review of test and inspection documents
REMARK (IF ANY)
|  |  |  | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-06
RATING |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.7
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR PAINTING
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | Check for brand, type & shade of paints. review manufacturers test certificate as applicable
2 | Check for proper surface preparation as per specification
3 | Confirm for brand, type & shade of paints
4 | Check for no. of coats and thickness dry film thickness(DFT)
5 | Check for curing of painted surface(as applicable)
6 | Review of test and inspection documents
REMARK(IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-07
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.8
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR SANITARY FITTING
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | Ensure that all pipes, fitting and fixture are as per relevant code and of approved brand
2 | Check for samples as applicable
3 | Check for completion of finishing work w.r.t line level and position
4 | Check for proper fixing of sanitary fitting to ensure that they are free from leakages
5 | Leak test on all sanitary fitting to ensure that they are free from leakages
6 | Review of test and inspection documents
REMARK (IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-08
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no. 9
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR WATER PROOFING
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | Surface preparation for screed
2 | Check for mix proportion, thickness for screed/plaster/concrete and slope toward rain water pipes
3 | Formation of groove at specified height on parapet wall
4 | Check for material, no of coats, application procedure and consumption
5 | Ensure termination of material in grooves on vertical plane
6 | Check for hollowness, bubbles in water proofing if any
7 | Conduct waterproofing test by flooding the area for specified period, as applicable
8 | Check for cleaning of surfaces
9 | Submission of guarantee in the prescribed Performa
10 | Review of test and inspection documents
REMARK (IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-09
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.10
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR FALSE CEILING & FALSE FLOORING
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | FALSE CEILING
1 | Ensure that false ceiling is done as per technical specification and drawing
2 | As applicable ensure that resin mineral wool is packed in black polythene and laid on top of ceiling panels
3 | Checking for proper line & horizontality of false ceiling and cut outs
4 | Check for proper surface preparation and painting of panel boards
5 | Review of test and inspection documents
2 | FALSE FLOORING
1 | Ensure that false flooring is done as per technical specification and drawing
2 | heck for proper cleaning of base floor
3 | Check for proper surface preparation and painting of base floor
4 | Check for proper line and layout of false flooring
5 | Review of test and inspection documents
REMARK (IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-10
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01

## CP no.11
PSWR-NAGPUR |  | Instrument Reg. No.
Date Of Inspection
Drawing/Doc. Reference
PROTOCOL FOR UNDER DECK INSULATION
AREA/ LOCATION |  |  |  | DATE
SR NO. | CHECK/CHARACTERISTICS |  |  | OK/NOT OK | REMARK
1 | Verification of manufacturers TC for type of wool thickness & density Thermal conductivity etc.
2 | Check for adhesive and fasteners for anchoring
3 | Fixing of scaffolding, ladders & platforms
4 | Fixing of under deck insulation with adhesive
5 | Fixing of dash fasteners at definite intervals
6 | Review of test and inspection documents
REMARK (IF ANY)
[5 empty] | NAME | SIG. / DATE | DOC. NO. QPE - CL - 001
PROJECT |  |  | CHECKED BY |  |  |  | REV NO.: 01
UNIT NO. |  |  | ACCEPTED BY |  |  |  | PROTOCOL NO. P-11
RATING |  |  | CUSTOMER |  |  |  | SHEET: 01 Of 01