## Sheet1
1x250 MW NSPCL, PP-II expansion, Rourkela, Odisha
BHEL PSER - DAILY PROGRESS REPORT
SL NO | SCOPE OF WORK | PLANT FACILITY / AREA |  |  | WORK EXECUTION SUMMARY |  |  | DATE OF UPDATE | MANPOWER STSTUS |  |  |  | DATE (MM/DD/YY) | 2020-06-16
|  | ITEM | UNIT | SCOPE | EXECUTED FOR THE DAY | EXECUTED FOR THE MONTH | CUMULATIVE UPTO DATE |  | ENGG/ SUP STAFF | SKILLED | UNSKILLED | TOTAL | AGENCY
1 | CIVIL | Main Plant PCC & RCC | CUM | 62055 | [8 empty] | M/S Bridge & Roof
|  | BOP Area PCC & RCC | CUM | 35489
2 | STRUCTURAL | Main Plant Erection | MT | 7984 | [8 empty] | M/S Bridge & Roof
|  | BOP Area Erection | MT | 6180
3 | BOILER & AUXILIARIES | Erection | MT | 17682 | [8 empty] | M/S Bridge & Roof
4 | TURBINE & AUXILIARIES | Erection | % | 100 | [8 empty] | M/S Golden Edge Pvt Ltd
5 | ELECTRICAL SYSTEM | Erection | % | 100 | [8 empty] | M/S Powertronix Pvt Ltd
6 | C&I SYSTEM | Erection | % | 100 | [8 empty] | M/S Nuvotronix Pvt Ltd
7 | IDCT COOLING TOWER | E&C | % | 100 | [8 empty] | M/S Hamon Shriram Cottrell Pvt Ltd
8 | COMPRESSOR SYSTEM | E&C | % | 100 | [8 empty] | M/S ELGI Equipments Limited
9 | AIR-CONDITIONING SYSTEM | E&C | % | 100 | [8 empty] | M/S Sterling and Wilson Pvt Ltd
10 | VENTILATION SYSTEM | E&C | % | 100 | [8 empty] | M/S Sterling and Wilson Pvt Ltd
11 | TG/ESP ELEVATOR | E&C | % | 100 | [8 empty] | M/S Bharat Elevators and Engg Pvt Ltd
12 | MILL REJECT SYSTEM | E&C | % | 100 | [8 empty] | M/S HV Equipments Pvt Ltd
13 | MISC TANKS | E&C | % | 100 | [8 empty] | M/S XICON International Ltd
14 | WATER TREATMENT SYSTEMS | E&C | % | 100 | [8 empty] | M/S ION Exchange (India) Limited
15 | CW TREATMENT SYSTEM | E&C | % | 100 | [8 empty] | M/S Chembond Water Technologies Ltd
16 | CHIMNEY SYSTEM | Accessories Erection | % | 100 | [8 empty] | M/S BYGGING Ltd
17 | RAW WATER SYSTEM | Excavation of Well & CER | Mtr | 15.5 | [8 empty] | M/S JUSCO Ltd
|  | PCC Footings | Nos. | 20
|  | Piping Erection | MTR | 6920
SL | SCOPE OF WORK | PLANT FACILITY / AREA | MAJOR ACTIVITY UNDER PROGRESS | [7 empty] | MAJOR CONSTRAINTS (IF ANY) |  |  | RESPONSIBILITY
1 | CIVIL | Main Plant PCC & RCC | Pipe Pedestal & trench, Parshal flume RCC, IDCT, Power House, Drain & roads | [7 empty] | Non-finalization of dedicated approach for project work. frequent stoppage of work as approach roads are common for O&M & project.
|  | BOP Area PCC & RCC | AHP Pipe rack foundations, ERH, CHP MCC, Silo utility Bldg | [7 empty] | Rerouting / removal of fire water line from chp mcc-iii area. Dismantling and removal of ht tower from coal stock pile area
2 | STRUCTURAL | Main Plant Erection | Pipe rack erection in progress | [7 empty] | No space for pre assembly of structures
|  | BOP Area Erection - CHP | Crusher House/ TP-2/TP-3/TP-5 | [7 empty] | Non-sequential supply of materials. Huge modification work involved which badly hampering erection.
3 | BOILER & AUXILIARIES | Erection | APH Module erection completed. Fabrication of ducting in ESP I/L, APH to wind box,ESP O/L,Pressuure parts - down comer's supports, roof screen casing ,LDO & Atomizing air piping, furnace insulation, pent house enclosers, lift cladding structure, erection of different floors, furnace guide , erection of ESP ' C' pass etc. | [7 empty] | Material for Duct support structure and Eco by-pass material not available . Fastners for LDO piping.
4 | TURBINE & AUXILIARIES | Erection | Condenser TSP welding, TG coupling bolt stretching started, Condensate discharge pipiing works U/P. | [7 empty] | Slow work progress due Shortage of consumables , T & Ps & manpower
5 | ELECTRICAL SYSTEM | Erection | LT Panels Erection in progress CHP HTSWGR Erection in Progress Tray Works in Progress | [7 empty] | Availibility of Fronts Availibility of Lighting materials |  |  | B&R PSERHQ
6 | C&I SYSTEM | Erection | UPS & 24V charger panel erection under progress. | [7 empty] | CER readiness.
7 | IDCT COOLING TOWER | E&C | Front not available | [7 empty] | Civil works under progress, No Front avalable till date |  |  | B&R
8 | COMPRESSOR SYSTEM | E&C | Front not available | [7 empty] | Compresssor house Civil works yet to sart, front not avalable till date. |  |  | B&R
9 | AIR-CONDITIONING SYSTEM | E&C | Ducting works in progress in TG building CCR portion.TG building Roof RE fans erection completed. Pipe support in AC plant roon under progress. | [7 empty] | Readiness of AHU Room & Cooling tower foundation with AC plant roon at Zero mtr.
10 | VENTILATION SYSTEM | E&C | Work not started, vendor has to mobilize manpower for ventilation works. | [7 empty] | Air Washer room not ready, erection of AHU held up |  |  | B&R
11 | TG/ESP ELEVATOR | E&C | Vendor not mobilized manpower.
12 | MILL REJECT SYSTEM | E&C | Front not available | [7 empty] | No front available
13 | MISC TANKS | E&C | Sheet short blasting done , painting of sheet done ,4th shell weding u/p,
14 | WATER TREATMENT SYSTEMS | E&C | No manpower available at site. | [7 empty] | Permit is required from NSPCL for changing existing manual valves by MOV .
15 | CW TREATMENT SYSTEM | E&C | Vendor not mobalize man power due to non availability of front. | [7 empty] | No front available till date
16 | CHIMNEY | E & C | Vendor not mobalize man power.
17 | RAW WATER SYSTEM | Excavation | Excavation of intake well in progress
|  | Erection and Piping | GRP Pipe laying in progress, footing work of switchgear bldg in progress. | [7 empty] | Tree cutting permission for GRP Pipe not yet received from NSPCL