## ABSTRACT
MAIN ELECTRICALS WORKS (PKG-A) MEASUREMENT SHEET
1 X 250 MW NSPCL ROURKELA TPP-II SITE
ABSTRACT BILLING (RA-07)
BILL PERIOD: 01.08.2019 - 31.08.2019 | [6 empty] | MEASUREMENT QUANTITY
SL NO | EQUIPMENT/ITEM DESCRIPTION | BBU QTY |  | % BREAKUP OF UNIT RATE | UNIT RATE (Rs) | ALLOTED AMOUNT (Rs)
|  | QTY | UOM |  |  |  | UP TO PREV | PRESENT BILL | CUM
1 | 2 | 3 | 4 | 5 | 6 | 7 = 3x5x6 | 8 | 9 | 10
SCH-3 TRANSFORMER & BUS DUCT
1.00 | BUS DUCTS & ASOCIATED EQUIPMENT
1.01 | SEGREGATED PHASE BUSDUCT (6.6 KV/ 4000 A)
(i) | Pre-assembly, alingnment, erection, welding etc | 300 | MTR | 65% | 5336.5018 | 1040617.8438 | 0 |  | 0
(ii) | Pre-commissioning checks & tests | 300 | MTR | 15% | 5336.5018 | 240142.5793 | 0 |  | 0
(iii) | Charging | 300 | MTR | 10% | 5336.5018 | 160095.0529 | 0 |  | 0
1.02 | COMMON CHAMBER FOR GENERATOR PH AND N-SIDE
(i) | Pre-assembly, alingnment, erection, welding etc | 1 | SET | 65% | 36055.4931 | 23436.0705 | 0 |  | 0
(ii) | Pre-commissioning checks & tests | 1 | SET | 15% | 36055.4931 | 5408.324 | 0 |  | 0
(iii) | Charging | 1 | SET | 10% | 36055.4931 | 3605.5493 | 0 |  | 0
1.03 | MAIN RUN ISOLATED PHASE BUSDUCT (21 KV, 12500A)
(i) | Pre-assembly, alingnment, erection, welding etc | 125 | MTR | 65% | 6850.7281 | 556621.6581 | 0 |  | 0
(ii) | Pre-commissioning checks & tests | 125 | MTR | 15% | 6850.7281 | 128451.1519 | 0 |  | 0
(iii) | Charging | 125 | MTR | 10% | 6850.7281 | 85634.1012 | 0 |  | 0
1.04 | TAP OFF IP BUS DUCT (21 KV, 1500 AMP)
(i) | Pre-assembly, alingnment, erection, welding etc | 100 | MTR | 65% | 5408.2002 | 351533.0132 | 0 |  | 0
(ii) | Pre-commissioning checks & tests | 100 | MTR | 15% | 5408.2002 | 81123.003 | 0 |  | 0
(iii) | Charging | 100 | MTR | 10% | 5408.2002 | 54082.002 | 0 |  | 0
1.05 | SPVT CUBICLE FOR IP BUSDUCT
(i) | Placenment ,Alingnment & Coupling | 1 | SET | 70% | 57690.0266 | 40383.0186 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 |  | 0
(iii) | Charging | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 |  | 0
1.06 | NG CUBICLE (WITH NGT & NGR ) FOR IP BUSDUCT
(i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0
(iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0
1.07 | HOT AIR BLOWING EQUIPMENT WITH PIPINGS
(i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0
(iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0
2.00 | 415V LV BUS-DUCT SET FOR DTT AND PMCC
2.01 | BUSDUCT FOR UNIT PMCC #1 DA
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 |  | 2
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2
(iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 |  | 0
2.02 | BUSDUCT FOR ESP PMCC #1DB-1
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 |  | 2
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2
(iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 |  | 0
2.03 | BUSDUCT FOR ESP PMCC #1DB-2
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 |  | 2
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 2 | 2
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0
2.04 | BUSDUCT FOR STATION PMCC #0DA
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 |  | 2
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0
2.05 | BUSDUCT FOR COOLING TOWER PMCC #1DC
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 0 |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0
2.06 | BUSDUCT FOR PTP PMCC #1DD
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0
(iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0
2.07 | BUSDUCT FOR ETP PMCC #1DE
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0
(iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0
3.00 | POWER TRANSFORMERS AND DTT | [5 empty] | 0 |  | 0
3.01 | GENERATOR TRANSFORMERS - 315 MVA | [5 empty] | 0 |  | 0
(i) | Placement on Foundation and alignment | 1 | NO | 35% | 951874.9193 | 333156.2218 | 1 |  | 1
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 951874.9193 | 190374.9839 | 0 |  | 0
(iii) | Completion of Oil filteration | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 |  | 0
(iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 951874.9193 | 142781.2379 | 0 |  | 0
(v) | Charging | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 |  | 0
3.02 | STATION TRANSFORMER - 37.5/30 MVA, 220/6.9 KV | [5 empty] | 0 |  | 0
(i) | Placement on Foundation and alignment | 1 | NO | 35% | 633718.9956 | 221801.6484 | 1 |  | 1
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 633718.9956 | 126743.7991 | 1 |  | 1
(iii) | Completion of Oil filteration | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 |  | 0
(iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 633718.9956 | 95057.8493 | 0 |  | 0
(v) | Charging | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 |  | 0
3.03 | UAT - 37.5/30 MVA,16.5/6.9 KV | [5 empty] | 0 |  | 0
(i) | Placement on Foundation and alignment | 2 | NO | 35% | 476803.4969 | 333762.4479 | 0 |  | 0
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 20% | 476803.4969 | 190721.3988 | 0 |  | 0
(iii) | Completion of Oil filteration | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 |  | 0
(iv) | Pre-commissioning checks & tests | 2 | NO | 15% | 476803.4969 | 143041.0491 | 0 |  | 0
(v) | Charging | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 |  | 0
3.04 | 2500KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 70% | 28845.4259 | 121150.7886 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 |  | 0
(iii) | Charging of Transformer | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 |  | 0
3.05 | 2000KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 28845.3227 | 40383.4518 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 28845.3227 | 5769.0645 | 2 |  | 2
(iii) | Charging of Transformer | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 |  | 0
3.06 | 1600KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 11 | NO | 70% | 25960.4163 | 199895.2058 | 4 |  | 4
(ii) | Pre-Commissioning Checks ,Testing | 11 | NO | 10% | 25960.4163 | 28556.458 | 4 |  | 4
(iii) | Charging of Transformer | 11 | NO | 10% | 25960.4163 | 28556.458 | 0 |  | 0
3.07 | 1250KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0
3.08 | 1000KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0
3.09 | 630KVA DTT, 6.6/0.415KV | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0
3.10 | 500KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | NO | 70% | 23076.2272 | 64613.4363 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 |  | 0
(iii) | Charging of Transformer | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 |  | 0
3.11 | 33/6.9KV 2MVA OIL FILLED RAW WATER TRF | [5 empty] | 0 |  | 0
(i) | Placement on Foundation and alignment | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 |  | 0
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 30% | 28845.3227 | 17307.1936 | 0 |  | 0
(iii) | Completion of Oil filteration | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 |  | 0
(iv) | Pre-commissioning checks & tests | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 |  | 0
(v) | Charging | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 |  | 0
3.12 | 6.6 KV NEUTRAL GROUNDING RESISTORS | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 70% | 20485.634 | 71699.7191 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 10% | 20485.634 | 10242.817 | 0 |  | 0
(iii) | Charging of Transformer | 5 | NO | 10% | 20485.634 | 10242.817 | 0 |  | 0
4.00 | HVR TRANSFORMER(95 KVp,1200mA)COMMISSIONING | [5 empty] | 0 |  | 0
(i) | Test of HVR including Interlock/Protection, OCC/SCC | 28 | NO | 50% | 8473.3569 | 118626.9969 | 0 |  | 0
(ii) | Charging (Field-Charging) | 28 | NO | 40% | 8473.3569 | 94901.5975 | 0 |  | 0
5.00 | BUS DUCTS & EQUIPMENT SUPPORT STRUCTURE | [5 empty] | 0 |  | 0
(i) | Pre-assembly, alignment, erection including welding | 50 | MT | 70% | 8654.3208 | 302901.2292 | 0 |  | 0
(ii) | Pre-Commissioning Checks /Testing & charging | 50 | MT | 10% | 8654.3208 | 43271.6042 | 0 |  | 0
(iii) | Charging | 50 | MT | 10% | 8654.3208 | 43271.6042 | 0 |  | 0
6 | GENERATOR CIRCUIT BREAKER | [5 empty] | 0 |  | 0
(i) | Placement, alignment, installation, internal wiring | 1 | NO | 60% | 36398.9377 | 21839.3626 | 0 |  | 0
(ii) | Pre-commissioning checks/testing | 1 | NO | 20% | 36398.9377 | 7279.7875 | 0 |  | 0
(iii) | Charging | 1 | NO | 10% | 36398.9377 | 3639.8938 | 0 |  | 0
7.0 | UNLOADING AND SHIFTING OF TRANSFORMERS | [5 empty] | 0 |  | 0
7.1 | GENERATOR TRANSFORMERS (GT) - 315 MVA | [5 empty] | 0 |  | 0
7.1.1 | UNLOADING OF GT FROM TRAILER | 1 | NO | 90% | 214172.0425 | 192754.8382 | 0 |  | 0
7.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 1 | NO | 90% | 160628.7225 | 144565.8502 | 0 |  | 0
8.1 | STATION /UNIT TRANSFORMER (ST/UT) (37.5/30 MVA) | [5 empty] | 0 |  | 0
8.1.1 | UNLOADING OF ST / UT FROM TRAILER | 1 | NO | 90% | 84371.0296 | 75933.9267 | 0 |  | 0
8.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 1 | NO | 90% | 63277.9628 | 56950.1665 | 1 |  | 1
[7 empty] | 0 |  | 0
| SCH-4-CABLING & EQUIPMENT | [5 empty] | 0 |  | 0
1.00 | CABLE TRAY SUPPORT SYSTEM WITH ACCESORIES | [5 empty] | 0 |  | 0
1.01 | CHANNEL | [5 empty] | 0 |  | 0
1.01.01 | SINGLE(SC1) | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 6600 | RM | 70% | 109.3923 | 505392.4429 | 2046 |  | 2046
(ii) | Final painting and marking of tray nos | 6600 | RM | 20% | 109.3923 | 144397.8408 | 0 |  | 0
1.01.02 | DOUBLE(DC1) | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5500 | RM | 70% | 127.6211 | 491341.1658 | 2280 | 600 | 2880
(ii) | Final painting and marking of tray nos | 5500 | RM | 20% | 127.6211 | 140383.1902 | 0 |  | 0
1.02 | CANTILEVER ARM | [5 empty] | 0 |  | 0
1.02.01 | 600 MM Cantilever Arm | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 12000 | NOS | 70% | 51.0519 | 428835.5511 | 5177 |  | 5177
(ii) | Final painting and marking of tray nos | 12000 | NOS | 20% | 51.0519 | 122524.4432 | 0 |  | 0
1.02.02 | 300 MM Cantilever Arm | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 6500 | NOS | 70% | 33.1867 | 150999.4646 | 1050 |  | 1050
(ii) | Final painting and marking of tray nos | 6500 | NOS | 20% | 33.1867 | 43142.7042 | 0 |  | 0
1.02.03 | 150 MM Cantilever Arm | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 1500 | NOS | 70% | 20.426 | 21447.2789 | 725 |  | 725
(ii) | Final painting and marking of tray nos | 1500 | NOS | 20% | 20.426 | 6127.794 | 0 |  | 0
1.02.04 | 100 MM Cantilever Arm | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 500 | NOS | 70% | 20.426 | 7149.093 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 500 | NOS | 20% | 20.426 | 2042.598 | 0 |  | 0
2 | LADDER TYPE CABLE TRAY | [5 empty] | 0 |  | 0
2.1 | 600 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 24790 | MTR | 70% | 58.0426 | 1007212.5052 | 4125 | 1000 | 5125
(ii) | Final painting and marking of tray nos | 24790 | MTR | 20% | 58.0426 | 287775.0015 | 0 |  | 0
2.2 | 450 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 50.3607 | 35252.5135 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 50.3607 | 10072.1467 | 0 |  | 0
2.3 | 300 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5050 | MTR | 70% | 43.5319 | 153885.2654 | 2250 |  | 2250
(ii) | Final painting and marking of tray nos | 5050 | MTR | 20% | 43.5319 | 43967.2187 | 0 |  | 0
2.4 | 150 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 4150 | MTR | 70% | 35.8498 | 104143.5366 | 625 | 250 | 875
(ii) | Final painting and marking of tray nos | 4150 | MTR | 20% | 35.8498 | 29755.2962 | 0 |  | 0
2.5 | 100 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 35.85 | 25095.0316 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 35.85 | 7170.009 | 0 |  | 0
2.6 | 50 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 17.9247 | 6273.6496 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 17.9247 | 1792.4713 | 0 |  | 0
3 | CABLE TRAY 90 DEG BEND HORIZONTAL | [5 empty] | 0 |  | 0
3.1.1 | 600 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 400 | NO | 70% | 173.274 | 48516.7146 | 132 |  | 132
(ii) | Final painting and marking of tray nos | 400 | NO | 20% | 173.274 | 13861.9185 | 0 |  | 0
3.1.2 | 450 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0
3.1.3 | 300 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 120 | NO | 70% | 144.2519 | 12117.1581 | 9 |  | 9
(ii) | Final painting and marking of tray nos | 120 | NO | 20% | 144.2519 | 3462.0452 | 0 |  | 0
3.1.4 | 150 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0
3.1.5 | 100 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0
3.1.6 | 50 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 68.2557 | 477.7902 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 68.2557 | 136.5115 | 0 |  | 0
3.2 | CABLE TRAY 90 DEG BEND VERTICAL-INSIDE | [5 empty] | 0 |  | 0
3.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 173.2755 | 24258.5739 | 50 |  | 50
(ii) | Final painting and marking of tray nos | 200 | NO | 20% | 173.2755 | 6931.0211 | 0 |  | 0
3.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0
3.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 144.2509 | 7573.1697 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 144.2509 | 2163.7628 | 0 |  | 0
3.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 |  | 0
3.3 | CABLE TRAY 90 DEG BEND VERTICAL-OUTSIDE | [5 empty] | 0 |  | 0
3.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 173.2735 | 18193.7138 | 50 |  | 50
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 173.2735 | 5198.204 | 0 |  | 0
3.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0
3.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 |  | 0
3.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0
3.4 | TEES | [5 empty] | 0 |  | 0
3.4.1 | 600 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 231.3177 | 32384.4727 | 50 |  | 50
(ii) | Final painting and marking of tray nos | 200 | NO | 20% | 231.3177 | 9252.7065 | 0 |  | 0
3.4.2 | 450 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 |  | 0
3.4.3 | 300 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 173.2693 | 2425.7708 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 173.2693 | 693.0774 | 0 |  | 0
3.4.4 | 150 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 137.4191 | 1442.9004 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 15 | NO | 20% | 137.4191 | 412.2573 | 0 |  | 0
3.4.5 | 100 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 |  | 0
3.4.6 | 50 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 68.3176 | 239.1117 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 68.3176 | 68.3176 | 0 |  | 0
3.5.0 | CROSSES | [5 empty] | 0 |  | 0
3.5.1 | 600 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 90 | NO | 70% | 260.3372 | 16401.2425 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 90 | NO | 20% | 260.3372 | 4686.0693 | 0 |  | 0
3.5.2 | 450 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 215.9679 | 1511.775 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 215.9679 | 431.9357 | 0 |  | 0
3.5.3 | 300 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 202.3126 | 2124.2821 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 15 | NO | 20% | 202.3126 | 606.9377 | 0 |  | 0
3.5.4 | 150 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 |  | 0
3.5.5 | 100 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 |  | 0
3.5.6 | 50 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 86.2634 | 301.9218 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 86.2634 | 86.2634 | 0 |  | 0
3.6 | REDUCERS LHS | [5 empty] | 0 |  | 0
3.6.1 | 600 MM-450 MM Reducer LHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 158.7642 | 5556.7477 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 158.7642 | 1587.6422 | 0 |  | 0
3.6.2 | 600 MM-300 MM Reducer LHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 144.2591 | 2524.5343 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 25 | NO | 20% | 144.2591 | 721.2955 | 0 |  | 0
3.6.3 | 450 MM -300 MM Reducer LHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 40 | NO | 70% | 137.4242 | 3847.8789 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 40 | NO | 20% | 137.4242 | 1099.394 | 0 |  | 0
3.6.4 | 300 MM -150 MM Reducer LHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0
3.7 | REDUCERS RHS | [5 empty] | 0 |  | 0
3.7.1 | 600 MM-450 MM Reducer RHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 158.758 | 2222.6125 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 158.758 | 635.0321 | 0 |  | 0
3.7.2 | 600 MM-300 MM Reducer RHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 |  | 0
3.7.3 | 450 MM -300 MM Reducer RHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0
3.7.4 | 300 MM -150 MM Reducer RHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 |  | 0
3.8 | CABLE TRAY COVER WITH FIXING HARDWARES | [5 empty] | 0 |  | 0
3.8.1 | 600 MM wide Tray Cover | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 58.0428 | 20314.9637 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 58.0428 | 5804.2753 | 0 |  | 0
3.8.2 | 450 MM wide Tray Cover | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 250 | MTR | 70% | 58.0428 | 10157.4819 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 250 | MTR | 20% | 58.0428 | 2902.1377 | 0 |  | 0
3.8.3 | 300 MM wide Tray Cover | [5 empty] | 0 |  | 0
| Fabrication and erection complete as applicable | 100 | MTR | 70% | 50.3595 | 3525.1647 | 70 |  | 70
| Final painting and marking of tray nos | 100 | MTR | 20% | 50.3595 | 1007.1899 | 0 |  | 0
3.8.4 | 150 MM wide Tray Cover | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 100 | MTR | 70% | 43.5339 | 3047.3745 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 100 | MTR | 20% | 43.5339 | 870.6784 | 0 |  | 0
3.8.5 | 100 MM wide Tray Cover | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 43.5277 | 1523.4707 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 43.5277 | 435.2773 | 0 |  | 0
3.8.6 | 50 MM wide Tray Cover | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 21.7701 | 761.9519 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 21.7701 | 217.7005 | 0 |  | 0
4.00 | PERFORATED TYPE CABLE TRAY | [5 empty] | 0 |  | 0
4.10 | 600 MM Perforated Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 7500 | MTR | 70% | 71.6997 | 376423.3085 | 1650 |  | 1650
(ii) | Final painting and marking of tray nos | 7500 | MTR | 20% | 71.6997 | 107549.5167 | 0 |  | 0
4.20 | 450 MM Perforated Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 64.8708 | 22704.7811 | 150 |  | 150
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 64.8708 | 6487.0803 | 0 |  | 0
4.30 | 300 MM Perforated Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 3500 | MTR | 70% | 58.0426 | 142204.3129 | 887.5 |  | 887.5
(ii) | Final painting and marking of tray nos | 3500 | MTR | 20% | 58.0426 | 40629.8037 | 0 |  | 0
4.40 | 150 MM Perforated Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 1500 | MTR | 70% | 43.5319 | 45708.4518 | 250 |  | 250
(ii) | Final painting and marking of tray nos | 1500 | MTR | 20% | 43.5319 | 13059.5577 | 0 |  | 0
4.50 | 100 MM Perforated Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 43.5321 | 30472.4456 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 43.5321 | 8706.413 | 0 |  | 0
4.60 | 50 MM Perforated Cable Tray | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 21.3394 | 14937.5498 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 21.3394 | 4267.8714 | 0 |  | 0
5.00 | CABLE TRAY ACCESSORIES (PERFORATED-TYPE) | [5 empty] | 0 |  | 0
5.10 | HORIZONTAL 90 DEG BEND PERFORATED | [5 empty] | 0 |  | 0
5.1.1 | 600 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 230 | NO | 70% | 187.7847 | 30233.3339 | 67 |  | 67
(ii) | Final painting and marking of tray nos | 230 | NO | 20% | 187.7847 | 8638.0954 | 0 |  | 0
5.1.2 | 450 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0
5.1.3 | 300 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 35 | NO | 70% | 158.7713 | 3889.8967 | 5 |  | 5
(ii) | Final painting and marking of tray nos | 35 | NO | 20% | 158.7713 | 1111.399 | 0 |  | 0
5.1.4 | 150 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 |  | 0
5.1.5 | 100 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0
5.1.6 | 50 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 72.5256 | 253.8396 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 72.5256 | 72.5256 | 0 |  | 0
5.20 | VERTICAL 90 DEG BEND PERFORATED (INSIDE) | [5 empty] | 0 |  | 0
5.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 187.7868 | 13145.0784 | 20 |  | 20
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 187.7868 | 3755.7367 | 0 |  | 0
5.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0
5.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 158.7642 | 11113.4954 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 158.7642 | 3175.2844 | 0 |  | 0
5.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 |  | 0
5.30 | VERTICAL 90 DEG BEND PERFORATED (OUTSIDE) | [5 empty] | 0 |  | 0
5.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 110 | NO | 70% | 187.7835 | 14459.3264 | 25 |  | 25
(ii) | Final painting and marking of tray nos | 110 | NO | 20% | 187.7835 | 4131.2361 | 0 |  | 0
5.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 173.2693 | 3032.2134 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 25 | NO | 20% | 173.2693 | 866.3467 | 0 |  | 0
5.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 60 | NO | 70% | 158.7683 | 6668.2705 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 60 | NO | 20% | 158.7683 | 1905.2202 | 0 |  | 0
5.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 144.2467 | 2019.4542 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 144.2467 | 576.9869 | 0 |  | 0
5.40 | TEES PERFORATED | [5 empty] | 0 |  | 0
5.4.1 | 600 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 130 | NO | 70% | 202.2967 | 18409.001 | 25 |  | 25
(ii) | Final painting and marking of tray nos | 130 | NO | 20% | 202.2967 | 5259.7146 | 0 |  | 0
5.4.2 | 450 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 |  | 0
5.4.3 | 300 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0
5.4.4 | 150 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0
5.4.5 | 100 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 158.789 | 555.7614 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 158.789 | 158.789 | 0 |  | 0
5.4.6 | 50 MM Tee-Joint | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 79.3326 | 277.6641 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 79.3326 | 79.3326 | 0 |  | 0
5.50 | CROSSES PERFORATED | [5 empty] | 0 |  | 0
5.5.1 | 600 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 288.4935 | 2019.4542 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 288.4935 | 576.9869 | 0 |  | 0
5.5.2 | 450 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 231.3146 | 809.601 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 231.3146 | 231.3146 | 0 |  | 0
5.5.3 | 300 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 215.9679 | 755.8875 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 215.9679 | 215.9679 | 0 |  | 0
5.5.4 | 150 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 |  | 0
5.5.5 | 100 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 |  | 0
5.5.6 | 50 MM Cross | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 53.7135 | 187.9972 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 53.7135 | 53.7135 | 0 |  | 0
5.60 | REDUCERS PERFORATED LHS | [5 empty] | 0 |  | 0
5.6.1 | 600 MM WIDE - 450 MM Reducer LHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0
5.6.2 | 450 MM WIDE - 300 MM Reducer LHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0
5.6.3 | 300 MM WIDE - 150 MM Reducer LHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0
5.70 | REDUCERS PERFORATED RHS | [5 empty] | 0 |  | 0
5.7.1 | 600 MM WIDE - 450 MM Reducer RHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0
5.7.2 | 450 MM WIDE - 300 MM Reducer RHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0
5.7.3 | 300 MM WIDE - 150 MM Reducer RHS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0
5.80 | CABLE TROUGHS HOT DIP GALVANISED | [5 empty] | 0 |  | 0
5.8.1 | 50MM WIDE | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 734.7504 | 90006.9243 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 734.7504 | 25716.2641 | 0 |  | 0
5.8.2 | 75MM WIDE | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 1102.8098 | 135094.2055 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 1102.8098 | 38598.3444 | 0 |  | 0
6.00 | CONDUITS | [5 empty] | 0 |  | 0
6.1 | RIGID GALVANISED MS CONDUITS | [5 empty] | 0 |  | 0
6.1.1 | 50 MM DIAMETER MS Conduit | [5 empty] | 0 |  | 0
(i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 108.4016 | 19512.2935 | 0 |  | 0
6.1.2 | 80 MM DIAMETER MS Conduit | [5 empty] | 0 |  | 0
(i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 122.9129 | 22124.3288 | 0 |  | 0
6.2 | GI FLEXIBLE METALLIC CONDUIT | [5 empty] | 0 |  | 0
(i) | Laying of conduit/pipe complete in all respect | 2240 | MTR | 90% | 35.8498 | 72273.1787 | 0 |  | 0
7.00 | PERFORATED MS SHEET TO COVER CABLE SHAFT | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 250 | SQM | 70% | 71.6989 | 12547.2992 | 0 |  | 0
(ii) | Painting as applicable | 250 | SQM | 20% | 71.6989 | 3584.9426 | 0 |  | 0
[7 empty] | 0 |  | 0
8.00 | DOUBLE COMPRESSION CABLE GLAND FOR UA/A CABLE | [5 empty] | 0 |  | 0
8.01 | 9-11 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0
(i) | Termination | 300 | NO. | 70% | 71.7005 | 15057.1056 | 0 |  | 0
(ii) | Testing of connected equipments/system | 300 | NO. | 20% | 71.7005 | 4302.0302 | 0 |  | 0
8.02 | 11-13 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0
(i) | Termination | 1000 | NO. | 70% | 71.6995 | 50189.6301 | 0 |  | 0
(ii) | Testing of connected equipments/system | 1000 | NO. | 20% | 71.6995 | 14339.8943 | 0 |  | 0
8.03 | 13-17 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0
(i) | Termination | 1500 | NO. | 70% | 79.3817 | 83350.7826 | 0 |  | 0
(ii) | Testing of connected equipments/system | 1500 | NO. | 20% | 79.3817 | 23814.5093 | 0 |  | 0
8.04 | 17-20 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0
(i) | Termination | 200 | NO. | 70% | 87.0647 | 12189.0649 | 0 |  | 0
(ii) | Testing of connected equipments/system | 200 | NO. | 20% | 87.0647 | 3482.59 | 0 |  | 0
8.05 | 20-23 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0
(i) | Termination | 70 | NO. | 70% | 94.75 | 4642.752 | 0 |  | 0
(ii) | Testing of connected equipments/system | 70 | NO. | 20% | 94.75 | 1326.5006 | 0 |  | 0
8.06 | 23-26 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0
(i) | Termination | 150 | NO. | 70% | 101.573 | 10665.161 | 0 |  | 0
(ii) | Testing of connected equipments/system | 150 | NO. | 20% | 101.573 | 3047.1889 | 0 |  | 0
8.07 | 26-30 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO. | 70% | 108.4047 | 3794.1654 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO. | 20% | 108.4047 | 1084.0472 | 0 |  | 0
8.08 | 30-35 (For 3.5C x 50, 2C x 95 Cables ) | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 122.9098 | 4301.8445 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 122.9098 | 1229.0984 | 0 |  | 0
8.09 | 35-40 (For 3.5C x 95, 2C x 120 Cables ) | [5 empty] | 0 |  | 0
(i) | Termination | 100 | NO | 70% | 130.5956 | 9141.6904 | 0 |  | 0
(ii) | Testing of connected equipments/system | 100 | NO | 20% | 130.5956 | 2611.9115 | 0 |  | 0
8.10 | 40-50 (For 3C x 150, 2C x 120 Cables ) | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 151.9325 | 5317.636 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 151.9325 | 1519.3246 | 0 |  | 0
8.11 | 50-60 (For 3C x 240, 2C x 120 Cables ) | [5 empty] | 0 |  | 0
(i) | Termination | 20 | NO | 70% | 166.4314 | 2330.0394 | 0 |  | 0
(ii) | Testing of connected equipments/system | 20 | NO | 20% | 166.4314 | 665.7256 | 0 |  | 0
8.12 | CABLE GLAND SUITABLE-16 PAIR,0.5SQ.MM | [5 empty] | 0 |  | 0
(i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 |  | 0
(ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 |  | 0
8.13 | CABLE GLAND SUITABLE-10 PAIR,0.6SQ.MM | [5 empty] | 0 |  | 0
(i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 |  | 0
(ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 |  | 0
[7 empty] | 0 |  | 0
8.20 | CRIMPING LUGS (RING/ROUND/FLAT TYPE) | [5 empty] | 0 |  | 0
8.2.1 | 0.5 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 7000 | NO | 70% | 22.1927 | 108744.2707 | 0 |  | 0
(ii) | Testing of connected equipments/system | 7000 | NO | 20% | 22.1927 | 31069.7916 | 0 |  | 0
8.2.2 | 1.5 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 800 | NO | 70% | 22.1924 | 12427.7434 | 0 |  | 0
(ii) | Testing of connected equipments/system | 800 | NO | 20% | 22.1924 | 3550.7838 | 0 |  | 0
8.2.3 | 2.5 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 5250 | NO | 70% | 22.1927 | 81558.3113 | 0 |  | 0
(ii) | Testing of connected equipments/system | 5250 | NO | 20% | 22.1927 | 23302.3747 | 0 |  | 0
8.2.4 | 16 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 250 | NO | 70% | 29.0201 | 5078.5243 | 0 |  | 0
(ii) | Testing of connected equipments/system | 250 | NO | 20% | 29.0201 | 1451.007 | 0 |  | 0
8.2.5 | 25 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 29.0226 | 1015.7915 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 29.0226 | 290.2261 | 0 |  | 0
8.2.6 | 35 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 43.5277 | 1523.4707 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 43.5277 | 435.2773 | 0 |  | 0
8.2.7 | 50 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 |  | 0
8.2.8 | 70 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 |  | 0
8.2.9 | 95 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 71.6964 | 2509.3732 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 71.6964 | 716.9638 | 0 |  | 0
8.2.10 | 120 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 |  | 0
8.2.11 | 150 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 |  | 0
8.2.12 | 185 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 |  | 0
8.2.13 | 240 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 |  | 0
8.2.10 | 300 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 130.5956 | 4570.8452 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 130.5956 | 1305.9558 | 0 |  | 0
8.2.11 | 630 Sq-mm Lugs | [5 empty] | 0 |  | 0
(i) | Termination | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 |  | 0
[7 empty] | 0 |  | 0
9.00 | EQUIPMENT EARTHING MATERIALS | [5 empty] | 0 |  | 0
9.01 | GI WIRE 14 SWG | [5 empty] | 0 |  | 0
(i) | Termination | 87500 | MTR | 70% | 7.6821 | 470528.9191 | 0 |  | 0
(ii) | Testing of connected equipments/system | 87500 | MTR | 20% | 7.6821 | 134436.834 | 0 |  | 0
9.02 | GI WIRE 8 SWG | [5 empty] | 0 |  | 0
(i) | Termination | 1450 | MTR | 70% | 7.6819 | 7797.1203 | 0 |  | 0
(ii) | Testing of connected equipments/system | 1450 | MTR | 20% | 7.6819 | 2227.7487 | 0 |  | 0
9.03 | GS FLAT 25 X 6 MM | [5 empty] | 0 |  | 0
(i) | Termination | 8 | MT | 70% | 12997.0569 | 72783.5188 | 1 |  | 1
(ii) | Testing of connected equipments/system | 8 | MT | 20% | 12997.0569 | 20795.2911 | 0 |  | 0
9.04 | GS FLAT 50 X 6 MM | [5 empty] | 0 |  | 0
(i) | Termination | 2 | MT | 70% | 8983.087 | 12576.3218 | 1.5 |  | 1.5
(ii) | Testing of connected equipments/system | 2 | MT | 20% | 8983.087 | 3593.2348 | 0 |  | 0
9.05 | GS FLAT 65 X 8 MM | [5 empty] | 0 |  | 0
(i) | Termination | 53 | MT | 70% | 10576.5403 | 392389.645 | 33 |  | 33
(ii) | Testing of connected equipments/system | 53 | MT | 20% | 10576.5403 | 112111.3271 | 0 |  | 0
9.06 | GS FLAT 75 X 10 MM | [5 empty] | 0 |  | 0
(i) | Termination | 6 | MT | 70% | 9787.4487 | 41107.2845 | 5.4985 |  | 5.4985
(ii) | Testing of connected equipments/system | 6 | MT | 20% | 9787.4487 | 11744.9384 | 0 |  | 0
9.07 | GS ROD 20 MM DIA.1000MM LONG | [5 empty] | 0 |  | 0
(i) | Termination | 84 | NOS | 70% | 341.8091 | 20098.377 | 0 |  | 0
(ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8091 | 5742.3934 | 0 |  | 0
9.08 | TEST LINK 150X25X6 MM GS FLAT WITH BOX | [5 empty] | 0 |  | 0
(i) | Termination | 84 | NOS | 70% | 341.8681 | 20101.8424 | 0 |  | 0
(ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8681 | 5743.3836 | 0 |  | 0
9.09 | 40NB GALV MS HEAVY DUTY PIPE (PERF) 3M | [5 empty] | 0 |  | 0
(i) | Termination | 112 | NOS | 70% | 454.2408 | 35612.4805 | 0 |  | 0
(ii) | Testing of connected equipments/system | 112 | NOS | 20% | 454.2408 | 10174.9944 | 0 |  | 0
9.10 | FLEXIBLE BRAIDED CONDUCTOR FOR FENCE GATE GND | [5 empty] | 0 |  | 0
(i) | Termination | 10 | NOS | 70% | 5048.821 | 35341.7472 | 0 |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 5048.821 | 10097.6421 | 0 |  | 0
[7 empty] | 0 |  | 0
10.00 | CABLE LAYING, DRESSING, CLAMPING, TAGGING | [5 empty] | 0 |  | 0
10.1 | 6.6 KV XLPE AL UA POWER CABLES | [5 empty] | 0 |  | 0
10.1.1 | 1C-400 Sq.mm | [5 empty] | 0 |  | 0
(i) | Laying of cable | 32000 | MTR | 55% | 31.7271 | 558396.7097 | 0 |  | 0
(ii) | After termination of cable | 32000 | MTR | 10% | 31.7271 | 101526.6745 | 0 |  | 0
(iii) | Dressing & Clamping | 32000 | MTR | 25% | 31.7271 | 253816.6862 | 0 |  | 0
10.1.2 | 3C-150 Sq.mm | [5 empty] | 0 |  | 0
(i) | Laying of cable | 13000 | MTR | 55% | 34.6138 | 247488.9209 | 0 |  | 0
(ii) | After termination of cable | 13000 | MTR | 10% | 34.6138 | 44997.9856 | 0 |  | 0
(iii) | Dressing & Clamping | 13000 | MTR | 25% | 34.6138 | 112494.964 | 0 |  | 0
10.1.3 | 3C-240 Sq.mm | [5 empty] | 0 |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 43.2673 | 118985.1694 | 0 |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 43.2673 | 21633.6672 | 0 |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 43.2673 | 54084.1679 | 0 |  | 0
10.2 | 33 KV XLPE AL UA POWER CABLES | [5 empty] | 0 |  | 0
10.2.1 | 3C-120 Sq.mm | [5 empty] | 0 |  | 0
(i) | Laying of cable | 1500 | MTR | 55% | 34.6139 | 28556.427 | 0 |  | 0
(ii) | After termination of cable | 1500 | MTR | 10% | 34.6139 | 5192.0776 | 0 |  | 0
(iii) | Dressing & Clamping | 1500 | MTR | 25% | 34.6139 | 12980.1941 | 0 |  | 0
10.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 |  | 0
10.3.1 | 3.5C - 25 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 12.2573 | 53931.9384 | 0 |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 12.2573 | 9805.807 | 0 |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 12.2573 | 24514.5175 | 0 |  | 0
10.3.2 | 3.5C - 50 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 14.4166 | 7929.1453 | 0 |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 14.4166 | 1441.6628 | 0 |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 14.4166 | 3604.157 | 0 |  | 0
10.3.3 | 3C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 10.0891 | 44392.2546 | 0 |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 10.0891 | 8071.319 | 0 |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 10.0891 | 20178.2975 | 0 |  | 0
10.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 |  | 0
10.4.1 | 1C - 35 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 8.6663 | 38131.5073 | 0 |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 8.6663 | 6933.0013 | 0 |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 8.6663 | 17332.5033 | 0 |  | 0
10.4.2 | 1C - 70 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 9.6291 | 74143.9925 | 0 |  | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 9.6291 | 13480.7259 | 0 |  | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 9.6291 | 33701.8148 | 0 |  | 0
10.4.3 | 1C - 120 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 2000 | MTR | 55% | 11.5555 | 12711.0697 | 0 |  | 0
(ii) | After termination of cable | 2000 | MTR | 10% | 11.5555 | 2311.1036 | 0 |  | 0
(iii) | Dressing & Clamping | 2000 | MTR | 25% | 11.5555 | 5777.759 | 0 |  | 0
10.4.4 | 1C - 400 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 13500 | MTR | 55% | 16.3706 | 121551.4121 | 0 | 2961 | 2961
(ii) | After termination of cable | 13500 | MTR | 10% | 16.3706 | 22100.2567 | 0 |  | 0
(iii) | Dressing & Clamping | 13500 | MTR | 25% | 16.3706 | 55250.6418 | 0 |  | 0
10.4.5 | 1C - 630 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 18000 | MTR | 55% | 17.3334 | 171600.6321 | 0 |  | 0
(ii) | After termination of cable | 18000 | MTR | 10% | 17.3334 | 31200.1149 | 0 |  | 0
(iii) | Dressing & Clamping | 18000 | MTR | 25% | 17.3334 | 78000.2873 | 0 |  | 0
10.4.6 | 2C - 10 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 8.6663 | 28598.6305 | 0 |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 8.6663 | 5199.751 | 0 |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 8.6663 | 12999.3775 | 0 |  | 0
10.4.7 | 2C - 25 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 9.6291 | 42367.8499 | 0 |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 9.6291 | 7703.2454 | 0 |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 9.6291 | 19258.1136 | 0 |  | 0
10.4.8 | 2C - 50 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 11.5558 | 6355.705 | 0 |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 11.5558 | 1155.5827 | 0 |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.5558 | 2888.9568 | 0 |  | 0
10.4.9 | 2C - 95 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 12.9998 | 42899.4773 | 0 |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 12.9998 | 7799.905 | 0 |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 12.9998 | 19499.7624 | 0 |  | 0
10.4.10 | 2C - 120 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 13.9626 | 61435.6456 | 0 |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 13.9626 | 11170.1174 | 0 |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 13.9626 | 27925.2935 | 0 |  | 0
10.4.11 | 3C - 10 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 36100 | MTR | 55% | 9.6291 | 191185.7606 | 0 |  | 0
(ii) | After termination of cable | 36100 | MTR | 10% | 9.6291 | 34761.0474 | 0 |  | 0
(iii) | Dressing & Clamping | 36100 | MTR | 25% | 9.6291 | 86902.6185 | 0 |  | 0
10.4.12 | 3C - 25 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 11.0742 | 85271.071 | 0 |  | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 11.0742 | 15503.8311 | 0 |  | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 11.0742 | 38759.5777 | 0 |  | 0
10.4.13 | 3C - 35 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 800 | MTR | 55% | 11.5557 | 5084.4959 | 0 |  | 0
(ii) | After termination of cable | 800 | MTR | 10% | 11.5557 | 924.4538 | 0 |  | 0
(iii) | Dressing & Clamping | 800 | MTR | 25% | 11.5557 | 2311.1345 | 0 |  | 0
10.4.14 | 3C - 50 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 2000 | MTR | 55% | 12.5184 | 13770.2404 | 0 |  | 0
(ii) | After termination of cable | 2000 | MTR | 10% | 12.5184 | 2503.6801 | 0 |  | 0
(iii) | Dressing & Clamping | 2000 | MTR | 25% | 12.5184 | 6259.2002 | 0 |  | 0
10.4.15 | 3C - 95 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 14.4441 | 63553.9871 | 0 |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 14.4441 | 11555.2704 | 0 |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 14.4441 | 28888.1759 | 0 |  | 0
10.4.16 | 3C - 150 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 750 | MTR | 55% | 19.2593 | 7944.4611 | 0 |  | 0
(ii) | After termination of cable | 750 | MTR | 10% | 19.2593 | 1444.4475 | 0 |  | 0
(iii) | Dressing & Clamping | 750 | MTR | 25% | 19.2593 | 3611.1187 | 0 |  | 0
10.4.17 | 3C - 240 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 6750 | MTR | 55% | 24.074 | 89374.6769 | 0 |  | 0
(ii) | After termination of cable | 6750 | MTR | 10% | 24.074 | 16249.9413 | 0 |  | 0
(iii) | Dressing & Clamping | 6750 | MTR | 25% | 24.074 | 40624.8531 | 0 |  | 0
10.4.18 | 3.5C - 25 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 11.267 | 37181.2488 | 0 |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 11.267 | 6760.227 | 0 |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 11.267 | 16900.5676 | 0 |  | 0
10.4.19 | 3.5C - 50 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 12000 | MTR | 55% | 12.9998 | 85798.9546 | 0 |  | 0
(ii) | After termination of cable | 12000 | MTR | 10% | 12.9998 | 15599.8099 | 0 |  | 0
(iii) | Dressing & Clamping | 12000 | MTR | 25% | 12.9998 | 38999.5248 | 0 |  | 0
10.4.20 | 3.5C - 95 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 14.9263 | 82094.9203 | 0 |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 14.9263 | 14926.3491 | 0 |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.9263 | 37315.8729 | 0 |  | 0
10.4.21 | 3.5C - 185 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 750 | MTR | 55% | 23.1108 | 9533.2172 | 0 |  | 0
(ii) | After termination of cable | 750 | MTR | 10% | 23.1108 | 1733.3122 | 0 |  | 0
(iii) | Dressing & Clamping | 750 | MTR | 25% | 23.1108 | 4333.2805 | 0 |  | 0
10.4.22 | 4C - 10 AL | [5 empty] | 0 |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.1105 | 83411.7363 | 0 |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.1105 | 15165.7702 | 0 |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.1105 | 37914.4256 | 0 |  | 0
10.4.23 | 2C - 1.5- CU | [5 empty] | 0 |  | 0
(i) | Laying of cable | 140 | MTR | 55% | 6.4446 | 496.231 | 0 |  | 0
(ii) | After termination of cable | 140 | MTR | 10% | 6.4446 | 90.2238 | 0 |  | 0
(iii) | Dressing & Clamping | 140 | MTR | 25% | 6.4446 | 225.5596 | 0 |  | 0
10.4.24 | 2C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Laying of cable | 68500 | MTR | 55% | 6.4461 | 242858.4525 | 0 |  | 0
(ii) | After termination of cable | 68500 | MTR | 10% | 6.4461 | 44156.0823 | 0 |  | 0
(iii) | Dressing & Clamping | 68500 | MTR | 25% | 6.4461 | 110390.2057 | 0 |  | 0
10.4.25 | 3C - 1.5- CU | [5 empty] | 0 |  | 0
(i) | Laying of cable | 9200 | MTR | 55% | 6.4461 | 32617.4891 | 0 |  | 0
(ii) | After termination of cable | 9200 | MTR | 10% | 6.4461 | 5930.4526 | 0 |  | 0
(iii) | Dressing & Clamping | 9200 | MTR | 25% | 6.4461 | 14826.1314 | 0 |  | 0
10.4.26 | 3C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Laying of cable | 95300 | MTR | 55% | 6.4461 | 337874.4387 | 0 |  | 0
(ii) | After termination of cable | 95300 | MTR | 10% | 6.4461 | 61431.7161 | 0 |  | 0
(iii) | Dressing & Clamping | 95300 | MTR | 25% | 6.4461 | 153579.2903 | 0 |  | 0
10.4.27 | 4C - 1.5- CU | [5 empty] | 0 |  | 0
(i) | Laying of cable | 5500 | MTR | 55% | 6.4462 | 19499.7005 | 0 |  | 0
(ii) | After termination of cable | 5500 | MTR | 10% | 6.4462 | 3545.4001 | 0 |  | 0
(iii) | Dressing & Clamping | 5500 | MTR | 25% | 6.4462 | 8863.5002 | 0 |  | 0
10.4.28 | 10C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8200 | MTR | 55% | 11.5402 | 52046.3967 | 0 |  | 0
(ii) | After termination of cable | 8200 | MTR | 10% | 11.5402 | 9462.9812 | 0 |  | 0
(iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5402 | 23657.453 | 0 |  | 0
10.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 |  | 0
10.5.1 | 2C-1.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 50000 | MTR | 55% | 5.2964 | 145650.6091 | 0 |  | 0
(ii) | After termination of cable | 50000 | MTR | 10% | 5.2964 | 26481.9289 | 0 |  | 0
(iii) | Dressing & Clamping | 50000 | MTR | 25% | 5.2964 | 66204.8223 | 0 |  | 0
10.5.2 | 2C-2.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 3000 | MTR | 55% | 6.2591 | 10327.5952 | 0 |  | 0
(ii) | After termination of cable | 3000 | MTR | 10% | 6.2591 | 1877.7446 | 0 |  | 0
(iii) | Dressing & Clamping | 3000 | MTR | 25% | 6.2591 | 4694.3615 | 0 |  | 0
10.5.3 | 3C-1.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 2500 | MTR | 55% | 9.6625 | 13285.9217 | 0 |  | 0
(ii) | After termination of cable | 2500 | MTR | 10% | 9.6625 | 2415.6221 | 0 |  | 0
(iii) | Dressing & Clamping | 2500 | MTR | 25% | 9.6625 | 6039.0553 | 0 |  | 0
10.5.4 | 3C-2.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 18500 | MTR | 55% | 8.9428 | 90993.3838 | 0 |  | 0
(ii) | After termination of cable | 18500 | MTR | 10% | 8.9428 | 16544.2516 | 0 |  | 0
(iii) | Dressing & Clamping | 18500 | MTR | 25% | 8.9428 | 41360.629 | 0 |  | 0
10.5.5 | 3C-16 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 1500 | MTR | 55% | 8.2625 | 6816.5396 | 0 |  | 0
(ii) | After termination of cable | 1500 | MTR | 10% | 8.2625 | 1239.3708 | 0 |  | 0
(iii) | Dressing & Clamping | 1500 | MTR | 25% | 8.2625 | 3098.4271 | 0 |  | 0
10.5.6 | 5C-1.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.0891 | 83235.4348 | 0 |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.0891 | 15133.7154 | 0 |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.0891 | 37834.2885 | 0 |  | 0
10.5.7 | 5C-2.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 7000 | MTR | 55% | 10.0891 | 38843.1802 | 0 |  | 0
(ii) | After termination of cable | 7000 | MTR | 10% | 10.0891 | 7062.3964 | 0 |  | 0
(iii) | Dressing & Clamping | 7000 | MTR | 25% | 10.0891 | 17655.991 | 0 |  | 0
10.5.8 | 7C-1.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 12000 | MTR | 55% | 10.3794 | 68504.0446 | 0 |  | 0
(ii) | After termination of cable | 12000 | MTR | 10% | 10.3794 | 12455.2808 | 0 |  | 0
(iii) | Dressing & Clamping | 12000 | MTR | 25% | 10.3794 | 31138.2021 | 0 |  | 0
10.5.9 | 7C-2.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 8.6666 | 4766.6086 | 0 |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 8.6666 | 866.6561 | 0 |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.6666 | 2166.6403 | 0 |  | 0
10.5.10 | 10C-1.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8200 | MTR | 55% | 11.5377 | 52034.8248 | 0 |  | 0
(ii) | After termination of cable | 8200 | MTR | 10% | 11.5377 | 9460.8772 | 0 |  | 0
(iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5377 | 23652.1931 | 0 |  | 0
10.5.11 | 10C-2.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 250 | MTR | 55% | 10.1115 | 1390.3317 | 0 |  | 0
(ii) | After termination of cable | 250 | MTR | 10% | 10.1115 | 252.7876 | 0 |  | 0
(iii) | Dressing & Clamping | 250 | MTR | 25% | 10.1115 | 631.969 | 0 |  | 0
10.5.12 | 12C-1.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.5928 | 87390.4335 | 0 |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.5928 | 15889.1697 | 0 |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.5928 | 39722.9243 | 0 |  | 0
10.5.13 | 12C-2.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 11.4506 | 31489.2272 | 0 |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 11.4506 | 5725.314 | 0 |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 11.4506 | 14313.2851 | 0 |  | 0
10.5.14 | 16C-2.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 4000 | MTR | 55% | 13.133 | 28892.6933 | 0 |  | 0
(ii) | After termination of cable | 4000 | MTR | 10% | 13.133 | 5253.217 | 0 |  | 0
(iii) | Dressing & Clamping | 4000 | MTR | 25% | 13.133 | 13133.0424 | 0 |  | 0
10.5.15 | 19C-1.5 | [5 empty] | 0 |  | 0
(i) | Laying of cable | 2500 | MTR | 55% | 13.7014 | 18839.4206 | 0 |  | 0
(ii) | After termination of cable | 2500 | MTR | 10% | 13.7014 | 3425.3492 | 0 |  | 0
(iii) | Dressing & Clamping | 2500 | MTR | 25% | 13.7014 | 8563.373 | 0 |  | 0
10.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 |  | 0
10.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 8.3652 | 2300.429 | 0 |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 8.3652 | 418.2598 | 0 |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 8.3652 | 1045.6495 | 0 |  | 0
10.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 9.3751 | 2578.155 | 0 |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 9.3751 | 468.7554 | 0 |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 9.3751 | 1171.8886 | 0 |  | 0
10.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 10.385 | 2855.8809 | 0 |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 10.385 | 519.2511 | 0 |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 10.385 | 1298.1277 | 0 |  | 0
10.6.4 | 5C - 6 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 |  | 0
10.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 10.817 | 2974.6633 | 0 |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 10.817 | 540.8479 | 0 |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 10.817 | 1352.1197 | 0 |  | 0
10.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 11.5379 | 1269.167 | 0 |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 11.5379 | 230.7576 | 0 |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 11.5379 | 576.8941 | 0 |  | 0
10.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 |  | 0
10.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 17.3084 | 1903.9206 | 0 |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 17.3084 | 346.1674 | 0 |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 17.3084 | 865.4185 | 0 |  | 0
10.7 | CONTROL/INSTRUMENT LT CABLES (SHIELDED) | [5 empty] | 0 |  | 0
10.7.1 | 2P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 8.5354 | 4694.4543 | 0 |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 8.5354 | 853.5371 | 0 |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.5354 | 2133.8429 | 0 |  | 0
10.7.2 | 4P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 9.3892 | 25820.3495 | 0 |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 9.3892 | 4694.609 | 0 |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 9.3892 | 11736.5225 | 0 |  | 0
10.7.3 | 6P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 11.0964 | 61029.9478 | 0 |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 11.0964 | 11096.3542 | 0 |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.0964 | 27740.8854 | 0 |  | 0
10.7.4 | 8P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 11.95 | 6572.5083 | 0 |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 11.95 | 1195.0015 | 0 |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.95 | 2987.5038 | 0 |  | 0
10.7.5 | 12P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 12.8035 | 105628.7952 | 0 |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 12.8035 | 19205.2355 | 0 |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 12.8035 | 48013.0887 | 0 |  | 0
10.7.6 | 16P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 14.5106 | 79808.4457 | 0 |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 14.5106 | 14510.6265 | 0 |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.5106 | 36276.5662 | 0 |  | 0
10.8 | SCREENED CABLES (OVERALL & INDIVIDUAL/OVERALL) | [5 empty] | 0 |  | 0
10.8.1 | 2P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 9.3892 | 30984.4874 | 0 |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 9.3892 | 5633.5432 | 0 |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 9.3892 | 14083.8579 | 0 |  | 0
10.8.2 | 4P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 10.2428 | 78869.7591 | 0 |  | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 10.2428 | 14339.9562 | 0 |  | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 10.2428 | 35849.8905 | 0 |  | 0
10.8.3 | 8P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 11.95 | 65724.7425 | 0 |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 11.95 | 11949.9532 | 0 |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.95 | 29874.8829 | 0 |  | 0
10.8.4 | 12 P - 0.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 13.6571 | 37556.9957 | 0 |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 13.6571 | 6828.5447 | 0 |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 13.6571 | 17071.3617 | 0 |  | 0
10.9 | SPECIALISED CABLING FOR COMMUNICATION SYSTEM | [5 empty] | 0 |  | 0
10.9.1 | OPTICAL FIBRE CABLE WITHOUT HDPE PIPE | [5 empty] | 0 |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 19.8096 | 87162.0584 | 0 |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 19.8096 | 15847.647 | 0 |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 19.8096 | 39619.1174 | 0 |  | 0
10.9.2 | OPTICAL FIBRE CABLE WITH HDPE PIPE | [5 empty] | 0 |  | 0
(i) | Laying of cable | 3000 | MTR | 55% | 29.0546 | 47940.0681 | 0 |  | 0
(ii) | After termination of cable | 3000 | MTR | 10% | 29.0546 | 8716.376 | 0 |  | 0
(iii) | Dressing & Clamping | 3000 | MTR | 25% | 29.0546 | 21790.94 | 0 |  | 0
10.9.3 | EARTH CABLE FOR ESP | [5 empty] | 0 |  | 0
(i) | Laying of cable | 280 | MTR | 55% | 9.2536 | 1425.0475 | 0 |  | 0
(ii) | After termination of cable | 280 | MTR | 10% | 9.2536 | 259.0995 | 0 |  | 0
(iii) | Dressing & Clamping | 280 | MTR | 25% | 9.2536 | 647.7489 | 0 |  | 0
[7 empty] | 0 |  | 0
11.0 | CABLE JOINITNG | [5 empty] | 0 |  | 0
11.10 | JOINT KIT 6.6KV 1C-400 AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | Termination | 12 | NOS | 70% | 2902.1067 | 24377.6966 | 0 |  | 0
(ii) | Testing of connected equipments/system | 12 | NOS | 20% | 2902.1067 | 6965.0562 | 0 |  | 0
11.20 | JOINT KIT 6.6KV 3C-150 AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | Termination | 8 | NOS | 70% | 2902.1067 | 16251.7977 | 0 |  | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 2902.1067 | 4643.3708 | 0 |  | 0
11.30 | JOINT KIT 6.6KV 3C-240 AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 |  | 0
11.40 | JOINT KIT 33KV 3C-120 AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 |  | 0
12.0 | CABLE TERMINATION | [5 empty] | 0 |  | 0
12.1 | 6.6 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 |  | 0
12.1.1 | TERM. KIT 6.6KV 1C-400 AL UNARM. CU LUG | [5 empty] | 0 |  | 0
(i) | Termination | 136 | NOS | 70% | 2902.1295 | 276282.7269 | 0 |  | 0
(ii) | Testing of connected equipments/system | 136 | NOS | 20% | 2902.1295 | 78937.922 | 0 |  | 0
12.1.2 | TERM. KIT 6.6KV 3C-150 AL UNARM. CU LUG | [5 empty] | 0 |  | 0
(i) | Termination | 94 | NOS | 70% | 2902.1298 | 190960.1392 | 0 |  | 0
(ii) | Testing of connected equipments/system | 94 | NOS | 20% | 2902.1298 | 54560.0398 | 0 |  | 0
12.1.3 | TERM. KIT 6.6KV 3C-240 AL UNARM. CU LUG | [5 empty] | 0 |  | 0
(i) | Termination | 46 | NOS | 70% | 2902.1269 | 93448.4866 | 0 |  | 0
(ii) | Testing of connected equipments/system | 46 | NOS | 20% | 2902.1269 | 26699.5676 | 0 |  | 0
12.2 | 33 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 |  | 0
12.2.1 | TERM. KIT 33KV 3C-120 AL UNARM. CU LUG | [5 empty] | 0 |  | 0
(i) | Termination | 6 | NOS | 70% | 2902.1583 | 12189.0649 | 0 |  | 0
(ii) | Testing of connected equipments/system | 6 | NOS | 20% | 2902.1583 | 3482.59 | 0 |  | 0
12.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 |  | 0
12.3.1 | 3.5C - 25 AL | [5 empty] | 0 |  | 0
(i) | Termination | 32 | NOS | 70% | 151.9394 | 3403.443 | 0 |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.9394 | 972.4123 | 0 |  | 0
12.3.2 | 3.5C - 50 AL | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 |  | 0
12.3.3 | 3C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Termination | 32 | NOS | 70% | 144.2622 | 3231.4732 | 0 |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 144.2622 | 923.2781 | 0 |  | 0
12.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 |  | 0
12.4.1 | 1C - 35 AL | [5 empty] | 0 |  | 0
(i) | Termination | 32 | NOS | 70% | 151.0885 | 3384.3834 | 0 |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.0885 | 966.9667 | 0 |  | 0
12.4.2 | 1C - 70 AL | [5 empty] | 0 |  | 0
(i) | Termination | 56 | NOS | 70% | 157.0585 | 6156.6928 | 0 |  | 0
(ii) | Testing of connected equipments/system | 56 | NOS | 20% | 157.0585 | 1759.0551 | 0 |  | 0
12.4.3 | 1C - 120 AL | [5 empty] | 0 |  | 0
(i) | Termination | 8 | NOS | 70% | 170.7167 | 956.0136 | 0 |  | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 170.7167 | 273.1467 | 0 |  | 0
12.4.4 | 1C - 400 AL | [5 empty] | 0 |  | 0
(i) | Termination | 54 | NOS | 70% | 183.5142 | 6936.838 | 0 | 36 | 36
(ii) | Testing of connected equipments/system | 54 | NOS | 20% | 183.5142 | 1981.9537 | 0 |  | 0
12.4.5 | 1C - 630 AL | [5 empty] | 0 |  | 0
(i) | Termination | 72 | NOS | 70% | 209.9773 | 10582.8581 | 0 |  | 0
(ii) | Testing of connected equipments/system | 72 | NOS | 20% | 209.9773 | 3023.6737 | 0 |  | 0
12.4.6 | 2C - 10 AL | [5 empty] | 0 |  | 0
(i) | Termination | 24 | NOS | 70% | 98.1602 | 1649.0909 | 0 |  | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 98.1602 | 471.1688 | 0 |  | 0
12.4.7 | 2C - 25 AL | [5 empty] | 0 |  | 0
(i) | Termination | 32 | NOS | 70% | 98.1602 | 2198.7879 | 0 |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 98.1602 | 628.2251 | 0 |  | 0
12.4.8 | 2C - 50 AL | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 131.4991 | 368.1973 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 131.4991 | 105.1992 | 0 |  | 0
12.4.9 | 2C - 95 AL | [5 empty] | 0 |  | 0
(i) | Termination | 24 | NOS | 70% | 157.0511 | 2638.4589 | 0 |  | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 157.0511 | 753.8454 | 0 |  | 0
12.4.10 | 2C - 120 AL | [5 empty] | 0 |  | 0
(i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 |  | 0
12.4.11 | 3C - 10 AL | [5 empty] | 0 |  | 0
(i) | Termination | 145 | NOS | 70% | 144.2531 | 14641.6924 | 0 |  | 0
(ii) | Testing of connected equipments/system | 145 | NOS | 20% | 144.2531 | 4183.3407 | 0 |  | 0
12.4.12 | 3C - 25 AL | [5 empty] | 0 |  | 0
(i) | Termination | 56 | NOS | 70% | 144.2511 | 5654.6449 | 0 |  | 0
(ii) | Testing of connected equipments/system | 56 | NOS | 20% | 144.2511 | 1615.6128 | 0 |  | 0
12.4.13 | 3C - 35 AL | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 151.1466 | 423.2104 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 151.1466 | 120.9172 | 0 |  | 0
12.4.14 | 3C - 50 AL | [5 empty] | 0 |  | 0
(i) | Termination | 8 | NOS | 70% | 157.0253 | 879.3419 | 0 |  | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 157.0253 | 251.2405 | 0 |  | 0
12.4.15 | 3C - 95 AL | [5 empty] | 0 |  | 0
(i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 |  | 0
12.4.16 | 3C - 150 AL | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 209.9344 | 587.8162 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 209.9344 | 167.9475 | 0 |  | 0
12.4.17 | 3C - 240 AL | [5 empty] | 0 |  | 0
(i) | Termination | 27 | NOS | 70% | 222.7749 | 4210.445 | 0 |  | 0
(ii) | Testing of connected equipments/system | 27 | NOS | 20% | 222.7749 | 1202.9843 | 0 |  | 0
12.4.18 | 3.5C - 25 AL | [5 empty] | 0 |  | 0
(i) | Termination | 24 | NOS | 70% | 131.4475 | 2208.3177 | 0 |  | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 131.4475 | 630.9479 | 0 |  | 0
12.4.19 | 3.5C - 50 AL | [5 empty] | 0 |  | 0
(i) | Termination | 48 | NOS | 70% | 144.2493 | 4846.7766 | 0 |  | 0
(ii) | Testing of connected equipments/system | 48 | NOS | 20% | 144.2493 | 1384.7933 | 0 |  | 0
12.4.20 | 3.5C - 95 AL | [5 empty] | 0 |  | 0
(i) | Termination | 40 | NOS | 70% | 163.8788 | 4588.6053 | 0 |  | 0
(ii) | Testing of connected equipments/system | 40 | NOS | 20% | 163.8788 | 1311.0301 | 0 |  | 0
12.4.21 | 3.5C - 185 AL | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 222.7749 | 623.7696 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 222.7749 | 178.2199 | 0 |  | 0
12.4.22 | 4C - 10 AL | [5 empty] | 0 |  | 0
(i) | Termination | 60 | NOS | 70% | 144.257 | 6058.7956 | 0 |  | 0
(ii) | Testing of connected equipments/system | 60 | NOS | 20% | 144.257 | 1731.0845 | 0 |  | 0
12.4.23 | 2C - 1.5- CU | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 |  | 0
12.4.24 | 2C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Termination | 274 | NOS | 70% | 117.7924 | 22592.5892 | 0 |  | 0
(ii) | Testing of connected equipments/system | 274 | NOS | 20% | 117.7924 | 6455.0255 | 0 |  | 0
12.4.25 | 3C - 1.5- CU | [5 empty] | 0 |  | 0
(i) | Termination | 26 | NOS | 70% | 144.2562 | 2625.4637 | 0 |  | 0
(ii) | Testing of connected equipments/system | 26 | NOS | 20% | 144.2562 | 750.1325 | 0 |  | 0
12.4.26 | 3C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Termination | 400 | NOS | 70% | 117.7922 | 32981.8188 | 0 |  | 0
(ii) | Testing of connected equipments/system | 400 | NOS | 20% | 117.7922 | 9423.3768 | 0 |  | 0
12.4.27 | 4C - 1.5- CU | [5 empty] | 0 |  | 0
(i) | Termination | 22 | NOS | 70% | 144.2411 | 2221.3129 | 0 |  | 0
(ii) | Testing of connected equipments/system | 22 | NOS | 20% | 144.2411 | 634.6608 | 0 |  | 0
12.4.28 | 10C - 2.5- CU | [5 empty] | 0 |  | 0
(i) | Termination | 32 | NOS | 70% | 158.7658 | 3556.3532 | 0 |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 158.7658 | 1016.1009 | 0 |  | 0
12.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 |  | 0
12.5.1 | 2C-1.5 | [5 empty] | 0 |  | 0
(i) | Termination | 96 | NOS | 70% | 108.4029 | 7284.6762 | 0 |  | 0
(ii) | Testing of connected equipments/system | 96 | NOS | 20% | 108.4029 | 2081.3361 | 0 |  | 0
12.5.2 | 2C-2.5 | [5 empty] | 0 |  | 0
(i) | Termination | 12 | NOS | 70% | 108.3965 | 910.5304 | 0 |  | 0
(ii) | Testing of connected equipments/system | 12 | NOS | 20% | 108.3965 | 260.1515 | 0 |  | 0
12.5.3 | 3C-1.5 | [5 empty] | 0 |  | 0
(i) | Termination | 10 | NOS | 70% | 108.4171 | 758.9197 | 0 |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 108.4171 | 216.8342 | 0 |  | 0
12.5.4 | 3C-2.5 | [5 empty] | 0 |  | 0
(i) | Termination | 74 | NOS | 70% | 108.402 | 5615.2261 | 0 |  | 0
(ii) | Testing of connected equipments/system | 74 | NOS | 20% | 108.402 | 1604.3503 | 0 |  | 0
12.5.5 | 3C-16 | [5 empty] | 0 |  | 0
(i) | Termination | 6 | NOS | 70% | 144.288 | 606.0095 | 0 |  | 0
(ii) | Testing of connected equipments/system | 6 | NOS | 20% | 144.288 | 173.1456 | 0 |  | 0
12.5.6 | 5C-1.5 | [5 empty] | 0 |  | 0
(i) | Termination | 44 | NOS | 70% | 116.0848 | 3575.4128 | 0 |  | 0
(ii) | Testing of connected equipments/system | 44 | NOS | 20% | 116.0848 | 1021.5465 | 0 |  | 0
12.5.7 | 5C-2.5 | [5 empty] | 0 |  | 0
(i) | Termination | 23 | NOS | 70% | 122.9028 | 1978.7359 | 0 |  | 0
(ii) | Testing of connected equipments/system | 23 | NOS | 20% | 122.9028 | 565.3531 | 0 |  | 0
12.5.8 | 7C-1.5 | [5 empty] | 0 |  | 0
(i) | Termination | 34 | NOS | 70% | 130.589 | 3108.0188 | 0 |  | 0
(ii) | Testing of connected equipments/system | 34 | NOS | 20% | 130.589 | 888.0054 | 0 |  | 0
12.5.9 | 7C-2.5 | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 |  | 0
12.5.10 | 10C-2.5 | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 |  | 0
12.5.11 | 12C-1.5 | [5 empty] | 0 |  | 0
(i) | Termination | 42 | NOS | 70% | 144.2585 | 4241.2003 | 0 |  | 0
(ii) | Testing of connected equipments/system | 42 | NOS | 20% | 144.2585 | 1211.7715 | 0 |  | 0
12.5.12 | 12C-2.5 | [5 empty] | 0 |  | 0
(i) | Termination | 14 | NOS | 70% | 144.2732 | 1413.8778 | 0 |  | 0
(ii) | Testing of connected equipments/system | 14 | NOS | 20% | 144.2732 | 403.9651 | 0 |  | 0
12.5.13 | 16C-2.5 | [5 empty] | 0 |  | 0
(i) | Termination | 16 | NOS | 70% | 144.2622 | 1615.7366 | 0 |  | 0
(ii) | Testing of connected equipments/system | 16 | NOS | 20% | 144.2622 | 461.639 | 0 |  | 0
12.5.14 | 19C-1.5 | [5 empty] | 0 |  | 0
(i) | Termination | 10 | NOS | 70% | 144.2467 | 1009.7271 | 0 |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 144.2467 | 288.4935 | 0 |  | 0
12.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 |  | 0
12.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 |  | 0
12.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 122.9903 | 344.3728 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 122.9903 | 98.3922 | 0 |  | 0
12.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 |  | 0
12.6.4 | 5C - 6 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 |  | 0
12.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 |  | 0
12.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 158.7271 | 444.4359 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 158.7271 | 126.9817 | 0 |  | 0
12.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 |  | 0
12.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 |  | 0
(i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 |  | 0
12.7 | OPTICAL FIBRE CABLE JOINTING | [5 empty] | 0 |  | 0
(i) | Termination | 10 | NOS. | 70% | 324.385 | 2270.6947 | 0 |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS. | 20% | 324.385 | 648.7699 | 0 |  | 0
13.00 | CABLE SHAFT COVERING | [5 empty] | 0 |  | 0
13.10 | MS SHEET FOR COVERING CABLE SHAFTS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 1000 | SQM | 70% | 2163.79 | 1514652.9917 | 0 |  | 0
(ii) | Painting as applicable | 1000 | SQM | 20% | 2163.79 | 432757.9976 | 0 |  | 0
[7 empty] | 0 |  | 0
| SCH-5 - SWITCHGEAR & EQUIPMENT | [5 empty] | 0 |  | 0
1.00 | HT SWITCHGEAR BOARD | [5 empty] | 0 |  | 0
1.01 | 6.6KV UNIT SWITCHBOARD | [5 empty] | 0 |  | 0
(i) | Placement,Alignment & Coupling as Applicable | 2 | SET | 50% | 222104.9936 | 222104.9936 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 |  | 0
(iii) | Charging | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 |  | 0
1.02 | 6.6KV STATION SWITCHBOARD | [5 empty] | 0 |  | 0
(i) | Placement,Alignment & Coupling as Applicable | 1 | SET | 50% | 242296.1316 | 121148.0658 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 |  | 0
1.03 | 6.6KV CHP SWITCHBOARD | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
1.04 | 6.6KV AHP SWITCHBOARD | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
1.05 | 6.6KV COMPRESSOR SWITCHBOARD | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
1.06 | 6.6KV RAW WATER SWITCHBOARD | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0
1.07 | 33KV RAW WATER PANELS | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | SET | 50% | 222104.9936 | 444209.9871 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 |  | 0
(iii) | Charging | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 |  | 0
1.08 | BTS panel | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 10096.0331 | 10096.0331 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 2 |  | 2
(iii) | Charging | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 0 |  | 0
1.09 | DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
2.00 | LT SWITCHGEAR BOARD & DCDB | [5 empty] | 0 |  | 0
2.01 | UNIT PMCC #1DA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 |  | 0
2.02 | TURBINE MCC #1KA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 114657.8914 | 57328.9457 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 0 |  | 0
2.03 | TURBINE VALVES & ACDB #1KB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 165064.4176 | 82532.2088 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 0 |  | 0
2.04 | BOILER VALVES & ACDB #1HB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 147756.667 | 73878.3335 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 147756.667 | 29551.3334 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 147756.667 | 29551.3334 | 0 |  | 0
2.05 | BOILER MCC #1HA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 131531.8498 | 65765.9249 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 131531.8498 | 26306.37 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 131531.8498 | 26306.37 | 0 |  | 0
2.06 | UNIT SERVICE ACDB #1QA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 |  | 0
2.07 | SOOT BLOWER MCC (Supply by Tnchy) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 115514.337 | 57757.1685 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 |  | 0
2.08 | ESP LT SWITCHGEAR(SUPPLY BY BAP RANIPET) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 131243.4801 | 131243.4801 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 131243.4801 | 52497.392 | 2 |  | 2
(iii) | Charging | 2 | NO | 20% | 131243.4801 | 52497.392 | 0 |  | 0
2.09 | UNIT EMERGENCY BOARD #1DG | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 181614.1148 | 90807.0574 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 181614.1148 | 36322.823 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 181614.1148 | 36322.823 | 0 |  | 0
2.10 | 220V UNIT DCDB #1FA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 |  | 0
2.11 | ESP A/C & VENT MCC #1TB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 52569.2988 | 26284.6494 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 0 |  | 0
2.12 | STATION PMCC #0DA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.13 | AC MCC #0TA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 78529.9964 | 39264.9982 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 | 1 | 1
(iii) | Charging | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 |  | 0
2.14 | VENTILATION & AIR WASHER MCC #1TA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 116605.9338 | 58302.9669 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 |  | 0
2.15 | MISC SERVICE MCC #0SA | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 1 |  | 1
(iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 |  | 0
2.16 | COOLING TOWER PMCC #1DC | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 191474.9966 | 95737.4983 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 |  | 0
2.17 | CWPH AND CHLORINATION MCC # 0SB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 126556.5445 | 63278.2722 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 |  | 0
2.18 | PTP PMCC #1DD | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.19 | FW & CLARIFIED WATER MCC #0SC | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0
2.20 | ETP PMCC #1DE | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.21 | ADMIN BUILDING MCC #0SB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0
2.22 | O&M ACDB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 |  | 0
2.23 | STP MCC #0SF | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.24 | WATER PMCC # 0DB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.25 | MODIFICATION OF DM PLANT MCC | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.26 | MODIFICATION OF FUEL OIL MCC | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 1 | 1
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.27 | 220V DC FUSE DB (WALL MOUNTED) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0
(iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0
2.28 | 415V AC FUSE DB (WALL MOUNTED) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0
(iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0
2.29 | LV SWITCHGEAR FOR SWITCHYARD | [5 empty] | 0 |  | 0
2.29.1 | SWITCHYARD PMCC | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0
2.29.2 | SWITCHYARD 415V ACDB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 7211.7174 | 3605.8587 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 |  | 0
2.29.3 | SWITCHYARD 220V DCDB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 |  | 0
2.30 | DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
3.00 | LT PANELS | [5 empty] | 0 |  | 0
3.01 | FEEDER FOR ELEVATOR (3 PHASE - 30 KW) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
3.02 | FEEDER FOR ELEVATOR (1 PHASE - 6 KW) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
(iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
4.00 | PROTECTION RELAY PANELS | [5 empty] | 0 |  | 0
4.01 | GENERATOR PROTECTION & RELAY PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NOS. | 50% | 43267.3343 | 108168.3358 | 5 |  | 5
(ii) | Pre-Commissioning Checks ,Testing | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 |  | 0
(iii) | Charging | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 |  | 0
4.02 | STATION TRANSFORMER RELAY PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
4.03 | ELECTRICAL CONTROL DESK CUM PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 36055.4931 | 18027.7466 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 |  | 0
5.00 | DIGITAL STATIC EXCITATION SYSTEM | [5 empty] | 0 |  | 0
5.1 | DIGITAL AUOTOMATIC VOLTAGE REGULATOR | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 38337.079 | 19168.5395 | 1 |  | 1
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 |  | 0
5.2 | HT DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
5.3 | LT DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0
5.4 | VARIABLE FREQUENCY DRIVE FOR ID FAN | [5 empty] | 0 |  | 0
5.4.1 | VARIABLE FREQUENCY DRIVE FOR ID FANS | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0
(iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0
5.4.2 | 6.6KV VFD SWITCH GEAR PANEL FOR ID FAN | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 2 |  | 2
(iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 |  | 0
5.5 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 |  | 0
5.5.1 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0
(iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0
5.5.2 | 6.6KV VFD SWITCH GEAR PANEL FOR CEP | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 0 | 2 | 2
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 |  | 0
(iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 |  | 0
6.00 | LOCAL CONTROL PANELS FOR PUMPS ETC | [5 empty] | 0 |  | 0
6.01 | LOCAL FAN CONTROL PANEL FOR ST | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
6.02 | LOCAL FAN CONTROL PANEL FOR GT | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
6.03 | LOCAL FAN CONTROL PANEL FOR UAT | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0
(iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0
6.04 | PANEL FOR OIL CENTRIFUGE UNIT | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
6.05 | PANEL FOR ON LOAD TUBE CLEANING SYSTEM | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0
(iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0
6.06 | PANEL FOR CENTRAL OIL PURIFICATION UNIT | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 7211.7174 | 3605.8587 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 |  | 0
6.07 | LCP for Sump Pumps of Condensor Pit, & Trf oil Pit | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | No | 50% | 3852.1487 | 7704.2974 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | No | 20% | 3852.1487 | 3081.719 | 0 |  | 0
(iii) | Charging | 4 | No | 20% | 3852.1487 | 3081.719 | 0 |  | 0
7.00 | MISC ITEMS OF ESP | [5 empty] | 0 |  | 0
7.01 | ELECTRONIC CONTROLLER (WITH BAPCON) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 36 | NO | 50% | 7211.7862 | 129812.1516 | 28 |  | 28
(ii) | Pre-Commissioning Checks ,Testing | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 |  | 0
(iii) | Charging | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 |  | 0
7.02 | RAPPER CONTROL PANEL (WITH RAPCON) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0
(iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0
7.03 | STATCON CONTROL PANEL | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0
(iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0
7.04 | IOS PERSONAL COMPUTER | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 5769.2502 | 2884.6251 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 |  | 0
7.05 | DATA LOGGER PC | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 2884.9345 | 1442.4673 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 |  | 0
7.06 | DOT MATRIX PRINTER | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 1081.6957 | 540.8479 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 |  | 0
7.07 | COMPUTER FURNITURE | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0
8.00 | MISCELLANEOUS-1 (ONLY COMMISSIONING RATE) | [5 empty] | 0 |  | 0
8.01 | THERMOSTAT | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 32 | NO | 50% | 721.2723 | 11540.3568 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 |  | 0
(iii) | Charging | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 |  | 0
8.02 | HOPPER/ SHAFT/ SUPPORT INSULATOR HEATER | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 812 | SET | 50% | 721.2641 | 292833.2286 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 |  | 0
(iii) | Charging | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 |  | 0
8.03 | ELECTRICALLY OPERATED HOIST | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0
(iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0
8.04 | ASH LEVEL INDICATORS & CONTROLLERS | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 112 | SET | 50% | 721.2668 | 40390.9395 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 |  | 0
(iii) | Charging | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 |  | 0
8.05 | RAPPING MOTORS FOR ESP | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 60 | NO | 50% | 1731.0329 | 51930.9869 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 |  | 0
(iii) | Charging | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 |  | 0
8.06 | TESTING OF GENERATOR / EXCITER / PMG | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0
8.07 | COMMISSIONING OF HYDROGEN GAS DRIER | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 721.2336 | 721.2336 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 |  | 0
(iii) | Charging | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 |  | 0
8.08 | COMMISSIONING OF EXCITER HEATER, STROBOSCOPE | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0
(iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0
9.00 | JUNCTION BOX/ MARSHALLING BOX /PB/STARTERS | [5 empty] | 0 |  | 0
9.01 | FRP JUNCTION BOX- 24 WAY | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 70 | NO | 50% | 337.1592 | 11800.5703 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 |  | 0
(iii) | Charging | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 |  | 0
9.02 | FRP JUNCTION BOX- 48 WAY | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO | 50% | 337.1574 | 8428.9346 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 |  | 0
(iii) | Charging | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 |  | 0
9.03 | FRP JUNCTION BOX- 72 WAY | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 337.1636 | 3371.6357 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 |  | 0
(iii) | Charging | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 |  | 0
9.04 | FRP JUNCTION BOX- 96 WAY | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 337.1326 | 842.8316 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 337.1326 | 337.1326 | 0 |  | 0
(iii) | Charging | 5 | NO | 20% | 337.1326 | 337.1326 | 0 |  | 0
9.05 | PUSH BUTTON/ STARTERS FOR RAPPING MOTORS | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 100 | NO | 50% | 721.2646 | 36063.2284 | 0 | 60 | 60
(ii) | Pre-Commissioning Checks ,Testing | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 |  | 0
(iii) | Charging | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 |  | 0
9.06 | FRP JUNCTION BOX FOR HEATERS(JBHH,SHHH,SUHH) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 40 | NO | 50% | 337.1636 | 6743.2714 | 0 | 32 | 32
(ii) | Pre-Commissioning Checks ,Testing | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 |  | 0
(iii) | Charging | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 |  | 0
9.07 | FRP JUNCTION BO X(CONTROL-HH, TH, ALI) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 80 | NO | 50% | 337.1558 | 13486.2334 | 0 | 32 | 32
(ii) | Pre-Commissioning Checks ,Testing | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 |  | 0
(iii) | Charging | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 |  | 0
10.00 | PUSH BUTTON, BOX & STARTER | [5 empty] | 0 |  | 0
10.10 | LOCAL PUSH BUTTON STATIONS (NON FLAME PROOF) | [5 empty] | 0 |  | 0
10.1.1 | TYPE A | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 150 | NO | 50% | 721.2625 | 54094.6878 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 |  | 0
(iii) | Charging | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 |  | 0
10.1.2 | TYPE C | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 1009.789 | 7573.4172 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 |  | 0
(iii) | Charging | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 |  | 0
10.20 | PUSH BUTTON BOX | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 46 | NO | 50% | 1154.0169 | 26542.3876 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 |  | 0
(iii) | Charging | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 |  | 0
10.30 | LOCAL MOTOR STARTER | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO. | 50% | 1154.0233 | 28850.5827 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 |  | 0
(iii) | Charging | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 |  | 0
11.00 | DC STRATER PANEL/ STARTING CABINET | [5 empty] | 0 |  | 0
11.10 | LOCALLY MOUNTED STARTER MODULE | [5 empty] | 0 |  | 0
11.1.1 | FOR MOTOR RATING upto 0.75 KW | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 504.4613 | 5044.6131 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 |  | 0
(iii) | Charging | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 |  | 0
11.1.4 | FOR MOTOR RATING above 0.75kW upto 1.5 kW | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 577.0282 | 4327.7112 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 |  | 0
(iii) | Charging | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 |  | 0
11.1.5 | FOR MOTOR RATING above 1.5W upto 2.2kW | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 10 | NO | 50% | 648.708 | 3243.5402 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 10 | NO | 20% | 648.708 | 1297.4161 | 0 |  | 0
(iii) | Charging | 10 | NO | 20% | 648.708 | 1297.4161 | 0 |  | 0
11.1.6 | SUITABLE FOR MOTOR RATING above 2.2W upto 4.5kW | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 721.2955 | 1803.2388 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 721.2955 | 721.2955 | 0 |  | 0
(iii) | Charging | 5 | NO | 20% | 721.2955 | 721.2955 | 0 |  | 0
11.1.6 | SUITABLE FOR MOTOR RATING above 4.5W upto 6kW | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 721.2336 | 721.2336 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 721.2336 | 288.4935 | 0 |  | 0
(iii) | Charging | 2 | NO | 20% | 721.2336 | 288.4935 | 0 |  | 0
12.00 | DC STARTER LOCAL PANEL | [5 empty] | 0 |  | 0
12.01 | STARTER CABINET FOR DC JACKING OIL MOTOR | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
12.02 | STARTER CABINET FOR DC SEAL OIL MOTOR | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
12.03 | STARTING CABINET FOR DC EMERGENCY LOP | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0
12.04 | SCANNER AIR FAN DC MOTOR STARTER BOX | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 4327.4018 | 2163.7009 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 |  | 0
(iii) | Charging | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 |  | 0
12.05 | FURNACE TEMPERATURE PROBE LOCAL STARTER BOX | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0
(iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0
13.00 | BATTERY SYSTEM | [5 empty] | 0 |  | 0
13.01 | 220V BATTERY (EACH SET 170 CELLS) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | SET | 50% | 146185.2791 | 438555.8373 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 |  | 0
(iii) | Charging | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 |  | 0
13.02 | 220V FCB CHARGER | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 29746.839 | 89240.5169 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 29746.839 | 35696.2068 | 2 |  | 2
(iii) | Charging | 6 | NO | 20% | 29746.839 | 35696.2068 | 0 |  | 0
13.03 | 220V DC BATTERY HEALTH MONITORING SYSTEM | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 3852.1487 | 11556.4461 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 |  | 0
(iii) | Charging | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 |  | 0
13.04 | DISCHARGE RESISTOR | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 2 |  | 2
(iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 |  | 0
13.05 | 220 V DC ISOLATION BOX | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 |  | 2
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 |  | 0
(iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 |  | 0
14.00 | DG SET | [5 empty] | 0 |  | 0
14.01 | DG Set 750kVA,415V, 0.8pf with acoustic enclosure | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 144223.8289 | 144223.8289 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 |  | 0
(iii) | Charging | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 |  | 0
14.02 | 990 litres fuel tank on stand including Fuel Piping | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 14422.8161 | 14422.8161 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 |  | 0
(iii) | Charging | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 |  | 0
14.03 | Battery with stand (24V DC 360AH) | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 28845.4774 | 57690.9548 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 |  | 0
(iii) | Charging | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 |  | 0
14.04 | Battery Charger | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 8654.3394 | 17308.6788 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 |  | 0
(iii) | Charging | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 |  | 0
14.05 | Exhaust Piping and Support Structure | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 695661.8562 | 695661.8562 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 |  | 0
(iii) | Charging | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 |  | 0
14.06 | DG AMF Panel | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 7211.7174 | 7211.7174 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 7211.7174 | 2884.687 | 0 |  | 0
(iii) | Charging | 2 | set | 20% | 7211.7174 | 2884.687 | 0 |  | 0
14.07 | DG Aux DB | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 5048.9448 | 5048.9448 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 |  | 0
(iii) | Charging | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 |  | 0
14.08 | Alternator extension terminal box | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 16088.0582 | 16088.0582 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 |  | 0
(iii) | Charging | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 |  | 0
14.09 | Miscellaneous cables for DG Set | [5 empty] | 0 |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | lot | 50% | 16100.1252 | 16100.1252 | 0 |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 |  | 0
(iii) | Charging | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 |  | 0
15.00 | MISCELLANEOUS FOR MOTORS & ACTUATORS | [5 empty] | 0 |  | 0
15.01 | DRYING OUT, TESTING OF OF HT MOTORS | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 42 | NO | 50% | 4327.5786 | 90879.1498 | 0 |  | 0
(ii) | Commissioning of individual items | 42 | NO | 40% | 4327.5786 | 72703.3198 | 0 |  | 0
15.02 | DRYING OUT, TESTING OF OF LT MOTORS | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 200 | NO | 50% | 2163.7937 | 216379.3701 | 0 |  | 0
(ii) | Commissioning of individual items | 200 | NO | 40% | 2163.7937 | 173103.4961 | 0 |  | 0
15.03 | MOUNTING OF CTs FOR HT MOTORS/ PANELS | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 |  | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 |  | 0
15.04 | MOUNTING OF MODULES INSIDE LT PANELS | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 |  | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 |  | 0
15.05 | CABLE TRAY RE-ROUTING & RELAYING OF CABLES | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 1000 | MTR | 50% | 108.4029 | 54201.4341 | 0 |  | 0
(ii) | Commissioning of individual items | 1000 | MTR | 40% | 108.4029 | 43361.1473 | 0 |  | 0
16.00 | ACTUATORS COMMISSIONING | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 300 | NO | 50% | 1442.5291 | 216379.3701 | 0 |  | 0
(ii) | Commissioning of individual items | 300 | NO | 40% | 1442.5291 | 173103.4961 | 0 |  | 0
17.00 | SOOT BLOWERS COMMISSIONING | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 80 | NO | 50% | 1081.4714 | 43258.8565 | 0 |  | 0
(ii) | Commissioning of individual items | 80 | NO | 40% | 1081.4714 | 34607.0852 | 0 |  | 0
18.00 | ELECTRICALLY OPTD MISC HOISTS COMMISSIONING | [5 empty] | 0 |  | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 2163.7628 | 10818.8138 | 0 |  | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 2163.7628 | 8655.051 | 0 |  | 0
19.00 | FABRICATION (SUPPLY OF MATL BY BHEL) | [5 empty] | 0 |  | 0
19.01 | BASE FRAMES FOR SWITCHGEAR, PANEL, PB | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 0 |  | 0
(ii) | Painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 |  | 0
20.00 | CHEQUERED PLATES | [5 empty] | 0 |  | 0
20.01 | INSTALLATION OF CHEQUERED PLATES 6 TO 8 MM | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 40 | MT | 70% | 25960.3882 | 726890.87 | 4.65 |  | 4.65
(ii) | Painting as applicable | 40 | MT | 20% | 25960.3882 | 207683.1057 | 0 |  | 0
21.00 | INSERT PLATES/ ANCHOR FASTENERS | [5 empty] | 0 |  | 0
21.01 | FABRICATION OF INSERT PLATES | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 |  | 0
(ii) | Painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 |  | 0
21.02 | INSTALLATION OF FRICTION ANCHOR FASTENERS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 3000 | SET | 70% | 296.1878 | 621994.4782 | 0 |  | 0
(ii) | Painting as applicable | 3000 | SET | 20% | 296.1878 | 177712.7081 | 0 |  | 0
22.00 | CANOPIES | [5 empty] | 0 |  | 0
22.01 | FABRICATION AND INSTALLATION OF CANOPIES | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 50 | SQM | 70% | 1211.2146 | 42392.5098 | 0 |  | 0
(ii) | Painting as applicable | 50 | SQM | 20% | 1211.2146 | 12112.1457 | 0 |  | 0
23.00 | IRREGULAR BENDS | [5 empty] | 0 |  | 0
23.1 | FABRICATION OF IRREGULAR BENDS (LADER-TYPE) | [5 empty] | 0 |  | 0
23.1.1 | 600 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | NO | 70% | 541.1616 | 378813.1259 | 300 |  | 300
(ii) | Final painting and marking of tray nos | 1000 | NO | 20% | 541.1616 | 108232.3217 | 0 |  | 0
23.1.2 | 450 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 500 | NO | 70% | 541.161 | 189406.3464 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 500 | NO | 20% | 541.161 | 54116.099 | 0 |  | 0
23.1.3 | 300 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 300 |  | 300
(ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 |  | 0
23.1.4 | 150 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 200 |  | 200
(ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 |  | 0
23.1.5 | 100 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 504.4613 | 17656.1457 | 20 |  | 20
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 504.4613 | 5044.6131 | 0 |  | 0
23.1.6 | 50 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 252.2307 | 8828.0729 | 20 |  | 20
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 252.2307 | 2522.3065 | 0 |  | 0
23.2 | FABRICATION OF IRREGULAR BENDS (PERFORATED) | [5 empty] | 0 |  | 0
23.2.1 | 600 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 577.0117 | 40390.8158 | 100 |  | 100
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 577.0117 | 11540.2331 | 0 |  | 0
23.2.2 | 450 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 577.0134 | 28273.6577 | 70 |  | 70
(ii) | Final painting and marking of tray nos | 70 | NO | 20% | 577.0134 | 8078.1879 | 0 |  | 0
23.2.3 | 300 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 541.1573 | 26516.7066 | 70 |  | 70
(ii) | Final painting and marking of tray nos | 70 | NO | 20% | 541.1573 | 7576.2019 | 0 |  | 0
23.2.4 | 150 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 541.1573 | 18940.5047 | 30 |  | 30
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 541.1573 | 5411.5728 | 0 |  | 0
23.2.5 | 100 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 541.1573 | 11364.3028 | 15 |  | 15
(ii) | Final painting and marking of tray nos | 30 | NO | 20% | 541.1573 | 3246.9437 | 0 |  | 0
23.2.6 | 50 MM WIDE TRAYS | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 270.589 | 5682.368 | 15 |  | 15
(ii) | Final painting and marking of tray nos | 30 | NO | 20% | 270.589 | 1623.5337 | 0 |  | 0
24.00 | RUBBER MAT | [5 empty] | 0 |  | 0
24.01 | INSULATING MAT FOR SWITCHGEAR ROOM | [5 empty] | 0 |  | 0
(i) | On completion of supply | 1 | SET | 80% | 64294.6826 | 51435.746 | 0 |  | 0
(ii) | On laying/ installation of material/ item | 1 | SET | 10% | 64294.6826 | 6429.4683 | 0 |  | 0
25.00 | DISPLAY BOARD | [5 empty] | 0 |  | 0
25.01 | ELECTRIC SHOCK TREATMENT DISPLAY BOARD | [5 empty] | 0 |  | 0
(i) | On completion of supply | 50 | NO | 80% | 721.2584 | 28850.3352 | 0 |  | 0
(ii) | On laying/ installation of material/ item | 50 | NO | 10% | 721.2584 | 3606.2919 | 0 |  | 0
26.00 | Electrical Lab equipment | 1 | LOT | 90% | 213391.7116 | 192052.5405 | 0 |  | 0
27.00 | COMMISSIONING SERVICES FOR TESTING | 300 | MDY | 90% | 7190.4507 | 1941421.6871 | 0 |  | 0
[7 empty] | 0 |  | 0
| SCH-6 - MISC ITEMS | [5 empty] | 0 |  | 0
1.00 | MISC WORKS | [5 empty] | 0 |  | 0
1.01 | ERECTION OF SUPPORT MATERIAL | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 19.1992 |  | 19.1992
(ii) | painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 |  | 0
1.02 | ERECTION OF CHEQUERED PLATES | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 10 | MT | 70% | 25960.3882 | 181722.7175 | 0 |  | 0
(ii) | painting as applicable | 10 | MT | 20% | 25960.3882 | 51920.7764 | 0 |  | 0
1.03 | ERECTION OF INSERT PLATES | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 |  | 0
(ii) | painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 |  | 0
1.04 | ERECTION OF CANOPY FROM 2 MM THICK GI SHEET | [5 empty] | 0 |  | 0
(i) | Fabrication and erection | 10 | SQM | 70% | 1211.2146 | 8478.502 | 0 |  | 0
(ii) | painting as applicable | 10 | SQM | 20% | 1211.2146 | 2422.4291 | 0 |  | 0
1.05 | FABRICATION OF IRREGULAR BEND | [5 empty] | 0 |  | 0
1.5.1 | FOR LADDER TYPE CABLE TRAY | [5 empty] | 0 |  | 0
1.5.1.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 250 | NO | 70% | 541.1622 | 94703.3898 | 200 |  | 200
(ii) | Final painting and marking of tray nos | 250 | NO | 20% | 541.1622 | 27058.1114 | 0 |  | 0
1.5.1.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 541.1614 | 56821.9472 | 100 |  | 100
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 541.1614 | 16234.8421 | 0 |  | 0
1.5.1.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 |  | 100
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 |  | 0
1.5.1.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 |  | 100
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 |  | 0
1.5.2 | FOR PERFORRATED TYPE CABLE TRAY | [5 empty] | 0 |  | 0
1.5.2.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 577.0117 | 30293.1118 | 50 |  | 50
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 577.0117 | 8655.1748 | 0 |  | 0
1.5.2.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 125 | NO | 70% | 577.0117 | 50488.5197 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 125 | NO | 20% | 577.0117 | 14425.2913 | 0 |  | 0
1.5.2.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 |  | 0
1.5.2.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 |  | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 |  | 0
1.06 | SUPPLY, INSTALLATION OF DANGER PLATE | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 25 | NO | 80% | 157.8979 | 3157.9575 | 0 |  | 0
(ii) | On laying/installation of material/item | 25 | NO | 10% | 157.8979 | 394.7447 | 0 |  | 0
1.07 | SUPPLY, INSTALLATION OF FASTENER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 25 | KG | 80% | 352.4298 | 7048.5967 | 0 |  | 0
(ii) | On laying/installation of material/item | 25 | KG | 10% | 352.4298 | 881.0746 | 0 |  | 0
1.08 | SUPPLY OF HEAVY DUTY ANCHOR FASTENERS | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | SET | 80% | 296.1916 | 11847.6624 | 0 |  | 0
(ii) | On laying/installation of material/item | 50 | SET | 10% | 296.1916 | 1480.9578 | 0 |  | 0
1.09 | INSTALLATION OF MS, CABLE GLAND ADAPTOR | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 100 | KG | 80% | 132.1736 | 10573.8852 | 0 |  | 0
(ii) | On laying/installation of material/item | 100 | KG | 10% | 132.1736 | 1321.7357 | 0 |  | 0
1.10 | APPLICATION OF MOISTURE SEALING COMPOUND | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 15 | SQM | 80% | 705.33 | 8463.9597 | 0 |  | 0
(ii) | On laying/installation of material/item | 15 | SQM | 10% | 705.33 | 1057.995 | 0 |  | 0
1.11 | MINOR CIVIL WORK | [5 empty] | 0 |  | 0
1.11.1 | CHIPPING | [5 empty] | 0 |  | 0
(i) | Prorata on completion of actual work | 1 | CUM | 90% | 462.8767 | 416.589 | 0 |  | 0
1.11.2 | BREAKING OF CONCRETE/WALL/ FLOOR | [5 empty] | 0 |  | 0
(i) | Prorata on completion of actual work | 1 | CUM | 90% | 792.7072 | 713.4365 | 0 |  | 0
1.11.3 | EARTH EXCAVATION & BACK FILLING | [5 empty] | 0 |  | 0
(i) | Prorata on completion of actual work | 5 | CUM | 90% | 594.6851 | 2676.0831 | 0 |  | 0
2.0 | SUPLY OF MISC ITEMS | [5 empty] | 0 |  | 0
2.1 | SUPPLY OF CABLE GLAND & LUG | [5 empty] | 0 |  | 0
2.1.1 | DOUBLE COMPRESSION HEAVY DUTY CABLE GLAND | [5 empty] | 0 |  | 0
| ABOVE (MM) UP TO (MM) | [5 empty] | 0 |  | 0
2.1.1.1 | -- 9 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 |  | 0
2.1.1.2 | 09 11 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 |  | 0
2.1.1.3 | 11 13 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 |  | 0
2.1.1.4 | 13 17 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 187.5888 | 7503.5525 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 187.5888 | 937.9441 | 0 |  | 0
2.1.1.5 | 17 20 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 243.1093 | 9724.3704 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 243.1093 | 1215.5463 | 0 |  | 0
2.1.1.6 | 20 23 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 316.2908 | 12651.6321 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 316.2908 | 1581.454 | 0 |  | 0
2.1.1.7 | 23 26 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 373.4821 | 14939.2825 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 373.4821 | 1867.4103 | 0 |  | 0
2.1.1.8 | 26 30 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 391.9971 | 15679.8851 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 391.9971 | 1959.9856 | 0 |  | 0
2.1.1.9 | 30 33 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 549.3009 | 21972.0374 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 549.3009 | 2746.5047 | 0 |  | 0
2.1.1.10 | 33 36 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 635.1064 | 25404.2555 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 635.1064 | 3175.5319 | 0 |  | 0
2.1.1.11 | 36 39 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 796.6058 | 31864.2316 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 796.6058 | 3983.0289 | 0 |  | 0
2.1.1.12 | 39 42 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 |  | 0
2.1.1.13 | 42 46 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 |  | 0
2.1.1.14 | 46 50 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 1032.1407 | 41285.6281 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1032.1407 | 5160.7035 | 0 |  | 0
2.1.1.15 | 54 58 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 1179.3578 | 47174.3104 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1179.3578 | 5896.7888 | 0 |  | 0
2.1.1.16 | 58 62 | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 1768.1889 | 70727.5543 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1768.1889 | 8840.9443 | 0 |  | 0
2.1.2 | AL/CU LUG (HEAVY DUTY TYPE) | [5 empty] | 0 |  | 0
2.1.2.1 | 4 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 7.5743 | 302.9738 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 7.5743 | 37.8717 | 0 |  | 0
2.1.2.2 | 6 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 9.2575 | 370.3013 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 9.2575 | 46.2877 | 0 |  | 0
2.1.2.3 | 10 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 10.0991 | 403.9651 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 10.0991 | 50.4956 | 0 |  | 0
2.1.2.4 | 16 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 13.4655 | 538.6201 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 13.4655 | 67.3275 | 0 |  | 0
2.1.2.5 | 25 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 20.1859 | 807.4351 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 20.1859 | 100.9294 | 0 |  | 0
2.1.2.6 | 35 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 26.9186 | 1076.7452 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 26.9186 | 134.5931 | 0 |  | 0
2.1.2.7 | 50 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 43.7505 | 1750.0203 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 43.7505 | 218.7525 | 0 |  | 0
2.1.2.8 | 70 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 64.7656 | 2590.6242 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 64.7656 | 323.828 | 0 |  | 0
2.1.2.9 | 95 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 94.2214 | 3768.8557 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 94.2214 | 471.107 | 0 |  | 0
2.1.2.10 | 120 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 125.3356 | 5013.4246 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 125.3356 | 626.6781 | 0 |  | 0
2.1.2.11 | 150 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 163.195 | 6527.7986 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 163.195 | 815.9748 | 0 |  | 0
2.1.2.12 | 185 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 213.6658 | 8546.6339 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 213.6658 | 1068.3292 | 0 |  | 0
2.1.2.13 | 240 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 328.0731 | 13122.9247 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 328.0731 | 1640.3656 | 0 |  | 0
2.1.2.14 | 300 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 503.038 | 20121.5209 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 503.038 | 2515.1901 | 0 |  | 0
2.1.2.15 | 400 SQMM | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 778.1031 | 31124.1239 | 0 | 50 | 50
(ii) | On laying/installation of material/item | 50 | NO | 10% | 778.1031 | 3890.5155 | 0 |  | 0
2.2 | MS HEXAGONAL HEAD CABLE GLAND | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | KG | 80% | 399.5838 | 15983.354 | 0 |  | 0
(ii) | On laying/installation of material/item | 50 | KG | 10% | 399.5838 | 1997.9192 | 0 |  | 0
2.3 | GALVANISED MS CONDUIT/ PIPE WITH ACCESORIES | [5 empty] | 0 |  | 0
2.3.1 | RIGID CONDUIT | [5 empty] | 0 |  | 0
2.3.2 | 20-30 MM DIAMETER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 35.8395 | 7167.9051 | 250 |  | 250
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 35.8395 | 895.9881 | 0 |  | 0
2.3.3 | 50 MM DIAMETER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 500 | MTR | 80% | 99.0309 | 39612.3414 | 500 |  | 500
(ii) | On laying/installation of material/item | 500 | MTR | 10% | 99.0309 | 4951.5427 | 0 |  | 0
2.3.4 | 75 MM DIAMETER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 205.6063 | 41121.2698 | 250 |  | 250
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 205.6063 | 5140.1587 | 0 |  | 0
2.3.5 | 100-125 MM DIAMETER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 456.0177 | 91203.5348 | 0 |  | 0
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 456.0177 | 11400.4418 | 0 |  | 0
2.4 | FLEXIBLE CONDUIT (COLD ROLLED ANNEALED) | [5 empty] | 0 |  | 0
2.4.1 | 20-25 MM DIAMETER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 61.3076 | 12261.5286 | 250 |  | 250
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 61.3076 | 1532.6911 | 0 |  | 0
2.4.2 | 40-50 MM DIAMETER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 100 | MTR | 80% | 190.5158 | 15241.2662 | 100 |  | 100
(ii) | On laying/installation of material/item | 100 | MTR | 10% | 190.5158 | 1905.1583 | 0 |  | 0
2.4.3 | 75-100 MM DIAMETER | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | MTR | 80% | 266.4511 | 10658.0446 | 50 |  | 50
(ii) | On laying/installation of material/item | 50 | MTR | 10% | 266.4511 | 1332.2556 | 0 |  | 0
2.5 | MISCELLANEOUS | [5 empty] | 0 |  | 0
2.5.1 | MOISTURE SEALING COMPOUNDS | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 50 | SQM | 80% | 1993.5009 | 79740.0352 | 0 |  | 0
(ii) | On laying/installation of material/item | 50 | SQM | 10% | 1993.5009 | 9967.5044 | 0 |  | 0
2.5.2 | DOL LOCAL STARTER PANEL (3phase,415V,3.7KW) | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 4 | NO | 80% | 1621.7701 | 5189.6642 | 0 | 4 | 4
(ii) | On laying/installation of material/item | 4 | NO | 10% | 1621.7701 | 648.708 | 0 |  | 0
2.5.3 | DOL LOCAL STARTER PANEL (3phase,415V,5.5KW) | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 1579.2263 | 2526.762 | 0 | 2 | 2
(ii) | On laying/installation of material/item | 2 | NO | 10% | 1579.2263 | 315.8453 | 0 |  | 0
2.5.4 | JOINT KIT 6.6KV 1CX400AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 3926.407 | 6282.2512 | 0 |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 3926.407 | 785.2814 | 0 |  | 0
2.5.5 | JOINT KIT 6.6KV 3CX150AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 12803.3666 | 20485.3865 | 0 |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 12803.3666 | 2560.6733 | 0 |  | 0
2.5.6 | JOINT KIT 6.6KV 3CX240AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 14510.6884 | 23217.1014 | 0 |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 14510.6884 | 2902.1377 | 0 |  | 0
2.5.7 | JOINT KIT 33KV 3CX120AL UNARMOURED | [5 empty] | 0 |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 16217.7008 | 25948.3212 | 0 |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 16217.7008 | 3243.5402 | 0 |  | 0
3.00 | COMMISSIONING SUPPORT | [5 empty] | 0 |  | 0
3.1 | SPECIALISED SKILLED TECHNICAL MANPOWER | 30 | MD | 90% | 7298.0014 | 197046.0391 | 0 |  | 0
3.2 | SUPPORT SERVICE BY UN-SKILLED MANPOWER | 60 | MD | 90% | 973.062 | 52545.3505 | 0 |  | 0

## WAM-6
WAM - 6 Sheet 1 of 5
Name of the Contractor |  |  | M/S POWERTRONIX ENGINEERING PVT LTD | [9 empty] | Department Bill No: RKL/ELEC/RA/07 |  |  |  | Date: 31.08.2019
Name of the Work |  |  | ERECTION,TESTING,COMMMISSIONING,HANDING OVER,ETC. OF GENERATOR TRANSFORMER, STATION TRANSFORMER, UNIT AUXILIARY TRANSFORMER, OTHER MOSC TRANSFORMER, HT/LT BUS DUCT, DG SET, RAW WATER INTAKE SYSTEM(ELECTRICAL WORKS), ASSOCLATED EQULPMENT/ITEMS/PANEL, CABLE TRAY & ACCESSORIES, CABLING, ETC ALONG WITH SUPPLY OF MINOR ACCESSORIES AT 1X250MWPP-II EXPANSION PROJECT,NSPCL, ROURKELA, ODISHA. | [9 empty] | Division: BHEL PSER |  |  |  | SubDivision: NSPCL Rourkela(PP-II)
Date of Commencement of the Work: 27.12.2018
Due Date of Completion as per Agreement: 26.12.2019
Sanctioned Estimate |  |  | Rs. 4,99,14,972.00 | [9 empty] | Due Date of Completion extended upto: na
Contract Agreement No |  |  | PSER: SCT: RKL-E 1903:19(CPES-ER/02500): WO(PKG-A):AMEND-01:7468 DATED: 02.08.2019 | [9 empty] | Bill Period: 01.08.2019 - 31.08.2019
On Account payment for work not Previously Measured |  |  | ITEM NO | EQUIPMENT/ITEM DESCRIPTION OF WORKS | BBU QTY |  | % BREAKUP OF UNIT RATE | UNIT RATE (Rs) | ALLOTED AMOUNT (Rs) | MEASUREMENT QUANTITY |  |  | CLAIMED AMOUNT |  |  | WITHELD AMOUNT ON PRESENT BILL |  | CUMULATIVE WITHELD AMOUNT UPTO DATE | WITHELD
Total as per last RA Bill | Since last RA Bill | Total Upto Date |  |  | QTY | UOM |  |  |  | UP TO PREV | PRESENT BILL | CUM | UP TO PREV | PRESENT BILL | CUMULATIVE | AMOUNT | REMARK |  | RA-01 | RA-02 | RA-03 | RA-04 | RA-05 | RA-06 | RA-07 | RA-08 | RA-09 | RA-10 | RA-11 | RA-12 | RA-13 | RA-14 | RA-15 | RA-16 | RA-17 | RA-18 | RA-19 | RA-20
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 = 6x8x9 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | bar: WITHELD RA-01 to WITHELD RA-02
|  |  |  | SCH-3 TRANSFORMER & BUS DUCT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.00 | BUS DUCTS & ASOCIATED EQUIPMENT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.01 | SEGREGATED PHASE BUSDUCT (6.6 KV/ 4000 A) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, welding etc | 300 | MTR | 65% | 5336.5018 | 1040617.8438 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 300 | MTR | 15% | 5336.5018 | 240142.5793 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 300 | MTR | 10% | 5336.5018 | 160095.0529 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02 | COMMON CHAMBER FOR GENERATOR PH AND N-SIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, welding etc | 1 | SET | 65% | 36055.4931 | 23436.0705 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 1 | SET | 15% | 36055.4931 | 5408.324 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 10% | 36055.4931 | 3605.5493 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.03 | MAIN RUN ISOLATED PHASE BUSDUCT (21 KV, 12500A) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, welding etc | 125 | MTR | 65% | 6850.7281 | 556621.6581 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 125 | MTR | 15% | 6850.7281 | 128451.1519 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 125 | MTR | 10% | 6850.7281 | 85634.1012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.04 | TAP OFF IP BUS DUCT (21 KV, 1500 AMP) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, welding etc | 100 | MTR | 65% | 5408.2002 | 351533.0132 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 100 | MTR | 15% | 5408.2002 | 81123.003 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 100 | MTR | 10% | 5408.2002 | 54082.002 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.05 | SPVT CUBICLE FOR IP BUSDUCT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placenment ,Alingnment & Coupling | 1 | SET | 70% | 57690.0266 | 40383.0186 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  |  | NG CUBICLE (WITH NGT & NGR ) FOR IP BUSDUCT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.07 | HOT AIR BLOWING EQUIPMENT WITH PIPINGS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 1 | 0 | 1 | 20191.9425 | 0 | 20191.9425 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.00 | 415V LV BUS-DUCT SET FOR DTT AND PMCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.01 | BUSDUCT FOR UNIT PMCC #1 DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 | 0 | 2 | 13126.0188 | 0 | 13126.0188 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2 | 0 | 1875.1455 | 1875.1455 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.02 | BUSDUCT FOR ESP PMCC #1DB-1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 | 0 | 2 | 13126.0188 | 0 | 13126.0188 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2 | 0 | 1875.1455 | 1875.1455 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.03 | BUSDUCT FOR ESP PMCC #1DB-2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 | 0 | 2 | 12520.0093 | 0 | 12520.0093 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 2 | 2 | 0 | 1788.5728 | 1788.5728 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.04 | BUSDUCT FOR STATION PMCC #0DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 | 0 | 2 | 12520.0093 | 0 | 12520.0093 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.05 | BUSDUCT FOR COOLING TOWER PMCC #1DC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.06 | BUSDUCT FOR PTP PMCC #1DD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.07 | BUSDUCT FOR ETP PMCC #1DE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.00 | POWER TRANSFORMERS AND DTT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.01 | GENERATOR TRANSFORMERS - 315 MVA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 166578.1109 | WITHELD RA-02: 166578.1109
|  |  | (i) | Placement on Foundation and alignment | 1 | NO | 35% | 951874.9193 | 333156.2218 | 1 | 0 | 1 | 333156.2218 | 0 | 333156.2218 |  |  | 0
|  |  | (ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 951874.9193 | 190374.9839 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Completion of Oil filteration | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 951874.9193 | 142781.2379 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (v) | Charging | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.02 | STATION TRANSFORMER - 37.5/30 MVA, 220/6.9 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 110900.8242 | WITHELD RA-02: 110900.8242
|  |  | (i) | Placement on Foundation and alignment | 1 | NO | 35% | 633718.9956 | 221801.6484 | 1 | 0 | 1 | 221801.6484 | 0 | 221801.6484 |  |  | 63371.8996 | WITHELD RA-02: 63371.8996
|  |  | (ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 633718.9956 | 126743.7991 | 1 | 0 | 1 | 126743.7991 | 0 | 126743.7991 |  |  | 0
|  |  | (iii) | Completion of Oil filteration | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 633718.9956 | 95057.8493 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (v) | Charging | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.03 | UAT - 37.5/30 MVA,16.5/6.9 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement on Foundation and alignment | 2 | NO | 35% | 476803.4969 | 333762.4479 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 20% | 476803.4969 | 190721.3988 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Completion of Oil filteration | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iv) | Pre-commissioning checks & tests | 2 | NO | 15% | 476803.4969 | 143041.0491 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (v) | Charging | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.04 | 2500KVA DTT 6.6/0.433 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 70% | 28845.4259 | 121150.7886 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging of Transformer | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.05 | 2000KVA DTT 6.6/0.433 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20191.7259 | WITHELD RA-02: 20191.7259
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 28845.3227 | 40383.4518 | 2 | 0 | 2 | 40383.4518 | 0 | 40383.4518 |  |  | 5769.0645 | WITHELD RA-02: 5769.0645
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 28845.3227 | 5769.0645 | 2 | 0 | 2 | 5769.0645 | 0 | 5769.0645 |  |  | 0
|  |  | (iii) | Charging of Transformer | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.06 | 1600KVA DTT 6.6/0.433 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20768.3331 | WITHELD RA-01: 20768.3331
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 11 | NO | 70% | 25960.4163 | 199895.2058 | 4 | 0 | 4 | 72689.1658 | 0 | 72689.1658 |  |  | 10384.1665 | WITHELD RA-01: 10384.1665
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 11 | NO | 10% | 25960.4163 | 28556.458 | 4 | 0 | 4 | 10384.1665 | 0 | 10384.1665 |  |  | 0
|  |  | (iii) | Charging of Transformer | 11 | NO | 10% | 25960.4163 | 28556.458 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.07 | 1250KVA DTT 6.6/0.433 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.08 | 1000KVA DTT 6.6/0.433 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.09 | 630KVA DTT, 6.6/0.415KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.10 | 500KVA DTT 6.6/0.433 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 4 | NO | 70% | 23076.2272 | 64613.4363 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging of Transformer | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.11 | 33/6.9KV 2MVA OIL FILLED RAW WATER TRF | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement on Foundation and alignment | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 30% | 28845.3227 | 17307.1936 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Completion of Oil filteration | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iv) | Pre-commissioning checks & tests | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (v) | Charging | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.12 | 6.6 KV NEUTRAL GROUNDING RESISTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 70% | 20485.634 | 71699.7191 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 10% | 20485.634 | 10242.817 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging of Transformer | 5 | NO | 10% | 20485.634 | 10242.817 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.00 | HVR TRANSFORMER(95 KVp,1200mA)COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Test of HVR including Interlock/Protection, OCC/SCC | 28 | NO | 50% | 8473.3569 | 118626.9969 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Charging (Field-Charging) | 28 | NO | 40% | 8473.3569 | 94901.5975 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.00 | BUS DUCTS & EQUIPMENT SUPPORT STRUCTURE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Pre-assembly, alignment, erection including welding | 50 | MT | 70% | 8654.3208 | 302901.2292 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks /Testing & charging | 50 | MT | 10% | 8654.3208 | 43271.6042 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 50 | MT | 10% | 8654.3208 | 43271.6042 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6 | GENERATOR CIRCUIT BREAKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement, alignment, installation, internal wiring | 1 | NO | 60% | 36398.9377 | 21839.3626 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-commissioning checks/testing | 1 | NO | 20% | 36398.9377 | 7279.7875 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 10% | 36398.9377 | 3639.8938 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.0 | UNLOADING AND SHIFTING OF TRANSFORMERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.1 | GENERATOR TRANSFORMERS (GT) - 315 MVA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.1.1 | UNLOADING OF GT FROM TRAILER | 1 | NO | 90% | 214172.0425 | 192754.8382 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 1 | NO | 90% | 160628.7225 | 144565.8502 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.1 | STATION /UNIT TRANSFORMER (ST/UT) (37.5/30 MVA) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.1.1 | UNLOADING OF ST / UT FROM TRAILER | 1 | NO | 90% | 84371.0296 | 75933.9267 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 1 | NO | 90% | 63277.9628 | 56950.1665 | 1 | 0 | 1 | 56950.1665 | 0 | 56950.1665 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  |  | SCH-4-CABLING & EQUIPMENT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.00 | CABLE TRAY SUPPORT SYSTEM WITH ACCESORIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.01 | CHANNEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.01.01 | SINGLE(SC1) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 6600 | RM | 70% | 109.3923 | 505392.4429 | 2046 | 0 | 2046 | 156671.6573 | 0 | 156671.6573 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 6600 | RM | 20% | 109.3923 | 144397.8408 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.01.02 | DOUBLE(DC1) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5500 | RM | 70% | 127.6211 | 491341.1658 | 2280 | 600 | 2880 | 203683.2469 | 53600.8545 | 257284.1014 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5500 | RM | 20% | 127.6211 | 140383.1902 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02 | CANTILEVER ARM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02.01 | 600 MM Cantilever Arm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 12000 | NOS | 70% | 51.0519 | 428835.5511 | 5177 | 0 | 5177 | 185006.804 | 0 | 185006.804 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 12000 | NOS | 20% | 51.0519 | 122524.4432 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02.02 | 300 MM Cantilever Arm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 6500 | NOS | 70% | 33.1867 | 150999.4646 | 1050 | 0 | 1050 | 24392.2212 | 0 | 24392.2212 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 6500 | NOS | 20% | 33.1867 | 43142.7042 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02.03 | 150 MM Cantilever Arm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 1500 | NOS | 70% | 20.426 | 21447.2789 | 725 | 0 | 725 | 10366.1848 | 0 | 10366.1848 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 1500 | NOS | 20% | 20.426 | 6127.794 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02.04 | 100 MM Cantilever Arm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 500 | NOS | 70% | 20.426 | 7149.093 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 500 | NOS | 20% | 20.426 | 2042.598 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2 | LADDER TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1 | 600 MM Ladder Type Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 24790 | MTR | 70% | 58.0426 | 1007212.5052 | 4125 | 1000 | 5125 | 167597.8856 | 40629.7904 | 208227.6761 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 24790 | MTR | 20% | 58.0426 | 287775.0015 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.2 | 450 MM Ladder Type Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 50.3607 | 35252.5135 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 50.3607 | 10072.1467 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.3 | 300 MM Ladder Type Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5050 | MTR | 70% | 43.5319 | 153885.2654 | 2250 | 0 | 2250 | 68562.742 | 0 | 68562.742 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5050 | MTR | 20% | 43.5319 | 43967.2187 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.4 | 150 MM Ladder Type Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 4150 | MTR | 70% | 35.8498 | 104143.5366 | 625 | 250 | 875 | 15684.2676 | 6273.707 | 21957.9746 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 4150 | MTR | 20% | 35.8498 | 29755.2962 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5 | 100 MM Ladder Type Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 35.85 | 25095.0316 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 35.85 | 7170.009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.6 | 50 MM Ladder Type Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 17.9247 | 6273.6496 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 17.9247 | 1792.4713 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3 | CABLE TRAY 90 DEG BEND HORIZONTAL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.1.1 | 600 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 400 | NO | 70% | 173.274 | 48516.7146 | 132 | 0 | 132 | 16010.5158 | 0 | 16010.5158 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 400 | NO | 20% | 173.274 | 13861.9185 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.1.2 | 450 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.1.3 | 300 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 120 | NO | 70% | 144.2519 | 12117.1581 | 9 | 0 | 9 | 908.7869 | 0 | 908.7869 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 120 | NO | 20% | 144.2519 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.1.4 | 150 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.1.5 | 100 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.1.6 | 50 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 68.2557 | 477.7902 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 68.2557 | 136.5115 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.2 | CABLE TRAY 90 DEG BEND VERTICAL-INSIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 173.2755 | 24258.5739 | 50 | 0 | 50 | 6064.6435 | 0 | 6064.6435 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 200 | NO | 20% | 173.2755 | 6931.0211 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 144.2509 | 7573.1697 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 75 | NO | 20% | 144.2509 | 2163.7628 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.3 | CABLE TRAY 90 DEG BEND VERTICAL-OUTSIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 173.2735 | 18193.7138 | 50 | 0 | 50 | 6064.5713 | 0 | 6064.5713 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 150 | NO | 20% | 173.2735 | 5198.204 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.4 | TEES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.4.1 | 600 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 231.3177 | 32384.4727 | 50 | 0 | 50 | 8096.1182 | 0 | 8096.1182 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 200 | NO | 20% | 231.3177 | 9252.7065 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.4.2 | 450 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.4.3 | 300 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 173.2693 | 2425.7708 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 20 | NO | 20% | 173.2693 | 693.0774 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.4.4 | 150 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 137.4191 | 1442.9004 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 15 | NO | 20% | 137.4191 | 412.2573 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.4.5 | 100 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.4.6 | 50 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 68.3176 | 239.1117 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 68.3176 | 68.3176 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.5.0 | CROSSES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.5.1 | 600 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 90 | NO | 70% | 260.3372 | 16401.2425 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 90 | NO | 20% | 260.3372 | 4686.0693 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.5.2 | 450 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 215.9679 | 1511.775 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 215.9679 | 431.9357 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.5.3 | 300 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 202.3126 | 2124.2821 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 15 | NO | 20% | 202.3126 | 606.9377 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.5.4 | 150 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.5.5 | 100 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.5.6 | 50 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 86.2634 | 301.9218 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 86.2634 | 86.2634 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.6 | REDUCERS LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.6.1 | 600 MM-450 MM Reducer LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 158.7642 | 5556.7477 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 50 | NO | 20% | 158.7642 | 1587.6422 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.6.2 | 600 MM-300 MM Reducer LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 144.2591 | 2524.5343 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 25 | NO | 20% | 144.2591 | 721.2955 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.6.3 | 450 MM -300 MM Reducer LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 40 | NO | 70% | 137.4242 | 3847.8789 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 40 | NO | 20% | 137.4242 | 1099.394 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.6.4 | 300 MM -150 MM Reducer LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.7 | REDUCERS RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.7.1 | 600 MM-450 MM Reducer RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 158.758 | 2222.6125 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 20 | NO | 20% | 158.758 | 635.0321 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.7.2 | 600 MM-300 MM Reducer RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.7.3 | 450 MM -300 MM Reducer RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.7.4 | 300 MM -150 MM Reducer RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.8 | CABLE TRAY COVER WITH FIXING HARDWARES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.8.1 | 600 MM wide Tray Cover | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 58.0428 | 20314.9637 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 58.0428 | 5804.2753 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.8.2 | 450 MM wide Tray Cover | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 250 | MTR | 70% | 58.0428 | 10157.4819 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 250 | MTR | 20% | 58.0428 | 2902.1377 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.8.3 | 300 MM wide Tray Cover | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  |  | Fabrication and erection complete as applicable | 100 | MTR | 70% | 50.3595 | 3525.1647 | 70 | 0 | 70 | 2467.6153 | 0 | 2467.6153 |  |  | 0
|  |  |  | Final painting and marking of tray nos | 100 | MTR | 20% | 50.3595 | 1007.1899 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.8.4 | 150 MM wide Tray Cover | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 100 | MTR | 70% | 43.5339 | 3047.3745 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 100 | MTR | 20% | 43.5339 | 870.6784 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.8.5 | 100 MM wide Tray Cover | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 43.5277 | 1523.4707 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 43.5277 | 435.2773 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.8.6 | 50 MM wide Tray Cover | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 21.7701 | 761.9519 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 21.7701 | 217.7005 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.00 | PERFORATED TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.10 | 600 MM Perforated Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 7500 | MTR | 70% | 71.6997 | 376423.3085 | 1650 | 0 | 1650 | 82813.1279 | 0 | 82813.1279 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 7500 | MTR | 20% | 71.6997 | 107549.5167 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.20 | 450 MM Perforated Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 64.8708 | 22704.7811 | 150 | 0 | 150 | 6811.4343 | 0 | 6811.4343 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 64.8708 | 6487.0803 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.30 | 300 MM Perforated Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 3500 | MTR | 70% | 58.0426 | 142204.3129 | 887.5 | 0 | 887.5 | 36058.9508 | 0 | 36058.9508 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 3500 | MTR | 20% | 58.0426 | 40629.8037 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.40 | 150 MM Perforated Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 1500 | MTR | 70% | 43.5319 | 45708.4518 | 250 | 0 | 250 | 7618.0753 | 0 | 7618.0753 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 1500 | MTR | 20% | 43.5319 | 13059.5577 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.50 | 100 MM Perforated Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 43.5321 | 30472.4456 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 43.5321 | 8706.413 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.60 | 50 MM Perforated Cable Tray | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 21.3394 | 14937.5498 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 21.3394 | 4267.8714 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.00 | CABLE TRAY ACCESSORIES (PERFORATED-TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.10 | HORIZONTAL 90 DEG BEND PERFORATED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.1.1 | 600 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 230 | NO | 70% | 187.7847 | 30233.3339 | 67 | 0 | 67 | 8807.1016 | 0 | 8807.1016 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 230 | NO | 20% | 187.7847 | 8638.0954 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.1.2 | 450 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.1.3 | 300 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 35 | NO | 70% | 158.7713 | 3889.8967 | 5 | 0 | 5 | 555.6995 | 0 | 555.6995 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 35 | NO | 20% | 158.7713 | 1111.399 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.1.4 | 150 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.1.5 | 100 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.1.6 | 50 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 72.5256 | 253.8396 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 72.5256 | 72.5256 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.20 | VERTICAL 90 DEG BEND PERFORATED (INSIDE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 187.7868 | 13145.0784 | 20 | 0 | 20 | 2629.0157 | 0 | 2629.0157 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 100 | NO | 20% | 187.7868 | 3755.7367 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 158.7642 | 11113.4954 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 100 | NO | 20% | 158.7642 | 3175.2844 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.30 | VERTICAL 90 DEG BEND PERFORATED (OUTSIDE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 110 | NO | 70% | 187.7835 | 14459.3264 | 25 | 0 | 25 | 3286.2105 | 0 | 3286.2105 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 110 | NO | 20% | 187.7835 | 4131.2361 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 173.2693 | 3032.2134 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 25 | NO | 20% | 173.2693 | 866.3467 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 60 | NO | 70% | 158.7683 | 6668.2705 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 60 | NO | 20% | 158.7683 | 1905.2202 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 144.2467 | 2019.4542 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 20 | NO | 20% | 144.2467 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.40 | TEES PERFORATED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.1 | 600 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 130 | NO | 70% | 202.2967 | 18409.001 | 25 | 0 | 25 | 3540.1925 | 0 | 3540.1925 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 130 | NO | 20% | 202.2967 | 5259.7146 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.2 | 450 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.3 | 300 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.4 | 150 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.5 | 100 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 158.789 | 555.7614 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 158.789 | 158.789 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.6 | 50 MM Tee-Joint | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 79.3326 | 277.6641 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 79.3326 | 79.3326 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.50 | CROSSES PERFORATED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.1 | 600 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 288.4935 | 2019.4542 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 288.4935 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.2 | 450 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 231.3146 | 809.601 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 231.3146 | 231.3146 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.3 | 300 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 215.9679 | 755.8875 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 215.9679 | 215.9679 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.4 | 150 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.5 | 100 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.6 | 50 MM Cross | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 53.7135 | 187.9972 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 53.7135 | 53.7135 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.60 | REDUCERS PERFORATED LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.6.1 | 600 MM WIDE - 450 MM Reducer LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.6.2 | 450 MM WIDE - 300 MM Reducer LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.6.3 | 300 MM WIDE - 150 MM Reducer LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.70 | REDUCERS PERFORATED RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.7.1 | 600 MM WIDE - 450 MM Reducer RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.7.2 | 450 MM WIDE - 300 MM Reducer RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.7.3 | 300 MM WIDE - 150 MM Reducer RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.80 | CABLE TROUGHS HOT DIP GALVANISED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.8.1 | 50MM WIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 734.7504 | 90006.9243 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 734.7504 | 25716.2641 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.8.2 | 75MM WIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 1102.8098 | 135094.2055 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 1102.8098 | 38598.3444 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.00 | CONDUITS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.1 | RIGID GALVANISED MS CONDUITS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.1.1 | 50 MM DIAMETER MS Conduit | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 108.4016 | 19512.2935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.1.2 | 80 MM DIAMETER MS Conduit | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 122.9129 | 22124.3288 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.2 | GI FLEXIBLE METALLIC CONDUIT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of conduit/pipe complete in all respect | 2240 | MTR | 90% | 35.8498 | 72273.1787 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.00 | PERFORATED MS SHEET TO COVER CABLE SHAFT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 250 | SQM | 70% | 71.6989 | 12547.2992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Painting as applicable | 250 | SQM | 20% | 71.6989 | 3584.9426 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.00 | DOUBLE COMPRESSION CABLE GLAND FOR UA/A CABLE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.01 | 9-11 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 300 | NO. | 70% | 71.7005 | 15057.1056 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 300 | NO. | 20% | 71.7005 | 4302.0302 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.02 | 11-13 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 1000 | NO. | 70% | 71.6995 | 50189.6301 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 1000 | NO. | 20% | 71.6995 | 14339.8943 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.03 | 13-17 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 1500 | NO. | 70% | 79.3817 | 83350.7826 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 1500 | NO. | 20% | 79.3817 | 23814.5093 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.04 | 17-20 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 200 | NO. | 70% | 87.0647 | 12189.0649 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 200 | NO. | 20% | 87.0647 | 3482.59 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.05 | 20-23 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 70 | NO. | 70% | 94.75 | 4642.752 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 70 | NO. | 20% | 94.75 | 1326.5006 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.06 | 23-26 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 150 | NO. | 70% | 101.573 | 10665.161 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 150 | NO. | 20% | 101.573 | 3047.1889 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.07 | 26-30 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO. | 70% | 108.4047 | 3794.1654 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO. | 20% | 108.4047 | 1084.0472 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.08 | 30-35 (For 3.5C x 50, 2C x 95 Cables ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 122.9098 | 4301.8445 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 122.9098 | 1229.0984 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.09 | 35-40 (For 3.5C x 95, 2C x 120 Cables ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 100 | NO | 70% | 130.5956 | 9141.6904 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 100 | NO | 20% | 130.5956 | 2611.9115 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.10 | 40-50 (For 3C x 150, 2C x 120 Cables ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 151.9325 | 5317.636 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 151.9325 | 1519.3246 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.11 | 50-60 (For 3C x 240, 2C x 120 Cables ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 20 | NO | 70% | 166.4314 | 2330.0394 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 20 | NO | 20% | 166.4314 | 665.7256 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.12 | CABLE GLAND SUITABLE-16 PAIR,0.5SQ.MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.13 | CABLE GLAND SUITABLE-10 PAIR,0.6SQ.MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.20 | CRIMPING LUGS (RING/ROUND/FLAT TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.1 | 0.5 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 7000 | NO | 70% | 22.1927 | 108744.2707 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 7000 | NO | 20% | 22.1927 | 31069.7916 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.2 | 1.5 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 800 | NO | 70% | 22.1924 | 12427.7434 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 800 | NO | 20% | 22.1924 | 3550.7838 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.3 | 2.5 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 5250 | NO | 70% | 22.1927 | 81558.3113 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 5250 | NO | 20% | 22.1927 | 23302.3747 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.4 | 16 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 250 | NO | 70% | 29.0201 | 5078.5243 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 250 | NO | 20% | 29.0201 | 1451.007 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.5 | 25 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 29.0226 | 1015.7915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 29.0226 | 290.2261 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.6 | 35 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 43.5277 | 1523.4707 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 43.5277 | 435.2773 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.7 | 50 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.8 | 70 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.9 | 95 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 71.6964 | 2509.3732 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 71.6964 | 716.9638 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.10 | 120 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.11 | 150 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.12 | 185 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.13 | 240 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.10 | 300 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 130.5956 | 4570.8452 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 130.5956 | 1305.9558 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.2.11 | 630 Sq-mm Lugs | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.00 | EQUIPMENT EARTHING MATERIALS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.01 | GI WIRE 14 SWG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 87500 | MTR | 70% | 7.6821 | 470528.9191 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 87500 | MTR | 20% | 7.6821 | 134436.834 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.02 | GI WIRE 8 SWG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 1450 | MTR | 70% | 7.6819 | 7797.1203 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 1450 | MTR | 20% | 7.6819 | 2227.7487 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.03 | GS FLAT 25 X 6 MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 8 | MT | 70% | 12997.0569 | 72783.5188 | 1 | 0 | 1 | 9097.9398 | 0 | 9097.9398 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 8 | MT | 20% | 12997.0569 | 20795.2911 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.04 | GS FLAT 50 X 6 MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 2 | MT | 70% | 8983.087 | 12576.3218 | 1.5 | 0 | 1.5 | 9432.2414 | 0 | 9432.2414 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 2 | MT | 20% | 8983.087 | 3593.2348 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.05 | GS FLAT 65 X 8 MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 53 | MT | 70% | 10576.5403 | 392389.645 | 33 | 0 | 33 | 244318.0809 | 0 | 244318.0809 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 53 | MT | 20% | 10576.5403 | 112111.3271 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.06 | GS FLAT 75 X 10 MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 6 | MT | 70% | 9787.4487 | 41107.2845 | 5.4985 | 0 | 5.4985 | 37671.4006 | 0 | 37671.4006 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 6 | MT | 20% | 9787.4487 | 11744.9384 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.07 | GS ROD 20 MM DIA.1000MM LONG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 84 | NOS | 70% | 341.8091 | 20098.377 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8091 | 5742.3934 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.08 | TEST LINK 150X25X6 MM GS FLAT WITH BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 84 | NOS | 70% | 341.8681 | 20101.8424 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8681 | 5743.3836 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.09 | 40NB GALV MS HEAVY DUTY PIPE (PERF) 3M | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 112 | NOS | 70% | 454.2408 | 35612.4805 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 112 | NOS | 20% | 454.2408 | 10174.9944 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.10 | FLEXIBLE BRAIDED CONDUCTOR FOR FENCE GATE GND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 10 | NOS | 70% | 5048.821 | 35341.7472 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 10 | NOS | 20% | 5048.821 | 10097.6421 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.00 | CABLE LAYING, DRESSING, CLAMPING, TAGGING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.1 | 6.6 KV XLPE AL UA POWER CABLES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.1.1 | 1C-400 Sq.mm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 32000 | MTR | 55% | 31.7271 | 558396.7097 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 32000 | MTR | 10% | 31.7271 | 101526.6745 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 32000 | MTR | 25% | 31.7271 | 253816.6862 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.1.2 | 3C-150 Sq.mm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 13000 | MTR | 55% | 34.6138 | 247488.9209 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 13000 | MTR | 10% | 34.6138 | 44997.9856 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 13000 | MTR | 25% | 34.6138 | 112494.964 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.1.3 | 3C-240 Sq.mm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 5000 | MTR | 55% | 43.2673 | 118985.1694 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 5000 | MTR | 10% | 43.2673 | 21633.6672 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 5000 | MTR | 25% | 43.2673 | 54084.1679 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.2 | 33 KV XLPE AL UA POWER CABLES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.2.1 | 3C-120 Sq.mm | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 1500 | MTR | 55% | 34.6139 | 28556.427 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 1500 | MTR | 10% | 34.6139 | 5192.0776 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 1500 | MTR | 25% | 34.6139 | 12980.1941 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.3.1 | 3.5C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8000 | MTR | 55% | 12.2573 | 53931.9384 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8000 | MTR | 10% | 12.2573 | 9805.807 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8000 | MTR | 25% | 12.2573 | 24514.5175 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.3.2 | 3.5C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 1000 | MTR | 55% | 14.4166 | 7929.1453 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 1000 | MTR | 10% | 14.4166 | 1441.6628 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 1000 | MTR | 25% | 14.4166 | 3604.157 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.3.3 | 3C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8000 | MTR | 55% | 10.0891 | 44392.2546 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8000 | MTR | 10% | 10.0891 | 8071.319 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8000 | MTR | 25% | 10.0891 | 20178.2975 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.1 | 1C - 35 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8000 | MTR | 55% | 8.6663 | 38131.5073 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8000 | MTR | 10% | 8.6663 | 6933.0013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8000 | MTR | 25% | 8.6663 | 17332.5033 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.2 | 1C - 70 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 14000 | MTR | 55% | 9.6291 | 74143.9925 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 14000 | MTR | 10% | 9.6291 | 13480.7259 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 14000 | MTR | 25% | 9.6291 | 33701.8148 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.3 | 1C - 120 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 2000 | MTR | 55% | 11.5555 | 12711.0697 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 2000 | MTR | 10% | 11.5555 | 2311.1036 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 2000 | MTR | 25% | 11.5555 | 5777.759 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.4 | 1C - 400 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 13500 | MTR | 55% | 16.3706 | 121551.4121 | 0 | 2961 | 2961 | 0 | 26660.2764 | 26660.2764 |  |  | 0
|  |  | (ii) | After termination of cable | 13500 | MTR | 10% | 16.3706 | 22100.2567 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 13500 | MTR | 25% | 16.3706 | 55250.6418 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.5 | 1C - 630 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 18000 | MTR | 55% | 17.3334 | 171600.6321 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 18000 | MTR | 10% | 17.3334 | 31200.1149 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 18000 | MTR | 25% | 17.3334 | 78000.2873 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.6 | 2C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 6000 | MTR | 55% | 8.6663 | 28598.6305 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 6000 | MTR | 10% | 8.6663 | 5199.751 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 6000 | MTR | 25% | 8.6663 | 12999.3775 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.7 | 2C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8000 | MTR | 55% | 9.6291 | 42367.8499 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8000 | MTR | 10% | 9.6291 | 7703.2454 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8000 | MTR | 25% | 9.6291 | 19258.1136 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.8 | 2C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 1000 | MTR | 55% | 11.5558 | 6355.705 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 1000 | MTR | 10% | 11.5558 | 1155.5827 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.5558 | 2888.9568 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.9 | 2C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 6000 | MTR | 55% | 12.9998 | 42899.4773 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 6000 | MTR | 10% | 12.9998 | 7799.905 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 6000 | MTR | 25% | 12.9998 | 19499.7624 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.10 | 2C - 120 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8000 | MTR | 55% | 13.9626 | 61435.6456 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8000 | MTR | 10% | 13.9626 | 11170.1174 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8000 | MTR | 25% | 13.9626 | 27925.2935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.11 | 3C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 36100 | MTR | 55% | 9.6291 | 191185.7606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 36100 | MTR | 10% | 9.6291 | 34761.0474 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 36100 | MTR | 25% | 9.6291 | 86902.6185 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.12 | 3C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 14000 | MTR | 55% | 11.0742 | 85271.071 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 14000 | MTR | 10% | 11.0742 | 15503.8311 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 14000 | MTR | 25% | 11.0742 | 38759.5777 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.13 | 3C - 35 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 800 | MTR | 55% | 11.5557 | 5084.4959 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 800 | MTR | 10% | 11.5557 | 924.4538 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 800 | MTR | 25% | 11.5557 | 2311.1345 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.14 | 3C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 2000 | MTR | 55% | 12.5184 | 13770.2404 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 2000 | MTR | 10% | 12.5184 | 2503.6801 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 2000 | MTR | 25% | 12.5184 | 6259.2002 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.15 | 3C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8000 | MTR | 55% | 14.4441 | 63553.9871 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8000 | MTR | 10% | 14.4441 | 11555.2704 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8000 | MTR | 25% | 14.4441 | 28888.1759 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.16 | 3C - 150 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 750 | MTR | 55% | 19.2593 | 7944.4611 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 750 | MTR | 10% | 19.2593 | 1444.4475 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 750 | MTR | 25% | 19.2593 | 3611.1187 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.17 | 3C - 240 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 6750 | MTR | 55% | 24.074 | 89374.6769 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 6750 | MTR | 10% | 24.074 | 16249.9413 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 6750 | MTR | 25% | 24.074 | 40624.8531 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.18 | 3.5C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 6000 | MTR | 55% | 11.267 | 37181.2488 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 6000 | MTR | 10% | 11.267 | 6760.227 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 6000 | MTR | 25% | 11.267 | 16900.5676 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.19 | 3.5C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 12000 | MTR | 55% | 12.9998 | 85798.9546 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 12000 | MTR | 10% | 12.9998 | 15599.8099 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 12000 | MTR | 25% | 12.9998 | 38999.5248 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.20 | 3.5C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 10000 | MTR | 55% | 14.9263 | 82094.9203 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 10000 | MTR | 10% | 14.9263 | 14926.3491 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.9263 | 37315.8729 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.21 | 3.5C - 185 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 750 | MTR | 55% | 23.1108 | 9533.2172 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 750 | MTR | 10% | 23.1108 | 1733.3122 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 750 | MTR | 25% | 23.1108 | 4333.2805 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.22 | 4C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 15000 | MTR | 55% | 10.1105 | 83411.7363 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 15000 | MTR | 10% | 10.1105 | 15165.7702 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.1105 | 37914.4256 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.23 | 2C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 140 | MTR | 55% | 6.4446 | 496.231 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 140 | MTR | 10% | 6.4446 | 90.2238 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 140 | MTR | 25% | 6.4446 | 225.5596 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.24 | 2C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 68500 | MTR | 55% | 6.4461 | 242858.4525 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 68500 | MTR | 10% | 6.4461 | 44156.0823 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 68500 | MTR | 25% | 6.4461 | 110390.2057 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.25 | 3C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 9200 | MTR | 55% | 6.4461 | 32617.4891 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 9200 | MTR | 10% | 6.4461 | 5930.4526 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 9200 | MTR | 25% | 6.4461 | 14826.1314 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.26 | 3C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 95300 | MTR | 55% | 6.4461 | 337874.4387 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 95300 | MTR | 10% | 6.4461 | 61431.7161 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 95300 | MTR | 25% | 6.4461 | 153579.2903 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.27 | 4C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 5500 | MTR | 55% | 6.4462 | 19499.7005 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 5500 | MTR | 10% | 6.4462 | 3545.4001 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 5500 | MTR | 25% | 6.4462 | 8863.5002 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.4.28 | 10C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8200 | MTR | 55% | 11.5402 | 52046.3967 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8200 | MTR | 10% | 11.5402 | 9462.9812 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5402 | 23657.453 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.1 | 2C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 50000 | MTR | 55% | 5.2964 | 145650.6091 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 50000 | MTR | 10% | 5.2964 | 26481.9289 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 50000 | MTR | 25% | 5.2964 | 66204.8223 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.2 | 2C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 3000 | MTR | 55% | 6.2591 | 10327.5952 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 3000 | MTR | 10% | 6.2591 | 1877.7446 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 3000 | MTR | 25% | 6.2591 | 4694.3615 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.3 | 3C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 2500 | MTR | 55% | 9.6625 | 13285.9217 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 2500 | MTR | 10% | 9.6625 | 2415.6221 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 2500 | MTR | 25% | 9.6625 | 6039.0553 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.4 | 3C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 18500 | MTR | 55% | 8.9428 | 90993.3838 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 18500 | MTR | 10% | 8.9428 | 16544.2516 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 18500 | MTR | 25% | 8.9428 | 41360.629 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.5 | 3C-16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 1500 | MTR | 55% | 8.2625 | 6816.5396 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 1500 | MTR | 10% | 8.2625 | 1239.3708 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 1500 | MTR | 25% | 8.2625 | 3098.4271 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.6 | 5C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 15000 | MTR | 55% | 10.0891 | 83235.4348 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 15000 | MTR | 10% | 10.0891 | 15133.7154 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.0891 | 37834.2885 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.7 | 5C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 7000 | MTR | 55% | 10.0891 | 38843.1802 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 7000 | MTR | 10% | 10.0891 | 7062.3964 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 7000 | MTR | 25% | 10.0891 | 17655.991 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.8 | 7C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 12000 | MTR | 55% | 10.3794 | 68504.0446 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 12000 | MTR | 10% | 10.3794 | 12455.2808 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 12000 | MTR | 25% | 10.3794 | 31138.2021 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.9 | 7C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 1000 | MTR | 55% | 8.6666 | 4766.6086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 1000 | MTR | 10% | 8.6666 | 866.6561 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.6666 | 2166.6403 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.10 | 10C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8200 | MTR | 55% | 11.5377 | 52034.8248 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8200 | MTR | 10% | 11.5377 | 9460.8772 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5377 | 23652.1931 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.11 | 10C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 250 | MTR | 55% | 10.1115 | 1390.3317 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 250 | MTR | 10% | 10.1115 | 252.7876 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 250 | MTR | 25% | 10.1115 | 631.969 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.12 | 12C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 15000 | MTR | 55% | 10.5928 | 87390.4335 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 15000 | MTR | 10% | 10.5928 | 15889.1697 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.5928 | 39722.9243 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.13 | 12C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 5000 | MTR | 55% | 11.4506 | 31489.2272 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 5000 | MTR | 10% | 11.4506 | 5725.314 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 5000 | MTR | 25% | 11.4506 | 14313.2851 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.14 | 16C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 4000 | MTR | 55% | 13.133 | 28892.6933 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 4000 | MTR | 10% | 13.133 | 5253.217 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 4000 | MTR | 25% | 13.133 | 13133.0424 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.5.15 | 19C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 2500 | MTR | 55% | 13.7014 | 18839.4206 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 2500 | MTR | 10% | 13.7014 | 3425.3492 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 2500 | MTR | 25% | 13.7014 | 8563.373 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 500 | MTR | 55% | 8.3652 | 2300.429 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 500 | MTR | 10% | 8.3652 | 418.2598 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 500 | MTR | 25% | 8.3652 | 1045.6495 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 500 | MTR | 55% | 9.3751 | 2578.155 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 500 | MTR | 10% | 9.3751 | 468.7554 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 500 | MTR | 25% | 9.3751 | 1171.8886 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 500 | MTR | 55% | 10.385 | 2855.8809 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 500 | MTR | 10% | 10.385 | 519.2511 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 500 | MTR | 25% | 10.385 | 1298.1277 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.4 | 5C - 6 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 500 | MTR | 55% | 10.817 | 2974.6633 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 500 | MTR | 10% | 10.817 | 540.8479 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 500 | MTR | 25% | 10.817 | 1352.1197 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 200 | MTR | 55% | 11.5379 | 1269.167 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 200 | MTR | 10% | 11.5379 | 230.7576 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 200 | MTR | 25% | 11.5379 | 576.8941 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 200 | MTR | 55% | 17.3084 | 1903.9206 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 200 | MTR | 10% | 17.3084 | 346.1674 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 200 | MTR | 25% | 17.3084 | 865.4185 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.7 | CONTROL/INSTRUMENT LT CABLES (SHIELDED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.7.1 | 2P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 1000 | MTR | 55% | 8.5354 | 4694.4543 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 1000 | MTR | 10% | 8.5354 | 853.5371 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.5354 | 2133.8429 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.7.2 | 4P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 5000 | MTR | 55% | 9.3892 | 25820.3495 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 5000 | MTR | 10% | 9.3892 | 4694.609 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 5000 | MTR | 25% | 9.3892 | 11736.5225 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.7.3 | 6P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 10000 | MTR | 55% | 11.0964 | 61029.9478 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 10000 | MTR | 10% | 11.0964 | 11096.3542 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.0964 | 27740.8854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.7.4 | 8P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 1000 | MTR | 55% | 11.95 | 6572.5083 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 1000 | MTR | 10% | 11.95 | 1195.0015 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.95 | 2987.5038 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.7.5 | 12P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 15000 | MTR | 55% | 12.8035 | 105628.7952 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 15000 | MTR | 10% | 12.8035 | 19205.2355 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 15000 | MTR | 25% | 12.8035 | 48013.0887 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.7.6 | 16P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 10000 | MTR | 55% | 14.5106 | 79808.4457 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 10000 | MTR | 10% | 14.5106 | 14510.6265 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.5106 | 36276.5662 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.8 | SCREENED CABLES (OVERALL & INDIVIDUAL/OVERALL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.8.1 | 2P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 6000 | MTR | 55% | 9.3892 | 30984.4874 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 6000 | MTR | 10% | 9.3892 | 5633.5432 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 6000 | MTR | 25% | 9.3892 | 14083.8579 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.8.2 | 4P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 14000 | MTR | 55% | 10.2428 | 78869.7591 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 14000 | MTR | 10% | 10.2428 | 14339.9562 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 14000 | MTR | 25% | 10.2428 | 35849.8905 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.8.3 | 8P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 10000 | MTR | 55% | 11.95 | 65724.7425 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 10000 | MTR | 10% | 11.95 | 11949.9532 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.95 | 29874.8829 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.8.4 | 12 P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 5000 | MTR | 55% | 13.6571 | 37556.9957 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 5000 | MTR | 10% | 13.6571 | 6828.5447 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 5000 | MTR | 25% | 13.6571 | 17071.3617 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.9 | SPECIALISED CABLING FOR COMMUNICATION SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.9.1 | OPTICAL FIBRE CABLE WITHOUT HDPE PIPE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 8000 | MTR | 55% | 19.8096 | 87162.0584 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 8000 | MTR | 10% | 19.8096 | 15847.647 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 8000 | MTR | 25% | 19.8096 | 39619.1174 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.9.2 | OPTICAL FIBRE CABLE WITH HDPE PIPE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 3000 | MTR | 55% | 29.0546 | 47940.0681 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 3000 | MTR | 10% | 29.0546 | 8716.376 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 3000 | MTR | 25% | 29.0546 | 21790.94 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.9.3 | EARTH CABLE FOR ESP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Laying of cable | 280 | MTR | 55% | 9.2536 | 1425.0475 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | After termination of cable | 280 | MTR | 10% | 9.2536 | 259.0995 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Dressing & Clamping | 280 | MTR | 25% | 9.2536 | 647.7489 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.0 | CABLE JOINITNG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.10 | JOINT KIT 6.6KV 1C-400 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 12 | NOS | 70% | 2902.1067 | 24377.6966 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 12 | NOS | 20% | 2902.1067 | 6965.0562 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.20 | JOINT KIT 6.6KV 3C-150 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 8 | NOS | 70% | 2902.1067 | 16251.7977 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 8 | NOS | 20% | 2902.1067 | 4643.3708 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.30 | JOINT KIT 6.6KV 3C-240 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.40 | JOINT KIT 33KV 3C-120 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.0 | CABLE TERMINATION | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.1 | 6.6 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.1.1 | TERM. KIT 6.6KV 1C-400 AL UNARM. CU LUG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 136 | NOS | 70% | 2902.1295 | 276282.7269 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 136 | NOS | 20% | 2902.1295 | 78937.922 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.1.2 | TERM. KIT 6.6KV 3C-150 AL UNARM. CU LUG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 94 | NOS | 70% | 2902.1298 | 190960.1392 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 94 | NOS | 20% | 2902.1298 | 54560.0398 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.1.3 | TERM. KIT 6.6KV 3C-240 AL UNARM. CU LUG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 46 | NOS | 70% | 2902.1269 | 93448.4866 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 46 | NOS | 20% | 2902.1269 | 26699.5676 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.2 | 33 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.2.1 | TERM. KIT 33KV 3C-120 AL UNARM. CU LUG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 6 | NOS | 70% | 2902.1583 | 12189.0649 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 6 | NOS | 20% | 2902.1583 | 3482.59 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.3.1 | 3.5C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 32 | NOS | 70% | 151.9394 | 3403.443 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.9394 | 972.4123 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.3.2 | 3.5C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.3.3 | 3C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 32 | NOS | 70% | 144.2622 | 3231.4732 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 32 | NOS | 20% | 144.2622 | 923.2781 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.1 | 1C - 35 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 32 | NOS | 70% | 151.0885 | 3384.3834 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.0885 | 966.9667 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.2 | 1C - 70 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 56 | NOS | 70% | 157.0585 | 6156.6928 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 56 | NOS | 20% | 157.0585 | 1759.0551 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.3 | 1C - 120 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 8 | NOS | 70% | 170.7167 | 956.0136 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 8 | NOS | 20% | 170.7167 | 273.1467 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.4 | 1C - 400 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 54 | NOS | 70% | 183.5142 | 6936.838 | 0 | 36 | 36 | 0 | 4624.5587 | 4624.5587 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 54 | NOS | 20% | 183.5142 | 1981.9537 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.5 | 1C - 630 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 72 | NOS | 70% | 209.9773 | 10582.8581 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 72 | NOS | 20% | 209.9773 | 3023.6737 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.6 | 2C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 24 | NOS | 70% | 98.1602 | 1649.0909 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 24 | NOS | 20% | 98.1602 | 471.1688 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.7 | 2C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 32 | NOS | 70% | 98.1602 | 2198.7879 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 32 | NOS | 20% | 98.1602 | 628.2251 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.8 | 2C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 131.4991 | 368.1973 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 131.4991 | 105.1992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.9 | 2C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 24 | NOS | 70% | 157.0511 | 2638.4589 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 24 | NOS | 20% | 157.0511 | 753.8454 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.10 | 2C - 120 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.11 | 3C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 145 | NOS | 70% | 144.2531 | 14641.6924 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 145 | NOS | 20% | 144.2531 | 4183.3407 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.12 | 3C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 56 | NOS | 70% | 144.2511 | 5654.6449 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 56 | NOS | 20% | 144.2511 | 1615.6128 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.13 | 3C - 35 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 151.1466 | 423.2104 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 151.1466 | 120.9172 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.14 | 3C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 8 | NOS | 70% | 157.0253 | 879.3419 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 8 | NOS | 20% | 157.0253 | 251.2405 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.15 | 3C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.16 | 3C - 150 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 209.9344 | 587.8162 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 209.9344 | 167.9475 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.17 | 3C - 240 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 27 | NOS | 70% | 222.7749 | 4210.445 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 27 | NOS | 20% | 222.7749 | 1202.9843 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.18 | 3.5C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 24 | NOS | 70% | 131.4475 | 2208.3177 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 24 | NOS | 20% | 131.4475 | 630.9479 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.19 | 3.5C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 48 | NOS | 70% | 144.2493 | 4846.7766 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 48 | NOS | 20% | 144.2493 | 1384.7933 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.20 | 3.5C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 40 | NOS | 70% | 163.8788 | 4588.6053 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 40 | NOS | 20% | 163.8788 | 1311.0301 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.21 | 3.5C - 185 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 222.7749 | 623.7696 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 222.7749 | 178.2199 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.22 | 4C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 60 | NOS | 70% | 144.257 | 6058.7956 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 60 | NOS | 20% | 144.257 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.23 | 2C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.24 | 2C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 274 | NOS | 70% | 117.7924 | 22592.5892 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 274 | NOS | 20% | 117.7924 | 6455.0255 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.25 | 3C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 26 | NOS | 70% | 144.2562 | 2625.4637 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 26 | NOS | 20% | 144.2562 | 750.1325 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.26 | 3C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 400 | NOS | 70% | 117.7922 | 32981.8188 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 400 | NOS | 20% | 117.7922 | 9423.3768 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.27 | 4C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 22 | NOS | 70% | 144.2411 | 2221.3129 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 22 | NOS | 20% | 144.2411 | 634.6608 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.4.28 | 10C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 32 | NOS | 70% | 158.7658 | 3556.3532 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 32 | NOS | 20% | 158.7658 | 1016.1009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.1 | 2C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 96 | NOS | 70% | 108.4029 | 7284.6762 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 96 | NOS | 20% | 108.4029 | 2081.3361 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.2 | 2C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 12 | NOS | 70% | 108.3965 | 910.5304 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 12 | NOS | 20% | 108.3965 | 260.1515 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.3 | 3C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 10 | NOS | 70% | 108.4171 | 758.9197 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 10 | NOS | 20% | 108.4171 | 216.8342 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.4 | 3C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 74 | NOS | 70% | 108.402 | 5615.2261 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 74 | NOS | 20% | 108.402 | 1604.3503 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.5 | 3C-16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 6 | NOS | 70% | 144.288 | 606.0095 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 6 | NOS | 20% | 144.288 | 173.1456 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.6 | 5C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 44 | NOS | 70% | 116.0848 | 3575.4128 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 44 | NOS | 20% | 116.0848 | 1021.5465 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.7 | 5C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 23 | NOS | 70% | 122.9028 | 1978.7359 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 23 | NOS | 20% | 122.9028 | 565.3531 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.8 | 7C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 34 | NOS | 70% | 130.589 | 3108.0188 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 34 | NOS | 20% | 130.589 | 888.0054 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.9 | 7C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.10 | 10C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.11 | 12C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 42 | NOS | 70% | 144.2585 | 4241.2003 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 42 | NOS | 20% | 144.2585 | 1211.7715 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.12 | 12C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 14 | NOS | 70% | 144.2732 | 1413.8778 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 14 | NOS | 20% | 144.2732 | 403.9651 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.13 | 16C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 16 | NOS | 70% | 144.2622 | 1615.7366 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 16 | NOS | 20% | 144.2622 | 461.639 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.5.14 | 19C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 10 | NOS | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 10 | NOS | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 122.9903 | 344.3728 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 122.9903 | 98.3922 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.4 | 5C - 6 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 158.7271 | 444.4359 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 158.7271 | 126.9817 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.7 | OPTICAL FIBRE CABLE JOINTING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Termination | 10 | NOS. | 70% | 324.385 | 2270.6947 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Testing of connected equipments/system | 10 | NOS. | 20% | 324.385 | 648.7699 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.00 | CABLE SHAFT COVERING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.10 | MS SHEET FOR COVERING CABLE SHAFTS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 1000 | SQM | 70% | 2163.79 | 1514652.9917 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Painting as applicable | 1000 | SQM | 20% | 2163.79 | 432757.9976 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  |  | SCH-5 - SWITCHGEAR & EQUIPMENT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.00 | HT SWITCHGEAR BOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.01 | 6.6KV UNIT SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Alignment & Coupling as Applicable | 2 | SET | 50% | 222104.9936 | 222104.9936 | 2 | 0 | 2 | 222104.9936 | 0 | 222104.9936 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02 | 6.6KV STATION SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Alignment & Coupling as Applicable | 1 | SET | 50% | 242296.1316 | 121148.0658 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.03 | 6.6KV CHP SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 | 0 | 1 | 111052.6515 | 0 | 111052.6515 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.04 | 6.6KV AHP SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 | 0 | 1 | 111052.6515 | 0 | 111052.6515 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.05 | 6.6KV COMPRESSOR SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.06 | 6.6KV RAW WATER SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.07 | 33KV RAW WATER PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 4 | SET | 50% | 222104.9936 | 444209.9871 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.08 | BTS panel | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 10096.0331 | 10096.0331 | 2 | 0 | 2 | 10096.0331 | 0 | 10096.0331 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 2 | 0 | 2 | 4038.4133 | 0 | 4038.4133 |  |  | 0
|  |  | (iii) | Charging | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.09 | DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.00 | LT SWITCHGEAR BOARD & DCDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.01 | UNIT PMCC #1DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 38552.8922 | WITHELD RA-02: 38552.8922
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 | 0 | 1 | 77105.7844 | 0 | 77105.7844 |  |  | 30842.3137 | WITHELD RA-02: 30842.3137
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 | 0 | 1 | 30842.3137 | 0 | 30842.3137 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.02 | TURBINE MCC #1KA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 22931.5783 | WITHELD RA-01: 22931.5783
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 114657.8914 | 57328.9457 | 1 | 0 | 1 | 57328.9457 | 0 | 57328.9457 |  |  | 22931.5783 | WITHELD RA-01: 22931.5783
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 1 | 0 | 1 | 22931.5783 | 0 | 22931.5783 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.03 | TURBINE VALVES & ACDB #1KB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 33012.8835 | WITHELD RA-01: 33012.8835
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 165064.4176 | 82532.2088 | 1 | 0 | 1 | 82532.2088 | 0 | 82532.2088 |  |  | 33012.8835 | WITHELD RA-01: 33012.8835
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 1 | 0 | 1 | 33012.8835 | 0 | 33012.8835 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.04 | BOILER VALVES & ACDB #1HB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 29551.3334 | WITHELD RA-01: 29551.3334
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 147756.667 | 73878.3335 | 1 | 0 | 1 | 73878.3335 | 0 | 73878.3335 |  |  | 29551.3334 | WITHELD RA-01: 29551.3334
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 147756.667 | 29551.3334 | 1 | 0 | 1 | 29551.3334 | 0 | 29551.3334 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 147756.667 | 29551.3334 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.05 | BOILER MCC #1HA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 26306.37 | WITHELD RA-01: 26306.37
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 131531.8498 | 65765.9249 | 1 | 0 | 1 | 65765.9249 | 0 | 65765.9249 |  |  | 26306.37 | WITHELD RA-01: 26306.37
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 131531.8498 | 26306.37 | 1 | 0 | 1 | 26306.37 | 0 | 26306.37 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 131531.8498 | 26306.37 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.06 | UNIT SERVICE ACDB #1QA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30842.3137 | WITHELD RA-01: 30842.3137
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 | 0 | 1 | 77105.7844 | 0 | 77105.7844 |  |  | 30842.3137 | WITHELD RA-01: 30842.3137
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 | 0 | 1 | 30842.3137 | 0 | 30842.3137 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.07 | SOOT BLOWER MCC (Supply by Tnchy) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 115514.337 | 57757.1685 | 1 | 0 | 1 | 57757.1685 | 0 | 57757.1685 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.08 | ESP LT SWITCHGEAR(SUPPLY BY BAP RANIPET) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 52497.392 | WITHELD RA-01: 52497.392
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 131243.4801 | 131243.4801 | 2 | 0 | 2 | 131243.4801 | 0 | 131243.4801 |  |  | 52497.392 | WITHELD RA-01: 52497.392
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 131243.4801 | 52497.392 | 2 | 0 | 2 | 52497.392 | 0 | 52497.392 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 131243.4801 | 52497.392 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.09 | UNIT EMERGENCY BOARD #1DG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36322.823 | WITHELD RA-01: 36322.823
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 181614.1148 | 90807.0574 | 1 | 0 | 1 | 90807.0574 | 0 | 90807.0574 |  |  | 36322.823 | WITHELD RA-01: 36322.823
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 181614.1148 | 36322.823 | 1 | 0 | 1 | 36322.823 | 0 | 36322.823 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 181614.1148 | 36322.823 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.10 | 220V UNIT DCDB #1FA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 23364.2875 | WITHELD RA-02: 23364.2875
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 1 | 0 | 1 | 46728.575 | 0 | 46728.575 |  |  | 18691.43 | WITHELD RA-02: 18691.43
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 1 | 0 | 1 | 18691.43 | 0 | 18691.43 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.11 | ESP A/C & VENT MCC #1TB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10513.8598 | WITHELD RA-01: 10513.8598
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 52569.2988 | 26284.6494 | 1 | 0 | 1 | 26284.6494 | 0 | 26284.6494 |  |  | 10513.8598 | WITHELD RA-01: 10513.8598
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 1 | 0 | 1 | 10513.8598 | 0 | 10513.8598 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.12 | STATION PMCC #0DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 32283.6362 | WITHELD RA-02: 32283.6362
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 | 0 | 1 | 64567.2724 | 0 | 64567.2724 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.13 | AC MCC #0TA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 78529.9964 | 39264.9982 | 1 | 0 | 1 | 39264.9982 | 0 | 39264.9982 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 | 1 | 1 | 0 | 15705.9993 | 15705.9993 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.14 | VENTILATION & AIR WASHER MCC #1TA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 116605.9338 | 58302.9669 | 1 | 0 | 1 | 58302.9669 | 0 | 58302.9669 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.15 | MISC SERVICE MCC #0SA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9583.6506 | WITHELD RA-02: 9583.6506
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 1 | 0 | 1 | 47918.2547 | 0 | 47918.2547 |  |  | 19167.3019 | WITHELD RA-02: 19167.3019
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 1 | 0 | 1 | 19167.3019 | 0 | 19167.3019 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.16 | COOLING TOWER PMCC #1DC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 191474.9966 | 95737.4983 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.17 | CWPH AND CHLORINATION MCC # 0SB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 126556.5445 | 63278.2722 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.18 | PTP PMCC #1DD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.19 | FW & CLARIFIED WATER MCC #0SC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.20 | ETP PMCC #1DE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.21 | ADMIN BUILDING MCC #0SB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.22 | O&M ACDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.23 | STP MCC #0SF | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.24 | WATER PMCC # 0DB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.25 | MODIFICATION OF DM PLANT MCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 | 0 | 1 | 64567.2724 | 0 | 64567.2724 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.26 | MODIFICATION OF FUEL OIL MCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 | 0 | 1 | 64567.2724 | 0 | 64567.2724 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 1 | 1 | 0 | 25826.9089 | 25826.9089 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.27 | 220V DC FUSE DB (WALL MOUNTED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5 | 7211.8412 | 10817.7618 | 18029.603 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.28 | 415V AC FUSE DB (WALL MOUNTED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5 | 7211.8412 | 10817.7618 | 18029.603 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.29 | LV SWITCHGEAR FOR SWITCHYARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.29.1 | SWITCHYARD PMCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.29.2 | SWITCHYARD 415V ACDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 7211.7174 | 3605.8587 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.29.3 | SWITCHYARD 220V DCDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.30 | DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.00 | LT PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.01 | FEEDER FOR ELEVATOR (3 PHASE - 30 KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.02 | FEEDER FOR ELEVATOR (1 PHASE - 6 KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.00 | PROTECTION RELAY PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.01 | GENERATOR PROTECTION & RELAY PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 5 | NOS. | 50% | 43267.3343 | 108168.3358 | 5 | 0 | 5 | 108168.3358 | 0 | 108168.3358 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.02 | STATION TRANSFORMER RELAY PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 4.03 | ELECTRICAL CONTROL DESK CUM PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 36055.4931 | 18027.7466 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.00 | DIGITAL STATIC EXCITATION SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.1 | DIGITAL AUOTOMATIC VOLTAGE REGULATOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 38337.079 | 19168.5395 | 1 | 0 | 1 | 19168.5395 | 0 | 19168.5395 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.2 | HT DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.3 | LT DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4 | VARIABLE FREQUENCY DRIVE FOR ID FAN | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.1 | VARIABLE FREQUENCY DRIVE FOR ID FANS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 | 0 | 2 | 67587.1094 | 0 | 67587.1094 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.4.2 | 6.6KV VFD SWITCH GEAR PANEL FOR ID FAN | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 26284.8041 | WITHELD RA-02: 26284.8041
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 2 | 0 | 2 | 52569.6082 | 0 | 52569.6082 |  |  | 21027.8433 | WITHELD RA-02: 21027.8433
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 2 | 0 | 2 | 21027.8433 | 0 | 21027.8433 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.1 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 | 0 | 2 | 67587.1094 | 0 | 67587.1094 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 5.5.2 | 6.6KV VFD SWITCH GEAR PANEL FOR CEP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 0 | 2 | 2 | 0 | 52569.6082 | 52569.6082 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.00 | LOCAL CONTROL PANELS FOR PUMPS ETC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.01 | LOCAL FAN CONTROL PANEL FOR ST | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.02 | LOCAL FAN CONTROL PANEL FOR GT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.03 | LOCAL FAN CONTROL PANEL FOR UAT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.04 | PANEL FOR OIL CENTRIFUGE UNIT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.05 | PANEL FOR ON LOAD TUBE CLEANING SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.06 | PANEL FOR CENTRAL OIL PURIFICATION UNIT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 7211.7174 | 3605.8587 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 6.07 | LCP for Sump Pumps of Condensor Pit, & Trf oil Pit | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 4 | No | 50% | 3852.1487 | 7704.2974 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 4 | No | 20% | 3852.1487 | 3081.719 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 4 | No | 20% | 3852.1487 | 3081.719 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.00 | MISC ITEMS OF ESP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.01 | ELECTRONIC CONTROLLER (WITH BAPCON) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50482.5034 | WITHELD RA-02: 50482.5034
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 36 | NO | 50% | 7211.7862 | 129812.1516 | 28 | 0 | 28 | 100965.0068 | 0 | 100965.0068 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.02 | RAPPER CONTROL PANEL (WITH RAPCON) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.03 | STATCON CONTROL PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.04 | IOS PERSONAL COMPUTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 5769.2502 | 2884.6251 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.05 | DATA LOGGER PC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 2884.9345 | 1442.4673 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.06 | DOT MATRIX PRINTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 1081.6957 | 540.8479 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 7.07 | COMPUTER FURNITURE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.00 | MISCELLANEOUS-1 (ONLY COMMISSIONING RATE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.01 | THERMOSTAT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 32 | NO | 50% | 721.2723 | 11540.3568 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.02 | HOPPER/ SHAFT/ SUPPORT INSULATOR HEATER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 812 | SET | 50% | 721.2641 | 292833.2286 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.03 | ELECTRICALLY OPERATED HOIST | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.04 | ASH LEVEL INDICATORS & CONTROLLERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 112 | SET | 50% | 721.2668 | 40390.9395 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.05 | RAPPING MOTORS FOR ESP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 60 | NO | 50% | 1731.0329 | 51930.9869 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.06 | TESTING OF GENERATOR / EXCITER / PMG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.07 | COMMISSIONING OF HYDROGEN GAS DRIER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 721.2336 | 721.2336 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 8.08 | COMMISSIONING OF EXCITER HEATER, STROBOSCOPE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.00 | JUNCTION BOX/ MARSHALLING BOX /PB/STARTERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.01 | FRP JUNCTION BOX- 24 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 70 | NO | 50% | 337.1592 | 11800.5703 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.02 | FRP JUNCTION BOX- 48 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO | 50% | 337.1574 | 8428.9346 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.03 | FRP JUNCTION BOX- 72 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 337.1636 | 3371.6357 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.04 | FRP JUNCTION BOX- 96 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 337.1326 | 842.8316 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 337.1326 | 337.1326 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 5 | NO | 20% | 337.1326 | 337.1326 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.05 | PUSH BUTTON/ STARTERS FOR RAPPING MOTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 100 | NO | 50% | 721.2646 | 36063.2284 | 0 | 60 | 60 | 0 | 21637.937 | 21637.937 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.06 | FRP JUNCTION BOX FOR HEATERS(JBHH,SHHH,SUHH) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 40 | NO | 50% | 337.1636 | 6743.2714 | 0 | 32 | 32 | 0 | 5394.6171 | 5394.6171 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 9.07 | FRP JUNCTION BO X(CONTROL-HH, TH, ALI) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 80 | NO | 50% | 337.1558 | 13486.2334 | 0 | 32 | 32 | 0 | 5394.4934 | 5394.4934 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.00 | PUSH BUTTON, BOX & STARTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.10 | LOCAL PUSH BUTTON STATIONS (NON FLAME PROOF) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.1.1 | TYPE A | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 150 | NO | 50% | 721.2625 | 54094.6878 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.1.2 | TYPE C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 1009.789 | 7573.4172 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.20 | PUSH BUTTON BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 46 | NO | 50% | 1154.0169 | 26542.3876 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10.30 | LOCAL MOTOR STARTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO. | 50% | 1154.0233 | 28850.5827 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.00 | DC STRATER PANEL/ STARTING CABINET | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.10 | LOCALLY MOUNTED STARTER MODULE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.1.1 | FOR MOTOR RATING upto 0.75 KW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 504.4613 | 5044.6131 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.1.4 | FOR MOTOR RATING above 0.75kW upto 1.5 kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 577.0282 | 4327.7112 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.1.5 | FOR MOTOR RATING above 1.5W upto 2.2kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 10 | NO | 50% | 648.708 | 3243.5402 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 10 | NO | 20% | 648.708 | 1297.4161 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 10 | NO | 20% | 648.708 | 1297.4161 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.1.6 | SUITABLE FOR MOTOR RATING above 2.2W upto 4.5kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 721.2955 | 1803.2388 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 721.2955 | 721.2955 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 5 | NO | 20% | 721.2955 | 721.2955 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 11.1.6 | SUITABLE FOR MOTOR RATING above 4.5W upto 6kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 721.2336 | 721.2336 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.00 | DC STARTER LOCAL PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.01 | STARTER CABINET FOR DC JACKING OIL MOTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.02 | STARTER CABINET FOR DC SEAL OIL MOTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.03 | STARTING CABINET FOR DC EMERGENCY LOP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.04 | SCANNER AIR FAN DC MOTOR STARTER BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 4327.4018 | 2163.7009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 12.05 | FURNACE TEMPERATURE PROBE LOCAL STARTER BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.00 | BATTERY SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.01 | 220V BATTERY (EACH SET 170 CELLS) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36546.3198 | WITHELD RA-02: 36546.3198
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 6 | SET | 50% | 146185.2791 | 438555.8373 | 2 | 0 | 2 | 146185.2791 | 0 | 146185.2791 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.02 | 220V FCB CHARGER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 11898.7356 | WITHELD RA-01: 11898.7356
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 29746.839 | 89240.5169 | 2 | 0 | 2 | 29746.839 | 0 | 29746.839 |  |  | 11898.7356 | WITHELD RA-01: 11898.7356
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 29746.839 | 35696.2068 | 2 | 0 | 2 | 11898.7356 | 0 | 11898.7356 |  |  | 0
|  |  | (iii) | Charging | 6 | NO | 20% | 29746.839 | 35696.2068 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.03 | 220V DC BATTERY HEALTH MONITORING SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 3852.1487 | 11556.4461 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.04 | DISCHARGE RESISTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1154.0151 | WITHELD RA-01: 1154.0151
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 | 0 | 2 | 2885.0376 | 0 | 2885.0376 |  |  | 1154.0151 | WITHELD RA-01: 1154.0151
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 2 | 0 | 2 | 1154.0151 | 0 | 1154.0151 |  |  | 0
|  |  | (iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 13.05 | 220 V DC ISOLATION BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 | 0 | 2 | 2885.0376 | 0 | 2885.0376 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.00 | DG SET | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.01 | DG Set 750kVA,415V, 0.8pf with acoustic enclosure | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 144223.8289 | 144223.8289 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.02 | 990 litres fuel tank on stand including Fuel Piping | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 14422.8161 | 14422.8161 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.03 | Battery with stand (24V DC 360AH) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 28845.4774 | 57690.9548 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.04 | Battery Charger | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 8654.3394 | 17308.6788 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.05 | Exhaust Piping and Support Structure | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 695661.8562 | 695661.8562 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.06 | DG AMF Panel | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 7211.7174 | 7211.7174 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | set | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.07 | DG Aux DB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 5048.9448 | 5048.9448 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.08 | Alternator extension terminal box | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 16088.0582 | 16088.0582 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 14.09 | Miscellaneous cables for DG Set | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Placement,Aliggnment & Coupling as Applicable | 2 | lot | 50% | 16100.1252 | 16100.1252 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Pre-Commissioning Checks ,Testing | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (iii) | Charging | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 15.00 | MISCELLANEOUS FOR MOTORS & ACTUATORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 15.01 | DRYING OUT, TESTING OF OF HT MOTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 42 | NO | 50% | 4327.5786 | 90879.1498 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 42 | NO | 40% | 4327.5786 | 72703.3198 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 15.02 | DRYING OUT, TESTING OF OF LT MOTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 200 | NO | 50% | 2163.7937 | 216379.3701 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 200 | NO | 40% | 2163.7937 | 173103.4961 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 15.03 | MOUNTING OF CTs FOR HT MOTORS/ PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 15.04 | MOUNTING OF MODULES INSIDE LT PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 15.05 | CABLE TRAY RE-ROUTING & RELAYING OF CABLES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 1000 | MTR | 50% | 108.4029 | 54201.4341 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 1000 | MTR | 40% | 108.4029 | 43361.1473 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 16.00 | ACTUATORS COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 300 | NO | 50% | 1442.5291 | 216379.3701 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 300 | NO | 40% | 1442.5291 | 173103.4961 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 17.00 | SOOT BLOWERS COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 80 | NO | 50% | 1081.4714 | 43258.8565 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 80 | NO | 40% | 1081.4714 | 34607.0852 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 18.00 | ELECTRICALLY OPTD MISC HOISTS COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 2163.7628 | 10818.8138 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Commissioning of individual items | 10 | NO | 40% | 2163.7628 | 8655.051 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 19.00 | FABRICATION (SUPPLY OF MATL BY BHEL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 19.01 | BASE FRAMES FOR SWITCHGEAR, PANEL, PB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 20.00 | CHEQUERED PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 20.01 | INSTALLATION OF CHEQUERED PLATES 6 TO 8 MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 40 | MT | 70% | 25960.3882 | 726890.87 | 4.65 | 0 | 4.65 | 84501.0636 | 0 | 84501.0636 |  |  | 0
|  |  | (ii) | Painting as applicable | 40 | MT | 20% | 25960.3882 | 207683.1057 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 21.00 | INSERT PLATES/ ANCHOR FASTENERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 21.01 | FABRICATION OF INSERT PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 21.02 | INSTALLATION OF FRICTION ANCHOR FASTENERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 3000 | SET | 70% | 296.1878 | 621994.4782 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Painting as applicable | 3000 | SET | 20% | 296.1878 | 177712.7081 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 22.00 | CANOPIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 22.01 | FABRICATION AND INSTALLATION OF CANOPIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 50 | SQM | 70% | 1211.2146 | 42392.5098 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Painting as applicable | 50 | SQM | 20% | 1211.2146 | 12112.1457 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.00 | IRREGULAR BENDS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.1 | FABRICATION OF IRREGULAR BENDS (LADER-TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.1.1 | 600 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 1000 | NO | 70% | 541.1616 | 378813.1259 | 300 | 0 | 300 | 113643.9378 | 0 | 113643.9378 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 1000 | NO | 20% | 541.1616 | 108232.3217 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.1.2 | 450 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 500 | NO | 70% | 541.161 | 189406.3464 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 500 | NO | 20% | 541.161 | 54116.099 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.1.3 | 300 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 300 | 0 | 300 | 105936.0079 | 0 | 105936.0079 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.1.4 | 150 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 200 | 0 | 200 | 70624.0053 | 0 | 70624.0053 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.1.5 | 100 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 504.4613 | 17656.1457 | 20 | 0 | 20 | 7062.4583 | 0 | 7062.4583 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 50 | NO | 20% | 504.4613 | 5044.6131 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.1.6 | 50 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 252.2307 | 8828.0729 | 20 | 0 | 20 | 3531.2291 | 0 | 3531.2291 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 50 | NO | 20% | 252.2307 | 2522.3065 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.2 | FABRICATION OF IRREGULAR BENDS (PERFORATED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.2.1 | 600 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 577.0117 | 40390.8158 | 100 | 0 | 100 | 40390.8158 | 0 | 40390.8158 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 100 | NO | 20% | 577.0117 | 11540.2331 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.2.2 | 450 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 577.0134 | 28273.6577 | 70 | 0 | 70 | 28273.6577 | 0 | 28273.6577 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 70 | NO | 20% | 577.0134 | 8078.1879 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.2.3 | 300 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 541.1573 | 26516.7066 | 70 | 0 | 70 | 26516.7066 | 0 | 26516.7066 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 70 | NO | 20% | 541.1573 | 7576.2019 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.2.4 | 150 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 541.1573 | 18940.5047 | 30 | 0 | 30 | 11364.3028 | 0 | 11364.3028 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 50 | NO | 20% | 541.1573 | 5411.5728 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.2.5 | 100 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 541.1573 | 11364.3028 | 15 | 0 | 15 | 5682.1514 | 0 | 5682.1514 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 30 | NO | 20% | 541.1573 | 3246.9437 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 23.2.6 | 50 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 270.589 | 5682.368 | 15 | 0 | 15 | 2841.184 | 0 | 2841.184 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 30 | NO | 20% | 270.589 | 1623.5337 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 24.00 | RUBBER MAT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 24.01 | INSULATING MAT FOR SWITCHGEAR ROOM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of supply | 1 | SET | 80% | 64294.6826 | 51435.746 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/ installation of material/ item | 1 | SET | 10% | 64294.6826 | 6429.4683 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 25.00 | DISPLAY BOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 25.01 | ELECTRIC SHOCK TREATMENT DISPLAY BOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of supply | 50 | NO | 80% | 721.2584 | 28850.3352 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/ installation of material/ item | 50 | NO | 10% | 721.2584 | 3606.2919 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 26.00 | Electrical Lab equipment | 1 | LOT | 90% | 213391.7116 | 192052.5405 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 27.00 | COMMISSIONING SERVICES FOR TESTING | 300 | MDY | 90% | 7190.4507 | 1941421.6871 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  |  | SCH-6 - MISC ITEMS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.00 | MISC WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.01 | ERECTION OF SUPPORT MATERIAL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 110001.7778 | WITHELD RA-01: 110001.7778
|  |  | (i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 19.1992 | 0 | 19.1992 | 348893.0798 | 0 | 348893.0798 |  |  | 0
|  |  | (ii) | painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.02 | ERECTION OF CHEQUERED PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 10 | MT | 70% | 25960.3882 | 181722.7175 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | painting as applicable | 10 | MT | 20% | 25960.3882 | 51920.7764 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.03 | ERECTION OF INSERT PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.04 | ERECTION OF CANOPY FROM 2 MM THICK GI SHEET | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection | 10 | SQM | 70% | 1211.2146 | 8478.502 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | painting as applicable | 10 | SQM | 20% | 1211.2146 | 2422.4291 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.05 | FABRICATION OF IRREGULAR BEND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.1 | FOR LADDER TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.1.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 250 | NO | 70% | 541.1622 | 94703.3898 | 200 | 0 | 200 | 75762.7118 | 0 | 75762.7118 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 250 | NO | 20% | 541.1622 | 27058.1114 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.1.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 541.1614 | 56821.9472 | 100 | 0 | 100 | 37881.2982 | 0 | 37881.2982 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 150 | NO | 20% | 541.1614 | 16234.8421 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.1.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 | 0 | 100 | 35312.0026 | 0 | 35312.0026 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.1.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 | 0 | 100 | 35312.0026 | 0 | 35312.0026 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.2 | FOR PERFORRATED TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.2.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 577.0117 | 30293.1118 | 50 | 0 | 50 | 20195.4079 | 0 | 20195.4079 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 75 | NO | 20% | 577.0117 | 8655.1748 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.2.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 125 | NO | 70% | 577.0117 | 50488.5197 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 125 | NO | 20% | 577.0117 | 14425.2913 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.2.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.5.2.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.06 | SUPPLY, INSTALLATION OF DANGER PLATE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 25 | NO | 80% | 157.8979 | 3157.9575 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 25 | NO | 10% | 157.8979 | 394.7447 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.07 | SUPPLY, INSTALLATION OF FASTENER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 25 | KG | 80% | 352.4298 | 7048.5967 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 25 | KG | 10% | 352.4298 | 881.0746 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.08 | SUPPLY OF HEAVY DUTY ANCHOR FASTENERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | SET | 80% | 296.1916 | 11847.6624 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | SET | 10% | 296.1916 | 1480.9578 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.09 | INSTALLATION OF MS, CABLE GLAND ADAPTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 100 | KG | 80% | 132.1736 | 10573.8852 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 100 | KG | 10% | 132.1736 | 1321.7357 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.10 | APPLICATION OF MOISTURE SEALING COMPOUND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 15 | SQM | 80% | 705.33 | 8463.9597 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 15 | SQM | 10% | 705.33 | 1057.995 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.11 | MINOR CIVIL WORK | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.11.1 | CHIPPING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Prorata on completion of actual work | 1 | CUM | 90% | 462.8767 | 416.589 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.11.2 | BREAKING OF CONCRETE/WALL/ FLOOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Prorata on completion of actual work | 1 | CUM | 90% | 792.7072 | 713.4365 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 1.11.3 | EARTH EXCAVATION & BACK FILLING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | Prorata on completion of actual work | 5 | CUM | 90% | 594.6851 | 2676.0831 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.0 | SUPLY OF MISC ITEMS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1 | SUPPLY OF CABLE GLAND & LUG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1 | DOUBLE COMPRESSION HEAVY DUTY CABLE GLAND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  |  | ABOVE (MM) UP TO (MM) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.1 | -- 9 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.2 | 09 11 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.3 | 11 13 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.4 | 13 17 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 187.5888 | 7503.5525 | 0 | 50 | 50 | 0 | 7503.5525 | 7503.5525 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 187.5888 | 937.9441 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.5 | 17 20 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 243.1093 | 9724.3704 | 0 | 50 | 50 | 0 | 9724.3704 | 9724.3704 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 243.1093 | 1215.5463 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.6 | 20 23 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 316.2908 | 12651.6321 | 0 | 50 | 50 | 0 | 12651.6321 | 12651.6321 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 316.2908 | 1581.454 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.7 | 23 26 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 373.4821 | 14939.2825 | 0 | 50 | 50 | 0 | 14939.2825 | 14939.2825 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 373.4821 | 1867.4103 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.8 | 26 30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 391.9971 | 15679.8851 | 0 | 50 | 50 | 0 | 15679.8851 | 15679.8851 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 391.9971 | 1959.9856 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.9 | 30 33 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 549.3009 | 21972.0374 | 0 | 50 | 50 | 0 | 21972.0374 | 21972.0374 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 549.3009 | 2746.5047 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.10 | 33 36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 635.1064 | 25404.2555 | 0 | 50 | 50 | 0 | 25404.2555 | 25404.2555 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 635.1064 | 3175.5319 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.11 | 36 39 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 796.6058 | 31864.2316 | 0 | 50 | 50 | 0 | 31864.2316 | 31864.2316 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 796.6058 | 3983.0289 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.12 | 39 42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50 | 0 | 37651.9226 | 37651.9226 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.13 | 42 46 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50 | 0 | 37651.9226 | 37651.9226 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.14 | 46 50 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 1032.1407 | 41285.6281 | 0 | 50 | 50 | 0 | 41285.6281 | 41285.6281 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 1032.1407 | 5160.7035 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.15 | 54 58 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 1179.3578 | 47174.3104 | 0 | 50 | 50 | 0 | 47174.3104 | 47174.3104 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 1179.3578 | 5896.7888 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.1.16 | 58 62 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | Nos | 80% | 1768.1889 | 70727.5543 | 0 | 50 | 50 | 0 | 70727.5543 | 70727.5543 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | Nos | 10% | 1768.1889 | 8840.9443 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2 | AL/CU LUG (HEAVY DUTY TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.1 | 4 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 7.5743 | 302.9738 | 0 | 50 | 50 | 0 | 302.9738 | 302.9738 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 7.5743 | 37.8717 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.2 | 6 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 9.2575 | 370.3013 | 0 | 50 | 50 | 0 | 370.3013 | 370.3013 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 9.2575 | 46.2877 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.3 | 10 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 10.0991 | 403.9651 | 0 | 50 | 50 | 0 | 403.9651 | 403.9651 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 10.0991 | 50.4956 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.4 | 16 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 13.4655 | 538.6201 | 0 | 50 | 50 | 0 | 538.6201 | 538.6201 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 13.4655 | 67.3275 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.5 | 25 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 20.1859 | 807.4351 | 0 | 50 | 50 | 0 | 807.4351 | 807.4351 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 20.1859 | 100.9294 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.6 | 35 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 26.9186 | 1076.7452 | 0 | 50 | 50 | 0 | 1076.7452 | 1076.7452 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 26.9186 | 134.5931 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.7 | 50 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 43.7505 | 1750.0203 | 0 | 50 | 50 | 0 | 1750.0203 | 1750.0203 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 43.7505 | 218.7525 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.8 | 70 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 64.7656 | 2590.6242 | 0 | 50 | 50 | 0 | 2590.6242 | 2590.6242 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 64.7656 | 323.828 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.9 | 95 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 94.2214 | 3768.8557 | 0 | 50 | 50 | 0 | 3768.8557 | 3768.8557 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 94.2214 | 471.107 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.10 | 120 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 125.3356 | 5013.4246 | 0 | 50 | 50 | 0 | 5013.4246 | 5013.4246 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 125.3356 | 626.6781 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.11 | 150 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 163.195 | 6527.7986 | 0 | 50 | 50 | 0 | 6527.7986 | 6527.7986 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 163.195 | 815.9748 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.12 | 185 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 213.6658 | 8546.6339 | 0 | 50 | 50 | 0 | 8546.6339 | 8546.6339 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 213.6658 | 1068.3292 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.13 | 240 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 328.0731 | 13122.9247 | 0 | 50 | 50 | 0 | 13122.9247 | 13122.9247 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 328.0731 | 1640.3656 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.14 | 300 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 503.038 | 20121.5209 | 0 | 50 | 50 | 0 | 20121.5209 | 20121.5209 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 503.038 | 2515.1901 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.1.2.15 | 400 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | NO | 80% | 778.1031 | 31124.1239 | 0 | 50 | 50 | 0 | 31124.1239 | 31124.1239 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | NO | 10% | 778.1031 | 3890.5155 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.2 | MS HEXAGONAL HEAD CABLE GLAND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | KG | 80% | 399.5838 | 15983.354 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | KG | 10% | 399.5838 | 1997.9192 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.3 | GALVANISED MS CONDUIT/ PIPE WITH ACCESORIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.3.1 | RIGID CONDUIT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.3.2 | 20-30 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 250 | MTR | 80% | 35.8395 | 7167.9051 | 250 | 0 | 250 | 7167.9051 | 0 | 7167.9051 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 250 | MTR | 10% | 35.8395 | 895.9881 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.3.3 | 50 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 500 | MTR | 80% | 99.0309 | 39612.3414 | 500 | 0 | 500 | 39612.3414 | 0 | 39612.3414 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 500 | MTR | 10% | 99.0309 | 4951.5427 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.3.4 | 75 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 250 | MTR | 80% | 205.6063 | 41121.2698 | 250 | 0 | 250 | 41121.2698 | 0 | 41121.2698 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 250 | MTR | 10% | 205.6063 | 5140.1587 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.3.5 | 100-125 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 250 | MTR | 80% | 456.0177 | 91203.5348 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 250 | MTR | 10% | 456.0177 | 11400.4418 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.4 | FLEXIBLE CONDUIT (COLD ROLLED ANNEALED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.4.1 | 20-25 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 250 | MTR | 80% | 61.3076 | 12261.5286 | 250 | 0 | 250 | 12261.5286 | 0 | 12261.5286 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 250 | MTR | 10% | 61.3076 | 1532.6911 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.4.2 | 40-50 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 100 | MTR | 80% | 190.5158 | 15241.2662 | 100 | 0 | 100 | 15241.2662 | 0 | 15241.2662 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 100 | MTR | 10% | 190.5158 | 1905.1583 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.4.3 | 75-100 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | MTR | 80% | 266.4511 | 10658.0446 | 50 | 0 | 50 | 10658.0446 | 0 | 10658.0446 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | MTR | 10% | 266.4511 | 1332.2556 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5 | MISCELLANEOUS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5.1 | MOISTURE SEALING COMPOUNDS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 50 | SQM | 80% | 1993.5009 | 79740.0352 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 50 | SQM | 10% | 1993.5009 | 9967.5044 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5.2 | DOL LOCAL STARTER PANEL (3phase,415V,3.7KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 4 | NO | 80% | 1621.7701 | 5189.6642 | 0 | 4 | 4 | 0 | 5189.6642 | 5189.6642 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 4 | NO | 10% | 1621.7701 | 648.708 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5.3 | DOL LOCAL STARTER PANEL (3phase,415V,5.5KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 2 | NO | 80% | 1579.2263 | 2526.762 | 0 | 2 | 2 | 0 | 2526.762 | 2526.762 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 2 | NO | 10% | 1579.2263 | 315.8453 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5.4 | JOINT KIT 6.6KV 1CX400AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 2 | NO | 80% | 3926.407 | 6282.2512 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 2 | NO | 10% | 3926.407 | 785.2814 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5.5 | JOINT KIT 6.6KV 3CX150AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 2 | NO | 80% | 12803.3666 | 20485.3865 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 2 | NO | 10% | 12803.3666 | 2560.6733 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5.6 | JOINT KIT 6.6KV 3CX240AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 2 | NO | 80% | 14510.6884 | 23217.1014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 2 | NO | 10% | 14510.6884 | 2902.1377 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 2.5.7 | JOINT KIT 33KV 3CX120AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (i) | On completion of Supply | 2 | NO | 80% | 16217.7008 | 25948.3212 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | (ii) | On laying/installation of material/item | 2 | NO | 10% | 16217.7008 | 3243.5402 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.00 | COMMISSIONING SUPPORT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.1 | SPECIALISED SKILLED TECHNICAL MANPOWER | 30 | MD | 90% | 7298.0014 | 197046.0391 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 3.2 | SUPPORT SERVICE BY UN-SKILLED MANPOWER | 60 | MD | 90% | 973.062 | 52545.3505 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
[19 empty] | 651217 | 673639
|  |  | 90% OF GROSS VALUE | [5 empty] | 44923474.9694 |  |  |  | 5984367.2628 | 782079.6003 | 6766446.8631 |  |  | 1324855
|  |  | 100% OF GROSS VALUE | [5 empty] | 44923474.9694 |  |  |  | 6649297 | 868977 | 7518274

## MemorandumOP
WAM-6 Sheet 2 of 5
II. MEMORANDUM OF PAYMENTS
1. Total value of work actually measured as per account No. 1, Column 16 | [10 empty] | 7518274
2. Total upto date 'On Account' payment for work covered by approx. or plan measurements as per Account No. 1 Column 3 | [10 empty] | 0
3. Total up-to-date Secured Advance on security of materials as per Column 8 of the enclosed Account (Form WAM-10) | [10 empty] | 0
4. Total upto date payment (1 + 2 + 3) | [10 empty] | 7518274
5. Total amount of payment already made as per entry of last Running Account | [10 empty] | 6649297
forwarded to accounts on |  |  | RKL/ELEP-1/RA/07 | [5 empty] | Dated | 31.08.2019
6. Balance (4 - 5) | [10 empty] | 868977
Total Gross Billing Value (6+7) | [10 empty] | 868977
8. Payment now to be made :
a) By Cash / Cheque | [8 empty] | 816837
b) By deduction for the value of materials supplied by BHEL vide Annexure - A | [8 empty] | 0
c) By deduction for hire charges for tools & plant vide Annexure - B | [8 empty] | 0
d) By deduction for other charges vide Annexure - C | [8 empty] | 0
e) By deduction on account of Retention @ 5% as per BBU/Annexure-4 of WO against Trial Run | [8 empty] | -43449
f) By deduction on account of Retention @ 5% as per BBU/Annexure-4 of WO against PG Test | [8 empty] | -43449
g) By deduction on account of Witheld for Pending issues | [8 empty] | 0
h) By deduction on account of Income Tax @ 2% | [8 empty] | -17380
i) By deduction on account of GST-TDS @ 2% | [8 empty] | -17380
j) By deduction on account of Recovery of SD As per Clause 4.2.2 @ 10% | [8 empty] | -86898
k) By Addition of CGST @9% on gross value | [8 empty] | 78208
l) By Addition of SGST @9% on gross value | [8 empty] | 78208
Note : | Amounts relating to item 4 to 6 above should be entered in column II and those relating to item 7 in column I. The amount shown against item 6 and the total of item 7 should agree with each other.
III. CERTIFICATE OF ENGINEER IN CHARGE
1. The measurement on which the entries in column 7 to 12 of Part-I to this bill (Account of work executed) are based were made by
Partha P Samanta (Mgr) and are recorded at pages of Measurement Book No
2. Certified that the method of measurement are correct and the work has been carried out in accordance with the terms and conditions, schedule specification and drawings etc. forming part of the contract agreement, subject to deviation included in deviation statement (Annexure D)
3. Certified that in addition to and quite a part from the quantities of work actually executed as shown in column 10 of part I some work has actually been done in connection with several items and the value of such work is, in no case, less than the On Account payment as per column 3 of part I made or proposed to be made, for the convenience of the contractor in anticipation of, and subject to the result of detailed measurement which will be made as soon as possible.
Signature of the Contractor | [5 empty] | Signature of Engineer in charge
| Date : |  |  |  |  | Designation :
Date :
IV. CERTIFICATE OF THE SENIOR ENGINEER
1.Certified that the measurements have been check measured to the prescribed extent by Partha P Samantaat at site & also by the undersigned and the relevant entries have been initialed in the M. B. vide pages of Measurement Book No.
2. Certified that all the measurements recorded in the measurement book have been correctly billed for.
3. Certified that all recoverable amounts in respect of materials tools and plant etc. Other charges have been correctly made vide Annexure A
and C attached Certified for payment Rs. |  |  |  | 816837
to be paid in case/by cheque in presence of ................................................ . The expenditure is chargeable as made under and to be in the accounts for...........................................
Ledger Head |  |  | Debit (Gross Amount) |  |  |  |  | Credit (Deduction)
|  |  | Rs. |  | P. |  |  | Rs. |  | P.
|  | Total |  |  |  |  | Total
Signature of Sr. Engineer
Date :

## Anx-A
V. ENTRIES TO BE MADE IN ACCOUNTS OFFICE | [10 empty] | WAM - 6 Sheet 3 of 5
Account Bill No. : | [7 empty] | ALLOCATION
Entered in Journal Book vide entry No. : |  |  |  |  | Dated : ...................... |  | Estimate No. :
Passed for ........................ |  |  | Rs. ............................... |  |  |  | Name of the Work :
Less Deduction................... |  |  | Rs. ............................... | [7 empty] | Code No.
Net Amount Payable .......... |  |  | Rs. .............................. |  |  |  | Ledger Head |  | Debit |  | Credit
(Rupees ........................................................................................................ only) | [8 empty] | (Gross Amount) |  | (Deduction)
Payable to Sri / M/s. .................................................................................................................... | [8 empty] | Rs. | P. | Rs. | P.
Entered in Contractor's Ledger No. ..................... Page :
Total
Assistant : | [5 empty] | Accountant : |  |  |  | Accounts Officer :
Date : | [5 empty] | Date : |  |  |  | Date :
VI. Received Rs. |  | as per memorandum of payment on accounts of this work
Signature of witness : | [8 empty] | Revenue Stamp :
Date : | [8 empty] | Signature of the Contractor :
Date :
VII. ENTRIES TO BE MADE BY TREASURY SECTION
Cash Book Entry No. & Date : | [6 empty] | Amount Paid |  | Rs. ....................................................
[7 empty] | Amount Unpaid |  | Rs. ....................................................
[7 empty] | Total |  | Rs. ....................................................
ANNEXURE - A
Statement Showing Details of Materials issued to the Contractor : M/S POWERTRONIX ENGG PVT LTD
in respect of Contract Agreement No. : REF.NO. PSER: SCT: RKL-E 1903:19(CPES-ER/02500): WO(PKG-A):AMEND-01:7468 DATED: 02.08.2019
Sl. No. | Store issue Voucher No. and date | Store issue Voucher No. and date allotted by store to SIV | Description of Materials issued to the contractor | Qty. issued in MT | Qty. used in MT | Qty. actually incorporated in the work | Whether recoverable from the contractor or supplied free | If recoverable from the Contractor |  |  |  | Remarks
[8 empty] | Rate at which recoverable | Amount recoverable | Amount recovered upto previous Bill | Balance now recovered
1 | NIL
2
3
Total | [8 empty] | 0 | 0 | 0
Signature of the Contractor : |  |  |  |  | Signature of Engineer in Charge : |  |  |  |  | Signature of Sr. Engr.
Date : |  |  |  |  | Date : |  |  |  |  | Date :

## Anx-B,C
ANNEXURE - B
WAM - 6 Page 4 of 5
Statement showing other charges to the Contractor : M/S POWERTRONIX ENGG PVT LTD
in respect of Contract Agreement No. : REF.NO. PSER: SCT: RKL-E 1903:19(CPES-ER/02500): WO(PKG-A):AMEND-01:7468 DATED: 02.08.2019 | [8 empty] | Date : | 31/08/19
Sl. No. | Description of Tools & Plant issued |  | Period for which issued | Rate which Recovery is to be made | Amount recoverable | Amount recovered upto previous Bill | Balance Now to be recovered | Remarks log book page no.
1 |  |  |  | NIL |  | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 0
4 | [5 empty] | 0 | 0
Total |  |  |  | 0 |  | 0 | 0
Signature of the Contractor : |  | Signature of Engineer in Charge : |  |  |  | Signature of Sr. Engr. :
Date : |  | Date : |  |  |  | Date :
ANNEXURE - C
Statement showing other charges to the Contractor M/S POWERTRONIX ENGG PVT LTD
in respect of Contract Agreement No. REF.NO. PSER: SCT: RKL-E 1903:19(CPES-ER/02500): WO(PKG-A):AMEND-01:7468 DATED: 02.08.2019
Sl. No. | Description | Unit | Quantity | Rate which Recovery is to be made | Amount recoverable | Amount recovered upto previous Bill | Balance Now to be recovered | Remarks
1
2 | NIL
3
| Total |  |  |  | 0 | 0 | 0
Signature of the Contractor : |  | Signature of Engineer in Charge : |  |  |  | Signature of Sr. Engr. :
Date : |  | Date : |  |  |  | Date :

## Anx-D
[8 empty] | ANNEXURE - D | [6 empty] | WAM - 6 Page 5 of 5
Nane of the Contractor: M/S POWERTRONIX ENGG PVT LTD | [14 empty] | Date: 31/08/19
Contract Agreement No.REF.NO. PSER: SCT: RKL-E 1903:19(CPES-ER/02500): WO(PKG-A):AMEND-01:7468 DATE-02.08.2019
Name of the Work |  | PKG-A MAIN ELECTRICAL WORKS - Erection, testing, commissioning, handing over, etc. of generator transformer, station transformer, unit auxiliary transformer, other misc transformer, HT/LT bus duct, DG set, Station illumination, Raw Water Intake System (Electrical Works), associated equipment/ items/ panel, cable tray & accessories, cabling,etc along with supply of minor electrical accessories of 1x250MW PP-II Expansion project, NSPCL, Rourkela, Odisha.
Sl. | Description of Item | Unit | Quantity |  |  |  | Rate |  | Amount |  |  |  | Difference |  | Reasons for deviation with authority if any
|  |  | as per agreement | as executed | further anticipated | on completion | as per agreement | as executed | as per agreement | as executed | further anticipated | on completion | Excess | Savings
N I L
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Signature of Engineer in Charge : | [12 empty] | Signature of Sr.Engr. :
Date : | [12 empty] | Date :

## GST-Invoice
Powertronix Engineering Private Limited
Registered Office: 207 Mahatma Gandhi Road, Kolkata -700 082
Email: ptronix1@rediffmail.com Website: www.powertronix.co.in
CIN:U93000WB2011PTC160665
An ISO 9001:2015 Company
INVOICE
GSTIN: | 21AAGCP0628N1ZG | [6 empty] | Details of Bill Receiver: BHARAT HEAVY ELECTRICALS LIMITED (PSER DIVISION)
Name: | POWERTRONIX ENGINEERING PVT LTD. | [6 empty] | Name: BHARAT HEAVY ELECTRICALS LIMITED
Address: | PARADEEP GARH,PARADEEP LAKH, ODISHA. PIN: 754142 | [6 empty] | Address: 1X250MW PP-II Expansion Project, NSPCL, Rourkela, Odisha.
State Code : 21 | [7 empty] | State: ODISHA
Place of Billing : NSPCL-ROURKELA ODISHA. PIN: -769011 | [7 empty] | State Code: 21
State : ODISHA | [7 empty] | GSTIN : 21AAACB4146P1ZR
State Code : 21 | [7 empty] | Place of Service: BHARAT HEAVY ELECTRICALS LIMITED
GSTIN: 21AAGCP0628N1ZG | [7 empty] | Address: 1X250MW PP-II Expansion Project, NSPCL, Rourkela, Odisha.
Serial No. of Invoice: RKL/RA-07/07 | [7 empty] | State: ODISHA
Date of Invoice: 31.08.2019 | [7 empty] | State Code:21
Work Order No:PSER: SCT: RKL-E 1903:19(CPES-ER/02500): WO(PKG-A):AMEND-01:7468 | [7 empty] | GSTIN : 21AAACB4146P1ZR
Work Order Date: 02.08.2019
Sr. No. | Description of Items | HSN/SAC | Qty. | Unit | Rate (per item) | Total | Discount | Taxable Value | CGST |  | SGST |  | IGST
[9 empty] | Rate | Amount | Rate | Amount | Rate | Amount
01 | Erection, Commissioning, Service | 995426 | 1 | Lot | 1000000 | #REF! | 0 | #REF! | 9% | #REF! | 9% | #REF! | 0% | #REF!
[6 empty] | #REF! | 0 | #REF! |  | #REF! |  | #REF! |  | #REF!
| Total Invoice Value (In figure) | #REF!
| Total Invoice Value (In words): | Ten Lakhs Twenty Five Thousand Tree Hundred Ninty Three Only
[9 empty] | CGST |  | SGST |  | IGST
[9 empty] | #REF! |  | #REF! |  | #REF!
For Powertronix Engineering Pvt Ltd
Authorised Signatory

## SHORT MB
MAIN ELECTRICALS WORKS (PKG-A) | [6 empty] | Name of the Work: |  |  | ERECTION,TESTING,COMMMISSIONING,HANDING OVER,ETC. OF GENERATOR TRANSFORMER, STATION TRANSFORMER, UNIT AUXILIARY TRANSFORMER, OTHER MOSC TRANSFORMER, HT/LT BUS DUCT, DG SET, RAW WATER INTAKE SYSTEM(ELECTRICAL WORKS), ASSOCLATED EQULPMENT/ITEMS/PANEL, CABLE TRAY & ACCESSORIES, CABLING, ETC ALONG WITH SUPPLY OF MINOR ACCESSORIES AT 1X250MWPP-II EXPANSION PROJECT,NSPCL, ROURKELA, ODISHA.
1 X 250 MW NSPCL ROURKELA TPP-II SITE
ABSTRACT BILLING (RA-07) | [6 empty] | Aggrement No. & Date: |  |  | PSER: SCT: RKL-E 1903:19(CPES-ER/02500): WO(PKG-A):AMEND-01:7468 DATED: 02.08.2019
BILL PERIOD: 01.08.2019 - 31.08.2019 | [6 empty] | Name of Contractor: |  |  | M/S POWERTRONIX ENGINEERING PVT LTD, 207 MAHATMA GANDHI ROAD, KOLKATA - 700 082
SL NO | EQUIPMENT/ITEM DESCRIPTION | BBU QTY |  | % BREAKUP OF UNIT RATE | UNIT RATE (Rs) | ALLOTED AMOUNT (Rs) | MEASUREMENT QUANTITY |  |  | CLAIMED AMOUNT |  |  | WITHELD AMOUNT ON PRESENT BILL |  | CUM WITHELD AMOUNT UPTO DATE
|  | QTY | UOM |  |  |  | UP TO PREV | PRESENT BILL | CUM | UP TO PREV | PRESENT BILL | CUMULATIVE | AMOUNT | REMARK
1 | 2 | 3 | 4 | 5 | 6 | 7 = 3x5x6 | 8 | 9 | 10 | 11 | 12 | 14 | 15 | 16 | 17
SCH-3 TRANSFORMER & BUS DUCT
1.00 | BUS DUCTS & ASOCIATED EQUIPMENT | [5 empty] | 17: 0
1.01 | SEGREGATED PHASE BUSDUCT (6.6 KV/ 4000 A) | [5 empty] | 17: 0
(i) | Pre-assembly, alingnment, erection, welding etc | 300 | MTR | 65% | 5336.5018 | 1040617.8438 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks & tests | 300 | MTR | 15% | 5336.5018 | 240142.5793 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 300 | MTR | 10% | 5336.5018 | 160095.0529 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02 | COMMON CHAMBER FOR GENERATOR PH AND N-SIDE | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, welding etc | 1 | SET | 65% | 36055.4931 | 23436.0705 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks & tests | 1 | SET | 15% | 36055.4931 | 5408.324 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 10% | 36055.4931 | 3605.5493 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.03 | MAIN RUN ISOLATED PHASE BUSDUCT (21 KV, 12500A) | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, welding etc | 125 | MTR | 65% | 6850.7281 | 556621.6581 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks & tests | 125 | MTR | 15% | 6850.7281 | 128451.1519 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 125 | MTR | 10% | 6850.7281 | 85634.1012 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.04 | TAP OFF IP BUS DUCT (21 KV, 1500 AMP) | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, welding etc | 100 | MTR | 65% | 5408.2002 | 351533.0132 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks & tests | 100 | MTR | 15% | 5408.2002 | 81123.003 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 100 | MTR | 10% | 5408.2002 | 54082.002 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.05 | SPVT CUBICLE FOR IP BUSDUCT | [5 empty] | 14: 0; 17: 0
(i) | Placenment ,Alingnment & Coupling | 1 | SET | 70% | 57690.0266 | 40383.0186 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.06 | NG CUBICLE (WITH NGT & NGR ) FOR IP BUSDUCT | [5 empty] | 14: 0; 17: 0
(i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.07 | HOT AIR BLOWING EQUIPMENT WITH PIPINGS | [5 empty] | 14: 0; 17: 0
(i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 1 |  | 1 | 20191.9425 | 0 | 20191.9425 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.00 | 415V LV BUS-DUCT SET FOR DTT AND PMCC | [5 empty] | 14: 0; 17: 0
2.01 | BUSDUCT FOR UNIT PMCC #1 DA | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 |  | 2 | 13126.0188 | 0 | 13126.0188 |  |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2 | 0 | 1875.1455 | 1875.1455 |  |  | 0
(iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.02 | BUSDUCT FOR ESP PMCC #1DB-1 | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 |  | 2 | 13126.0188 | 0 | 13126.0188 |  |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2 | 0 | 1875.1455 | 1875.1455 |  |  | 0
(iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.03 | BUSDUCT FOR ESP PMCC #1DB-2 | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 |  | 2 | 12520.0093 | 0 | 12520.0093 |  |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 2 | 2 | 0 | 1788.5728 | 1788.5728 |  |  | 0
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.04 | BUSDUCT FOR STATION PMCC #0DA | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 |  | 2 | 12520.0093 | 0 | 12520.0093 |  |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.05 | BUSDUCT FOR COOLING TOWER PMCC #1DC | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.06 | BUSDUCT FOR PTP PMCC #1DD | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.07 | BUSDUCT FOR ETP PMCC #1DE | [5 empty] | 14: 0; 17: 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.00 | POWER TRANSFORMERS AND DTT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.01 | GENERATOR TRANSFORMERS - 315 MVA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement on Foundation and alignment | 1 | NO | 35% | 951874.9193 | 333156.2218 | 1 |  | 1 | 333156.2218 | 0 | 333156.2218 |  |  | 0
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 951874.9193 | 190374.9839 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Completion of Oil filteration | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 951874.9193 | 142781.2379 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(v) | Charging | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.02 | STATION TRANSFORMER - 37.5/30 MVA, 220/6.9 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement on Foundation and alignment | 1 | NO | 35% | 633718.9956 | 221801.6484 | 1 |  | 1 | 221801.6484 | 0 | 221801.6484 |  |  | 0
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 633718.9956 | 126743.7991 | 1 |  | 1 | 126743.7991 | 0 | 126743.7991 |  |  | 0
(iii) | Completion of Oil filteration | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 633718.9956 | 95057.8493 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(v) | Charging | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.03 | UAT - 37.5/30 MVA,16.5/6.9 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement on Foundation and alignment | 2 | NO | 35% | 476803.4969 | 333762.4479 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 20% | 476803.4969 | 190721.3988 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Completion of Oil filteration | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iv) | Pre-commissioning checks & tests | 2 | NO | 15% | 476803.4969 | 143041.0491 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(v) | Charging | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.04 | 2500KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 70% | 28845.4259 | 121150.7886 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging of Transformer | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.05 | 2000KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 28845.3227 | 40383.4518 | 2 |  | 2 | 40383.4518 | 0 | 40383.4518 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 28845.3227 | 5769.0645 | 2 |  | 2 | 5769.0645 | 0 | 5769.0645 |  |  | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.06 | 1600KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 11 | NO | 70% | 25960.4163 | 199895.2058 | 4 |  | 4 | 72689.1658 | 0 | 72689.1658 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 11 | NO | 10% | 25960.4163 | 28556.458 | 4 |  | 4 | 10384.1665 | 0 | 10384.1665 |  |  | 0
(iii) | Charging of Transformer | 11 | NO | 10% | 25960.4163 | 28556.458 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.07 | 1250KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.08 | 1000KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.09 | 630KVA DTT, 6.6/0.415KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.10 | 500KVA DTT 6.6/0.433 KV | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | NO | 70% | 23076.2272 | 64613.4363 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging of Transformer | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.11 | 33/6.9KV 2MVA OIL FILLED RAW WATER TRF | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement on Foundation and alignment | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 30% | 28845.3227 | 17307.1936 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Completion of Oil filteration | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iv) | Pre-commissioning checks & tests | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(v) | Charging | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.12 | 6.6 KV NEUTRAL GROUNDING RESISTORS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 70% | 20485.634 | 71699.7191 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 10% | 20485.634 | 10242.817 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging of Transformer | 5 | NO | 10% | 20485.634 | 10242.817 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.00 | HVR TRANSFORMER(95 KVp,1200mA)COMMISSIONING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Test of HVR including Interlock/Protection, OCC/SCC | 28 | NO | 50% | 8473.3569 | 118626.9969 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Charging (Field-Charging) | 28 | NO | 40% | 8473.3569 | 94901.5975 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.00 | BUS DUCTS & EQUIPMENT SUPPORT STRUCTURE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Pre-assembly, alignment, erection including welding | 50 | MT | 70% | 8654.3208 | 302901.2292 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks /Testing & charging | 50 | MT | 10% | 8654.3208 | 43271.6042 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 50 | MT | 10% | 8654.3208 | 43271.6042 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6 | GENERATOR CIRCUIT BREAKER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement, alignment, installation, internal wiring | 1 | NO | 60% | 36398.9377 | 21839.3626 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-commissioning checks/testing | 1 | NO | 20% | 36398.9377 | 7279.7875 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 10% | 36398.9377 | 3639.8938 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.0 | UNLOADING AND SHIFTING OF TRANSFORMERS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.1 | GENERATOR TRANSFORMERS (GT) - 315 MVA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.1.1 | UNLOADING OF GT FROM TRAILER | 1 | NO | 90% | 214172.0425 | 192754.8382 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 1 | NO | 90% | 160628.7225 | 144565.8502 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.1 | STATION /UNIT TRANSFORMER (ST/UT) (37.5/30 MVA) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.1.1 | UNLOADING OF ST / UT FROM TRAILER | 1 | NO | 90% | 84371.0296 | 75933.9267 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 1 | NO | 90% | 63277.9628 | 56950.1665 | 1 |  | 1 | 56950.1665 | 0 | 56950.1665 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
| SCH-4-CABLING & EQUIPMENT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.00 | CABLE TRAY SUPPORT SYSTEM WITH ACCESORIES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.01 | CHANNEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.01.01 | SINGLE(SC1) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 6600 | RM | 70% | 109.3923 | 505392.4429 | 2046 |  | 2046 | 156671.6573 | 0 | 156671.6573 |  |  | 0
(ii) | Final painting and marking of tray nos | 6600 | RM | 20% | 109.3923 | 144397.8408 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.01.02 | DOUBLE(DC1) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5500 | RM | 70% | 127.6211 | 491341.1658 | 2280 | 600 | 2880 | 203683.2469 | 53600.8545 | 257284.1014 |  |  | 0
(ii) | Final painting and marking of tray nos | 5500 | RM | 20% | 127.6211 | 140383.1902 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02 | CANTILEVER ARM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02.01 | 600 MM Cantilever Arm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 12000 | NOS | 70% | 51.0519 | 428835.5511 | 5177 |  | 5177 | 185006.804 | 0 | 185006.804 |  |  | 0
(ii) | Final painting and marking of tray nos | 12000 | NOS | 20% | 51.0519 | 122524.4432 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02.02 | 300 MM Cantilever Arm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 6500 | NOS | 70% | 33.1867 | 150999.4646 | 1050 |  | 1050 | 24392.2212 | 0 | 24392.2212 |  |  | 0
(ii) | Final painting and marking of tray nos | 6500 | NOS | 20% | 33.1867 | 43142.7042 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02.03 | 150 MM Cantilever Arm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 1500 | NOS | 70% | 20.426 | 21447.2789 | 725 |  | 725 | 10366.1848 | 0 | 10366.1848 |  |  | 0
(ii) | Final painting and marking of tray nos | 1500 | NOS | 20% | 20.426 | 6127.794 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02.04 | 100 MM Cantilever Arm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 500 | NOS | 70% | 20.426 | 7149.093 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 500 | NOS | 20% | 20.426 | 2042.598 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2 | LADDER TYPE CABLE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1 | 600 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 24790 | MTR | 70% | 58.0426 | 1007212.5052 | 4125 | 1000 | 5125 | 167597.8856 | 40629.7904 | 208227.6761 |  |  | 0
(ii) | Final painting and marking of tray nos | 24790 | MTR | 20% | 58.0426 | 287775.0015 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.2 | 450 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 50.3607 | 35252.5135 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 50.3607 | 10072.1467 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.3 | 300 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5050 | MTR | 70% | 43.5319 | 153885.2654 | 2250 |  | 2250 | 68562.742 | 0 | 68562.742 |  |  | 0
(ii) | Final painting and marking of tray nos | 5050 | MTR | 20% | 43.5319 | 43967.2187 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.4 | 150 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 4150 | MTR | 70% | 35.8498 | 104143.5366 | 625 | 250 | 875 | 15684.2676 | 6273.707 | 21957.9746 |  |  | 0
(ii) | Final painting and marking of tray nos | 4150 | MTR | 20% | 35.8498 | 29755.2962 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5 | 100 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 35.85 | 25095.0316 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 35.85 | 7170.009 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.6 | 50 MM Ladder Type Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 17.9247 | 6273.6496 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 17.9247 | 1792.4713 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3 | CABLE TRAY 90 DEG BEND HORIZONTAL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.1.1 | 600 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 400 | NO | 70% | 173.274 | 48516.7146 | 132 |  | 132 | 16010.5158 | 0 | 16010.5158 |  |  | 0
(ii) | Final painting and marking of tray nos | 400 | NO | 20% | 173.274 | 13861.9185 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.1.2 | 450 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.1.3 | 300 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 120 | NO | 70% | 144.2519 | 12117.1581 | 9 |  | 9 | 908.7869 | 0 | 908.7869 |  |  | 0
(ii) | Final painting and marking of tray nos | 120 | NO | 20% | 144.2519 | 3462.0452 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.1.4 | 150 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.1.5 | 100 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.1.6 | 50 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 68.2557 | 477.7902 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 68.2557 | 136.5115 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.2 | CABLE TRAY 90 DEG BEND VERTICAL-INSIDE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 173.2755 | 24258.5739 | 50 |  | 50 | 6064.6435 | 0 | 6064.6435 |  |  | 0
(ii) | Final painting and marking of tray nos | 200 | NO | 20% | 173.2755 | 6931.0211 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 144.2509 | 7573.1697 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 144.2509 | 2163.7628 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.3 | CABLE TRAY 90 DEG BEND VERTICAL-OUTSIDE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 173.2735 | 18193.7138 | 50 |  | 50 | 6064.5713 | 0 | 6064.5713 |  |  | 0
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 173.2735 | 5198.204 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.4 | TEES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.4.1 | 600 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 231.3177 | 32384.4727 | 50 |  | 50 | 8096.1182 | 0 | 8096.1182 |  |  | 0
(ii) | Final painting and marking of tray nos | 200 | NO | 20% | 231.3177 | 9252.7065 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.4.2 | 450 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.4.3 | 300 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 173.2693 | 2425.7708 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 173.2693 | 693.0774 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.4.4 | 150 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 137.4191 | 1442.9004 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 15 | NO | 20% | 137.4191 | 412.2573 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.4.5 | 100 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.4.6 | 50 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 68.3176 | 239.1117 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 68.3176 | 68.3176 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.5.0 | CROSSES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.5.1 | 600 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 90 | NO | 70% | 260.3372 | 16401.2425 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 90 | NO | 20% | 260.3372 | 4686.0693 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.5.2 | 450 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 215.9679 | 1511.775 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 215.9679 | 431.9357 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.5.3 | 300 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 202.3126 | 2124.2821 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 15 | NO | 20% | 202.3126 | 606.9377 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.5.4 | 150 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.5.5 | 100 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.5.6 | 50 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 86.2634 | 301.9218 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 86.2634 | 86.2634 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.6 | REDUCERS LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.6.1 | 600 MM-450 MM Reducer LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 158.7642 | 5556.7477 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 158.7642 | 1587.6422 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.6.2 | 600 MM-300 MM Reducer LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 144.2591 | 2524.5343 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 25 | NO | 20% | 144.2591 | 721.2955 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.6.3 | 450 MM -300 MM Reducer LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 40 | NO | 70% | 137.4242 | 3847.8789 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 40 | NO | 20% | 137.4242 | 1099.394 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.6.4 | 300 MM -150 MM Reducer LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.7 | REDUCERS RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.7.1 | 600 MM-450 MM Reducer RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 158.758 | 2222.6125 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 158.758 | 635.0321 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.7.2 | 600 MM-300 MM Reducer RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.7.3 | 450 MM -300 MM Reducer RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.7.4 | 300 MM -150 MM Reducer RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.8 | CABLE TRAY COVER WITH FIXING HARDWARES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.8.1 | 600 MM wide Tray Cover | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 58.0428 | 20314.9637 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 58.0428 | 5804.2753 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.8.2 | 450 MM wide Tray Cover | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 250 | MTR | 70% | 58.0428 | 10157.4819 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 250 | MTR | 20% | 58.0428 | 2902.1377 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.8.3 | 300 MM wide Tray Cover | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 100 | MTR | 70% | 50.3595 | 3525.1647 | 70 |  | 70 | 2467.6153 | 0 | 2467.6153 |  |  | 0
(ii) | Final painting and marking of tray nos | 100 | MTR | 20% | 50.3595 | 1007.1899 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.8.4 | 150 MM wide Tray Cover | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 100 | MTR | 70% | 43.5339 | 3047.3745 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 100 | MTR | 20% | 43.5339 | 870.6784 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.8.5 | 100 MM wide Tray Cover | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 43.5277 | 1523.4707 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 43.5277 | 435.2773 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.8.6 | 50 MM wide Tray Cover | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 21.7701 | 761.9519 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 21.7701 | 217.7005 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.00 | PERFORATED TYPE CABLE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.10 | 600 MM Perforated Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 7500 | MTR | 70% | 71.6997 | 376423.3085 | 1650 |  | 1650 | 82813.1279 | 0 | 82813.1279 |  |  | 0
(ii) | Final painting and marking of tray nos | 7500 | MTR | 20% | 71.6997 | 107549.5167 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.20 | 450 MM Perforated Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 64.8708 | 22704.7811 | 150 |  | 150 | 6811.4343 | 0 | 6811.4343 |  |  | 0
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 64.8708 | 6487.0803 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.30 | 300 MM Perforated Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 3500 | MTR | 70% | 58.0426 | 142204.3129 | 887.5 |  | 887.5 | 36058.9508 | 0 | 36058.9508 |  |  | 0
(ii) | Final painting and marking of tray nos | 3500 | MTR | 20% | 58.0426 | 40629.8037 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.40 | 150 MM Perforated Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 1500 | MTR | 70% | 43.5319 | 45708.4518 | 250 |  | 250 | 7618.0753 | 0 | 7618.0753 |  |  | 0
(ii) | Final painting and marking of tray nos | 1500 | MTR | 20% | 43.5319 | 13059.5577 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.50 | 100 MM Perforated Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 43.5321 | 30472.4456 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 43.5321 | 8706.413 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.60 | 50 MM Perforated Cable Tray | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 21.3394 | 14937.5498 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 21.3394 | 4267.8714 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.00 | CABLE TRAY ACCESSORIES (PERFORATED-TYPE) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.10 | HORIZONTAL 90 DEG BEND PERFORATED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.1.1 | 600 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 230 | NO | 70% | 187.7847 | 30233.3339 | 67 |  | 67 | 8807.1016 | 0 | 8807.1016 |  |  | 0
(ii) | Final painting and marking of tray nos | 230 | NO | 20% | 187.7847 | 8638.0954 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.1.2 | 450 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.1.3 | 300 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 35 | NO | 70% | 158.7713 | 3889.8967 | 5 |  | 5 | 555.6995 | 0 | 555.6995 |  |  | 0
(ii) | Final painting and marking of tray nos | 35 | NO | 20% | 158.7713 | 1111.399 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.1.4 | 150 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.1.5 | 100 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.1.6 | 50 MM Tray Bend 90Deg Horizontal | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 72.5256 | 253.8396 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 72.5256 | 72.5256 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.20 | VERTICAL 90 DEG BEND PERFORATED (INSIDE) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 187.7868 | 13145.0784 | 20 |  | 20 | 2629.0157 | 0 | 2629.0157 |  |  | 0
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 187.7868 | 3755.7367 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 158.7642 | 11113.4954 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 158.7642 | 3175.2844 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.30 | VERTICAL 90 DEG BEND PERFORATED (OUTSIDE) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 110 | NO | 70% | 187.7835 | 14459.3264 | 25 |  | 25 | 3286.2105 | 0 | 3286.2105 |  |  | 0
(ii) | Final painting and marking of tray nos | 110 | NO | 20% | 187.7835 | 4131.2361 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 173.2693 | 3032.2134 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 25 | NO | 20% | 173.2693 | 866.3467 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 60 | NO | 70% | 158.7683 | 6668.2705 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 60 | NO | 20% | 158.7683 | 1905.2202 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 144.2467 | 2019.4542 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 144.2467 | 576.9869 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.40 | TEES PERFORATED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.1 | 600 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 130 | NO | 70% | 202.2967 | 18409.001 | 25 |  | 25 | 3540.1925 | 0 | 3540.1925 |  |  | 0
(ii) | Final painting and marking of tray nos | 130 | NO | 20% | 202.2967 | 5259.7146 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.2 | 450 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.3 | 300 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.4 | 150 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.5 | 100 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 158.789 | 555.7614 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 158.789 | 158.789 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.6 | 50 MM Tee-Joint | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 79.3326 | 277.6641 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 79.3326 | 79.3326 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.50 | CROSSES PERFORATED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.1 | 600 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 288.4935 | 2019.4542 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 288.4935 | 576.9869 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.2 | 450 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 231.3146 | 809.601 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 231.3146 | 231.3146 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.3 | 300 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 215.9679 | 755.8875 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 215.9679 | 215.9679 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.4 | 150 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.5 | 100 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.6 | 50 MM Cross | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 53.7135 | 187.9972 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 53.7135 | 53.7135 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.60 | REDUCERS PERFORATED LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.6.1 | 600 MM WIDE - 450 MM Reducer LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.6.2 | 450 MM WIDE - 300 MM Reducer LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.6.3 | 300 MM WIDE - 150 MM Reducer LHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.70 | REDUCERS PERFORATED RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.7.1 | 600 MM WIDE - 450 MM Reducer RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.7.2 | 450 MM WIDE - 300 MM Reducer RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.7.3 | 300 MM WIDE - 150 MM Reducer RHS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.80 | CABLE TROUGHS HOT DIP GALVANISED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.8.1 | 50MM WIDE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 734.7504 | 90006.9243 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 734.7504 | 25716.2641 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.8.2 | 75MM WIDE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 1102.8098 | 135094.2055 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 1102.8098 | 38598.3444 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.00 | CONDUITS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.1 | RIGID GALVANISED MS CONDUITS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.1.1 | 50 MM DIAMETER MS Conduit | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 108.4016 | 19512.2935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.1.2 | 80 MM DIAMETER MS Conduit | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 122.9129 | 22124.3288 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.2 | GI FLEXIBLE METALLIC CONDUIT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of conduit/pipe complete in all respect | 2240 | MTR | 90% | 35.8498 | 72273.1787 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.00 | PERFORATED MS SHEET TO COVER CABLE SHAFT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 250 | SQM | 70% | 71.6989 | 12547.2992 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Painting as applicable | 250 | SQM | 20% | 71.6989 | 3584.9426 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.00 | DOUBLE COMPRESSION CABLE GLAND FOR UA/A CABLE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.01 | 9-11 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 300 | NO. | 70% | 71.7005 | 15057.1056 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 300 | NO. | 20% | 71.7005 | 4302.0302 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.02 | 11-13 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 1000 | NO. | 70% | 71.6995 | 50189.6301 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 1000 | NO. | 20% | 71.6995 | 14339.8943 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.03 | 13-17 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 1500 | NO. | 70% | 79.3817 | 83350.7826 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 1500 | NO. | 20% | 79.3817 | 23814.5093 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.04 | 17-20 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 200 | NO. | 70% | 87.0647 | 12189.0649 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 200 | NO. | 20% | 87.0647 | 3482.59 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.05 | 20-23 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 70 | NO. | 70% | 94.75 | 4642.752 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 70 | NO. | 20% | 94.75 | 1326.5006 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.06 | 23-26 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 150 | NO. | 70% | 101.573 | 10665.161 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 150 | NO. | 20% | 101.573 | 3047.1889 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.07 | 26-30 (Above-mm to Upto-mm Cable Gland) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO. | 70% | 108.4047 | 3794.1654 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO. | 20% | 108.4047 | 1084.0472 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.08 | 30-35 (For 3.5C x 50, 2C x 95 Cables ) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 122.9098 | 4301.8445 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 122.9098 | 1229.0984 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.09 | 35-40 (For 3.5C x 95, 2C x 120 Cables ) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 100 | NO | 70% | 130.5956 | 9141.6904 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 100 | NO | 20% | 130.5956 | 2611.9115 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.10 | 40-50 (For 3C x 150, 2C x 120 Cables ) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 151.9325 | 5317.636 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 151.9325 | 1519.3246 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.11 | 50-60 (For 3C x 240, 2C x 120 Cables ) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 20 | NO | 70% | 166.4314 | 2330.0394 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 20 | NO | 20% | 166.4314 | 665.7256 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.12 | CABLE GLAND SUITABLE-16 PAIR,0.5SQ.MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.13 | CABLE GLAND SUITABLE-10 PAIR,0.6SQ.MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.20 | CRIMPING LUGS (RING/ROUND/FLAT TYPE) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.1 | 0.5 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 7000 | NO | 70% | 22.1927 | 108744.2707 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 7000 | NO | 20% | 22.1927 | 31069.7916 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.2 | 1.5 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 800 | NO | 70% | 22.1924 | 12427.7434 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 800 | NO | 20% | 22.1924 | 3550.7838 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.3 | 2.5 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 5250 | NO | 70% | 22.1927 | 81558.3113 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 5250 | NO | 20% | 22.1927 | 23302.3747 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.4 | 16 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 250 | NO | 70% | 29.0201 | 5078.5243 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 250 | NO | 20% | 29.0201 | 1451.007 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.5 | 25 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 29.0226 | 1015.7915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 29.0226 | 290.2261 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.6 | 35 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 43.5277 | 1523.4707 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 43.5277 | 435.2773 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.7 | 50 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.8 | 70 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.9 | 95 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 71.6964 | 2509.3732 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 71.6964 | 716.9638 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.10 | 120 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.11 | 150 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.12 | 185 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.13 | 240 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.10 | 300 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 130.5956 | 4570.8452 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 130.5956 | 1305.9558 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.2.11 | 630 Sq-mm Lugs | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.00 | EQUIPMENT EARTHING MATERIALS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.01 | GI WIRE 14 SWG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 87500 | MTR | 70% | 7.6821 | 470528.9191 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 87500 | MTR | 20% | 7.6821 | 134436.834 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.02 | GI WIRE 8 SWG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 1450 | MTR | 70% | 7.6819 | 7797.1203 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 1450 | MTR | 20% | 7.6819 | 2227.7487 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.03 | GS FLAT 25 X 6 MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 8 | MT | 70% | 12997.0569 | 72783.5188 | 1 |  | 1 | 9097.9398 | 0 | 9097.9398 |  |  | 0
(ii) | Testing of connected equipments/system | 8 | MT | 20% | 12997.0569 | 20795.2911 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.04 | GS FLAT 50 X 6 MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 2 | MT | 70% | 8983.087 | 12576.3218 | 1.5 |  | 1.5 | 9432.2414 | 0 | 9432.2414 |  |  | 0
(ii) | Testing of connected equipments/system | 2 | MT | 20% | 8983.087 | 3593.2348 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.05 | GS FLAT 65 X 8 MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 53 | MT | 70% | 10576.5403 | 392389.645 | 33 |  | 33 | 244318.0809 | 0 | 244318.0809 |  |  | 0
(ii) | Testing of connected equipments/system | 53 | MT | 20% | 10576.5403 | 112111.3271 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.06 | GS FLAT 75 X 10 MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 6 | MT | 70% | 9787.4487 | 41107.2845 | 5.4985 |  | 5.4985 | 37671.4006 | 0 | 37671.4006 |  |  | 0
(ii) | Testing of connected equipments/system | 6 | MT | 20% | 9787.4487 | 11744.9384 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.07 | GS ROD 20 MM DIA.1000MM LONG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 84 | NOS | 70% | 341.8091 | 20098.377 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8091 | 5742.3934 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.08 | TEST LINK 150X25X6 MM GS FLAT WITH BOX | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 84 | NOS | 70% | 341.8681 | 20101.8424 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8681 | 5743.3836 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.09 | 40NB GALV MS HEAVY DUTY PIPE (PERF) 3M | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 112 | NOS | 70% | 454.2408 | 35612.4805 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 112 | NOS | 20% | 454.2408 | 10174.9944 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.10 | FLEXIBLE BRAIDED CONDUCTOR FOR FENCE GATE GND | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 10 | NOS | 70% | 5048.821 | 35341.7472 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 5048.821 | 10097.6421 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.00 | CABLE LAYING, DRESSING, CLAMPING, TAGGING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.1 | 6.6 KV XLPE AL UA POWER CABLES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.1.1 | 1C-400 Sq.mm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 32000 | MTR | 55% | 31.7271 | 558396.7097 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 32000 | MTR | 10% | 31.7271 | 101526.6745 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 32000 | MTR | 25% | 31.7271 | 253816.6862 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.1.2 | 3C-150 Sq.mm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 13000 | MTR | 55% | 34.6138 | 247488.9209 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 13000 | MTR | 10% | 34.6138 | 44997.9856 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 13000 | MTR | 25% | 34.6138 | 112494.964 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.1.3 | 3C-240 Sq.mm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 43.2673 | 118985.1694 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 43.2673 | 21633.6672 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 43.2673 | 54084.1679 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.2 | 33 KV XLPE AL UA POWER CABLES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.2.1 | 3C-120 Sq.mm | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 1500 | MTR | 55% | 34.6139 | 28556.427 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 1500 | MTR | 10% | 34.6139 | 5192.0776 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 1500 | MTR | 25% | 34.6139 | 12980.1941 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.3.1 | 3.5C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 12.2573 | 53931.9384 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 12.2573 | 9805.807 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 12.2573 | 24514.5175 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.3.2 | 3.5C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 14.4166 | 7929.1453 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 14.4166 | 1441.6628 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 14.4166 | 3604.157 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.3.3 | 3C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 10.0891 | 44392.2546 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 10.0891 | 8071.319 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 10.0891 | 20178.2975 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.1 | 1C - 35 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 8.6663 | 38131.5073 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 8.6663 | 6933.0013 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 8.6663 | 17332.5033 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.2 | 1C - 70 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 9.6291 | 74143.9925 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 9.6291 | 13480.7259 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 9.6291 | 33701.8148 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.3 | 1C - 120 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 2000 | MTR | 55% | 11.5555 | 12711.0697 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 2000 | MTR | 10% | 11.5555 | 2311.1036 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 2000 | MTR | 25% | 11.5555 | 5777.759 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.4 | 1C - 400 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 13500 | MTR | 55% | 16.3706 | 121551.4121 | 0 | 2961 | 2961 | 0 | 26660.2764 | 26660.2764 |  |  | 0
(ii) | After termination of cable | 13500 | MTR | 10% | 16.3706 | 22100.2567 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 13500 | MTR | 25% | 16.3706 | 55250.6418 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.5 | 1C - 630 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 18000 | MTR | 55% | 17.3334 | 171600.6321 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 18000 | MTR | 10% | 17.3334 | 31200.1149 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 18000 | MTR | 25% | 17.3334 | 78000.2873 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.6 | 2C - 10 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 8.6663 | 28598.6305 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 8.6663 | 5199.751 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 8.6663 | 12999.3775 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.7 | 2C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 9.6291 | 42367.8499 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 9.6291 | 7703.2454 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 9.6291 | 19258.1136 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.8 | 2C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 11.5558 | 6355.705 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 11.5558 | 1155.5827 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.5558 | 2888.9568 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.9 | 2C - 95 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 12.9998 | 42899.4773 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 12.9998 | 7799.905 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 12.9998 | 19499.7624 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.10 | 2C - 120 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 13.9626 | 61435.6456 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 13.9626 | 11170.1174 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 13.9626 | 27925.2935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.11 | 3C - 10 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 36100 | MTR | 55% | 9.6291 | 191185.7606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 36100 | MTR | 10% | 9.6291 | 34761.0474 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 36100 | MTR | 25% | 9.6291 | 86902.6185 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.12 | 3C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 11.0742 | 85271.071 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 11.0742 | 15503.8311 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 11.0742 | 38759.5777 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.13 | 3C - 35 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 800 | MTR | 55% | 11.5557 | 5084.4959 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 800 | MTR | 10% | 11.5557 | 924.4538 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 800 | MTR | 25% | 11.5557 | 2311.1345 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.14 | 3C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 2000 | MTR | 55% | 12.5184 | 13770.2404 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 2000 | MTR | 10% | 12.5184 | 2503.6801 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 2000 | MTR | 25% | 12.5184 | 6259.2002 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.15 | 3C - 95 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 14.4441 | 63553.9871 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 14.4441 | 11555.2704 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 14.4441 | 28888.1759 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.16 | 3C - 150 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 750 | MTR | 55% | 19.2593 | 7944.4611 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 750 | MTR | 10% | 19.2593 | 1444.4475 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 750 | MTR | 25% | 19.2593 | 3611.1187 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.17 | 3C - 240 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 6750 | MTR | 55% | 24.074 | 89374.6769 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 6750 | MTR | 10% | 24.074 | 16249.9413 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 6750 | MTR | 25% | 24.074 | 40624.8531 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.18 | 3.5C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 11.267 | 37181.2488 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 11.267 | 6760.227 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 11.267 | 16900.5676 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.19 | 3.5C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 12000 | MTR | 55% | 12.9998 | 85798.9546 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 12000 | MTR | 10% | 12.9998 | 15599.8099 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 12000 | MTR | 25% | 12.9998 | 38999.5248 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.20 | 3.5C - 95 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 14.9263 | 82094.9203 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 14.9263 | 14926.3491 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.9263 | 37315.8729 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.21 | 3.5C - 185 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 750 | MTR | 55% | 23.1108 | 9533.2172 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 750 | MTR | 10% | 23.1108 | 1733.3122 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 750 | MTR | 25% | 23.1108 | 4333.2805 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.22 | 4C - 10 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.1105 | 83411.7363 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.1105 | 15165.7702 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.1105 | 37914.4256 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.23 | 2C - 1.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 140 | MTR | 55% | 6.4446 | 496.231 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 140 | MTR | 10% | 6.4446 | 90.2238 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 140 | MTR | 25% | 6.4446 | 225.5596 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.24 | 2C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 68500 | MTR | 55% | 6.4461 | 242858.4525 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 68500 | MTR | 10% | 6.4461 | 44156.0823 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 68500 | MTR | 25% | 6.4461 | 110390.2057 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.25 | 3C - 1.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 9200 | MTR | 55% | 6.4461 | 32617.4891 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 9200 | MTR | 10% | 6.4461 | 5930.4526 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 9200 | MTR | 25% | 6.4461 | 14826.1314 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.26 | 3C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 95300 | MTR | 55% | 6.4461 | 337874.4387 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 95300 | MTR | 10% | 6.4461 | 61431.7161 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 95300 | MTR | 25% | 6.4461 | 153579.2903 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.27 | 4C - 1.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 5500 | MTR | 55% | 6.4462 | 19499.7005 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 5500 | MTR | 10% | 6.4462 | 3545.4001 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 5500 | MTR | 25% | 6.4462 | 8863.5002 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.4.28 | 10C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8200 | MTR | 55% | 11.5402 | 52046.3967 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8200 | MTR | 10% | 11.5402 | 9462.9812 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5402 | 23657.453 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.1 | 2C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 50000 | MTR | 55% | 5.2964 | 145650.6091 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 50000 | MTR | 10% | 5.2964 | 26481.9289 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 50000 | MTR | 25% | 5.2964 | 66204.8223 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.2 | 2C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 3000 | MTR | 55% | 6.2591 | 10327.5952 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 3000 | MTR | 10% | 6.2591 | 1877.7446 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 3000 | MTR | 25% | 6.2591 | 4694.3615 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.3 | 3C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 2500 | MTR | 55% | 9.6625 | 13285.9217 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 2500 | MTR | 10% | 9.6625 | 2415.6221 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 2500 | MTR | 25% | 9.6625 | 6039.0553 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.4 | 3C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 18500 | MTR | 55% | 8.9428 | 90993.3838 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 18500 | MTR | 10% | 8.9428 | 16544.2516 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 18500 | MTR | 25% | 8.9428 | 41360.629 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.5 | 3C-16 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 1500 | MTR | 55% | 8.2625 | 6816.5396 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 1500 | MTR | 10% | 8.2625 | 1239.3708 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 1500 | MTR | 25% | 8.2625 | 3098.4271 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.6 | 5C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.0891 | 83235.4348 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.0891 | 15133.7154 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.0891 | 37834.2885 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.7 | 5C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 7000 | MTR | 55% | 10.0891 | 38843.1802 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 7000 | MTR | 10% | 10.0891 | 7062.3964 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 7000 | MTR | 25% | 10.0891 | 17655.991 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.8 | 7C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 12000 | MTR | 55% | 10.3794 | 68504.0446 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 12000 | MTR | 10% | 10.3794 | 12455.2808 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 12000 | MTR | 25% | 10.3794 | 31138.2021 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.9 | 7C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 8.6666 | 4766.6086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 8.6666 | 866.6561 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.6666 | 2166.6403 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.10 | 10C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8200 | MTR | 55% | 11.5377 | 52034.8248 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8200 | MTR | 10% | 11.5377 | 9460.8772 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5377 | 23652.1931 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.11 | 10C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 250 | MTR | 55% | 10.1115 | 1390.3317 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 250 | MTR | 10% | 10.1115 | 252.7876 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 250 | MTR | 25% | 10.1115 | 631.969 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.12 | 12C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.5928 | 87390.4335 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.5928 | 15889.1697 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.5928 | 39722.9243 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.13 | 12C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 11.4506 | 31489.2272 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 11.4506 | 5725.314 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 11.4506 | 14313.2851 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.14 | 16C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 4000 | MTR | 55% | 13.133 | 28892.6933 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 4000 | MTR | 10% | 13.133 | 5253.217 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 4000 | MTR | 25% | 13.133 | 13133.0424 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.5.15 | 19C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 2500 | MTR | 55% | 13.7014 | 18839.4206 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 2500 | MTR | 10% | 13.7014 | 3425.3492 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 2500 | MTR | 25% | 13.7014 | 8563.373 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 8.3652 | 2300.429 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 8.3652 | 418.2598 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 8.3652 | 1045.6495 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 9.3751 | 2578.155 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 9.3751 | 468.7554 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 9.3751 | 1171.8886 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 10.385 | 2855.8809 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 10.385 | 519.2511 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 10.385 | 1298.1277 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.4 | 5C - 6 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 500 | MTR | 55% | 10.817 | 2974.6633 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 500 | MTR | 10% | 10.817 | 540.8479 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 10.817 | 1352.1197 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 11.5379 | 1269.167 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 11.5379 | 230.7576 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 11.5379 | 576.8941 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 200 | MTR | 55% | 17.3084 | 1903.9206 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 200 | MTR | 10% | 17.3084 | 346.1674 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 17.3084 | 865.4185 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.7 | CONTROL/INSTRUMENT LT CABLES (SHIELDED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.7.1 | 2P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 8.5354 | 4694.4543 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 8.5354 | 853.5371 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.5354 | 2133.8429 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.7.2 | 4P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 9.3892 | 25820.3495 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 9.3892 | 4694.609 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 9.3892 | 11736.5225 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.7.3 | 6P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 11.0964 | 61029.9478 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 11.0964 | 11096.3542 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.0964 | 27740.8854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.7.4 | 8P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 11.95 | 6572.5083 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 11.95 | 1195.0015 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.95 | 2987.5038 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.7.5 | 12P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 12.8035 | 105628.7952 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 12.8035 | 19205.2355 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 12.8035 | 48013.0887 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.7.6 | 16P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 14.5106 | 79808.4457 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 14.5106 | 14510.6265 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.5106 | 36276.5662 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.8 | SCREENED CABLES (OVERALL & INDIVIDUAL/OVERALL) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.8.1 | 2P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 9.3892 | 30984.4874 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 9.3892 | 5633.5432 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 9.3892 | 14083.8579 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.8.2 | 4P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 10.2428 | 78869.7591 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 10.2428 | 14339.9562 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 10.2428 | 35849.8905 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.8.3 | 8P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 11.95 | 65724.7425 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 11.95 | 11949.9532 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.95 | 29874.8829 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.8.4 | 12 P - 0.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 13.6571 | 37556.9957 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 13.6571 | 6828.5447 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 13.6571 | 17071.3617 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.9 | SPECIALISED CABLING FOR COMMUNICATION SYSTEM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.9.1 | OPTICAL FIBRE CABLE WITHOUT HDPE PIPE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 19.8096 | 87162.0584 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 19.8096 | 15847.647 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 19.8096 | 39619.1174 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.9.2 | OPTICAL FIBRE CABLE WITH HDPE PIPE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 3000 | MTR | 55% | 29.0546 | 47940.0681 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 3000 | MTR | 10% | 29.0546 | 8716.376 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 3000 | MTR | 25% | 29.0546 | 21790.94 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.9.3 | EARTH CABLE FOR ESP | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Laying of cable | 280 | MTR | 55% | 9.2536 | 1425.0475 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | After termination of cable | 280 | MTR | 10% | 9.2536 | 259.0995 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Dressing & Clamping | 280 | MTR | 25% | 9.2536 | 647.7489 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.0 | CABLE JOINITNG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.10 | JOINT KIT 6.6KV 1C-400 AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 12 | NOS | 70% | 2902.1067 | 24377.6966 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 12 | NOS | 20% | 2902.1067 | 6965.0562 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.20 | JOINT KIT 6.6KV 3C-150 AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 8 | NOS | 70% | 2902.1067 | 16251.7977 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 2902.1067 | 4643.3708 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.30 | JOINT KIT 6.6KV 3C-240 AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.40 | JOINT KIT 33KV 3C-120 AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.0 | CABLE TERMINATION | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.1 | 6.6 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.1.1 | TERM. KIT 6.6KV 1C-400 AL UNARM. CU LUG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 136 | NOS | 70% | 2902.1295 | 276282.7269 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 136 | NOS | 20% | 2902.1295 | 78937.922 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.1.2 | TERM. KIT 6.6KV 3C-150 AL UNARM. CU LUG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 94 | NOS | 70% | 2902.1298 | 190960.1392 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 94 | NOS | 20% | 2902.1298 | 54560.0398 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.1.3 | TERM. KIT 6.6KV 3C-240 AL UNARM. CU LUG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 46 | NOS | 70% | 2902.1269 | 93448.4866 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 46 | NOS | 20% | 2902.1269 | 26699.5676 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.2 | 33 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.2.1 | TERM. KIT 33KV 3C-120 AL UNARM. CU LUG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 6 | NOS | 70% | 2902.1583 | 12189.0649 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 6 | NOS | 20% | 2902.1583 | 3482.59 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.3.1 | 3.5C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 32 | NOS | 70% | 151.9394 | 3403.443 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.9394 | 972.4123 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.3.2 | 3.5C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.3.3 | 3C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 32 | NOS | 70% | 144.2622 | 3231.4732 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 144.2622 | 923.2781 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.1 | 1C - 35 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 32 | NOS | 70% | 151.0885 | 3384.3834 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.0885 | 966.9667 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.2 | 1C - 70 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 56 | NOS | 70% | 157.0585 | 6156.6928 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 56 | NOS | 20% | 157.0585 | 1759.0551 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.3 | 1C - 120 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 8 | NOS | 70% | 170.7167 | 956.0136 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 170.7167 | 273.1467 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.4 | 1C - 400 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 54 | NOS | 70% | 183.5142 | 6936.838 | 0 | 36 | 36 | 0 | 4624.5587 | 4624.5587 |  |  | 0
(ii) | Testing of connected equipments/system | 54 | NOS | 20% | 183.5142 | 1981.9537 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.5 | 1C - 630 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 72 | NOS | 70% | 209.9773 | 10582.8581 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 72 | NOS | 20% | 209.9773 | 3023.6737 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.6 | 2C - 10 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 24 | NOS | 70% | 98.1602 | 1649.0909 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 98.1602 | 471.1688 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.7 | 2C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 32 | NOS | 70% | 98.1602 | 2198.7879 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 98.1602 | 628.2251 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.8 | 2C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 131.4991 | 368.1973 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 131.4991 | 105.1992 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.9 | 2C - 95 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 24 | NOS | 70% | 157.0511 | 2638.4589 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 157.0511 | 753.8454 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.10 | 2C - 120 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.11 | 3C - 10 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 145 | NOS | 70% | 144.2531 | 14641.6924 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 145 | NOS | 20% | 144.2531 | 4183.3407 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.12 | 3C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 56 | NOS | 70% | 144.2511 | 5654.6449 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 56 | NOS | 20% | 144.2511 | 1615.6128 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.13 | 3C - 35 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 151.1466 | 423.2104 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 151.1466 | 120.9172 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.14 | 3C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 8 | NOS | 70% | 157.0253 | 879.3419 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 157.0253 | 251.2405 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.15 | 3C - 95 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.16 | 3C - 150 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 209.9344 | 587.8162 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 209.9344 | 167.9475 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.17 | 3C - 240 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 27 | NOS | 70% | 222.7749 | 4210.445 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 27 | NOS | 20% | 222.7749 | 1202.9843 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.18 | 3.5C - 25 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 24 | NOS | 70% | 131.4475 | 2208.3177 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 131.4475 | 630.9479 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.19 | 3.5C - 50 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 48 | NOS | 70% | 144.2493 | 4846.7766 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 48 | NOS | 20% | 144.2493 | 1384.7933 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.20 | 3.5C - 95 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 40 | NOS | 70% | 163.8788 | 4588.6053 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 40 | NOS | 20% | 163.8788 | 1311.0301 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.21 | 3.5C - 185 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 222.7749 | 623.7696 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 222.7749 | 178.2199 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.22 | 4C - 10 AL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 60 | NOS | 70% | 144.257 | 6058.7956 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 60 | NOS | 20% | 144.257 | 1731.0845 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.23 | 2C - 1.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.24 | 2C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 274 | NOS | 70% | 117.7924 | 22592.5892 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 274 | NOS | 20% | 117.7924 | 6455.0255 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.25 | 3C - 1.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 26 | NOS | 70% | 144.2562 | 2625.4637 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 26 | NOS | 20% | 144.2562 | 750.1325 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.26 | 3C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 400 | NOS | 70% | 117.7922 | 32981.8188 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 400 | NOS | 20% | 117.7922 | 9423.3768 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.27 | 4C - 1.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 22 | NOS | 70% | 144.2411 | 2221.3129 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 22 | NOS | 20% | 144.2411 | 634.6608 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.4.28 | 10C - 2.5- CU | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 32 | NOS | 70% | 158.7658 | 3556.3532 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 158.7658 | 1016.1009 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.1 | 2C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 96 | NOS | 70% | 108.4029 | 7284.6762 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 96 | NOS | 20% | 108.4029 | 2081.3361 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.2 | 2C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 12 | NOS | 70% | 108.3965 | 910.5304 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 12 | NOS | 20% | 108.3965 | 260.1515 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.3 | 3C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 10 | NOS | 70% | 108.4171 | 758.9197 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 108.4171 | 216.8342 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.4 | 3C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 74 | NOS | 70% | 108.402 | 5615.2261 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 74 | NOS | 20% | 108.402 | 1604.3503 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.5 | 3C-16 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 6 | NOS | 70% | 144.288 | 606.0095 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 6 | NOS | 20% | 144.288 | 173.1456 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.6 | 5C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 44 | NOS | 70% | 116.0848 | 3575.4128 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 44 | NOS | 20% | 116.0848 | 1021.5465 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.7 | 5C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 23 | NOS | 70% | 122.9028 | 1978.7359 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 23 | NOS | 20% | 122.9028 | 565.3531 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.8 | 7C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 34 | NOS | 70% | 130.589 | 3108.0188 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 34 | NOS | 20% | 130.589 | 888.0054 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.9 | 7C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.10 | 10C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.11 | 12C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 42 | NOS | 70% | 144.2585 | 4241.2003 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 42 | NOS | 20% | 144.2585 | 1211.7715 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.12 | 12C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 14 | NOS | 70% | 144.2732 | 1413.8778 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 14 | NOS | 20% | 144.2732 | 403.9651 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.13 | 16C-2.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 16 | NOS | 70% | 144.2622 | 1615.7366 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 16 | NOS | 20% | 144.2622 | 461.639 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.5.14 | 19C-1.5 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 10 | NOS | 70% | 144.2467 | 1009.7271 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 144.2467 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 122.9903 | 344.3728 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 122.9903 | 98.3922 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.4 | 5C - 6 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 158.7271 | 444.4359 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 158.7271 | 126.9817 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.7 | OPTICAL FIBRE CABLE JOINTING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Termination | 10 | NOS. | 70% | 324.385 | 2270.6947 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Testing of connected equipments/system | 10 | NOS. | 20% | 324.385 | 648.7699 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.00 | CABLE SHAFT COVERING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.10 | MS SHEET FOR COVERING CABLE SHAFTS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 1000 | SQM | 70% | 2163.79 | 1514652.9917 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Painting as applicable | 1000 | SQM | 20% | 2163.79 | 432757.9976 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
| SCH-5 - SWITCHGEAR & EQUIPMENT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.00 | HT SWITCHGEAR BOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.01 | 6.6KV UNIT SWITCHBOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Alignment & Coupling as Applicable | 2 | SET | 50% | 222104.9936 | 222104.9936 | 2 |  | 2 | 222104.9936 | 0 | 222104.9936 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02 | 6.6KV STATION SWITCHBOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Alignment & Coupling as Applicable | 1 | SET | 50% | 242296.1316 | 121148.0658 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.03 | 6.6KV CHP SWITCHBOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 |  | 1 | 111052.6515 | 0 | 111052.6515 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.04 | 6.6KV AHP SWITCHBOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 |  | 1 | 111052.6515 | 0 | 111052.6515 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.05 | 6.6KV COMPRESSOR SWITCHBOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.06 | 6.6KV RAW WATER SWITCHBOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.07 | 33KV RAW WATER PANELS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | SET | 50% | 222104.9936 | 444209.9871 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.08 | BTS panel | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 10096.0331 | 10096.0331 | 2 |  | 2 | 10096.0331 | 0 | 10096.0331 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 2 |  | 2 | 4038.4133 | 0 | 4038.4133 |  |  | 0
(iii) | Charging | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.09 | DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.00 | LT SWITCHGEAR BOARD & DCDB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.01 | UNIT PMCC #1DA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 |  | 1 | 77105.7844 | 0 | 77105.7844 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 |  | 1 | 30842.3137 | 0 | 30842.3137 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.02 | TURBINE MCC #1KA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 114657.8914 | 57328.9457 | 1 |  | 1 | 57328.9457 | 0 | 57328.9457 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 1 |  | 1 | 22931.5783 | 0 | 22931.5783 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.03 | TURBINE VALVES & ACDB #1KB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 165064.4176 | 82532.2088 | 1 |  | 1 | 82532.2088 | 0 | 82532.2088 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 1 |  | 1 | 33012.8835 | 0 | 33012.8835 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.04 | BOILER VALVES & ACDB #1HB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 147756.667 | 73878.3335 | 1 |  | 1 | 73878.3335 | 0 | 73878.3335 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 147756.667 | 29551.3334 | 1 |  | 1 | 29551.3334 | 0 | 29551.3334 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 147756.667 | 29551.3334 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.05 | BOILER MCC #1HA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 131531.8498 | 65765.9249 | 1 |  | 1 | 65765.9249 | 0 | 65765.9249 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 131531.8498 | 26306.37 | 1 |  | 1 | 26306.37 | 0 | 26306.37 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 131531.8498 | 26306.37 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.06 | UNIT SERVICE ACDB #1QA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 |  | 1 | 77105.7844 | 0 | 77105.7844 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 |  | 1 | 30842.3137 | 0 | 30842.3137 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.07 | SOOT BLOWER MCC (Supply by Tnchy) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 115514.337 | 57757.1685 | 1 |  | 1 | 57757.1685 | 0 | 57757.1685 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.08 | ESP LT SWITCHGEAR(SUPPLY BY BAP RANIPET) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 131243.4801 | 131243.4801 | 2 |  | 2 | 131243.4801 | 0 | 131243.4801 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 131243.4801 | 52497.392 | 2 |  | 2 | 52497.392 | 0 | 52497.392 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 131243.4801 | 52497.392 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.09 | UNIT EMERGENCY BOARD #1DG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 181614.1148 | 90807.0574 | 1 |  | 1 | 90807.0574 | 0 | 90807.0574 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 181614.1148 | 36322.823 | 1 |  | 1 | 36322.823 | 0 | 36322.823 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 181614.1148 | 36322.823 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.10 | 220V UNIT DCDB #1FA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 1 |  | 1 | 46728.575 | 0 | 46728.575 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 1 |  | 1 | 18691.43 | 0 | 18691.43 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.11 | ESP A/C & VENT MCC #1TB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 52569.2988 | 26284.6494 | 1 |  | 1 | 26284.6494 | 0 | 26284.6494 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 1 |  | 1 | 10513.8598 | 0 | 10513.8598 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.12 | STATION PMCC #0DA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 |  | 1 | 64567.2724 | 0 | 64567.2724 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.13 | AC MCC #0TA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 78529.9964 | 39264.9982 | 1 |  | 1 | 39264.9982 | 0 | 39264.9982 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 | 1 | 1 | 0 | 15705.9993 | 15705.9993 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.14 | VENTILATION & AIR WASHER MCC #1TA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 116605.9338 | 58302.9669 | 1 |  | 1 | 58302.9669 | 0 | 58302.9669 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.15 | MISC SERVICE MCC #0SA | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 1 |  | 1 | 47918.2547 | 0 | 47918.2547 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 1 |  | 1 | 19167.3019 | 0 | 19167.3019 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.16 | COOLING TOWER PMCC #1DC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 191474.9966 | 95737.4983 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.17 | CWPH AND CHLORINATION MCC # 0SB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 126556.5445 | 63278.2722 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.18 | PTP PMCC #1DD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.19 | FW & CLARIFIED WATER MCC #0SC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.20 | ETP PMCC #1DE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.21 | ADMIN BUILDING MCC #0SB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.22 | O&M ACDB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.23 | STP MCC #0SF | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.24 | WATER PMCC # 0DB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.25 | MODIFICATION OF DM PLANT MCC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 |  | 1 | 64567.2724 | 0 | 64567.2724 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.26 | MODIFICATION OF FUEL OIL MCC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 |  | 1 | 64567.2724 | 0 | 64567.2724 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 1 | 1 | 0 | 25826.9089 | 25826.9089 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.27 | 220V DC FUSE DB (WALL MOUNTED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5 | 7211.8412 | 10817.7618 | 18029.603 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.28 | 415V AC FUSE DB (WALL MOUNTED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5 | 7211.8412 | 10817.7618 | 18029.603 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.29 | LV SWITCHGEAR FOR SWITCHYARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.29.1 | SWITCHYARD PMCC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.29.2 | SWITCHYARD 415V ACDB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 7211.7174 | 3605.8587 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.29.3 | SWITCHYARD 220V DCDB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.30 | DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.00 | LT PANELS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.01 | FEEDER FOR ELEVATOR (3 PHASE - 30 KW) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.02 | FEEDER FOR ELEVATOR (1 PHASE - 6 KW) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.00 | PROTECTION RELAY PANELS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.01 | GENERATOR PROTECTION & RELAY PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NOS. | 50% | 43267.3343 | 108168.3358 | 5 |  | 5 | 108168.3358 | 0 | 108168.3358 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.02 | STATION TRANSFORMER RELAY PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
4.03 | ELECTRICAL CONTROL DESK CUM PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 36055.4931 | 18027.7466 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.00 | DIGITAL STATIC EXCITATION SYSTEM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.1 | DIGITAL AUOTOMATIC VOLTAGE REGULATOR | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 38337.079 | 19168.5395 | 1 |  | 1 | 19168.5395 | 0 | 19168.5395 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.2 | HT DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.3 | LT DATA CONCENTRATOR PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4 | VARIABLE FREQUENCY DRIVE FOR ID FAN | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.1 | VARIABLE FREQUENCY DRIVE FOR ID FANS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 |  | 2 | 67587.1094 | 0 | 67587.1094 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.4.2 | 6.6KV VFD SWITCH GEAR PANEL FOR ID FAN | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 2 |  | 2 | 52569.6082 | 0 | 52569.6082 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 2 |  | 2 | 21027.8433 | 0 | 21027.8433 |  |  | 0
(iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.1 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 |  | 2 | 67587.1094 | 0 | 67587.1094 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
5.5.2 | 6.6KV VFD SWITCH GEAR PANEL FOR CEP | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 0 | 2 | 2 | 0 | 52569.6082 | 52569.6082 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.00 | LOCAL CONTROL PANELS FOR PUMPS ETC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.01 | LOCAL FAN CONTROL PANEL FOR ST | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.02 | LOCAL FAN CONTROL PANEL FOR GT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.03 | LOCAL FAN CONTROL PANEL FOR UAT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.04 | PANEL FOR OIL CENTRIFUGE UNIT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.05 | PANEL FOR ON LOAD TUBE CLEANING SYSTEM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.06 | PANEL FOR CENTRAL OIL PURIFICATION UNIT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 7211.7174 | 3605.8587 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
6.07 | LCP for Sump Pumps of Condensor Pit, & Trf oil Pit | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | No | 50% | 3852.1487 | 7704.2974 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | No | 20% | 3852.1487 | 3081.719 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 4 | No | 20% | 3852.1487 | 3081.719 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.00 | MISC ITEMS OF ESP | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.01 | ELECTRONIC CONTROLLER (WITH BAPCON) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 36 | NO | 50% | 7211.7862 | 129812.1516 | 28 |  | 28 | 100965.0068 | 0 | 100965.0068 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.02 | RAPPER CONTROL PANEL (WITH RAPCON) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.03 | STATCON CONTROL PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.04 | IOS PERSONAL COMPUTER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 5769.2502 | 2884.6251 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.05 | DATA LOGGER PC | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 2884.9345 | 1442.4673 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.06 | DOT MATRIX PRINTER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 1081.6957 | 540.8479 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
7.07 | COMPUTER FURNITURE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.00 | MISCELLANEOUS-1 (ONLY COMMISSIONING RATE) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.01 | THERMOSTAT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 32 | NO | 50% | 721.2723 | 11540.3568 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.02 | HOPPER/ SHAFT/ SUPPORT INSULATOR HEATER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 812 | SET | 50% | 721.2641 | 292833.2286 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.03 | ELECTRICALLY OPERATED HOIST | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.04 | ASH LEVEL INDICATORS & CONTROLLERS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 112 | SET | 50% | 721.2668 | 40390.9395 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.05 | RAPPING MOTORS FOR ESP | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 60 | NO | 50% | 1731.0329 | 51930.9869 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.06 | TESTING OF GENERATOR / EXCITER / PMG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.07 | COMMISSIONING OF HYDROGEN GAS DRIER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 721.2336 | 721.2336 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
8.08 | COMMISSIONING OF EXCITER HEATER, STROBOSCOPE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.00 | JUNCTION BOX/ MARSHALLING BOX /PB/STARTERS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.01 | FRP JUNCTION BOX- 24 WAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 70 | NO | 50% | 337.1592 | 11800.5703 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.02 | FRP JUNCTION BOX- 48 WAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO | 50% | 337.1574 | 8428.9346 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.03 | FRP JUNCTION BOX- 72 WAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 337.1636 | 3371.6357 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.04 | FRP JUNCTION BOX- 96 WAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 337.1326 | 842.8316 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 337.1326 | 337.1326 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 5 | NO | 20% | 337.1326 | 337.1326 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.05 | PUSH BUTTON/ STARTERS FOR RAPPING MOTORS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 100 | NO | 50% | 721.2646 | 36063.2284 | 0 | 60 | 60 | 0 | 21637.937 | 21637.937 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.06 | FRP JUNCTION BOX FOR HEATERS(JBHH,SHHH,SUHH) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 40 | NO | 50% | 337.1636 | 6743.2714 | 0 | 32 | 32 | 0 | 5394.6171 | 5394.6171 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
9.07 | FRP JUNCTION BO X(CONTROL-HH, TH, ALI) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 80 | NO | 50% | 337.1558 | 13486.2334 | 0 | 32 | 32 | 0 | 5394.4934 | 5394.4934 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.00 | PUSH BUTTON, BOX & STARTER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.10 | LOCAL PUSH BUTTON STATIONS (NON FLAME PROOF) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.1.1 | TYPE A | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 150 | NO | 50% | 721.2625 | 54094.6878 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.1.2 | TYPE C | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 1009.789 | 7573.4172 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.20 | PUSH BUTTON BOX | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 46 | NO | 50% | 1154.0169 | 26542.3876 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
10.30 | LOCAL MOTOR STARTER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO. | 50% | 1154.0233 | 28850.5827 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.00 | DC STRATER PANEL/ STARTING CABINET | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.10 | LOCALLY MOUNTED STARTER MODULE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.1.1 | FOR MOTOR RATING upto 0.75 KW | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 504.4613 | 5044.6131 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.1.4 | FOR MOTOR RATING above 0.75kW upto 1.5 kW | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 577.0282 | 4327.7112 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.1.5 | FOR MOTOR RATING above 1.5W upto 2.2kW | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 10 | NO | 50% | 648.708 | 3243.5402 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 10 | NO | 20% | 648.708 | 1297.4161 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 10 | NO | 20% | 648.708 | 1297.4161 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.1.6 | SUITABLE FOR MOTOR RATING above 2.2W upto 4.5kW | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 721.2955 | 1803.2388 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 721.2955 | 721.2955 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 5 | NO | 20% | 721.2955 | 721.2955 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
11.1.6 | SUITABLE FOR MOTOR RATING above 4.5W upto 6kW | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 721.2336 | 721.2336 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 721.2336 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 721.2336 | 288.4935 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.00 | DC STARTER LOCAL PANEL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.01 | STARTER CABINET FOR DC JACKING OIL MOTOR | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.02 | STARTER CABINET FOR DC SEAL OIL MOTOR | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.03 | STARTING CABINET FOR DC EMERGENCY LOP | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.04 | SCANNER AIR FAN DC MOTOR STARTER BOX | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 4327.4018 | 2163.7009 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
12.05 | FURNACE TEMPERATURE PROBE LOCAL STARTER BOX | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.00 | BATTERY SYSTEM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.01 | 220V BATTERY (EACH SET 170 CELLS) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | SET | 50% | 146185.2791 | 438555.8373 | 2 |  | 2 | 146185.2791 | 0 | 146185.2791 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.02 | 220V FCB CHARGER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 29746.839 | 89240.5169 | 2 |  | 2 | 29746.839 | 0 | 29746.839 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 29746.839 | 35696.2068 | 2 |  | 2 | 11898.7356 | 0 | 11898.7356 |  |  | 0
(iii) | Charging | 6 | NO | 20% | 29746.839 | 35696.2068 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.03 | 220V DC BATTERY HEALTH MONITORING SYSTEM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 3852.1487 | 11556.4461 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.04 | DISCHARGE RESISTOR | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 |  | 2 | 2885.0376 | 0 | 2885.0376 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 2 |  | 2 | 1154.0151 | 0 | 1154.0151 |  |  | 0
(iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
13.05 | 220 V DC ISOLATION BOX | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 |  | 2 | 2885.0376 | 0 | 2885.0376 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.00 | DG SET | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.01 | DG Set 750kVA,415V, 0.8pf with acoustic enclosure | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 144223.8289 | 144223.8289 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.02 | 990 litres fuel tank on stand including Fuel Piping | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 14422.8161 | 14422.8161 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.03 | Battery with stand (24V DC 360AH) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 28845.4774 | 57690.9548 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.04 | Battery Charger | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 8654.3394 | 17308.6788 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.05 | Exhaust Piping and Support Structure | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 695661.8562 | 695661.8562 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.06 | DG AMF Panel | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 7211.7174 | 7211.7174 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 7211.7174 | 2884.687 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | set | 20% | 7211.7174 | 2884.687 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.07 | DG Aux DB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 5048.9448 | 5048.9448 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.08 | Alternator extension terminal box | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 16088.0582 | 16088.0582 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
14.09 | Miscellaneous cables for DG Set | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | lot | 50% | 16100.1252 | 16100.1252 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(iii) | Charging | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
15.00 | MISCELLANEOUS FOR MOTORS & ACTUATORS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
15.01 | DRYING OUT, TESTING OF OF HT MOTORS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 42 | NO | 50% | 4327.5786 | 90879.1498 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 42 | NO | 40% | 4327.5786 | 72703.3198 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
15.02 | DRYING OUT, TESTING OF OF LT MOTORS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 200 | NO | 50% | 2163.7937 | 216379.3701 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 200 | NO | 40% | 2163.7937 | 173103.4961 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
15.03 | MOUNTING OF CTs FOR HT MOTORS/ PANELS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
15.04 | MOUNTING OF MODULES INSIDE LT PANELS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
15.05 | CABLE TRAY RE-ROUTING & RELAYING OF CABLES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 1000 | MTR | 50% | 108.4029 | 54201.4341 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 1000 | MTR | 40% | 108.4029 | 43361.1473 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
16.00 | ACTUATORS COMMISSIONING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 300 | NO | 50% | 1442.5291 | 216379.3701 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 300 | NO | 40% | 1442.5291 | 173103.4961 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
17.00 | SOOT BLOWERS COMMISSIONING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 80 | NO | 50% | 1081.4714 | 43258.8565 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 80 | NO | 40% | 1081.4714 | 34607.0852 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
18.00 | ELECTRICALLY OPTD MISC HOISTS COMMISSIONING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 2163.7628 | 10818.8138 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 2163.7628 | 8655.051 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
19.00 | FABRICATION (SUPPLY OF MATL BY BHEL) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
19.01 | BASE FRAMES FOR SWITCHGEAR, PANEL, PB | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
20.00 | CHEQUERED PLATES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
20.01 | INSTALLATION OF CHEQUERED PLATES 6 TO 8 MM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 40 | MT | 70% | 25960.3882 | 726890.87 | 4.65 |  | 4.65 | 84501.0636 | 0 | 84501.0636 |  |  | 0
(ii) | Painting as applicable | 40 | MT | 20% | 25960.3882 | 207683.1057 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
21.00 | INSERT PLATES/ ANCHOR FASTENERS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
21.01 | FABRICATION OF INSERT PLATES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
21.02 | INSTALLATION OF FRICTION ANCHOR FASTENERS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 3000 | SET | 70% | 296.1878 | 621994.4782 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Painting as applicable | 3000 | SET | 20% | 296.1878 | 177712.7081 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
22.00 | CANOPIES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
22.01 | FABRICATION AND INSTALLATION OF CANOPIES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 50 | SQM | 70% | 1211.2146 | 42392.5098 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Painting as applicable | 50 | SQM | 20% | 1211.2146 | 12112.1457 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.00 | IRREGULAR BENDS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.1 | FABRICATION OF IRREGULAR BENDS (LADER-TYPE) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.1.1 | 600 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 1000 | NO | 70% | 541.1616 | 378813.1259 | 300 |  | 300 | 113643.9378 | 0 | 113643.9378 |  |  | 0
(ii) | Final painting and marking of tray nos | 1000 | NO | 20% | 541.1616 | 108232.3217 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.1.2 | 450 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 500 | NO | 70% | 541.161 | 189406.3464 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 500 | NO | 20% | 541.161 | 54116.099 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.1.3 | 300 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 300 |  | 300 | 105936.0079 | 0 | 105936.0079 |  |  | 0
(ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.1.4 | 150 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 200 |  | 200 | 70624.0053 | 0 | 70624.0053 |  |  | 0
(ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.1.5 | 100 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 504.4613 | 17656.1457 | 20 |  | 20 | 7062.4583 | 0 | 7062.4583 |  |  | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 504.4613 | 5044.6131 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.1.6 | 50 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 252.2307 | 8828.0729 | 20 |  | 20 | 3531.2291 | 0 | 3531.2291 |  |  | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 252.2307 | 2522.3065 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.2 | FABRICATION OF IRREGULAR BENDS (PERFORATED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.2.1 | 600 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 577.0117 | 40390.8158 | 100 |  | 100 | 40390.8158 | 0 | 40390.8158 |  |  | 0
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 577.0117 | 11540.2331 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.2.2 | 450 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 577.0134 | 28273.6577 | 70 |  | 70 | 28273.6577 | 0 | 28273.6577 |  |  | 0
(ii) | Final painting and marking of tray nos | 70 | NO | 20% | 577.0134 | 8078.1879 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.2.3 | 300 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 541.1573 | 26516.7066 | 70 |  | 70 | 26516.7066 | 0 | 26516.7066 |  |  | 0
(ii) | Final painting and marking of tray nos | 70 | NO | 20% | 541.1573 | 7576.2019 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.2.4 | 150 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 541.1573 | 18940.5047 | 30 |  | 30 | 11364.3028 | 0 | 11364.3028 |  |  | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 541.1573 | 5411.5728 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.2.5 | 100 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 541.1573 | 11364.3028 | 15 |  | 15 | 5682.1514 | 0 | 5682.1514 |  |  | 0
(ii) | Final painting and marking of tray nos | 30 | NO | 20% | 541.1573 | 3246.9437 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
23.2.6 | 50 MM WIDE TRAYS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 270.589 | 5682.368 | 15 |  | 15 | 2841.184 | 0 | 2841.184 |  |  | 0
(ii) | Final painting and marking of tray nos | 30 | NO | 20% | 270.589 | 1623.5337 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
24.00 | RUBBER MAT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
24.01 | INSULATING MAT FOR SWITCHGEAR ROOM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of supply | 1 | SET | 80% | 64294.6826 | 51435.746 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/ installation of material/ item | 1 | SET | 10% | 64294.6826 | 6429.4683 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
25.00 | DISPLAY BOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
25.01 | ELECTRIC SHOCK TREATMENT DISPLAY BOARD | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of supply | 50 | NO | 80% | 721.2584 | 28850.3352 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/ installation of material/ item | 50 | NO | 10% | 721.2584 | 3606.2919 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
26.00 | Electrical Lab equipment | 1 | LOT | 90% | 213391.7116 | 192052.5405 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
27.00 | COMMISSIONING SERVICES FOR TESTING | 300 | MDY | 90% | 7190.4507 | 1941421.6871 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
| SCH-6 - MISC ITEMS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.00 | MISC WORKS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.01 | ERECTION OF SUPPORT MATERIAL | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 19.1992 |  | 19.1992 | 348893.0798 | 0 | 348893.0798 |  |  | 0
(ii) | painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.02 | ERECTION OF CHEQUERED PLATES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 10 | MT | 70% | 25960.3882 | 181722.7175 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | painting as applicable | 10 | MT | 20% | 25960.3882 | 51920.7764 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.03 | ERECTION OF INSERT PLATES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.04 | ERECTION OF CANOPY FROM 2 MM THICK GI SHEET | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection | 10 | SQM | 70% | 1211.2146 | 8478.502 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | painting as applicable | 10 | SQM | 20% | 1211.2146 | 2422.4291 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.05 | FABRICATION OF IRREGULAR BEND | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.1 | FOR LADDER TYPE CABLE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.1.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 250 | NO | 70% | 541.1622 | 94703.3898 | 200 |  | 200 | 75762.7118 | 0 | 75762.7118 |  |  | 0
(ii) | Final painting and marking of tray nos | 250 | NO | 20% | 541.1622 | 27058.1114 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.1.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 541.1614 | 56821.9472 | 100 |  | 100 | 37881.2982 | 0 | 37881.2982 |  |  | 0
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 541.1614 | 16234.8421 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.1.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 |  | 100 | 35312.0026 | 0 | 35312.0026 |  |  | 0
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.1.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 |  | 100 | 35312.0026 | 0 | 35312.0026 |  |  | 0
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.2 | FOR PERFORRATED TYPE CABLE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.2.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 577.0117 | 30293.1118 | 50 |  | 50 | 20195.4079 | 0 | 20195.4079 |  |  | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 577.0117 | 8655.1748 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.2.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 125 | NO | 70% | 577.0117 | 50488.5197 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 125 | NO | 20% | 577.0117 | 14425.2913 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.2.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.5.2.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.06 | SUPPLY, INSTALLATION OF DANGER PLATE | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 25 | NO | 80% | 157.8979 | 3157.9575 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 25 | NO | 10% | 157.8979 | 394.7447 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.07 | SUPPLY, INSTALLATION OF FASTENER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 25 | KG | 80% | 352.4298 | 7048.5967 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 25 | KG | 10% | 352.4298 | 881.0746 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.08 | SUPPLY OF HEAVY DUTY ANCHOR FASTENERS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | SET | 80% | 296.1916 | 11847.6624 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 50 | SET | 10% | 296.1916 | 1480.9578 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.09 | INSTALLATION OF MS, CABLE GLAND ADAPTOR | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 100 | KG | 80% | 132.1736 | 10573.8852 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 100 | KG | 10% | 132.1736 | 1321.7357 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.10 | APPLICATION OF MOISTURE SEALING COMPOUND | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 15 | SQM | 80% | 705.33 | 8463.9597 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 15 | SQM | 10% | 705.33 | 1057.995 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.11 | MINOR CIVIL WORK | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.11.1 | CHIPPING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Prorata on completion of actual work | 1 | CUM | 90% | 462.8767 | 416.589 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.11.2 | BREAKING OF CONCRETE/WALL/ FLOOR | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Prorata on completion of actual work | 1 | CUM | 90% | 792.7072 | 713.4365 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
1.11.3 | EARTH EXCAVATION & BACK FILLING | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | Prorata on completion of actual work | 5 | CUM | 90% | 594.6851 | 2676.0831 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.0 | SUPLY OF MISC ITEMS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1 | SUPPLY OF CABLE GLAND & LUG | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1 | DOUBLE COMPRESSION HEAVY DUTY CABLE GLAND | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
| ABOVE (MM) UP TO (MM) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.1 | -- 9 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.2 | 09 11 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.3 | 11 13 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.4 | 13 17 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 187.5888 | 7503.5525 | 0 | 50 | 50 | 0 | 7503.5525 | 7503.5525 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 187.5888 | 937.9441 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.5 | 17 20 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 243.1093 | 9724.3704 | 0 | 50 | 50 | 0 | 9724.3704 | 9724.3704 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 243.1093 | 1215.5463 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.6 | 20 23 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 316.2908 | 12651.6321 | 0 | 50 | 50 | 0 | 12651.6321 | 12651.6321 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 316.2908 | 1581.454 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.7 | 23 26 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 373.4821 | 14939.2825 | 0 | 50 | 50 | 0 | 14939.2825 | 14939.2825 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 373.4821 | 1867.4103 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.8 | 26 30 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 391.9971 | 15679.8851 | 0 | 50 | 50 | 0 | 15679.8851 | 15679.8851 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 391.9971 | 1959.9856 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.9 | 30 33 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 549.3009 | 21972.0374 | 0 | 50 | 50 | 0 | 21972.0374 | 21972.0374 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 549.3009 | 2746.5047 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.10 | 33 36 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 635.1064 | 25404.2555 | 0 | 50 | 50 | 0 | 25404.2555 | 25404.2555 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 635.1064 | 3175.5319 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.11 | 36 39 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 796.6058 | 31864.2316 | 0 | 50 | 50 | 0 | 31864.2316 | 31864.2316 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 796.6058 | 3983.0289 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.12 | 39 42 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50 | 0 | 37651.9226 | 37651.9226 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.13 | 42 46 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50 | 0 | 37651.9226 | 37651.9226 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.14 | 46 50 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 1032.1407 | 41285.6281 | 0 | 50 | 50 | 0 | 41285.6281 | 41285.6281 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1032.1407 | 5160.7035 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.15 | 54 58 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 1179.3578 | 47174.3104 | 0 | 50 | 50 | 0 | 47174.3104 | 47174.3104 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1179.3578 | 5896.7888 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.1.16 | 58 62 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | Nos | 80% | 1768.1889 | 70727.5543 | 0 | 50 | 50 | 0 | 70727.5543 | 70727.5543 |  |  | 0
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1768.1889 | 8840.9443 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2 | AL/CU LUG (HEAVY DUTY TYPE) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.1 | 4 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 7.5743 | 302.9738 | 0 | 50 | 50 | 0 | 302.9738 | 302.9738 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 7.5743 | 37.8717 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.2 | 6 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 9.2575 | 370.3013 | 0 | 50 | 50 | 0 | 370.3013 | 370.3013 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 9.2575 | 46.2877 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.3 | 10 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 10.0991 | 403.9651 | 0 | 50 | 50 | 0 | 403.9651 | 403.9651 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 10.0991 | 50.4956 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.4 | 16 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 13.4655 | 538.6201 | 0 | 50 | 50 | 0 | 538.6201 | 538.6201 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 13.4655 | 67.3275 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.5 | 25 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 20.1859 | 807.4351 | 0 | 50 | 50 | 0 | 807.4351 | 807.4351 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 20.1859 | 100.9294 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.6 | 35 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 26.9186 | 1076.7452 | 0 | 50 | 50 | 0 | 1076.7452 | 1076.7452 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 26.9186 | 134.5931 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.7 | 50 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 43.7505 | 1750.0203 | 0 | 50 | 50 | 0 | 1750.0203 | 1750.0203 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 43.7505 | 218.7525 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.8 | 70 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 64.7656 | 2590.6242 | 0 | 50 | 50 | 0 | 2590.6242 | 2590.6242 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 64.7656 | 323.828 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.9 | 95 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 94.2214 | 3768.8557 | 0 | 50 | 50 | 0 | 3768.8557 | 3768.8557 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 94.2214 | 471.107 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.10 | 120 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 125.3356 | 5013.4246 | 0 | 50 | 50 | 0 | 5013.4246 | 5013.4246 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 125.3356 | 626.6781 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.11 | 150 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 163.195 | 6527.7986 | 0 | 50 | 50 | 0 | 6527.7986 | 6527.7986 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 163.195 | 815.9748 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.12 | 185 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 213.6658 | 8546.6339 | 0 | 50 | 50 | 0 | 8546.6339 | 8546.6339 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 213.6658 | 1068.3292 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.13 | 240 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 328.0731 | 13122.9247 | 0 | 50 | 50 | 0 | 13122.9247 | 13122.9247 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 328.0731 | 1640.3656 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.14 | 300 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 503.038 | 20121.5209 | 0 | 50 | 50 | 0 | 20121.5209 | 20121.5209 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 503.038 | 2515.1901 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.1.2.15 | 400 SQMM | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | NO | 80% | 778.1031 | 31124.1239 | 0 | 50 | 50 | 0 | 31124.1239 | 31124.1239 |  |  | 0
(ii) | On laying/installation of material/item | 50 | NO | 10% | 778.1031 | 3890.5155 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.2 | MS HEXAGONAL HEAD CABLE GLAND | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | KG | 80% | 399.5838 | 15983.354 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 50 | KG | 10% | 399.5838 | 1997.9192 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.3 | GALVANISED MS CONDUIT/ PIPE WITH ACCESORIES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.3.1 | RIGID CONDUIT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.3.2 | 20-30 MM DIAMETER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 35.8395 | 7167.9051 | 250 |  | 250 | 7167.9051 | 0 | 7167.9051 |  |  | 0
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 35.8395 | 895.9881 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.3.3 | 50 MM DIAMETER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 500 | MTR | 80% | 99.0309 | 39612.3414 | 500 |  | 500 | 39612.3414 | 0 | 39612.3414 |  |  | 0
(ii) | On laying/installation of material/item | 500 | MTR | 10% | 99.0309 | 4951.5427 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.3.4 | 75 MM DIAMETER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 205.6063 | 41121.2698 | 250 |  | 250 | 41121.2698 | 0 | 41121.2698 |  |  | 0
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 205.6063 | 5140.1587 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.3.5 | 100-125 MM DIAMETER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 456.0177 | 91203.5348 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 456.0177 | 11400.4418 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.4 | FLEXIBLE CONDUIT (COLD ROLLED ANNEALED) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.4.1 | 20-25 MM DIAMETER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 250 | MTR | 80% | 61.3076 | 12261.5286 | 250 |  | 250 | 12261.5286 | 0 | 12261.5286 |  |  | 0
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 61.3076 | 1532.6911 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.4.2 | 40-50 MM DIAMETER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 100 | MTR | 80% | 190.5158 | 15241.2662 | 100 |  | 100 | 15241.2662 | 0 | 15241.2662 |  |  | 0
(ii) | On laying/installation of material/item | 100 | MTR | 10% | 190.5158 | 1905.1583 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.4.3 | 75-100 MM DIAMETER | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | MTR | 80% | 266.4511 | 10658.0446 | 50 |  | 50 | 10658.0446 | 0 | 10658.0446 |  |  | 0
(ii) | On laying/installation of material/item | 50 | MTR | 10% | 266.4511 | 1332.2556 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5 | MISCELLANEOUS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5.1 | MOISTURE SEALING COMPOUNDS | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 50 | SQM | 80% | 1993.5009 | 79740.0352 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 50 | SQM | 10% | 1993.5009 | 9967.5044 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5.2 | DOL LOCAL STARTER PANEL (3phase,415V,3.7KW) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 4 | NO | 80% | 1621.7701 | 5189.6642 | 0 | 4 | 4 | 0 | 5189.6642 | 5189.6642 |  |  | 0
(ii) | On laying/installation of material/item | 4 | NO | 10% | 1621.7701 | 648.708 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5.3 | DOL LOCAL STARTER PANEL (3phase,415V,5.5KW) | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 1579.2263 | 2526.762 | 0 | 2 | 2 | 0 | 2526.762 | 2526.762 |  |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 1579.2263 | 315.8453 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5.4 | JOINT KIT 6.6KV 1CX400AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 3926.407 | 6282.2512 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 3926.407 | 785.2814 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5.5 | JOINT KIT 6.6KV 3CX150AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 12803.3666 | 20485.3865 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 12803.3666 | 2560.6733 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5.6 | JOINT KIT 6.6KV 3CX240AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 14510.6884 | 23217.1014 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 14510.6884 | 2902.1377 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
2.5.7 | JOINT KIT 33KV 3CX120AL UNARMOURED | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(i) | On completion of Supply | 2 | NO | 80% | 16217.7008 | 25948.3212 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 16217.7008 | 3243.5402 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.00 | COMMISSIONING SUPPORT | [5 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.1 | SPECIALISED SKILLED TECHNICAL MANPOWER | 30 | MD | 90% | 7298.0014 | 197046.0391 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
3.2 | SUPPORT SERVICE BY UN-SKILLED MANPOWER | 60 | MD | 90% | 973.062 | 52545.3505 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0
0
90% OF GROSS VALUE | [5 empty] | 40431127.4725 | 11: 5984367.2628; 12: 782079.6003; 14: 6766446.8631; 15: 0; 17: 0
100% OF GROSS VALUE | [5 empty] | 44923474.9694 | 12: 868977.3337
| GROSS BILL VALUE | [5 empty] | 12: 868977.3337
| ADD: CGST @ 9% OF GROSS BILL VALUE | [5 empty] | 12: 78208
| ADD: SGST @ 9% OF GROSS BILL VALUE | [5 empty] | 12: 78208
| NET INVOICE VALUE | [5 empty] | 12: 1025393.3337
| LESS: FOR I.T. @2.00% OF GROSS BILL VALUE & SERVICE TAX | [5 empty] | 12: 17380
| LESS: S.D @10.00% OF GROSS BILL VALUE (AGAINST CL 4.2.2) | [5 empty] | 12: 86898
| LESS: GST +TDS @ 2.00% OF GROSS BILL VALUE . | [5 empty] | 12: 17380
| RETENTION @5% AGAINST TRIAL RUN OF UNIT | [5 empty] | 12: 43449
| RETENTION @5% AGAINST PG TEST OF UNIT | [5 empty] | 12: 43449
| WITHELD FOR PENDING JOBS | [5 empty] | 12: 0
| NET VALUE PAYABLE | [5 empty] | 12: 816837.3337

## Calc1 (hidden)
SL NO | EQUIPMENT/ITEM DESCRIPTION | BBU QTY |  | % BREAKUP OF UNIT RATE | UNIT RATE (Rs) | ALLOTED AMOUNT (Rs) | MEASUREMENT QUANTITY |  |  | CLAIMED AMOUNT | [8 empty] | 3826611.6883
|  | QTY | UOM |  |  |  | UP TO PREV | PRESENT BILL | CUM | UP TO PREV | PRESENT BILL | CUMULATIVE | Alloted | Present | Cumulative |  |  |  | NON
1 | 2 | 3 | 4 | 5 | 6 | 7 = 3x5x6 | 8 | 9 | 10 | 11 | 12 | 14 |  |  |  | SCOPE | PRESENT | CUM | EXECUTABLE
0 | SCH-3 TRANSFORMER & BUS DUCT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.00 | BUS DUCTS & ASOCIATED EQUIPMENT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.01 | SEGREGATED PHASE BUSDUCT (6.6 KV/ 4000 A) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1600950.5289 | 0 | 0 | 1600950.5289 | 0 | 0
(i) | Pre-assembly, alingnment, erection, welding etc | 300 | MTR | 65% | 5336.5018 | 1040617.8438 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | SPBD
(ii) | Pre-commissioning checks & tests | 300 | MTR | 15% | 5336.5018 | 240142.5793 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 300 | MTR | 10% | 5336.5018 | 160095.0529 | 0 | 0 | 0 | 0 | 0 | 0
1.02 | COMMON CHAMBER FOR GENERATOR PH AND N-SIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 36055.4931 | 0 | 0 | 1808227.4418 | 0 | 20191.9425
(i) | Pre-assembly, alingnment, erection, welding etc | 1 | SET | 65% | 36055.4931 | 23436.0705 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | IPBD
(ii) | Pre-commissioning checks & tests | 1 | SET | 15% | 36055.4931 | 5408.324 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 10% | 36055.4931 | 3605.5493 | 0 | 0 | 0 | 0 | 0 | 0
1.03 | MAIN RUN ISOLATED PHASE BUSDUCT (21 KV, 12500A) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 856341.0125 | 0 | 0
(i) | Pre-assembly, alingnment, erection, welding etc | 125 | MTR | 65% | 6850.7281 | 556621.6581 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-commissioning checks & tests | 125 | MTR | 15% | 6850.7281 | 128451.1519 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 125 | MTR | 10% | 6850.7281 | 85634.1012 | 0 | 0 | 0 | 0 | 0 | 0
1.04 | TAP OFF IP BUS DUCT (21 KV, 1500 AMP) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 540820.0203 | 0 | 0
(i) | Pre-assembly, alingnment, erection, welding etc | 100 | MTR | 65% | 5408.2002 | 351533.0132 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-commissioning checks & tests | 100 | MTR | 15% | 5408.2002 | 81123.003 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 100 | MTR | 10% | 5408.2002 | 54082.002 | 0 | 0 | 0 | 0 | 0 | 0
1.05 | SPVT CUBICLE FOR IP BUSDUCT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 57690.0266 | 0 | 0
(i) | Placenment ,Alingnment & Coupling | 1 | SET | 70% | 57690.0266 | 40383.0186 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 10% | 57690.0266 | 5769.0027 | 0 | 0 | 0 | 0 | 0 | 0
1.06 | NG CUBICLE (WITH NGT & NGR ) FOR IP BUSDUCT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 28845.6321 | 0 | 0
(i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
1.07 | HOT AIR BLOWING EQUIPMENT WITH PIPINGS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 28845.6321 | 0 | 20191.9425
(i) | Placenment ,Alingnment & coupling as Applicable | 1 | SET | 70% | 28845.6321 | 20191.9425 | 1 | 0 | 1 | 20191.9425 | 0 | 20191.9425
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 10% | 28845.6321 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
2.00 | 415V LV BUS-DUCT SET FOR DTT AND PMCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 124333.7464 | 5538.8638 | 56830.9201
2.01 | BUSDUCT FOR UNIT PMCC #1 DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 18751.4555 | 1875.1455 | 15001.1644 | LT DUCT
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 | 0 | 2 | 13126.0188 | 0 | 13126.0188
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2 | 0 | 1875.1455 | 1875.1455
(iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 0 | 0 | 0 | 0 | 0
2.02 | BUSDUCT FOR ESP PMCC #1DB-1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 18751.4555 | 1875.1455 | 15001.1644
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 9375.7277 | 13126.0188 | 2 | 0 | 2 | 13126.0188 | 0 | 13126.0188
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 2 | 2 | 0 | 1875.1455 | 1875.1455
(iii) | Charging | 2 | SET | 10% | 9375.7277 | 1875.1455 | 0 | 0 | 0 | 0 | 0 | 0
2.03 | BUSDUCT FOR ESP PMCC #1DB-2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17885.7276 | 1788.5728 | 14308.5821
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 | 0 | 2 | 12520.0093 | 0 | 12520.0093
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 2 | 2 | 0 | 1788.5728 | 1788.5728
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0
2.04 | BUSDUCT FOR STATION PMCC #0DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17885.7276 | 0 | 12520.0093
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 2 | 0 | 2 | 12520.0093 | 0 | 12520.0093
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0
2.05 | BUSDUCT FOR COOLING TOWER PMCC #1DC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17885.7276 | 0 | 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8942.8638 | 12520.0093 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 10% | 8942.8638 | 1788.5728 | 0 | 0 | 0 | 0 | 0 | 0
2.06 | BUSDUCT FOR PTP PMCC #1DD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16586.8264 | 0 | 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0
2.07 | BUSDUCT FOR ETP PMCC #1DE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16586.8264 | 0 | 0
(i) | Pre-assembly, alingnment, erection, Coupling | 2 | SET | 70% | 8293.4132 | 11610.7784 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-commissioning checks & tests | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 10% | 8293.4132 | 1658.6826 | 0 | 0 | 0 | 0 | 0 | 0
3.00 | POWER TRANSFORMERS AND DTT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.01 | GENERATOR TRANSFORMERS - 315 MVA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 951874.9193 | 0 | 333156.2218 | 951874.9193 | 0 | 333156.2218
(i) | Placement on Foundation and alignment | 1 | NO | 35% | 951874.9193 | 333156.2218 | 1 | 0 | 1 | 333156.2218 | 0 | 333156.2218 |  |  |  | GT
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 951874.9193 | 190374.9839 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Completion of Oil filteration | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 | 0 | 0 | 0 | 0 | 0
(iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 951874.9193 | 142781.2379 | 0 | 0 | 0 | 0 | 0 | 0
(v) | Charging | 1 | NO | 10% | 951874.9193 | 95187.4919 | 0 | 0 | 0 | 0 | 0 | 0
3.02 | STATION TRANSFORMER - 37.5/30 MVA, 220/6.9 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 633718.9956 | 0 | 348545.4476 | 717482.5924 | 0 | 411823.4104
(i) | Placement on Foundation and alignment | 1 | NO | 35% | 633718.9956 | 221801.6484 | 1 | 0 | 1 | 221801.6484 | 0 | 221801.6484 |  |  |  | ST
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 1 | NO | 20% | 633718.9956 | 126743.7991 | 1 | 0 | 1 | 126743.7991 | 0 | 126743.7991
(iii) | Completion of Oil filteration | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 | 0 | 0 | 0 | 0 | 0
(iv) | Pre-commissioning checks & tests | 1 | NO | 15% | 633718.9956 | 95057.8493 | 0 | 0 | 0 | 0 | 0 | 0
(v) | Charging | 1 | NO | 10% | 633718.9956 | 63371.8996 | 0 | 0 | 0 | 0 | 0 | 0
3.03 | UAT - 37.5/30 MVA,16.5/6.9 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 953606.9939 | 0 | 0 | 1121134.1876 | 0 | 0
(i) | Placement on Foundation and alignment | 2 | NO | 35% | 476803.4969 | 333762.4479 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | UT
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 20% | 476803.4969 | 190721.3988 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Completion of Oil filteration | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 | 0 | 0 | 0 | 0 | 0
(iv) | Pre-commissioning checks & tests | 2 | NO | 15% | 476803.4969 | 143041.0491 | 0 | 0 | 0 | 0 | 0 | 0
(v) | Charging | 2 | NO | 10% | 476803.4969 | 95360.6994 | 0 | 0 | 0 | 0 | 0 | 0
3.04 | 2500KVA DTT 6.6/0.433 KV | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 57690.8517 | 0 | 0 | 115381.4972 | 0 | 46152.5164 | 115381.7034
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 70% | 28845.4259 | 121150.7886 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2500KVA
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging of Transformer | 6 | NO | 10% | 28845.4259 | 17307.2555 | 0 | 0 | 0 | 0 | 0 | 0
3.05 | 2000KVA DTT 6.6/0.433 KV | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 57690.6454 | 0 | 46152.5164
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 28845.3227 | 40383.4518 | 2 | 0 | 2 | 40383.4518 | 0 | 40383.4518
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 28845.3227 | 5769.0645 | 2 | 0 | 2 | 5769.0645 | 0 | 5769.0645
(iii) | Charging of Transformer | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 | 0 | 0 | 0 | 0 | 0
3.06 | 1600KVA DTT 6.6/0.433 KV | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 207683.3307 | 0 | 83073.3323 | 253835.7852 | 0 | 83073.3323 | 77881.249
(i) | Placement,Aliggnment & Coupling as Applicable | 11 | NO | 70% | 25960.4163 | 199895.2058 | 4 | 0 | 4 | 72689.1658 | 0 | 72689.1658 |  |  |  | DTT
(ii) | Pre-Commissioning Checks ,Testing | 11 | NO | 10% | 25960.4163 | 28556.458 | 4 | 0 | 4 | 10384.1665 | 0 | 10384.1665
(iii) | Charging of Transformer | 11 | NO | 10% | 25960.4163 | 28556.458 | 0 | 0 | 0 | 0 | 0 | 0
3.07 | 1250KVA DTT 6.6/0.433 KV | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 46152.1451
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0
3.08 | 1000KVA DTT 6.6/0.433 KV | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 46152.1451
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0
3.09 | 630KVA DTT, 6.6/0.415KV | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 46152.1451
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 70% | 23076.0725 | 32306.5015 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging of Transformer | 2 | NO | 10% | 23076.0725 | 4615.2145 | 0 | 0 | 0 | 0 | 0 | 0
3.10 | 500KVA DTT 6.6/0.433 KV | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 46152.4545 | 0 | 0 |  |  |  | 46152.4545
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | NO | 70% | 23076.2272 | 64613.4363 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging of Transformer | 4 | NO | 10% | 23076.2272 | 9230.4909 | 0 | 0 | 0 | 0 | 0 | 0
3.11 | 33/6.9KV 2MVA OIL FILLED RAW WATER TRF | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 57690.6454 | 0 | 0 | 98661.9135 | 0 | 0
(i) | Placement on Foundation and alignment | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | RW
(ii) | Fixing of fitting, piping ,radiator banks, accesories | 2 | NO | 30% | 28845.3227 | 17307.1936 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Completion of Oil filteration | 2 | NO | 20% | 28845.3227 | 11538.1291 | 0 | 0 | 0 | 0 | 0 | 0
(iv) | Pre-commissioning checks & tests | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 | 0 | 0 | 0 | 0 | 0
(v) | Charging | 2 | NO | 10% | 28845.3227 | 5769.0645 | 0 | 0 | 0 | 0 | 0 | 0
3.12 | 6.6 KV NEUTRAL GROUNDING RESISTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 102428.1701 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 70% | 20485.634 | 71699.7191 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 10% | 20485.634 | 10242.817 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging of Transformer | 5 | NO | 10% | 20485.634 | 10242.817 | 0 | 0 | 0 | 0 | 0 | 0
4.00 | HVR TRANSFORMER(95 KVp,1200mA)COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 237253.9938 | 0 | 0
(i) | Test of HVR including Interlock/Protection, OCC/SCC | 28 | NO | 50% | 8473.3569 | 118626.9969 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | HVR
(ii) | Charging (Field-Charging) | 28 | NO | 40% | 8473.3569 | 94901.5975 | 0 | 0 | 0 | 0 | 0 | 0
5.00 | BUS DUCTS & EQUIPMENT SUPPORT STRUCTURE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 259629.625 | 0 | 0
(i) | Pre-assembly, alignment, erection including welding | 30 | MT | 70% | 8654.3208 | 181740.7375 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 173086.4167
(ii) | Pre-Commissioning Checks /Testing & charging | 30 | MT | 10% | 8654.3208 | 25962.9625 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 30 | MT | 10% | 8654.3208 | 25962.9625 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36398.9377 | 0 | 0
6 | GENERATOR CIRCUIT BREAKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 36398.9377 | 0 | 0 | GCB
(i) | Placement, alignment, installation, internal wiring | 1 | NO | 60% | 36398.9377 | 21839.3626 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-commissioning checks/testing | 1 | NO | 20% | 36398.9377 | 7279.7875 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 10% | 36398.9377 | 3639.8938 | 0 | 0 | 0 | 0 | 0 | 0
7.0 | UNLOADING AND SHIFTING OF TRANSFORMERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
7.1 | GENERATOR TRANSFORMERS (GT) - 315 MVA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
7.1.1 | UNLOADING OF GT FROM TRAILER | 1 | NO | 90% | 214172.0425 | 192754.8382 | 0 | 0 | 0 | 0 | 0 | 0 | 214172.0425 | 0 | 0 |  |  |  | 214172.0425
7.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 1 | NO | 90% | 160628.7225 | 144565.8502 | 0 | 0 | 0 | 0 | 0 | 0 | 160628.7225 | 0 | 0 |  |  |  | 160628.7225
8.1 | STATION /UNIT TRANSFORMER (ST/UT) (37.5/30 MVA) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
8.1.1 | UNLOADING OF ST / UT FROM TRAILER | 1 | NO | 90% | 84371.0296 | 75933.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 84371.0296 | 0 | 0 |  |  |  | 84371.0296
8.1.2 | Dragging/Shifting (Approx 10-15Mtr) and Placement | 3 | NO | 90% | 63277.9628 | 170850.4996 | 1 | 0 | 1 | 56950.1665 | 0 | 56950.1665 | 189833.8885 | 0 | 56950.1665
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| SCH-4-CABLING & EQUIPMENT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.00 | CABLE TRAY SUPPORT SYSTEM WITH ACCESORIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.01 | CHANNEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.01.01 | SINGLE(SC1) | 6018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 658322.8834 | 0 | 156671.6573 | 3916995.243 | 100504.3519 | 1124201.4203 | 63666.3207
(i) | Fabrication and erection complete as applicable | 6600 | RM | 70% | 109.3923 | 505392.4429 | 2046 | 0 | 2046 | 156671.6573 | 0 | 156671.6573
(ii) | Final painting and marking of tray nos | 6600 | RM | 20% | 109.3923 | 144397.8408 | 0 | 0 | 0 | 0 | 0 | 0
1.01.02 | DOUBLE(DC1) | 5030 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 641934.0426 | 53600.8545 | 257284.1014 |  |  |  | 59981.9086
(i) | Fabrication and erection complete as applicable | 5500 | RM | 70% | 127.6211 | 491341.1658 | 2280 | 600 | 2880 | 203683.2469 | 53600.8545 | 257284.1014
(ii) | Final painting and marking of tray nos | 5500 | RM | 20% | 127.6211 | 140383.1902 | 0 | 0 | 0 | 0 | 0 | 0
1.02 | CANTILEVER ARM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.02.01 | 600 MM Cantilever Arm | 9780 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 499287.1059 | 0 | 185006.804 |  |  |  | 113335.1099
(i) | Fabrication and erection complete as applicable | 12000 | NOS | 70% | 51.0519 | 428835.5511 | 5177 | 0 | 5177 | 185006.804 | 0 | 185006.804
(ii) | Final painting and marking of tray nos | 12000 | NOS | 20% | 51.0519 | 122524.4432 | 0 | 0 | 0 | 0 | 0 | 0
1.02.02 | 300 MM Cantilever Arm | 6220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 206421.2461 | 0 | 24392.2212 |  |  |  | 9292.2747
(i) | Fabrication and erection complete as applicable | 6500 | NOS | 70% | 33.1867 | 150999.4646 | 1050 | 0 | 1050 | 24392.2212 | 0 | 24392.2212
(ii) | Final painting and marking of tray nos | 6500 | NOS | 20% | 33.1867 | 43142.7042 | 0 | 0 | 0 | 0 | 0 | 0
1.02.03 | 150 MM Cantilever Arm | 1082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 22100.9102 | 0 | 10366.1848 |  |  |  | 8538.0596
(i) | Fabrication and erection complete as applicable | 1500 | NOS | 70% | 20.426 | 21447.2789 | 725 | 0 | 725 | 10366.1848 | 0 | 10366.1848
(ii) | Final painting and marking of tray nos | 1500 | NOS | 20% | 20.426 | 6127.794 | 0 | 0 | 0 | 0 | 0 | 0
1.02.04 | 100 MM Cantilever Arm | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10212.9899
(i) | Fabrication and erection complete as applicable | 500 | NOS | 70% | 20.426 | 7149.093 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 500 | NOS | 20% | 20.426 | 2042.598 | 0 | 0 | 0 | 0 | 0 | 0
2 | LADDER TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.1 | 600 MM Ladder Type Cable Tray | 14000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 812595.809 | 40629.7904 | 208227.6761 |  |  |  | 626279.1985
(i) | Fabrication and erection complete as applicable | 24790 | MTR | 70% | 58.0426 | 1007212.5052 | 4125 | 1000 | 5125 | 167597.8856 | 40629.7904 | 208227.6761
(ii) | Final painting and marking of tray nos | 24790 | MTR | 20% | 58.0426 | 287775.0015 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | 450 MM Ladder Type Cable Tray | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50360.7336
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 50.3607 | 35252.5135 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 50.3607 | 10072.1467 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | 300 MM Ladder Type Cable Tray | 3500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 152361.6489 | 0 | 68562.742 |  |  |  | 67474.4445
(i) | Fabrication and erection complete as applicable | 5050 | MTR | 70% | 43.5319 | 153885.2654 | 2250 | 0 | 2250 | 68562.742 | 0 | 68562.742
(ii) | Final painting and marking of tray nos | 5050 | MTR | 20% | 43.5319 | 43967.2187 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | 150 MM Ladder Type Cable Tray | 1050 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37642.2421 | 6273.707 | 21957.9746 |  |  |  | 111134.2387
(i) | Fabrication and erection complete as applicable | 4150 | MTR | 70% | 35.8498 | 104143.5366 | 625 | 250 | 875 | 15684.2676 | 6273.707 | 21957.9746
(ii) | Final painting and marking of tray nos | 4150 | MTR | 20% | 35.8498 | 29755.2962 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | 100 MM Ladder Type Cable Tray | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17925.0226 | 0 | 0 |  |  |  | 17925.0226
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 35.85 | 25095.0316 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 35.85 | 7170.009 | 0 | 0 | 0 | 0 | 0 | 0
2.6 | 50 MM Ladder Type Cable Tray | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8962.3566 | 0 | 0 |  |  |  | 0
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 17.9247 | 6273.6496 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 17.9247 | 1792.4713 | 0 | 0 | 0 | 0 | 0 | 0
3 | CABLE TRAY 90 DEG BEND HORIZONTAL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | 600 MM Tray Bend 90Deg Horizontal | 132 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 22872.1655 | 0 | 16010.5158 |  |  |  | 46437.4268
(i) | Fabrication and erection complete as applicable | 400 | NO | 70% | 173.274 | 48516.7146 | 132 | 0 | 132 | 16010.5158 | 0 | 16010.5158
(ii) | Final painting and marking of tray nos | 400 | NO | 20% | 173.274 | 13861.9185 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2 | 450 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1587.8897
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3 | 300 MM Tray Bend 90Deg Horizontal | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1298.2669 | 0 | 908.7869 |  |  |  | 16011.9589
(i) | Fabrication and erection complete as applicable | 120 | NO | 70% | 144.2519 | 12117.1581 | 9 | 0 | 9 | 908.7869 | 0 | 908.7869
(ii) | Final painting and marking of tray nos | 120 | NO | 20% | 144.2519 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4 | 150 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1374.3972
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0
3.1.5 | 100 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1374.3972
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0
3.1.6 | 50 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 682.5574
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 68.2557 | 477.7902 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 68.2557 | 136.5115 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | CABLE TRAY 90 DEG BEND VERTICAL-INSIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17327.5528 | 0 | 6064.6435 |  |  |  | 17327.5528
(i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 173.2755 | 24258.5739 | 50 | 0 | 50 | 6064.6435 | 0 | 6064.6435
(ii) | Final painting and marking of tray nos | 200 | NO | 20% | 173.2755 | 6931.0211 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1587.8897
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0
3.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | 125 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18031.3563 | 0 | 0 |  |  |  | -7212.5425
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 144.2509 | 7573.1697 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 144.2509 | 2163.7628 | 0 | 0 | 0 | 0 | 0 | 0
3.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 686.8892
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | CABLE TRAY 90 DEG BEND VERTICAL-OUTSIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17327.3465 | 0 | 6064.5713 |  |  |  | 8663.6733
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 173.2735 | 18193.7138 | 50 | 0 | 50 | 6064.5713 | 0 | 6064.5713
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 173.2735 | 5198.204 | 0 | 0 | 0 | 0 | 0 | 0
3.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1587.8897
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0
3.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | 125 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18030.8407 | 0 | 0 |  |  |  | -10818.5044
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 | 0 | 0 | 0 | 0 | 0
3.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1374.3972
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | TEES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.4.1 | 600 MM Tee-Joint | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11565.8831 | 0 | 8096.1182 |  |  |  | 34697.6494
(i) | Fabrication and erection complete as applicable | 200 | NO | 70% | 231.3177 | 32384.4727 | 50 | 0 | 50 | 8096.1182 | 0 | 8096.1182
(ii) | Final painting and marking of tray nos | 200 | NO | 20% | 231.3177 | 9252.7065 | 0 | 0 | 0 | 0 | 0 | 0
3.4.2 | 450 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1878.1159
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 | 0 | 0 | 0 | 0 | 0
3.4.3 | 300 MM Tee-Joint | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 866.3467 | 0 | 0 |  |  |  | 2599.0401
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 173.2693 | 2425.7708 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 173.2693 | 693.0774 | 0 | 0 | 0 | 0 | 0 | 0
3.4.4 | 150 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2061.2863
(i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 137.4191 | 1442.9004 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 15 | NO | 20% | 137.4191 | 412.2573 | 0 | 0 | 0 | 0 | 0 | 0
3.4.5 | 100 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 686.8892
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 | 0 | 0 | 0 | 0 | 0
3.4.6 | 50 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 341.5881
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 68.3176 | 239.1117 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 68.3176 | 68.3176 | 0 | 0 | 0 | 0 | 0 | 0
3.5.0 | CROSSES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.5.1 | 600 MM Cross | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2343.0346 | 0 | 0 |  |  |  | 21087.3118
(i) | Fabrication and erection complete as applicable | 90 | NO | 70% | 260.3372 | 16401.2425 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 90 | NO | 20% | 260.3372 | 4686.0693 | 0 | 0 | 0 | 0 | 0 | 0
3.5.2 | 450 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2159.6786
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 215.9679 | 1511.775 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 215.9679 | 431.9357 | 0 | 0 | 0 | 0 | 0 | 0
3.5.3 | 300 MM Cross | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1011.5629 | 0 | 0 |  |  |  | 2023.1258
(i) | Fabrication and erection complete as applicable | 15 | NO | 70% | 202.3126 | 2124.2821 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 15 | NO | 20% | 202.3126 | 606.9377 | 0 | 0 | 0 | 0 | 0 | 0
3.5.4 | 150 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 866.3467
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 | 0 | 0 | 0 | 0 | 0
3.5.5 | 100 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 866.3467
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 173.2693 | 606.4427 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 173.2693 | 173.2693 | 0 | 0 | 0 | 0 | 0 | 0
3.5.6 | 50 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 431.3169
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 86.2634 | 301.9218 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 86.2634 | 86.2634 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | REDUCERS LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.6.1 | 600 MM-450 MM Reducer LHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7938.211
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 158.7642 | 5556.7477 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 158.7642 | 1587.6422 | 0 | 0 | 0 | 0 | 0 | 0
3.6.2 | 600 MM-300 MM Reducer LHS | 27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3894.9957 | 0 | 0 |  |  |  | -288.5182
(i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 144.2591 | 2524.5343 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 25 | NO | 20% | 144.2591 | 721.2955 | 0 | 0 | 0 | 0 | 0 | 0
3.6.3 | 450 MM -300 MM Reducer LHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5496.9698
(i) | Fabrication and erection complete as applicable | 40 | NO | 70% | 137.4242 | 3847.8789 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 40 | NO | 20% | 137.4242 | 1099.394 | 0 | 0 | 0 | 0 | 0 | 0
3.6.4 | 300 MM -150 MM Reducer LHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1374.3972
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0
3.7 | REDUCERS RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.7.1 | 600 MM-450 MM Reducer RHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3175.1606
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 158.758 | 2222.6125 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 158.758 | 635.0321 | 0 | 0 | 0 | 0 | 0 | 0
3.7.2 | 600 MM-300 MM Reducer RHS | 27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3894.6616 | 0 | 0 |  |  |  | -2452.1943
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
3.7.3 | 450 MM -300 MM Reducer RHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1374.3972
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 137.4397 | 962.078 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 137.4397 | 274.8794 | 0 | 0 | 0 | 0 | 0 | 0
3.7.4 | 300 MM -150 MM Reducer RHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 686.8892
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 137.3778 | 480.8224 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 137.3778 | 137.3778 | 0 | 0 | 0 | 0 | 0 | 0
3.8 | CABLE TRAY COVER WITH FIXING HARDWARES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.8.1 | 600 MM wide Tray Cover | 70 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4062.9927 | 0 | 0 |  |  |  | 24958.384
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 58.0428 | 20314.9637 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 58.0428 | 5804.2753 | 0 | 0 | 0 | 0 | 0 | 0
3.8.2 | 450 MM wide Tray Cover | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14510.6884
(i) | Fabrication and erection complete as applicable | 250 | MTR | 70% | 58.0428 | 10157.4819 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 250 | MTR | 20% | 58.0428 | 2902.1377 | 0 | 0 | 0 | 0 | 0 | 0
3.8.3 | 300 MM wide Tray Cover | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2467.6153 |  |  |  | 5035.9496
| Fabrication and erection complete as applicable | 100 | MTR | 70% | 50.3595 | 3525.1647 | 70 | 0 | 70 | 2467.6153 | 0 | 2467.6153
| Final painting and marking of tray nos | 100 | MTR | 20% | 50.3595 | 1007.1899 | 0 | 0 | 0 | 0 | 0 | 0
3.8.4 | 150 MM wide Tray Cover | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4353.3922
(i) | Fabrication and erection complete as applicable | 100 | MTR | 70% | 43.5339 | 3047.3745 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 100 | MTR | 20% | 43.5339 | 870.6784 | 0 | 0 | 0 | 0 | 0 | 0
3.8.5 | 100 MM wide Tray Cover | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2176.3867
(i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 43.5277 | 1523.4707 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 43.5277 | 435.2773 | 0 | 0 | 0 | 0 | 0 | 0
3.8.6 | 50 MM wide Tray Cover | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1088.5027
(i) | Fabrication and erection complete as applicable | 50 | MTR | 70% | 21.7701 | 761.9519 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 50 | MTR | 20% | 21.7701 | 217.7005 | 0 | 0 | 0 | 0 | 0 | 0
4.00 | PERFORATED TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
4.10 | 600 MM Perforated Cable Tray | 5250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 376423.3085 | 0 | 82813.1279 |  |  |  | 161324.2751
(i) | Fabrication and erection complete as applicable | 7500 | MTR | 70% | 71.6997 | 376423.3085 | 1650 | 0 | 1650 | 82813.1279 | 0 | 82813.1279
(ii) | Final painting and marking of tray nos | 7500 | MTR | 20% | 71.6997 | 107549.5167 | 0 | 0 | 0 | 0 | 0 | 0
4.20 | 450 MM Perforated Cable Tray | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6811.4343 |  |  |  | 32435.4016
(i) | Fabrication and erection complete as applicable | 500 | MTR | 70% | 64.8708 | 22704.7811 | 150 | 0 | 150 | 6811.4343 | 0 | 6811.4343
(ii) | Final painting and marking of tray nos | 500 | MTR | 20% | 64.8708 | 6487.0803 | 0 | 0 | 0 | 0 | 0 | 0
4.30 | 300 MM Perforated Cable Tray | 2450 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 142204.3129 | 0 | 36058.9508 |  |  |  | 60944.7055
(i) | Fabrication and erection complete as applicable | 3500 | MTR | 70% | 58.0426 | 142204.3129 | 887.5 | 0 | 887.5 | 36058.9508 | 0 | 36058.9508
(ii) | Final painting and marking of tray nos | 3500 | MTR | 20% | 58.0426 | 40629.8037 | 0 | 0 | 0 | 0 | 0 | 0
4.40 | 150 MM Perforated Cable Tray | 1050 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45708.4518 | 0 | 7618.0753 |  |  |  | 19589.3365
(i) | Fabrication and erection complete as applicable | 1500 | MTR | 70% | 43.5319 | 45708.4518 | 250 | 0 | 250 | 7618.0753 | 0 | 7618.0753
(ii) | Final painting and marking of tray nos | 1500 | MTR | 20% | 43.5319 | 13059.5577 | 0 | 0 | 0 | 0 | 0 | 0
4.50 | 100 MM Perforated Cable Tray | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 30472.4456 | 0 | 0 |  |  |  | 13059.6195
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 43.5321 | 30472.4456 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 43.5321 | 8706.413 | 0 | 0 | 0 | 0 | 0 | 0
4.60 | 50 MM Perforated Cable Tray | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 14937.5498 | 0 | 0 |  |  |  | 6401.807
(i) | Fabrication and erection complete as applicable | 1000 | MTR | 70% | 21.3394 | 14937.5498 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 1000 | MTR | 20% | 21.3394 | 4267.8714 | 0 | 0 | 0 | 0 | 0 | 0
5.00 | CABLE TRAY ACCESSORIES (PERFORATED-TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.10 | HORIZONTAL 90 DEG BEND PERFORATED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.1.1 | 600 MM Tray Bend 90Deg Horizontal | 70 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 13144.9278 | 0 | 8807.1016 |  |  |  | 30045.5492
(i) | Fabrication and erection complete as applicable | 230 | NO | 70% | 187.7847 | 30233.3339 | 67 | 0 | 67 | 8807.1016 | 0 | 8807.1016
(ii) | Final painting and marking of tray nos | 230 | NO | 20% | 187.7847 | 8638.0954 | 0 | 0 | 0 | 0 | 0 | 0
5.1.2 | 450 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1732.6934
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0
5.1.3 | 300 MM Tray Bend 90Deg Horizontal | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 793.8565 | 0 | 555.6995 |  |  |  | 4763.1388
(i) | Fabrication and erection complete as applicable | 35 | NO | 70% | 158.7713 | 3889.8967 | 5 | 0 | 5 | 555.6995 | 0 | 555.6995
(ii) | Final painting and marking of tray nos | 35 | NO | 20% | 158.7713 | 1111.399 | 0 | 0 | 0 | 0 | 0 | 0
5.1.4 | 150 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1442.4673
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
5.1.5 | 100 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 721.543
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
5.1.6 | 50 MM Tray Bend 90Deg Horizontal | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 362.628
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 72.5256 | 253.8396 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 72.5256 | 72.5256 | 0 | 0 | 0 | 0 | 0 | 0
5.20 | VERTICAL 90 DEG BEND PERFORATED (INSIDE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.2.1 | 600 MM Tray Bend 90Deg Vertical-Inside | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 938.9342 | 0 | 2629.0157 |  |  |  | 17839.7493
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 187.7868 | 13145.0784 | 20 | 0 | 20 | 2629.0157 | 0 | 2629.0157
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 187.7868 | 3755.7367 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2 | 450 MM Tray Bend 90Deg Vertical-Inside | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 866.3467 | 0 | 0 |  |  |  | 866.3467
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0
5.2.3 | 300 MM Tray Bend 90Deg Vertical-Inside | 16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2540.2275 | 0 | 0 |  |  |  | 13336.1945
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 158.7642 | 11113.4954 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 158.7642 | 3175.2844 | 0 | 0 | 0 | 0 | 0 | 0
5.2.4 | 150 MM Tray Bend 90Deg Vertical-Inside | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1442.4673
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
5.30 | VERTICAL 90 DEG BEND PERFORATED (OUTSIDE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.3.1 | 600 MM Tray Bend 90Deg Vertical-Outside | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1690.0511 | 0 | 3286.2105 |  |  |  | 18966.1294
(i) | Fabrication and erection complete as applicable | 110 | NO | 70% | 187.7835 | 14459.3264 | 25 | 0 | 25 | 3286.2105 | 0 | 3286.2105
(ii) | Final painting and marking of tray nos | 110 | NO | 20% | 187.7835 | 4131.2361 | 0 | 0 | 0 | 0 | 0 | 0
5.3.2 | 450 MM Tray Bend 90Deg Vertical-Outside | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4331.7335
(i) | Fabrication and erection complete as applicable | 25 | NO | 70% | 173.2693 | 3032.2134 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 25 | NO | 20% | 173.2693 | 866.3467 | 0 | 0 | 0 | 0 | 0 | 0
5.3.3 | 300 MM Tray Bend 90Deg Vertical-Outside | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 793.8417 | 0 | 0 |  |  |  | 8732.259
(i) | Fabrication and erection complete as applicable | 60 | NO | 70% | 158.7683 | 6668.2705 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 60 | NO | 20% | 158.7683 | 1905.2202 | 0 | 0 | 0 | 0 | 0 | 0
5.3.4 | 150 MM Tray Bend 90Deg Vertical-Outside | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2884.9345
(i) | Fabrication and erection complete as applicable | 20 | NO | 70% | 144.2467 | 2019.4542 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 20 | NO | 20% | 144.2467 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0
5.40 | TEES PERFORATED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.4.1 | 600 MM Tee-Joint | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1820.6704 | 0 | 3540.1925 |  |  |  | 24477.9024
(i) | Fabrication and erection complete as applicable | 130 | NO | 70% | 202.2967 | 18409.001 | 25 | 0 | 25 | 3540.1925 | 0 | 3540.1925
(ii) | Final painting and marking of tray nos | 130 | NO | 20% | 202.2967 | 5259.7146 | 0 | 0 | 0 | 0 | 0 | 0
5.4.2 | 450 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1878.1159
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 187.8116 | 1314.6811 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 187.8116 | 375.6232 | 0 | 0 | 0 | 0 | 0 | 0
5.4.3 | 300 MM Tee-Joint | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 866.3467 | 0 | 0 |  |  |  | 866.3467
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0
5.4.4 | 150 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1587.8897
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 158.789 | 1111.5228 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 158.789 | 317.5779 | 0 | 0 | 0 | 0 | 0 | 0
5.4.5 | 100 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 793.9449
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 158.789 | 555.7614 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 158.789 | 158.789 | 0 | 0 | 0 | 0 | 0 | 0
5.4.6 | 50 MM Tee-Joint | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 396.663
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 79.3326 | 277.6641 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 79.3326 | 79.3326 | 0 | 0 | 0 | 0 | 0 | 0
5.50 | CROSSES PERFORATED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.5.1 | 600 MM Cross | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2596.4411 | 0 | 0 |  |  |  | 288.4935
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 288.4935 | 2019.4542 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 288.4935 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0
5.5.2 | 450 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1156.5728
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 231.3146 | 809.601 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 231.3146 | 231.3146 | 0 | 0 | 0 | 0 | 0 | 0
5.5.3 | 300 MM Cross | 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1079.8393 | 0 | 0 |  |  |  | 0
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 215.9679 | 755.8875 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 215.9679 | 215.9679 | 0 | 0 | 0 | 0 | 0 | 0
5.5.4 | 150 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 533.422
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 | 0 | 0 | 0 | 0 | 0
5.5.5 | 100 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 533.422
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 106.6844 | 373.3954 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 106.6844 | 106.6844 | 0 | 0 | 0 | 0 | 0 | 0
5.5.6 | 50 MM Cross | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 268.5675
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 53.7135 | 187.9972 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 53.7135 | 53.7135 | 0 | 0 | 0 | 0 | 0 | 0
5.60 | REDUCERS PERFORATED LHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.6.1 | 600 MM WIDE - 450 MM Reducer LHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1732.6934
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0
5.6.2 | 450 MM WIDE - 300 MM Reducer LHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 721.543
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
5.6.3 | 300 MM WIDE - 150 MM Reducer LHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 721.543
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
5.70 | REDUCERS PERFORATED RHS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.7.1 | 600 MM WIDE - 450 MM Reducer RHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1732.6934
(i) | Fabrication and erection complete as applicable | 10 | NO | 70% | 173.2693 | 1212.8854 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 10 | NO | 20% | 173.2693 | 346.5387 | 0 | 0 | 0 | 0 | 0 | 0
5.7.2 | 450 MM WIDE - 300 MM Reducer RHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 721.543
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
5.7.3 | 300 MM WIDE - 150 MM Reducer RHS | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 721.543
(i) | Fabrication and erection complete as applicable | 5 | NO | 70% | 144.3086 | 505.0801 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 5 | NO | 20% | 144.3086 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
5.80 | CABLE TROUGHS HOT DIP GALVANISED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.8.1 | 50MM WIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 128581.3205
(i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 734.7504 | 90006.9243 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 734.7504 | 25716.2641 | 0 | 0 | 0 | 0 | 0 | 0
5.8.2 | 75MM WIDE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 192991.7222
(i) | Fabrication and erection complete as applicable | 175 | MTR | 70% | 1102.8098 | 135094.2055 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 175 | MTR | 20% | 1102.8098 | 38598.3444 | 0 | 0 | 0 | 0 | 0 | 0
6.00 | CONDUITS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
6.1 | RIGID GALVANISED MS CONDUITS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
6.1.1 | 50 MM DIAMETER MS Conduit | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21680.3261 | 0 | 0 |  |  |  | 0
(i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 108.4016 | 19512.2935 | 0 | 0 | 0 | 0 | 0 | 0
6.1.2 | 80 MM DIAMETER MS Conduit | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24582.5876 | 0 | 0 |  |  |  | 0
(i) | Laying of conduit/pipe complete in all respect | 200 | MTR | 90% | 122.9129 | 22124.3288 | 0 | 0 | 0 | 0 | 0 | 0
6.2 | GI FLEXIBLE METALLIC CONDUIT | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 35849.791 | 0 | 0 |  |  |  | 44453.7409
(i) | Laying of conduit/pipe complete in all respect | 2240 | MTR | 90% | 35.8498 | 72273.1787 | 0 | 0 | 0 | 0 | 0 | 0
7.00 | PERFORATED MS SHEET TO COVER CABLE SHAFT | 250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17924.7132 | 0 | 0 |  |  |  | 0
(i) | Fabrication and erection | 250 | SQM | 70% | 71.6989 | 12547.2992 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Painting as applicable | 250 | SQM | 20% | 71.6989 | 3584.9426 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
8.00 | DOUBLE COMPRESSION CABLE GLAND FOR UA/A CABLE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11780283.4245 | 31284.8351 | 331804.4978
8.01 | 9-11 (Above-mm to Upto-mm Cable Gland) | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21510.1509 | 0 | 0 | CABLE |  |  | 0
(i) | Termination | 300 | NO. | 70% | 71.7005 | 15057.1056 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 300 | NO. | 20% | 71.7005 | 4302.0302 | 0 | 0 | 0 | 0 | 0 | 0
8.02 | 11-13 (Above-mm to Upto-mm Cable Gland) | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 71699.4715 | 0 | 0 |  |  |  | 0
(i) | Termination | 1000 | NO. | 70% | 71.6995 | 50189.6301 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 1000 | NO. | 20% | 71.6995 | 14339.8943 | 0 | 0 | 0 | 0 | 0 | 0
8.03 | 13-17 (Above-mm to Upto-mm Cable Gland) | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 119072.5466 | 0 | 0 |  |  |  | 0
(i) | Termination | 1500 | NO. | 70% | 79.3817 | 83350.7826 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 1500 | NO. | 20% | 79.3817 | 23814.5093 | 0 | 0 | 0 | 0 | 0 | 0
8.04 | 17-20 (Above-mm to Upto-mm Cable Gland) | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17412.9498 | 0 | 0 |  |  |  | 0
(i) | Termination | 200 | NO. | 70% | 87.0647 | 12189.0649 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 200 | NO. | 20% | 87.0647 | 3482.59 | 0 | 0 | 0 | 0 | 0 | 0
8.05 | 20-23 (Above-mm to Upto-mm Cable Gland) | 70 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6632.5028 | 0 | 0 |  |  |  | 0
(i) | Termination | 70 | NO. | 70% | 94.75 | 4642.752 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 70 | NO. | 20% | 94.75 | 1326.5006 | 0 | 0 | 0 | 0 | 0 | 0
8.06 | 23-26 (Above-mm to Upto-mm Cable Gland) | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15235.9443 | 0 | 0 |  |  |  | 0
(i) | Termination | 150 | NO. | 70% | 101.573 | 10665.161 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 150 | NO. | 20% | 101.573 | 3047.1889 | 0 | 0 | 0 | 0 | 0 | 0
8.07 | 26-30 (Above-mm to Upto-mm Cable Gland) | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5420.2362 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO. | 70% | 108.4047 | 3794.1654 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO. | 20% | 108.4047 | 1084.0472 | 0 | 0 | 0 | 0 | 0 | 0
8.08 | 30-35 (For 3.5C x 50, 2C x 95 Cables ) | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6145.4922 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 122.9098 | 4301.8445 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 122.9098 | 1229.0984 | 0 | 0 | 0 | 0 | 0 | 0
8.09 | 35-40 (For 3.5C x 95, 2C x 120 Cables ) | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 13059.5577 | 0 | 0 |  |  |  | 0
(i) | Termination | 100 | NO | 70% | 130.5956 | 9141.6904 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 100 | NO | 20% | 130.5956 | 2611.9115 | 0 | 0 | 0 | 0 | 0 | 0
8.10 | 40-50 (For 3C x 150, 2C x 120 Cables ) | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7596.6229 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 151.9325 | 5317.636 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 151.9325 | 1519.3246 | 0 | 0 | 0 | 0 | 0 | 0
8.11 | 50-60 (For 3C x 240, 2C x 120 Cables ) | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3328.6278 | 0 | 0 |  |  |  | 0
(i) | Termination | 20 | NO | 70% | 166.4314 | 2330.0394 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 20 | NO | 20% | 166.4314 | 665.7256 | 0 | 0 | 0 | 0 | 0 | 0
8.12 | CABLE GLAND SUITABLE-16 PAIR,0.5SQ.MM | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 573.6453 | 0 | 0 |  |  |  | 0
(i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 | 0 | 0 | 0 | 0 | 0
8.13 | CABLE GLAND SUITABLE-10 PAIR,0.6SQ.MM | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 573.6453 | 0 | 0 |  |  |  | 0
(i) | Termination | 8 | NO. | 70% | 71.7057 | 401.5517 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 8 | NO. | 20% | 71.7057 | 114.7291 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
8.20 | CRIMPING LUGS (RING/ROUND/FLAT TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
8.2.1 | 0.5 Sq-mm Lugs | 7000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 155348.9582 | 0 | 0 |  |  |  | 0
(i) | Termination | 7000 | NO | 70% | 22.1927 | 108744.2707 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 7000 | NO | 20% | 22.1927 | 31069.7916 | 0 | 0 | 0 | 0 | 0 | 0
8.2.2 | 1.5 Sq-mm Lugs | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17753.9191 | 0 | 0 |  |  |  | 0
(i) | Termination | 800 | NO | 70% | 22.1924 | 12427.7434 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 800 | NO | 20% | 22.1924 | 3550.7838 | 0 | 0 | 0 | 0 | 0 | 0
8.2.3 | 2.5 Sq-mm Lugs | 52500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1165118.7332 | 0 | 0 |  |  |  | -1048606.8599
(i) | Termination | 5250 | NO | 70% | 22.1927 | 81558.3113 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 5250 | NO | 20% | 22.1927 | 23302.3747 | 0 | 0 | 0 | 0 | 0 | 0
8.2.4 | 16 Sq-mm Lugs | 250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7255.0348 | 0 | 0 |  |  |  | 0
(i) | Termination | 250 | NO | 70% | 29.0201 | 5078.5243 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 250 | NO | 20% | 29.0201 | 1451.007 | 0 | 0 | 0 | 0 | 0 | 0
8.2.5 | 25 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1451.1307 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 29.0226 | 1015.7915 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 29.0226 | 290.2261 | 0 | 0 | 0 | 0 | 0 | 0
8.2.6 | 35 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2176.3867 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 43.5277 | 1523.4707 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 43.5277 | 435.2773 | 0 | 0 | 0 | 0 | 0 | 0
8.2.7 | 50 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2902.2614 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 | 0 | 0 | 0 | 0 | 0
8.2.8 | 70 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2902.2614 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 58.0452 | 2031.583 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 58.0452 | 580.4523 | 0 | 0 | 0 | 0 | 0 | 0
8.2.9 | 95 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3584.8189 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 71.6964 | 2509.3732 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 71.6964 | 716.9638 | 0 | 0 | 0 | 0 | 0 | 0
8.2.10 | 120 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4353.3922 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 | 0 | 0 | 0 | 0 | 0
8.2.11 | 150 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4353.3922 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 87.0678 | 3047.3745 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 87.0678 | 870.6784 | 0 | 0 | 0 | 0 | 0 | 0
8.2.12 | 185 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5078.6481 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 | 0 | 0 | 0 | 0 | 0
8.2.13 | 240 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5078.6481 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 101.573 | 3555.0537 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 101.573 | 1015.7296 | 0 | 0 | 0 | 0 | 0 | 0
8.2.10 | 300 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6529.7788 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 130.5956 | 4570.8452 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 130.5956 | 1305.9558 | 0 | 0 | 0 | 0 | 0 | 0
8.2.11 | 630 Sq-mm Lugs | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7212.3363 | 0 | 0 |  |  |  | 0
(i) | Termination | 50 | NO | 70% | 144.2467 | 5048.6354 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 50 | NO | 20% | 144.2467 | 1442.4673 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
9.00 | EQUIPMENT EARTHING MATERIALS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
9.01 | GI WIRE 14 SWG | 87500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 672184.1701 | 0 | 0 |  |  |  | 0
(i) | Termination | 87500 | MTR | 70% | 7.6821 | 470528.9191 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 87500 | MTR | 20% | 7.6821 | 134436.834 | 0 | 0 | 0 | 0 | 0 | 0
9.02 | GI WIRE 8 SWG | 1450 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11138.7433 | 0 | 0 |  |  |  | 0
(i) | Termination | 1450 | MTR | 70% | 7.6819 | 7797.1203 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 1450 | MTR | 20% | 7.6819 | 2227.7487 | 0 | 0 | 0 | 0 | 0 | 0
9.03 | GS FLAT 25 X 6 MM | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 103976.4554 | 0 | 9097.9398 |  |  |  | 0
(i) | Termination | 8 | MT | 70% | 12997.0569 | 72783.5188 | 1 | 0 | 1 | 9097.9398 | 0 | 9097.9398
(ii) | Testing of connected equipments/system | 8 | MT | 20% | 12997.0569 | 20795.2911 | 0 | 0 | 0 | 0 | 0 | 0
9.04 | GS FLAT 50 X 6 MM | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17966.1741 | 0 | 9432.2414 |  |  |  | 0
(i) | Termination | 2 | MT | 70% | 8983.087 | 12576.3218 | 1.5 | 0 | 1.5 | 9432.2414 | 0 | 9432.2414
(ii) | Testing of connected equipments/system | 2 | MT | 20% | 8983.087 | 3593.2348 | 0 | 0 | 0 | 0 | 0 | 0
9.05 | GS FLAT 65 X 8 MM | 53 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 560556.6357 | 0 | 244318.0809 |  |  |  | 0
(i) | Termination | 53 | MT | 70% | 10576.5403 | 392389.645 | 33 | 0 | 33 | 244318.0809 | 0 | 244318.0809
(ii) | Testing of connected equipments/system | 53 | MT | 20% | 10576.5403 | 112111.3271 | 0 | 0 | 0 | 0 | 0 | 0
9.06 | GS FLAT 75 X 10 MM | 6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 58724.6921 | 0 | 37671.4006 |  |  |  | 0
(i) | Termination | 6 | MT | 70% | 9787.4487 | 41107.2845 | 5.4985 | 0 | 5.4985 | 37671.4006 | 0 | 37671.4006
(ii) | Testing of connected equipments/system | 6 | MT | 20% | 9787.4487 | 11744.9384 | 0 | 0 | 0 | 0 | 0 | 0
9.07 | GS ROD 20 MM DIA.1000MM LONG | 84 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28711.9672 | 0 | 0 |  |  |  | 0
(i) | Termination | 84 | NOS | 70% | 341.8091 | 20098.377 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8091 | 5742.3934 | 0 | 0 | 0 | 0 | 0 | 0
9.08 | TEST LINK 150X25X6 MM GS FLAT WITH BOX | 84 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 28716.9178 | 0 | 0 |  |  |  | 0
(i) | Termination | 84 | NOS | 70% | 341.8681 | 20101.8424 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 84 | NOS | 20% | 341.8681 | 5743.3836 | 0 | 0 | 0 | 0 | 0 | 0
9.09 | 40NB GALV MS HEAVY DUTY PIPE (PERF) 3M | 112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50874.9722 | 0 | 0 |  |  |  | 0
(i) | Termination | 112 | NOS | 70% | 454.2408 | 35612.4805 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 112 | NOS | 20% | 454.2408 | 10174.9944 | 0 | 0 | 0 | 0 | 0 | 0
9.10 | FLEXIBLE BRAIDED CONDUCTOR FOR FENCE GATE GND | 10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50488.2103 | 0 | 0 |  |  |  | 0
(i) | Termination | 10 | NOS | 70% | 5048.821 | 35341.7472 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 5048.821 | 10097.6421 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.00 | CABLE LAYING, DRESSING, CLAMPING, TAGGING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.1 | 6.6 KV XLPE AL UA POWER CABLES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.1.1 | 1C-400 Sq.mm | 32000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1015266.7448 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 32000 | MTR | 55% | 31.7271 | 558396.7097 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 32000 | MTR | 10% | 31.7271 | 101526.6745 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 32000 | MTR | 25% | 31.7271 | 253816.6862 | 0 | 0 | 0 | 0 | 0 | 0
10.1.2 | 3C-150 Sq.mm | 13000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 449979.8561 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 13000 | MTR | 55% | 34.6138 | 247488.9209 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 13000 | MTR | 10% | 34.6138 | 44997.9856 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 13000 | MTR | 25% | 34.6138 | 112494.964 | 0 | 0 | 0 | 0 | 0 | 0
10.1.3 | 3C-240 Sq.mm | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 216336.6716 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 43.2673 | 118985.1694 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 43.2673 | 21633.6672 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 43.2673 | 54084.1679 | 0 | 0 | 0 | 0 | 0 | 0
10.2 | 33 KV XLPE AL UA POWER CABLES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.2.1 | 3C-120 Sq.mm | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 51920.7764 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 1500 | MTR | 55% | 34.6139 | 28556.427 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 1500 | MTR | 10% | 34.6139 | 5192.0776 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 1500 | MTR | 25% | 34.6139 | 12980.1941 | 0 | 0 | 0 | 0 | 0 | 0
10.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.3.1 | 3.5C - 25 AL | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 98058.0698 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 12.2573 | 53931.9384 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 12.2573 | 9805.807 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 12.2573 | 24514.5175 | 0 | 0 | 0 | 0 | 0 | 0
10.3.2 | 3.5C - 50 AL | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 14416.6279 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 14.4166 | 7929.1453 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 14.4166 | 1441.6628 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 14.4166 | 3604.157 | 0 | 0 | 0 | 0 | 0 | 0
10.3.3 | 3C - 2.5- CU | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 80713.1901 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 10.0891 | 44392.2546 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 10.0891 | 8071.319 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 10.0891 | 20178.2975 | 0 | 0 | 0 | 0 | 0 | 0
10.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.4.1 | 1C - 35 AL | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 69330.0133 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 8.6663 | 38131.5073 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 8.6663 | 6933.0013 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 8.6663 | 17332.5033 | 0 | 0 | 0 | 0 | 0 | 0
10.4.2 | 1C - 70 AL | 14000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 134807.2591 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 9.6291 | 74143.9925 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 9.6291 | 13480.7259 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 9.6291 | 33701.8148 | 0 | 0 | 0 | 0 | 0 | 0
10.4.3 | 1C - 120 AL | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23111.0358 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 2000 | MTR | 55% | 11.5555 | 12711.0697 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 2000 | MTR | 10% | 11.5555 | 2311.1036 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 2000 | MTR | 25% | 11.5555 | 5777.759 | 0 | 0 | 0 | 0 | 0 | 0
10.4.4 | 1C - 400 AL | 13500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 221002.5674 | 26660.2764 | 26660.2764 |  |  |  | 0
(i) | Laying of cable | 13500 | MTR | 55% | 16.3706 | 121551.4121 | 0 | 2961 | 2961 | 0 | 26660.2764 | 26660.2764
(ii) | After termination of cable | 13500 | MTR | 10% | 16.3706 | 22100.2567 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 13500 | MTR | 25% | 16.3706 | 55250.6418 | 0 | 0 | 0 | 0 | 0 | 0
10.4.5 | 1C - 630 AL | 18000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 312001.1493 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 18000 | MTR | 55% | 17.3334 | 171600.6321 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 18000 | MTR | 10% | 17.3334 | 31200.1149 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 18000 | MTR | 25% | 17.3334 | 78000.2873 | 0 | 0 | 0 | 0 | 0 | 0
10.4.6 | 2C - 10 AL | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 51997.51 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 8.6663 | 28598.6305 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 8.6663 | 5199.751 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 8.6663 | 12999.3775 | 0 | 0 | 0 | 0 | 0 | 0
10.4.7 | 2C - 25 AL | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 77032.4543 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 9.6291 | 42367.8499 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 9.6291 | 7703.2454 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 9.6291 | 19258.1136 | 0 | 0 | 0 | 0 | 0 | 0
10.4.8 | 2C - 50 AL | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11555.8273 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 11.5558 | 6355.705 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 11.5558 | 1155.5827 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.5558 | 2888.9568 | 0 | 0 | 0 | 0 | 0 | 0
10.4.9 | 2C - 95 AL | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 77999.0497 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 12.9998 | 42899.4773 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 12.9998 | 7799.905 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 12.9998 | 19499.7624 | 0 | 0 | 0 | 0 | 0 | 0
10.4.10 | 2C - 120 AL | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 111701.1739 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 13.9626 | 61435.6456 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 13.9626 | 11170.1174 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 13.9626 | 27925.2935 | 0 | 0 | 0 | 0 | 0 | 0
10.4.11 | 3C - 10 AL | 36000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 346647.5639 | 0 | 0 |  |  |  | 962.9099
(i) | Laying of cable | 36100 | MTR | 55% | 9.6291 | 191185.7606 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 36100 | MTR | 10% | 9.6291 | 34761.0474 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 36100 | MTR | 25% | 9.6291 | 86902.6185 | 0 | 0 | 0 | 0 | 0 | 0
10.4.12 | 3C - 25 AL | 14000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 155038.311 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 11.0742 | 85271.071 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 11.0742 | 15503.8311 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 11.0742 | 38759.5777 | 0 | 0 | 0 | 0 | 0 | 0
10.4.13 | 3C - 35 AL | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9244.5381 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 800 | MTR | 55% | 11.5557 | 5084.4959 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 800 | MTR | 10% | 11.5557 | 924.4538 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 800 | MTR | 25% | 11.5557 | 2311.1345 | 0 | 0 | 0 | 0 | 0 | 0
10.4.14 | 3C - 50 AL | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25036.8008 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 2000 | MTR | 55% | 12.5184 | 13770.2404 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 2000 | MTR | 10% | 12.5184 | 2503.6801 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 2000 | MTR | 25% | 12.5184 | 6259.2002 | 0 | 0 | 0 | 0 | 0 | 0
10.4.15 | 3C - 95 AL | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 115552.7038 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 14.4441 | 63553.9871 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 14.4441 | 11555.2704 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 14.4441 | 28888.1759 | 0 | 0 | 0 | 0 | 0 | 0
10.4.16 | 3C - 150 AL | 750 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 14444.4747 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 750 | MTR | 55% | 19.2593 | 7944.4611 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 750 | MTR | 10% | 19.2593 | 1444.4475 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 750 | MTR | 25% | 19.2593 | 3611.1187 | 0 | 0 | 0 | 0 | 0 | 0
10.4.17 | 3C - 240 AL | 6750 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 162499.4125 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 6750 | MTR | 55% | 24.074 | 89374.6769 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 6750 | MTR | 10% | 24.074 | 16249.9413 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 6750 | MTR | 25% | 24.074 | 40624.8531 | 0 | 0 | 0 | 0 | 0 | 0
10.4.18 | 3.5C - 25 AL | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 67602.2705 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 11.267 | 37181.2488 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 11.267 | 6760.227 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 11.267 | 16900.5676 | 0 | 0 | 0 | 0 | 0 | 0
10.4.19 | 3.5C - 50 AL | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 155998.0994 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 12000 | MTR | 55% | 12.9998 | 85798.9546 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 12000 | MTR | 10% | 12.9998 | 15599.8099 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 12000 | MTR | 25% | 12.9998 | 38999.5248 | 0 | 0 | 0 | 0 | 0 | 0
10.4.20 | 3.5C - 95 AL | 10000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 149263.4914 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 14.9263 | 82094.9203 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 14.9263 | 14926.3491 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.9263 | 37315.8729 | 0 | 0 | 0 | 0 | 0 | 0
10.4.21 | 3.5C - 185 AL | 750 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17333.1222 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 750 | MTR | 55% | 23.1108 | 9533.2172 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 750 | MTR | 10% | 23.1108 | 1733.3122 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 750 | MTR | 25% | 23.1108 | 4333.2805 | 0 | 0 | 0 | 0 | 0 | 0
10.4.22 | 4C - 10 AL | 15000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 151657.7024 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.1105 | 83411.7363 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.1105 | 15165.7702 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.1105 | 37914.4256 | 0 | 0 | 0 | 0 | 0 | 0
10.4.23 | 2C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 902.2382
(i) | Laying of cable | 140 | MTR | 55% | 6.4446 | 496.231 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 140 | MTR | 10% | 6.4446 | 90.2238 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 140 | MTR | 25% | 6.4446 | 225.5596 | 0 | 0 | 0 | 0 | 0 | 0
10.4.24 | 2C - 2.5- CU | 68000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 438337.751 | 0 | 0 |  |  |  | 3223.0717
(i) | Laying of cable | 68500 | MTR | 55% | 6.4461 | 242858.4525 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 68500 | MTR | 10% | 6.4461 | 44156.0823 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 68500 | MTR | 25% | 6.4461 | 110390.2057 | 0 | 0 | 0 | 0 | 0 | 0
10.4.25 | 3C - 1.5- CU | 9000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 58015.2968 | 0 | 0 |  |  |  | 1289.2288
(i) | Laying of cable | 9200 | MTR | 55% | 6.4461 | 32617.4891 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 9200 | MTR | 10% | 6.4461 | 5930.4526 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 9200 | MTR | 25% | 6.4461 | 14826.1314 | 0 | 0 | 0 | 0 | 0 | 0
10.4.26 | 3C - 2.5- CU | 90000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 580152.6182 | 0 | 0 |  |  |  | 34164.5431
(i) | Laying of cable | 95300 | MTR | 55% | 6.4461 | 337874.4387 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 95300 | MTR | 10% | 6.4461 | 61431.7161 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 95300 | MTR | 25% | 6.4461 | 153579.2903 | 0 | 0 | 0 | 0 | 0 | 0
10.4.27 | 4C - 1.5- CU | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 32230.91 | 0 | 0 |  |  |  | 3223.091
(i) | Laying of cable | 5500 | MTR | 55% | 6.4462 | 19499.7005 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 5500 | MTR | 10% | 6.4462 | 3545.4001 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 5500 | MTR | 25% | 6.4462 | 8863.5002 | 0 | 0 | 0 | 0 | 0 | 0
10.4.28 | 10C - 2.5- CU | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 92321.768 | 0 | 0 |  |  |  | 2308.0442
(i) | Laying of cable | 8200 | MTR | 55% | 11.5402 | 52046.3967 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8200 | MTR | 10% | 11.5402 | 9462.9812 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5402 | 23657.453 | 0 | 0 | 0 | 0 | 0 | 0
10.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.5.1 | 2C-1.5 | 50000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 264819.2893 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 50000 | MTR | 55% | 5.2964 | 145650.6091 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 50000 | MTR | 10% | 5.2964 | 26481.9289 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 50000 | MTR | 25% | 5.2964 | 66204.8223 | 0 | 0 | 0 | 0 | 0 | 0
10.5.2 | 2C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18777.4459
(i) | Laying of cable | 3000 | MTR | 55% | 6.2591 | 10327.5952 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 3000 | MTR | 10% | 6.2591 | 1877.7446 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 3000 | MTR | 25% | 6.2591 | 4694.3615 | 0 | 0 | 0 | 0 | 0 | 0
10.5.3 | 3C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 24156.2212
(i) | Laying of cable | 2500 | MTR | 55% | 9.6625 | 13285.9217 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 2500 | MTR | 10% | 9.6625 | 2415.6221 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 2500 | MTR | 25% | 9.6625 | 6039.0553 | 0 | 0 | 0 | 0 | 0 | 0
10.5.4 | 3C-2.5 | 18000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 160971.0967 | 0 | 0 |  |  |  | 4471.4194
(i) | Laying of cable | 18500 | MTR | 55% | 8.9428 | 90993.3838 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 18500 | MTR | 10% | 8.9428 | 16544.2516 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 18500 | MTR | 25% | 8.9428 | 41360.629 | 0 | 0 | 0 | 0 | 0 | 0
10.5.5 | 3C-16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12393.7083
(i) | Laying of cable | 1500 | MTR | 55% | 8.2625 | 6816.5396 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 1500 | MTR | 10% | 8.2625 | 1239.3708 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 1500 | MTR | 25% | 8.2625 | 3098.4271 | 0 | 0 | 0 | 0 | 0 | 0
10.5.6 | 5C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 151337.1541 | 0 | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.0891 | 83235.4348 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.0891 | 15133.7154 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.0891 | 37834.2885 | 0 | 0 | 0 | 0 | 0 | 0
10.5.7 | 5C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 70623.964
(i) | Laying of cable | 7000 | MTR | 55% | 10.0891 | 38843.1802 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 7000 | MTR | 10% | 10.0891 | 7062.3964 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 7000 | MTR | 25% | 10.0891 | 17655.991 | 0 | 0 | 0 | 0 | 0 | 0
10.5.8 | 7C-1.5 | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 124552.8083 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 12000 | MTR | 55% | 10.3794 | 68504.0446 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 12000 | MTR | 10% | 10.3794 | 12455.2808 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 12000 | MTR | 25% | 10.3794 | 31138.2021 | 0 | 0 | 0 | 0 | 0 | 0
10.5.9 | 7C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8666.5611
(i) | Laying of cable | 1000 | MTR | 55% | 8.6666 | 4766.6086 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 8.6666 | 866.6561 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.6666 | 2166.6403 | 0 | 0 | 0 | 0 | 0 | 0
10.5.10 | 10C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 94608.7723
(i) | Laying of cable | 8200 | MTR | 55% | 11.5377 | 52034.8248 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8200 | MTR | 10% | 11.5377 | 9460.8772 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8200 | MTR | 25% | 11.5377 | 23652.1931 | 0 | 0 | 0 | 0 | 0 | 0
10.5.11 | 10C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2527.8759
(i) | Laying of cable | 250 | MTR | 55% | 10.1115 | 1390.3317 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 250 | MTR | 10% | 10.1115 | 252.7876 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 250 | MTR | 25% | 10.1115 | 631.969 | 0 | 0 | 0 | 0 | 0 | 0
10.5.12 | 12C-1.5 | 15000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 158891.6973 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 10.5928 | 87390.4335 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 10.5928 | 15889.1697 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 10.5928 | 39722.9243 | 0 | 0 | 0 | 0 | 0 | 0
10.5.13 | 12C-2.5 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 57253.1404 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 11.4506 | 31489.2272 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 11.4506 | 5725.314 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 11.4506 | 14313.2851 | 0 | 0 | 0 | 0 | 0 | 0
10.5.14 | 16C-2.5 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 52532.1697 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 4000 | MTR | 55% | 13.133 | 28892.6933 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 4000 | MTR | 10% | 13.133 | 5253.217 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 4000 | MTR | 25% | 13.133 | 13133.0424 | 0 | 0 | 0 | 0 | 0 | 0
10.5.15 | 19C-1.5 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 34253.492 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 2500 | MTR | 55% | 13.7014 | 18839.4206 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 2500 | MTR | 10% | 13.7014 | 3425.3492 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 2500 | MTR | 25% | 13.7014 | 8563.373 | 0 | 0 | 0 | 0 | 0 | 0
10.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4182.5981
(i) | Laying of cable | 500 | MTR | 55% | 8.3652 | 2300.429 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 500 | MTR | 10% | 8.3652 | 418.2598 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 8.3652 | 1045.6495 | 0 | 0 | 0 | 0 | 0 | 0
10.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4687.5545
(i) | Laying of cable | 500 | MTR | 55% | 9.3751 | 2578.155 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 500 | MTR | 10% | 9.3751 | 468.7554 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 9.3751 | 1171.8886 | 0 | 0 | 0 | 0 | 0 | 0
10.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5192.5108
(i) | Laying of cable | 500 | MTR | 55% | 10.385 | 2855.8809 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 500 | MTR | 10% | 10.385 | 519.2511 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 10.385 | 1298.1277 | 0 | 0 | 0 | 0 | 0 | 0
10.6.4 | 5C - 6 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2884.3157
(i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 | 0 | 0 | 0 | 0 | 0
10.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5408.4787
(i) | Laying of cable | 500 | MTR | 55% | 10.817 | 2974.6633 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 500 | MTR | 10% | 10.817 | 540.8479 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 500 | MTR | 25% | 10.817 | 1352.1197 | 0 | 0 | 0 | 0 | 0 | 0
10.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2307.5763
(i) | Laying of cable | 200 | MTR | 55% | 11.5379 | 1269.167 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 200 | MTR | 10% | 11.5379 | 230.7576 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 11.5379 | 576.8941 | 0 | 0 | 0 | 0 | 0 | 0
10.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2884.3157
(i) | Laying of cable | 200 | MTR | 55% | 14.4216 | 1586.3736 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 200 | MTR | 10% | 14.4216 | 288.4316 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 14.4216 | 721.0789 | 0 | 0 | 0 | 0 | 0 | 0
10.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3461.6739
(i) | Laying of cable | 200 | MTR | 55% | 17.3084 | 1903.9206 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 200 | MTR | 10% | 17.3084 | 346.1674 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 200 | MTR | 25% | 17.3084 | 865.4185 | 0 | 0 | 0 | 0 | 0 | 0
10.7 | CONTROL/INSTRUMENT LT CABLES (SHIELDED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.7.1 | 2P - 0.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8535.3714
(i) | Laying of cable | 1000 | MTR | 55% | 8.5354 | 4694.4543 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 8.5354 | 853.5371 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 8.5354 | 2133.8429 | 0 | 0 | 0 | 0 | 0 | 0
10.7.2 | 4P - 0.5 SQ MM | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 46946.0899 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 9.3892 | 25820.3495 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 9.3892 | 4694.609 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 9.3892 | 11736.5225 | 0 | 0 | 0 | 0 | 0 | 0
10.7.3 | 6P - 0.5 SQ MM | 10000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 110963.5415 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 11.0964 | 61029.9478 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 11.0964 | 11096.3542 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.0964 | 27740.8854 | 0 | 0 | 0 | 0 | 0 | 0
10.7.4 | 8P - 0.5 SQ MM | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11950.0151 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 1000 | MTR | 55% | 11.95 | 6572.5083 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 1000 | MTR | 10% | 11.95 | 1195.0015 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 1000 | MTR | 25% | 11.95 | 2987.5038 | 0 | 0 | 0 | 0 | 0 | 0
10.7.5 | 12P - 0.5 SQ MM | 15000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 192052.3548 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 15000 | MTR | 55% | 12.8035 | 105628.7952 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 15000 | MTR | 10% | 12.8035 | 19205.2355 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 15000 | MTR | 25% | 12.8035 | 48013.0887 | 0 | 0 | 0 | 0 | 0 | 0
10.7.6 | 16P - 0.5 SQ MM | 10000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 145106.2649 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 10000 | MTR | 55% | 14.5106 | 79808.4457 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 14.5106 | 14510.6265 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 14.5106 | 36276.5662 | 0 | 0 | 0 | 0 | 0 | 0
10.8 | SCREENED CABLES (OVERALL & INDIVIDUAL/OVERALL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.8.1 | 2P - 0.5 SQ MM | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 56335.4317 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 6000 | MTR | 55% | 9.3892 | 30984.4874 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 6000 | MTR | 10% | 9.3892 | 5633.5432 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 6000 | MTR | 25% | 9.3892 | 14083.8579 | 0 | 0 | 0 | 0 | 0 | 0
10.8.2 | 4P - 0.5 SQ MM | 14000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 143399.5619 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 14000 | MTR | 55% | 10.2428 | 78869.7591 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 14000 | MTR | 10% | 10.2428 | 14339.9562 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 14000 | MTR | 25% | 10.2428 | 35849.8905 | 0 | 0 | 0 | 0 | 0 | 0
10.8.3 | 8P - 0.5 SQ MM | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11949.9532 | 0 | 0 |  |  |  | 107549.5786
(i) | Laying of cable | 10000 | MTR | 55% | 11.95 | 65724.7425 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 10000 | MTR | 10% | 11.95 | 11949.9532 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 10000 | MTR | 25% | 11.95 | 29874.8829 | 0 | 0 | 0 | 0 | 0 | 0
10.8.4 | 12 P - 0.5 SQ MM | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 68285.4467 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 5000 | MTR | 55% | 13.6571 | 37556.9957 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 5000 | MTR | 10% | 13.6571 | 6828.5447 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 5000 | MTR | 25% | 13.6571 | 17071.3617 | 0 | 0 | 0 | 0 | 0 | 0
10.9 | SPECIALISED CABLING FOR COMMUNICATION SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.9.1 | OPTICAL FIBRE CABLE WITHOUT HDPE PIPE | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 158476.4697 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 8000 | MTR | 55% | 19.8096 | 87162.0584 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 8000 | MTR | 10% | 19.8096 | 15847.647 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 8000 | MTR | 25% | 19.8096 | 39619.1174 | 0 | 0 | 0 | 0 | 0 | 0
10.9.2 | OPTICAL FIBRE CABLE WITH HDPE PIPE | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 87163.7601 | 0 | 0 |  |  |  | 0
(i) | Laying of cable | 3000 | MTR | 55% | 29.0546 | 47940.0681 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 3000 | MTR | 10% | 29.0546 | 8716.376 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 3000 | MTR | 25% | 29.0546 | 21790.94 | 0 | 0 | 0 | 0 | 0 | 0
10.9.3 | EARTH CABLE FOR ESP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2590.9954
(i) | Laying of cable | 280 | MTR | 55% | 9.2536 | 1425.0475 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | After termination of cable | 280 | MTR | 10% | 9.2536 | 259.0995 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Dressing & Clamping | 280 | MTR | 25% | 9.2536 | 647.7489 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
11.0 | CABLE JOINITNG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
11.10 | JOINT KIT 6.6KV 1C-400 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 34825.2808
(i) | Termination | 12 | NOS | 70% | 2902.1067 | 24377.6966 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 12 | NOS | 20% | 2902.1067 | 6965.0562 | 0 | 0 | 0 | 0 | 0 | 0
11.20 | JOINT KIT 6.6KV 3C-150 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 23216.8539
(i) | Termination | 8 | NOS | 70% | 2902.1067 | 16251.7977 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 2902.1067 | 4643.3708 | 0 | 0 | 0 | 0 | 0 | 0
11.30 | JOINT KIT 6.6KV 3C-240 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11608.4269
(i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 | 0 | 0 | 0 | 0 | 0
11.40 | JOINT KIT 33KV 3C-120 AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11608.4269
(i) | Termination | 4 | NOS | 70% | 2902.1067 | 8125.8989 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 2902.1067 | 2321.6854 | 0 | 0 | 0 | 0 | 0 | 0
12.0 | CABLE TERMINATION | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.1 | 6.6 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.1.1 | TERM. KIT 6.6KV 1C-400 AL UNARM. CU LUG | 136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 394689.6099 | 0 | 0 |  |  |  | 0
(i) | Termination | 136 | NOS | 70% | 2902.1295 | 276282.7269 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 136 | NOS | 20% | 2902.1295 | 78937.922 | 0 | 0 | 0 | 0 | 0 | 0
12.1.2 | TERM. KIT 6.6KV 3C-150 AL UNARM. CU LUG | 94 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 272800.1988 | 0 | 0 |  |  |  | 0
(i) | Termination | 94 | NOS | 70% | 2902.1298 | 190960.1392 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 94 | NOS | 20% | 2902.1298 | 54560.0398 | 0 | 0 | 0 | 0 | 0 | 0
12.1.3 | TERM. KIT 6.6KV 3C-240 AL UNARM. CU LUG | 46 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 133497.838 | 0 | 0 |  |  |  | 0
(i) | Termination | 46 | NOS | 70% | 2902.1269 | 93448.4866 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 46 | NOS | 20% | 2902.1269 | 26699.5676 | 0 | 0 | 0 | 0 | 0 | 0
12.2 | 33 KV XLPE UNARMOURED POWER CABLES (AL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.2.1 | TERM. KIT 33KV 3C-120 AL UNARM. CU LUG | 6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 17412.9498 | 0 | 0 |  |  |  | 0
(i) | Termination | 6 | NOS | 70% | 2902.1583 | 12189.0649 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 6 | NOS | 20% | 2902.1583 | 3482.59 | 0 | 0 | 0 | 0 | 0 | 0
12.3 | LT XLPE POWER CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.3.1 | 3.5C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4862.0614
(i) | Termination | 32 | NOS | 70% | 151.9394 | 3403.443 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.9394 | 972.4123 | 0 | 0 | 0 | 0 | 0 | 0
12.3.2 | 3.5C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 693.0774
(i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 | 0 | 0 | 0 | 0 | 0
12.3.3 | 3C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4616.3903
(i) | Termination | 32 | NOS | 70% | 144.2622 | 3231.4732 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 144.2622 | 923.2781 | 0 | 0 | 0 | 0 | 0 | 0
12.4 | LT XLPE POWER CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.4.1 | 1C - 35 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4834.8334
(i) | Termination | 32 | NOS | 70% | 151.0885 | 3384.3834 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 151.0885 | 966.9667 | 0 | 0 | 0 | 0 | 0 | 0
12.4.2 | 1C - 70 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8795.2754
(i) | Termination | 56 | NOS | 70% | 157.0585 | 6156.6928 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 56 | NOS | 20% | 157.0585 | 1759.0551 | 0 | 0 | 0 | 0 | 0 | 0
12.4.3 | 1C - 120 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1365.7337
(i) | Termination | 8 | NOS | 70% | 170.7167 | 956.0136 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 170.7167 | 273.1467 | 0 | 0 | 0 | 0 | 0 | 0
12.4.4 | 1C - 400 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4624.5587 | 4624.5587 |  |  |  | 9909.7686
(i) | Termination | 54 | NOS | 70% | 183.5142 | 6936.838 | 0 | 36 | 36 | 0 | 4624.5587 | 4624.5587
(ii) | Testing of connected equipments/system | 54 | NOS | 20% | 183.5142 | 1981.9537 | 0 | 0 | 0 | 0 | 0 | 0
12.4.5 | 1C - 630 AL | 72 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15118.3687 | 0 | 0 |  |  |  | 0
(i) | Termination | 72 | NOS | 70% | 209.9773 | 10582.8581 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 72 | NOS | 20% | 209.9773 | 3023.6737 | 0 | 0 | 0 | 0 | 0 | 0
12.4.6 | 2C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2355.8442
(i) | Termination | 24 | NOS | 70% | 98.1602 | 1649.0909 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 98.1602 | 471.1688 | 0 | 0 | 0 | 0 | 0 | 0
12.4.7 | 2C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3141.1256
(i) | Termination | 32 | NOS | 70% | 98.1602 | 2198.7879 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 98.1602 | 628.2251 | 0 | 0 | 0 | 0 | 0 | 0
12.4.8 | 2C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 525.9962
(i) | Termination | 4 | NOS | 70% | 131.4991 | 368.1973 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 131.4991 | 105.1992 | 0 | 0 | 0 | 0 | 0 | 0
12.4.9 | 2C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3769.227
(i) | Termination | 24 | NOS | 70% | 157.0511 | 2638.4589 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 157.0511 | 753.8454 | 0 | 0 | 0 | 0 | 0 | 0
12.4.10 | 2C - 120 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5026.0485
(i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 | 0 | 0 | 0 | 0 | 0
12.4.11 | 3C - 10 AL | 145 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 20916.7034 | 0 | 0 |  |  |  | 0
(i) | Termination | 145 | NOS | 70% | 144.2531 | 14641.6924 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 145 | NOS | 20% | 144.2531 | 4183.3407 | 0 | 0 | 0 | 0 | 0 | 0
12.4.12 | 3C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8078.0641
(i) | Termination | 56 | NOS | 70% | 144.2511 | 5654.6449 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 56 | NOS | 20% | 144.2511 | 1615.6128 | 0 | 0 | 0 | 0 | 0 | 0
12.4.13 | 3C - 35 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 604.5862
(i) | Termination | 4 | NOS | 70% | 151.1466 | 423.2104 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 151.1466 | 120.9172 | 0 | 0 | 0 | 0 | 0 | 0
12.4.14 | 3C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1256.2027
(i) | Termination | 8 | NOS | 70% | 157.0253 | 879.3419 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 8 | NOS | 20% | 157.0253 | 251.2405 | 0 | 0 | 0 | 0 | 0 | 0
12.4.15 | 3C - 95 AL | 32 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5026.0485 | 0 | 0 |  |  |  | 0
(i) | Termination | 32 | NOS | 70% | 157.064 | 3518.2339 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 157.064 | 1005.2097 | 0 | 0 | 0 | 0 | 0 | 0
12.4.16 | 3C - 150 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 839.7375
(i) | Termination | 4 | NOS | 70% | 209.9344 | 587.8162 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 209.9344 | 167.9475 | 0 | 0 | 0 | 0 | 0 | 0
12.4.17 | 3C - 240 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6014.9214
(i) | Termination | 27 | NOS | 70% | 222.7749 | 4210.445 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 27 | NOS | 20% | 222.7749 | 1202.9843 | 0 | 0 | 0 | 0 | 0 | 0
12.4.18 | 3.5C - 25 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3154.7396
(i) | Termination | 24 | NOS | 70% | 131.4475 | 2208.3177 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 24 | NOS | 20% | 131.4475 | 630.9479 | 0 | 0 | 0 | 0 | 0 | 0
12.4.19 | 3.5C - 50 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6923.9666
(i) | Termination | 48 | NOS | 70% | 144.2493 | 4846.7766 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 48 | NOS | 20% | 144.2493 | 1384.7933 | 0 | 0 | 0 | 0 | 0 | 0
12.4.20 | 3.5C - 95 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6555.1504
(i) | Termination | 40 | NOS | 70% | 163.8788 | 4588.6053 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 40 | NOS | 20% | 163.8788 | 1311.0301 | 0 | 0 | 0 | 0 | 0 | 0
12.4.21 | 3.5C - 185 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 891.0995
(i) | Termination | 4 | NOS | 70% | 222.7749 | 623.7696 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 222.7749 | 178.2199 | 0 | 0 | 0 | 0 | 0 | 0
12.4.22 | 4C - 10 AL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8655.4223
(i) | Termination | 60 | NOS | 70% | 144.257 | 6058.7956 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 60 | NOS | 20% | 144.257 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0
12.4.23 | 2C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 464.1143
(i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 | 0 | 0 | 0 | 0 | 0
12.4.24 | 2C - 2.5- CU | 274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 32275.1274 | 0 | 0 |  |  |  | 0
(i) | Termination | 274 | NOS | 70% | 117.7924 | 22592.5892 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 274 | NOS | 20% | 117.7924 | 6455.0255 | 0 | 0 | 0 | 0 | 0 | 0
12.4.25 | 3C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3750.6624
(i) | Termination | 26 | NOS | 70% | 144.2562 | 2625.4637 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 26 | NOS | 20% | 144.2562 | 750.1325 | 0 | 0 | 0 | 0 | 0 | 0
12.4.26 | 3C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 47116.884
(i) | Termination | 400 | NOS | 70% | 117.7922 | 32981.8188 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 400 | NOS | 20% | 117.7922 | 9423.3768 | 0 | 0 | 0 | 0 | 0 | 0
12.4.27 | 4C - 1.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3173.3042
(i) | Termination | 22 | NOS | 70% | 144.2411 | 2221.3129 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 22 | NOS | 20% | 144.2411 | 634.6608 | 0 | 0 | 0 | 0 | 0 | 0
12.4.28 | 10C - 2.5- CU | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5080.5046
(i) | Termination | 32 | NOS | 70% | 158.7658 | 3556.3532 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 32 | NOS | 20% | 158.7658 | 1016.1009 | 0 | 0 | 0 | 0 | 0 | 0
12.5 | LT PVC CONTROL CABLES (UNARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.5.1 | 2C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10406.6803
(i) | Termination | 96 | NOS | 70% | 108.4029 | 7284.6762 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 96 | NOS | 20% | 108.4029 | 2081.3361 | 0 | 0 | 0 | 0 | 0 | 0
12.5.2 | 2C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1300.7577
(i) | Termination | 12 | NOS | 70% | 108.3965 | 910.5304 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 12 | NOS | 20% | 108.3965 | 260.1515 | 0 | 0 | 0 | 0 | 0 | 0
12.5.3 | 3C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1084.171
(i) | Termination | 10 | NOS | 70% | 108.4171 | 758.9197 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 108.4171 | 216.8342 | 0 | 0 | 0 | 0 | 0 | 0
12.5.4 | 3C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8021.7516
(i) | Termination | 74 | NOS | 70% | 108.402 | 5615.2261 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 74 | NOS | 20% | 108.402 | 1604.3503 | 0 | 0 | 0 | 0 | 0 | 0
12.5.5 | 3C-16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 865.7279
(i) | Termination | 6 | NOS | 70% | 144.288 | 606.0095 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 6 | NOS | 20% | 144.288 | 173.1456 | 0 | 0 | 0 | 0 | 0 | 0
12.5.6 | 5C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5107.7326
(i) | Termination | 44 | NOS | 70% | 116.0848 | 3575.4128 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 44 | NOS | 20% | 116.0848 | 1021.5465 | 0 | 0 | 0 | 0 | 0 | 0
12.5.7 | 5C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2826.7655
(i) | Termination | 23 | NOS | 70% | 122.9028 | 1978.7359 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 23 | NOS | 20% | 122.9028 | 565.3531 | 0 | 0 | 0 | 0 | 0 | 0
12.5.8 | 7C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4440.0268
(i) | Termination | 34 | NOS | 70% | 130.589 | 3108.0188 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 34 | NOS | 20% | 130.589 | 888.0054 | 0 | 0 | 0 | 0 | 0 | 0
12.5.9 | 7C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 522.2833
(i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 | 0 | 0 | 0 | 0 | 0
12.5.10 | 10C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 576.7394
(i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 | 0 | 0 | 0 | 0 | 0
12.5.11 | 12C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6058.8575
(i) | Termination | 42 | NOS | 70% | 144.2585 | 4241.2003 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 42 | NOS | 20% | 144.2585 | 1211.7715 | 0 | 0 | 0 | 0 | 0 | 0
12.5.12 | 12C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2019.8254
(i) | Termination | 14 | NOS | 70% | 144.2732 | 1413.8778 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 14 | NOS | 20% | 144.2732 | 403.9651 | 0 | 0 | 0 | 0 | 0 | 0
12.5.13 | 16C-2.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2308.1951
(i) | Termination | 16 | NOS | 70% | 144.2622 | 1615.7366 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 16 | NOS | 20% | 144.2622 | 461.639 | 0 | 0 | 0 | 0 | 0 | 0
12.5.14 | 19C-1.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1442.4673
(i) | Termination | 10 | NOS | 70% | 144.2467 | 1009.7271 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 10 | NOS | 20% | 144.2467 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
12.6 | LT PVC CONTROL CABLES (ARMOURED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.6.1 | 2C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 464.1143
(i) | Termination | 4 | NOS | 70% | 116.0286 | 324.88 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 116.0286 | 92.8229 | 0 | 0 | 0 | 0 | 0 | 0
12.6.2 | 3C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 491.9612
(i) | Termination | 4 | NOS | 70% | 122.9903 | 344.3728 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 122.9903 | 98.3922 | 0 | 0 | 0 | 0 | 0 | 0
12.6.3 | 5C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 522.2833
(i) | Termination | 4 | NOS | 70% | 130.5708 | 365.5983 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 130.5708 | 104.4567 | 0 | 0 | 0 | 0 | 0 | 0
12.6.4 | 5C - 6 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 751.2464
(i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 | 0 | 0 | 0 | 0 | 0
12.6.5 | 7C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 576.7394
(i) | Termination | 4 | NOS | 70% | 144.1848 | 403.7176 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 144.1848 | 115.3479 | 0 | 0 | 0 | 0 | 0 | 0
12.6.6 | 12C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 634.9084
(i) | Termination | 4 | NOS | 70% | 158.7271 | 444.4359 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 158.7271 | 126.9817 | 0 | 0 | 0 | 0 | 0 | 0
12.6.7 | 14C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 693.0774
(i) | Termination | 4 | NOS | 70% | 173.2693 | 485.1542 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 173.2693 | 138.6155 | 0 | 0 | 0 | 0 | 0 | 0
12.6.8 | 16C - 2.5 SQ MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 751.2464
(i) | Termination | 4 | NOS | 70% | 187.8116 | 525.8724 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 4 | NOS | 20% | 187.8116 | 150.2493 | 0 | 0 | 0 | 0 | 0 | 0
12.7 | OPTICAL FIBRE CABLE JOINTING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3243.8496
(i) | Termination | 10 | NOS. | 70% | 324.385 | 2270.6947 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Testing of connected equipments/system | 10 | NOS. | 20% | 324.385 | 648.7699 | 0 | 0 | 0 | 0 | 0 | 0
13.00 | CABLE SHAFT COVERING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
13.10 | MS SHEET FOR COVERING CABLE SHAFTS | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1514652.9917 | 0 | 0 |  |  |  | 649136.9965
(i) | Fabrication and erection | 1000 | SQM | 70% | 2163.79 | 1514652.9917 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Painting as applicable | 1000 | SQM | 20% | 2163.79 | 432757.9976 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| SCH-5 - SWITCHGEAR & EQUIPMENT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.00 | HT SWITCHGEAR BOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2463347.3048 | 0 | 444210.2965
1.01 | 6.6KV UNIT SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 444209.9871 | 0 | 222104.9936 | HTSWGR
(i) | Placement,Alignment & Coupling as Applicable | 2 | SET | 50% | 222104.9936 | 222104.9936 | 2 | 0 | 2 | 222104.9936 | 0 | 222104.9936
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 20% | 222104.9936 | 88841.9974 | 0 | 0 | 0 | 0 | 0 | 0
1.02 | 6.6KV STATION SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 242296.1316 | 0 | 0
(i) | Placement,Alignment & Coupling as Applicable | 1 | SET | 50% | 242296.1316 | 121148.0658 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 242296.1316 | 48459.2263 | 0 | 0 | 0 | 0 | 0 | 0
1.03 | 6.6KV CHP SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 222105.303 | 0 | 111052.6515
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 | 0 | 1 | 111052.6515 | 0 | 111052.6515
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
1.04 | 6.6KV AHP SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 222105.303 | 0 | 111052.6515
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 1 | 0 | 1 | 111052.6515 | 0 | 111052.6515
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
1.05 | 6.6KV COMPRESSOR SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 222105.303 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
1.06 | 6.6KV RAW WATER SWITCHBOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 222105.303 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 222105.303 | 111052.6515 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 222105.303 | 44421.0606 | 0 | 0 | 0 | 0 | 0 | 0
1.07 | 33KV RAW WATER PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 888419.9742 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | SET | 50% | 222104.9936 | 444209.9871 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 4 | SET | 20% | 222104.9936 | 177683.9948 | 0 | 0 | 0 | 0 | 0 | 0
1.08 | BTS panel | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 20192.0663 | 0 | 14134.4464 | 378975.9372 | 0 | 141471.3217
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 10096.0331 | 10096.0331 | 2 | 0 | 2 | 10096.0331 | 0 | 10096.0331 |  |  |  | CONTROL PANELS
(ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 2 | 0 | 2 | 4038.4133 | 0 | 4038.4133
(iii) | Charging | 2 | NOS. | 20% | 10096.0331 | 4038.4133 | 0 | 0 | 0 | 0 | 0 | 0
1.09 | DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10816.9573 | 0 | 0 | 43267.8294 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | DC
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
2.00 | LT SWITCHGEAR BOARD & DCDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3535213.717 | 63168.4318 | 1513997.6623
2.01 | UNIT PMCC #1DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 154211.5687 | 0 | 107948.0981 | LTSWGR
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 | 0 | 1 | 77105.7844 | 0 | 77105.7844
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 | 0 | 1 | 30842.3137 | 0 | 30842.3137
(iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 | 0 | 0 | 0 | 0 | 0
2.02 | TURBINE MCC #1KA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 114657.8914 | 0 | 80260.524
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 114657.8914 | 57328.9457 | 1 | 0 | 1 | 57328.9457 | 0 | 57328.9457
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 1 | 0 | 1 | 22931.5783 | 0 | 22931.5783
(iii) | Charging | 1 | NO. | 20% | 114657.8914 | 22931.5783 | 0 | 0 | 0 | 0 | 0 | 0
2.03 | TURBINE VALVES & ACDB #1KB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 165064.4176 | 0 | 115545.0923
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 165064.4176 | 82532.2088 | 1 | 0 | 1 | 82532.2088 | 0 | 82532.2088
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 1 | 0 | 1 | 33012.8835 | 0 | 33012.8835
(iii) | Charging | 1 | NO. | 20% | 165064.4176 | 33012.8835 | 0 | 0 | 0 | 0 | 0 | 0
2.04 | BOILER VALVES & ACDB #1HB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 147756.667 | 0 | 103429.6669
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 147756.667 | 73878.3335 | 1 | 0 | 1 | 73878.3335 | 0 | 73878.3335
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 147756.667 | 29551.3334 | 1 | 0 | 1 | 29551.3334 | 0 | 29551.3334
(iii) | Charging | 1 | NO. | 20% | 147756.667 | 29551.3334 | 0 | 0 | 0 | 0 | 0 | 0
2.05 | BOILER MCC #1HA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 131531.8498 | 0 | 92072.2948
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 131531.8498 | 65765.9249 | 1 | 0 | 1 | 65765.9249 | 0 | 65765.9249
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 131531.8498 | 26306.37 | 1 | 0 | 1 | 26306.37 | 0 | 26306.37
(iii) | Charging | 1 | NO. | 20% | 131531.8498 | 26306.37 | 0 | 0 | 0 | 0 | 0 | 0
2.06 | UNIT SERVICE ACDB #1QA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 154211.5687 | 0 | 107948.0981
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 154211.5687 | 77105.7844 | 1 | 0 | 1 | 77105.7844 | 0 | 77105.7844
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 1 | 0 | 1 | 30842.3137 | 0 | 30842.3137
(iii) | Charging | 1 | NO. | 20% | 154211.5687 | 30842.3137 | 0 | 0 | 0 | 0 | 0 | 0
2.07 | SOOT BLOWER MCC (Supply by Tnchy) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 115514.337 | 0 | 57757.1685
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 115514.337 | 57757.1685 | 1 | 0 | 1 | 57757.1685 | 0 | 57757.1685
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 115514.337 | 23102.8674 | 0 | 0 | 0 | 0 | 0 | 0
2.08 | ESP LT SWITCHGEAR(SUPPLY BY BAP RANIPET) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 262486.9602 | 0 | 183740.8721
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 131243.4801 | 131243.4801 | 2 | 0 | 2 | 131243.4801 | 0 | 131243.4801
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 131243.4801 | 52497.392 | 2 | 0 | 2 | 52497.392 | 0 | 52497.392
(iii) | Charging | 2 | NO | 20% | 131243.4801 | 52497.392 | 0 | 0 | 0 | 0 | 0 | 0
2.09 | UNIT EMERGENCY BOARD #1DG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 181614.1148 | 0 | 127129.8803
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 181614.1148 | 90807.0574 | 1 | 0 | 1 | 90807.0574 | 0 | 90807.0574
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 181614.1148 | 36322.823 | 1 | 0 | 1 | 36322.823 | 0 | 36322.823
(iii) | Charging | 1 | NO. | 20% | 181614.1148 | 36322.823 | 0 | 0 | 0 | 0 | 0 | 0
2.10 | 220V UNIT DCDB #1FA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 93457.15 | 0 | 65420.005
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 1 | 0 | 1 | 46728.575 | 0 | 46728.575
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 1 | 0 | 1 | 18691.43 | 0 | 18691.43
(iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 | 0 | 0 | 0 | 0 | 0
2.11 | ESP A/C & VENT MCC #1TB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 52569.2988 | 0 | 36798.5092
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 52569.2988 | 26284.6494 | 1 | 0 | 1 | 26284.6494 | 0 | 26284.6494
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 1 | 0 | 1 | 10513.8598 | 0 | 10513.8598
(iii) | Charging | 1 | NO. | 20% | 52569.2988 | 10513.8598 | 0 | 0 | 0 | 0 | 0 | 0
2.12 | STATION PMCC #0DA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 0 | 64567.2724
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 | 0 | 1 | 64567.2724 | 0 | 64567.2724
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.13 | AC MCC #0TA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 78529.9964 | 15705.9993 | 54970.9975
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 78529.9964 | 39264.9982 | 1 | 0 | 1 | 39264.9982 | 0 | 39264.9982
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 | 1 | 1 | 0 | 15705.9993 | 15705.9993
(iii) | Charging | 1 | NO. | 20% | 78529.9964 | 15705.9993 | 0 | 0 | 0 | 0 | 0 | 0
2.14 | VENTILATION & AIR WASHER MCC #1TA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 116605.9338 | 0 | 58302.9669
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 116605.9338 | 58302.9669 | 1 | 0 | 1 | 58302.9669 | 0 | 58302.9669
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 116605.9338 | 23321.1868 | 0 | 0 | 0 | 0 | 0 | 0
2.15 | MISC SERVICE MCC #0SA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 95836.5094 | 0 | 67085.5566
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 1 | 0 | 1 | 47918.2547 | 0 | 47918.2547
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 1 | 0 | 1 | 19167.3019 | 0 | 19167.3019
(iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 | 0 | 0 | 0 | 0 | 0
2.16 | COOLING TOWER PMCC #1DC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 191474.9966 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 191474.9966 | 95737.4983 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 191474.9966 | 38294.9993 | 0 | 0 | 0 | 0 | 0 | 0
2.17 | CWPH AND CHLORINATION MCC # 0SB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 126556.5445 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 126556.5445 | 63278.2722 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 126556.5445 | 25311.3089 | 0 | 0 | 0 | 0 | 0 | 0
2.18 | PTP PMCC #1DD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.19 | FW & CLARIFIED WATER MCC #0SC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 140618.589 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0
2.20 | ETP PMCC #1DE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.21 | ADMIN BUILDING MCC #0SB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 140618.589 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 140618.589 | 70309.2945 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 140618.589 | 28123.7178 | 0 | 0 | 0 | 0 | 0 | 0
2.22 | O&M ACDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 95836.5094 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 95836.5094 | 47918.2547 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 95836.5094 | 19167.3019 | 0 | 0 | 0 | 0 | 0 | 0
2.23 | STP MCC #0SF | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.24 | WATER PMCC # 0DB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.25 | MODIFICATION OF DM PLANT MCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 0 | 64567.2724
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 | 0 | 1 | 64567.2724 | 0 | 64567.2724
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.26 | MODIFICATION OF FUEL OIL MCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 25826.9089 | 90394.1813
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 1 | 0 | 1 | 64567.2724 | 0 | 64567.2724
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 1 | 1 | 0 | 25826.9089 | 25826.9089
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.27 | 220V DC FUSE DB (WALL MOUNTED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 36059.206 | 10817.7618 | 18029.603
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5 | 7211.8412 | 10817.7618 | 18029.603
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0
2.28 | 415V AC FUSE DB (WALL MOUNTED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 36059.206 | 10817.7618 | 18029.603
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO. | 50% | 7211.8412 | 18029.603 | 2 | 3 | 5 | 7211.8412 | 10817.7618 | 18029.603
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 5 | NO. | 20% | 7211.8412 | 7211.8412 | 0 | 0 | 0 | 0 | 0 | 0
2.29 | LV SWITCHGEAR FOR SWITCHYARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.29.1 | SWITCHYARD PMCC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 129134.5447 | 0 | 0 |  |  |  | 129134.5447
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 129134.5447 | 64567.2724 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 129134.5447 | 25826.9089 | 0 | 0 | 0 | 0 | 0 | 0
2.29.2 | SWITCHYARD 415V ACDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7211.7174 | 0 | 0 |  |  |  | 7211.7174
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 7211.7174 | 3605.8587 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0
2.29.3 | SWITCHYARD 220V DCDB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 93457.15 | 0 | 0 |  |  |  | 93457.15
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 93457.15 | 46728.575 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 93457.15 | 18691.43 | 0 | 0 | 0 | 0 | 0 | 0
2.30 | DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10816.9573 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
3.00 | LT PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.01 | FEEDER FOR ELEVATOR (3 PHASE - 30 KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14422.8161
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
3.02 | FEEDER FOR ELEVATOR (1 PHASE - 6 KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14422.8161
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO. | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO. | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
4.00 | PROTECTION RELAY PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
4.01 | GENERATOR PROTECTION & RELAY PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 216336.6716 | 0 | 108168.3358
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NOS. | 50% | 43267.3343 | 108168.3358 | 5 | 0 | 5 | 108168.3358 | 0 | 108168.3358
(ii) | Pre-Commissioning Checks ,Testing | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 5 | NOS. | 20% | 43267.3343 | 43267.3343 | 0 | 0 | 0 | 0 | 0 | 0
4.02 | STATION TRANSFORMER RELAY PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14422.8161
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
4.03 | ELECTRICAL CONTROL DESK CUM PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 36055.4931 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 36055.4931 | 18027.7466 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 36055.4931 | 7211.0986 | 0 | 0 | 0 | 0 | 0 | 0
5.00 | DIGITAL STATIC EXCITATION SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5.1 | DIGITAL AUOTOMATIC VOLTAGE REGULATOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 38337.079 | 0 | 19168.5395
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 38337.079 | 19168.5395 | 1 | 0 | 1 | 19168.5395 | 0 | 19168.5395
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 38337.079 | 7667.4158 | 0 | 0 | 0 | 0 | 0 | 0
5.2 | HT DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10816.9573 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
5.3 | LT DATA CONCENTRATOR PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10816.9573 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 10816.9573 | 5408.4787 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 10816.9573 | 2163.3915 | 0 | 0 | 0 | 0 | 0 | 0
5.4 | VARIABLE FREQUENCY DRIVE FOR ID FAN | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 240313.4353 | 0 | 141184.5609
5.4.1 | VARIABLE FREQUENCY DRIVE FOR ID FANS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 135174.2188 | 0 | 67587.1094 | ID
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 | 0 | 2 | 67587.1094 | 0 | 67587.1094
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0
5.4.2 | 6.6KV VFD SWITCH GEAR PANEL FOR ID FAN | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 105139.2165 | 0 | 73597.4515
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 2 | 0 | 2 | 52569.6082 | 0 | 52569.6082
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 2 | 0 | 2 | 21027.8433 | 0 | 21027.8433
(iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 | 0 | 0 | 0 | 0 | 0
5.5 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 240313.4353 | 52569.6082 | 120156.7176
5.5.1 | VARIABLE FREQUENCY DRIVE FOR CEP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 135174.2188 | 0 | 67587.1094 | ID
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 67587.1094 | 67587.1094 | 2 | 0 | 2 | 67587.1094 | 0 | 67587.1094
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 20% | 67587.1094 | 27034.8438 | 0 | 0 | 0 | 0 | 0 | 0
5.5.2 | 6.6KV VFD SWITCH GEAR PANEL FOR CEP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 105139.2165 | 52569.6082 | 52569.6082
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | SET | 50% | 52569.6082 | 52569.6082 | 0 | 2 | 2 | 0 | 52569.6082 | 52569.6082
(ii) | Pre-Commissioning Checks ,Testing | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | SET | 20% | 52569.6082 | 21027.8433 | 0 | 0 | 0 | 0 | 0 | 0
6.00 | LOCAL CONTROL PANELS FOR PUMPS ETC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 68054.6272 | 0 | 0
6.01 | LOCAL FAN CONTROL PANEL FOR ST | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6490.7932 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
6.02 | LOCAL FAN CONTROL PANEL FOR GT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6490.7932 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
6.03 | LOCAL FAN CONTROL PANEL FOR UAT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12980.9676 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0
6.04 | PANEL FOR OIL CENTRIFUGE UNIT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6490.7932 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
6.05 | PANEL FOR ON LOAD TUBE CLEANING SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12980.9676 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 6490.4838 | 6490.4838 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NO | 20% | 6490.4838 | 2596.1935 | 0 | 0 | 0 | 0 | 0 | 0
6.06 | PANEL FOR CENTRAL OIL PURIFICATION UNIT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7211.7174 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 7211.7174 | 3605.8587 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 7211.7174 | 1442.3435 | 0 | 0 | 0 | 0 | 0 | 0
6.07 | LCP for Sump Pumps of Condensor Pit, & Trf oil Pit | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15408.5948 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | No | 50% | 3852.1487 | 7704.2974 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | No | 20% | 3852.1487 | 3081.719 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 4 | No | 20% | 3852.1487 | 3081.719 | 0 | 0 | 0 | 0 | 0 | 0
7.00 | MISC ITEMS OF ESP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
7.01 | ELECTRONIC CONTROLLER (WITH BAPCON) | 28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 201930.0136 | 0 | 100965.0068 | 201930.0136 | 0 | 100965.0068 | 57694.2896
(i) | Placement,Aliggnment & Coupling as Applicable | 36 | NO | 50% | 7211.7862 | 129812.1516 | 28 | 0 | 28 | 100965.0068 | 0 | 100965.0068 |  |  |  | HVR
(ii) | Pre-Commissioning Checks ,Testing | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 36 | NO | 20% | 7211.7862 | 51924.8606 | 0 | 0 | 0 | 0 | 0 | 0
7.02 | RAPPER CONTROL PANEL (WITH RAPCON) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14423.4349 | 0 | 0 | 151821.6895 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | control panel
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0
7.03 | STATCON CONTROL PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14423.4349 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 7211.7174 | 7211.7174 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NO | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0
7.04 | IOS PERSONAL COMPUTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5769.2502 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 5769.2502 | 2884.6251 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 5769.2502 | 1153.85 | 0 | 0 | 0 | 0 | 0 | 0
7.05 | DATA LOGGER PC | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2884.9345 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 2884.9345 | 1442.4673 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 2884.9345 | 576.9869 | 0 | 0 | 0 | 0 | 0 | 0
7.06 | DOT MATRIX PRINTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1081.6957 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 1081.6957 | 540.8479 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 1081.6957 | 216.3391 | 0 | 0 | 0 | 0 | 0 | 0
7.07 | COMPUTER FURNITURE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 721.543 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
8.00 | MISCELLANEOUS-1 (ONLY COMMISSIONING RATE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
8.01 | THERMOSTAT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 23080.7137 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 32 | NO | 50% | 721.2723 | 11540.3568 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 32 | NO | 20% | 721.2723 | 4616.1427 | 0 | 0 | 0 | 0 | 0 | 0
8.02 | HOPPER/ SHAFT/ SUPPORT INSULATOR HEATER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 585666.4571 | 0 | 0 | 617402.5931 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 812 | SET | 50% | 721.2641 | 292833.2286 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 812 | SET | 20% | 721.2641 | 117133.2914 | 0 | 0 | 0 | 0 | 0 | 0
8.03 | ELECTRICALLY OPERATED HOIST | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8655.4223 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0
8.04 | ASH LEVEL INDICATORS & CONTROLLERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 80781.879 | 0 | 0 | 80781.879 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 112 | SET | 50% | 721.2668 | 40390.9395 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 112 | SET | 20% | 721.2668 | 16156.3758 | 0 | 0 | 0 | 0 | 0 | 0
8.05 | RAPPING MOTORS FOR ESP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 103861.9739 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 60 | NO | 50% | 1731.0329 | 51930.9869 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 60 | NO | 20% | 1731.0329 | 20772.3948 | 0 | 0 | 0 | 0 | 0 | 0
8.06 | TESTING OF GENERATOR / EXCITER / PMG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14422.8161 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 14422.8161 | 7211.408 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 14422.8161 | 2884.5632 | 0 | 0 | 0 | 0 | 0 | 0
8.07 | COMMISSIONING OF HYDROGEN GAS DRIER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1442.4673 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NOS. | 50% | 721.2336 | 721.2336 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NOS. | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
8.08 | COMMISSIONING OF EXCITER HEATER, STROBOSCOPE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 721.543 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | SET | 50% | 721.543 | 360.7715 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | SET | 20% | 721.543 | 144.3086 | 0 | 0 | 0 | 0 | 0 | 0
9.00 | JUNCTION BOX/ MARSHALLING BOX /PB/STARTERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
9.01 | FRP JUNCTION BOX- 24 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 23601.1405 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 70 | NO | 50% | 337.1592 | 11800.5703 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 70 | NO | 20% | 337.1592 | 4720.2281 | 0 | 0 | 0 | 0 | 0 | 0
9.02 | FRP JUNCTION BOX- 48 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16857.8691 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO | 50% | 337.1574 | 8428.9346 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 50 | NO | 20% | 337.1574 | 3371.5738 | 0 | 0 | 0 | 0 | 0 | 0
9.03 | FRP JUNCTION BOX- 72 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6743.2714 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 337.1636 | 3371.6357 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 20 | NO | 20% | 337.1636 | 1348.6543 | 0 | 0 | 0 | 0 | 0 | 0
9.04 | FRP JUNCTION BOX- 96 WAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1685.6631 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 337.1326 | 842.8316 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 337.1326 | 337.1326 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 5 | NO | 20% | 337.1326 | 337.1326 | 0 | 0 | 0 | 0 | 0 | 0
9.05 | PUSH BUTTON/ STARTERS FOR RAPPING MOTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 72126.4567 | 21637.937 | 21637.937
(i) | Placement,Aliggnment & Coupling as Applicable | 100 | NO | 50% | 721.2646 | 36063.2284 | 0 | 60 | 60 | 0 | 21637.937 | 21637.937
(ii) | Pre-Commissioning Checks ,Testing | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 100 | NO | 20% | 721.2646 | 14425.2913 | 0 | 0 | 0 | 0 | 0 | 0
9.06 | FRP JUNCTION BOX FOR HEATERS(JBHH,SHHH,SUHH) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 13486.5428 | 5394.6171 | 5394.6171
(i) | Placement,Aliggnment & Coupling as Applicable | 40 | NO | 50% | 337.1636 | 6743.2714 | 0 | 32 | 32 | 0 | 5394.6171 | 5394.6171
(ii) | Pre-Commissioning Checks ,Testing | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 40 | NO | 20% | 337.1636 | 2697.3086 | 0 | 0 | 0 | 0 | 0 | 0
9.07 | FRP JUNCTION BO X(CONTROL-HH, TH, ALI) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 26972.4668 | 5394.4934 | 5394.4934
(i) | Placement,Aliggnment & Coupling as Applicable | 80 | NO | 50% | 337.1558 | 13486.2334 | 0 | 32 | 32 | 0 | 5394.4934 | 5394.4934
(ii) | Pre-Commissioning Checks ,Testing | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 80 | NO | 20% | 337.1558 | 5394.4934 | 0 | 0 | 0 | 0 | 0 | 0
10.00 | PUSH BUTTON, BOX & STARTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.10 | LOCAL PUSH BUTTON STATIONS (NON FLAME PROOF) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10.1.1 | TYPE A | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 108189.3756 | 0 | 0 | 244211.3766 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 150 | NO | 50% | 721.2625 | 54094.6878 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 150 | NO | 20% | 721.2625 | 21637.8751 | 0 | 0 | 0 | 0 | 0 | 0
10.1.2 | TYPE C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15146.8344 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 1009.789 | 7573.4172 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 15 | NO | 20% | 1009.789 | 3029.3669 | 0 | 0 | 0 | 0 | 0 | 0
10.20 | PUSH BUTTON BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 53084.7751 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 46 | NO | 50% | 1154.0169 | 26542.3876 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 46 | NO | 20% | 1154.0169 | 10616.955 | 0 | 0 | 0 | 0 | 0 | 0
10.30 | LOCAL MOTOR STARTER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 57701.1654 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 50 | NO. | 50% | 1154.0233 | 28850.5827 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 50 | NO. | 20% | 1154.0233 | 11540.2331 | 0 | 0 | 0 | 0 | 0 | 0
11.00 | DC STRATER PANEL/ STARTING CABINET | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
11.10 | LOCALLY MOUNTED STARTER MODULE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
11.1.1 | FOR MOTOR RATING upto 0.75 KW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10089.2261 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 20 | NO | 50% | 504.4613 | 5044.6131 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 20 | NO | 20% | 504.4613 | 2017.8452 | 0 | 0 | 0 | 0 | 0 | 0
11.1.4 | FOR MOTOR RATING above 0.75kW upto 1.5 kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8655.4223 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 15 | NO | 50% | 577.0282 | 4327.7112 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 15 | NO | 20% | 577.0282 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0
11.1.5 | FOR MOTOR RATING above 1.5W upto 2.2kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6487.0803 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 10 | NO | 50% | 648.708 | 3243.5402 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 10 | NO | 20% | 648.708 | 1297.4161 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 10 | NO | 20% | 648.708 | 1297.4161 | 0 | 0 | 0 | 0 | 0 | 0
11.1.6 | SUITABLE FOR MOTOR RATING above 2.2W upto 4.5kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3606.4775 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 5 | NO | 50% | 721.2955 | 1803.2388 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 5 | NO | 20% | 721.2955 | 721.2955 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 5 | NO | 20% | 721.2955 | 721.2955 | 0 | 0 | 0 | 0 | 0 | 0
11.1.6 | SUITABLE FOR MOTOR RATING above 4.5W upto 6kW | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1442.4673 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 721.2336 | 721.2336 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NO | 20% | 721.2336 | 288.4935 | 0 | 0 | 0 | 0 | 0 | 0
12.00 | DC STARTER LOCAL PANEL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12.01 | STARTER CABINET FOR DC JACKING OIL MOTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6490.7932 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
12.02 | STARTER CABINET FOR DC SEAL OIL MOTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6490.7932 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
12.03 | STARTING CABINET FOR DC EMERGENCY LOP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6490.7932 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 6490.7932 | 3245.3966 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 6490.7932 | 1298.1586 | 0 | 0 | 0 | 0 | 0 | 0
12.04 | SCANNER AIR FAN DC MOTOR STARTER BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4327.4018 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 1 | NO | 50% | 4327.4018 | 2163.7009 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 1 | NO | 20% | 4327.4018 | 865.4804 | 0 | 0 | 0 | 0 | 0 | 0
12.05 | FURNACE TEMPERATURE PROBE LOCAL STARTER BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8655.4223 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | NO | 50% | 4327.7112 | 4327.7112 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | NO | 20% | 4327.7112 | 1731.0845 | 0 | 0 | 0 | 0 | 0 | 0
13.00 | BATTERY SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
13.01 | 220V BATTERY (EACH SET 170 CELLS) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 877111.6745 | 0 | 146185.2791 | 371108.6841 | 0 | 194754.944 |  | 742217.3682 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | SET | 50% | 146185.2791 | 438555.8373 | 2 | 0 | 2 | 146185.2791 | 0 | 146185.2791 | [5 empty] | btg |  | bop
(ii) | Pre-Commissioning Checks ,Testing | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 6 | SET | 20% | 146185.2791 | 175422.3349 | 0 | 0 | 0 | 0 | 0 | 0
13.02 | 220V FCB CHARGER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 178481.0338 | 0 | 41645.5746
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 29746.839 | 89240.5169 | 2 | 0 | 2 | 29746.839 | 0 | 29746.839
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 29746.839 | 35696.2068 | 2 | 0 | 2 | 11898.7356 | 0 | 11898.7356
(iii) | Charging | 6 | NO | 20% | 29746.839 | 35696.2068 | 0 | 0 | 0 | 0 | 0 | 0
13.03 | 220V DC BATTERY HEALTH MONITORING SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 23112.8923 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 3852.1487 | 11556.4461 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 6 | NO | 20% | 3852.1487 | 4622.5785 | 0 | 0 | 0 | 0 | 0 | 0
13.04 | DISCHARGE RESISTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17310.2258 | 0 | 4039.0527
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 | 0 | 2 | 2885.0376 | 0 | 2885.0376
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 2 | 0 | 2 | 1154.0151 | 0 | 1154.0151
(iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0
13.05 | 220 V DC ISOLATION BOX | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17310.2258 | 0 | 2885.0376
(i) | Placement,Aliggnment & Coupling as Applicable | 6 | NO | 50% | 2885.0376 | 8655.1129 | 2 | 0 | 2 | 2885.0376 | 0 | 2885.0376
(ii) | Pre-Commissioning Checks ,Testing | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 6 | NO | 20% | 2885.0376 | 3462.0452 | 0 | 0 | 0 | 0 | 0 | 0
14.00 | DG SET | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1947513.9609 | 0 | 0
14.01 | DG Set 750kVA,415V, 0.8pf with acoustic enclosure | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 288447.6578 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 144223.8289 | 144223.8289 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | Set | 20% | 144223.8289 | 57689.5316 | 0 | 0 | 0 | 0 | 0 | 0
14.02 | 990 litres fuel tank on stand including Fuel Piping | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 28845.6321 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | Set | 50% | 14422.8161 | 14422.8161 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | Set | 20% | 14422.8161 | 5769.1264 | 0 | 0 | 0 | 0 | 0 | 0
14.03 | Battery with stand (24V DC 360AH) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 115381.9097 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 28845.4774 | 57690.9548 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 4 | set | 20% | 28845.4774 | 23076.3819 | 0 | 0 | 0 | 0 | 0 | 0
14.04 | Battery Charger | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 34617.3576 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 4 | set | 50% | 8654.3394 | 17308.6788 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 4 | set | 20% | 8654.3394 | 6923.4715 | 0 | 0 | 0 | 0 | 0 | 0
14.05 | Exhaust Piping and Support Structure | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1391323.7125 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 695661.8562 | 695661.8562 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | set | 20% | 695661.8562 | 278264.7425 | 0 | 0 | 0 | 0 | 0 | 0
14.06 | DG AMF Panel | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14423.4349 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 7211.7174 | 7211.7174 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | set | 20% | 7211.7174 | 2884.687 | 0 | 0 | 0 | 0 | 0 | 0
14.07 | DG Aux DB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10097.8896 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 5048.9448 | 5048.9448 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | set | 20% | 5048.9448 | 2019.5779 | 0 | 0 | 0 | 0 | 0 | 0
14.08 | Alternator extension terminal box | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 32176.1164 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | set | 50% | 16088.0582 | 16088.0582 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | set | 20% | 16088.0582 | 6435.2233 | 0 | 0 | 0 | 0 | 0 | 0
14.09 | Miscellaneous cables for DG Set | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 32200.2503 | 0 | 0
(i) | Placement,Aliggnment & Coupling as Applicable | 2 | lot | 50% | 16100.1252 | 16100.1252 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Pre-Commissioning Checks ,Testing | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 | 0 | 0 | 0 | 0 | 0
(iii) | Charging | 2 | lot | 20% | 16100.1252 | 6440.0501 | 0 | 0 | 0 | 0 | 0 | 0
15.00 | MISCELLANEOUS FOR MOTORS & ACTUATORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 181758.2996 | 0 | 0
15.01 | DRYING OUT, TESTING OF OF HT MOTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 181758.2996 | 0 | 0 | HT Motor
(i) | Testing, commissioning of individual items,limit SW | 42 | NO | 50% | 4327.5786 | 90879.1498 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 42 | NO | 40% | 4327.5786 | 72703.3198 | 0 | 0 | 0 | 0 | 0 | 0
15.02 | DRYING OUT, TESTING OF OF LT MOTORS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 432758.7402 | 0 | 0 | 570012.1911 | 0 | 0
(i) | Testing, commissioning of individual items,limit SW | 200 | NO | 50% | 2163.7937 | 216379.3701 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 200 | NO | 40% | 2163.7937 | 173103.4961 | 0 | 0 | 0 | 0 | 0 | 0
15.03 | MOUNTING OF CTs FOR HT MOTORS/ PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14425.2913 | 0 | 0 | 137253.4509 | 0 | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 | 0 | 0 | 0 | 0 | 0
15.04 | MOUNTING OF MODULES INSIDE LT PANELS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14425.2913 | 0 | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 1442.5291 | 7212.6457 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 1442.5291 | 5770.1165 | 0 | 0 | 0 | 0 | 0 | 0
15.05 | CABLE TRAY RE-ROUTING & RELAYING OF CABLES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 108402.8682 | 0 | 0
(i) | Testing, commissioning of individual items,limit SW | 1000 | MTR | 50% | 108.4029 | 54201.4341 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 1000 | MTR | 40% | 108.4029 | 43361.1473 | 0 | 0 | 0 | 0 | 0 | 0
16.00 | ACTUATORS COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 432758.7402 | 0 | 0 | 519276.4532 | 0 | 0
(i) | Testing, commissioning of individual items,limit SW | 300 | NO | 50% | 1442.5291 | 216379.3701 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 300 | NO | 40% | 1442.5291 | 173103.4961 | 0 | 0 | 0 | 0 | 0 | 0
17.00 | SOOT BLOWERS COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 86517.713 | 0 | 0 | 86517.713 | 0 | 0
(i) | Testing, commissioning of individual items,limit SW | 80 | NO | 50% | 1081.4714 | 43258.8565 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 80 | NO | 40% | 1081.4714 | 34607.0852 | 0 | 0 | 0 | 0 | 0 | 0
18.00 | ELECTRICALLY OPTD MISC HOISTS COMMISSIONING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
(i) | Testing, commissioning of individual items,limit SW | 10 | NO | 50% | 2163.7628 | 10818.8138 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Commissioning of individual items | 10 | NO | 40% | 2163.7628 | 8655.051 | 0 | 0 | 0 | 0 | 0 | 0
19.00 | FABRICATION (SUPPLY OF MATL BY BHEL) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
19.01 | BASE FRAMES FOR SWITCHGEAR, PANEL, PB | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 519207.7643 | 0 | 0
(i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 | 0 | 0 | 0 | 0 | 0
20.00 | CHEQUERED PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
20.01 | INSTALLATION OF CHEQUERED PLATES 6 TO 8 MM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1038415.5286 | 0 | 84501.0636
(i) | Fabrication and erection | 40 | MT | 70% | 25960.3882 | 726890.87 | 4.65 | 0 | 4.65 | 84501.0636 | 0 | 84501.0636
(ii) | Painting as applicable | 40 | MT | 20% | 25960.3882 | 207683.1057 | 0 | 0 | 0 | 0 | 0 | 0
21.00 | INSERT PLATES/ ANCHOR FASTENERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
21.01 | FABRICATION OF INSERT PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 25960.6976 | 0 | 0
(i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 | 0 | 0 | 0 | 0 | 0
21.02 | INSTALLATION OF FRICTION ANCHOR FASTENERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 888563.5403 | 0 | 0
(i) | Fabrication and erection | 3000 | SET | 70% | 296.1878 | 621994.4782 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Painting as applicable | 3000 | SET | 20% | 296.1878 | 177712.7081 | 0 | 0 | 0 | 0 | 0 | 0
22.00 | CANOPIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
22.01 | FABRICATION AND INSTALLATION OF CANOPIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 60560.7283 | 0 | 0
(i) | Fabrication and erection | 50 | SQM | 70% | 1211.2146 | 42392.5098 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Painting as applicable | 50 | SQM | 20% | 1211.2146 | 12112.1457 | 0 | 0 | 0 | 0 | 0 | 0
23.00 | IRREGULAR BENDS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
23.1 | FABRICATION OF IRREGULAR BENDS (LADER-TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
23.1.1 | 600 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 541161.6084 | 0 | 113643.9378
(i) | Fabrication and erection complete as applicable | 1000 | NO | 70% | 541.1616 | 378813.1259 | 300 | 0 | 300 | 113643.9378 | 0 | 113643.9378
(ii) | Final painting and marking of tray nos | 1000 | NO | 20% | 541.1616 | 108232.3217 | 0 | 0 | 0 | 0 | 0 | 0
23.1.2 | 450 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 270580.4948 | 0 | 0
(i) | Fabrication and erection complete as applicable | 500 | NO | 70% | 541.161 | 189406.3464 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 500 | NO | 20% | 541.161 | 54116.099 | 0 | 0 | 0 | 0 | 0 | 0
23.1.3 | 300 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 151337.1541 | 0 | 105936.0079
(i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 300 | 0 | 300 | 105936.0079 | 0 | 105936.0079
(ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 | 0 | 0 | 0 | 0 | 0
23.1.4 | 150 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 151337.1541 | 0 | 70624.0053
(i) | Fabrication and erection complete as applicable | 300 | NO | 70% | 504.4572 | 105936.0079 | 200 | 0 | 200 | 70624.0053 | 0 | 70624.0053
(ii) | Final painting and marking of tray nos | 300 | NO | 20% | 504.4572 | 30267.4308 | 0 | 0 | 0 | 0 | 0 | 0
23.1.5 | 100 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 25223.0653 | 0 | 7062.4583
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 504.4613 | 17656.1457 | 20 | 0 | 20 | 7062.4583 | 0 | 7062.4583
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 504.4613 | 5044.6131 | 0 | 0 | 0 | 0 | 0 | 0
23.1.6 | 50 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12611.5326 | 0 | 3531.2291
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 252.2307 | 8828.0729 | 20 | 0 | 20 | 3531.2291 | 0 | 3531.2291
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 252.2307 | 2522.3065 | 0 | 0 | 0 | 0 | 0 | 0
23.2 | FABRICATION OF IRREGULAR BENDS (PERFORATED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
23.2.1 | 600 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 57701.1654 | 0 | 40390.8158
(i) | Fabrication and erection complete as applicable | 100 | NO | 70% | 577.0117 | 40390.8158 | 100 | 0 | 100 | 40390.8158 | 0 | 40390.8158
(ii) | Final painting and marking of tray nos | 100 | NO | 20% | 577.0117 | 11540.2331 | 0 | 0 | 0 | 0 | 0 | 0
23.2.2 | 450 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 40390.9395 | 0 | 28273.6577
(i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 577.0134 | 28273.6577 | 70 | 0 | 70 | 28273.6577 | 0 | 28273.6577
(ii) | Final painting and marking of tray nos | 70 | NO | 20% | 577.0134 | 8078.1879 | 0 | 0 | 0 | 0 | 0 | 0
23.2.3 | 300 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 37881.0094 | 0 | 26516.7066
(i) | Fabrication and erection complete as applicable | 70 | NO | 70% | 541.1573 | 26516.7066 | 70 | 0 | 70 | 26516.7066 | 0 | 26516.7066
(ii) | Final painting and marking of tray nos | 70 | NO | 20% | 541.1573 | 7576.2019 | 0 | 0 | 0 | 0 | 0 | 0
23.2.4 | 150 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 27057.8638 | 0 | 11364.3028
(i) | Fabrication and erection complete as applicable | 50 | NO | 70% | 541.1573 | 18940.5047 | 30 | 0 | 30 | 11364.3028 | 0 | 11364.3028
(ii) | Final painting and marking of tray nos | 50 | NO | 20% | 541.1573 | 5411.5728 | 0 | 0 | 0 | 0 | 0 | 0
23.2.5 | 100 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16234.7183 | 0 | 5682.1514
(i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 541.1573 | 11364.3028 | 15 | 0 | 15 | 5682.1514 | 0 | 5682.1514
(ii) | Final painting and marking of tray nos | 30 | NO | 20% | 541.1573 | 3246.9437 | 0 | 0 | 0 | 0 | 0 | 0
23.2.6 | 50 MM WIDE TRAYS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8117.6686 | 0 | 2841.184
(i) | Fabrication and erection complete as applicable | 30 | NO | 70% | 270.589 | 5682.368 | 15 | 0 | 15 | 2841.184 | 0 | 2841.184
(ii) | Final painting and marking of tray nos | 30 | NO | 20% | 270.589 | 1623.5337 | 0 | 0 | 0 | 0 | 0 | 0
24.00 | RUBBER MAT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
24.01 | INSULATING MAT FOR SWITCHGEAR ROOM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 64294.6826 | 0 | 0
(i) | On completion of supply | 1 | SET | 80% | 64294.6826 | 51435.746 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/ installation of material/ item | 1 | SET | 10% | 64294.6826 | 6429.4683 | 0 | 0 | 0 | 0 | 0 | 0
25.00 | DISPLAY BOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
25.01 | ELECTRIC SHOCK TREATMENT DISPLAY BOARD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 36062.9189 | 0 | 0
(i) | On completion of supply | 50 | NO | 80% | 721.2584 | 28850.3352 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/ installation of material/ item | 50 | NO | 10% | 721.2584 | 3606.2919 | 0 | 0 | 0 | 0 | 0 | 0
26.00 | Electrical Lab equipment | 1 | LOT | 90% | 213391.7116 | 192052.5405 | 0 | 0 | 0 | 0 | 0 | 0 | 213391.7116 | 0 | 0
27.00 | COMMISSIONING SERVICES FOR TESTING | 300 | MDY | 90% | 7190.4507 | 1941421.6871 | 0 | 0 | 0 | 0 | 0 | 0 | 2157135.2079 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| SCH-6 - MISC ITEMS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.00 | MISC WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.01 | ERECTION OF SUPPORT MATERIAL | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 519207.7643 | 0 | 348893.0798
(i) | Fabrication and erection | 20 | MT | 70% | 25960.3882 | 363445.435 | 19.1992 | 0 | 19.1992 | 348893.0798 | 0 | 348893.0798
(ii) | painting as applicable | 20 | MT | 20% | 25960.3882 | 103841.5529 | 0 | 0 | 0 | 0 | 0 | 0
1.02 | ERECTION OF CHEQUERED PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 259603.8822 | 0 | 0
(i) | Fabrication and erection | 10 | MT | 70% | 25960.3882 | 181722.7175 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | painting as applicable | 10 | MT | 20% | 25960.3882 | 51920.7764 | 0 | 0 | 0 | 0 | 0 | 0
1.03 | ERECTION OF INSERT PLATES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 25960.6976 | 0 | 0
(i) | Fabrication and erection | 1 | MT | 70% | 25960.6976 | 18172.4883 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | painting as applicable | 1 | MT | 20% | 25960.6976 | 5192.1395 | 0 | 0 | 0 | 0 | 0 | 0
1.04 | ERECTION OF CANOPY FROM 2 MM THICK GI SHEET | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12112.1457 | 0 | 0
(i) | Fabrication and erection | 10 | SQM | 70% | 1211.2146 | 8478.502 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | painting as applicable | 10 | SQM | 20% | 1211.2146 | 2422.4291 | 0 | 0 | 0 | 0 | 0 | 0
1.05 | FABRICATION OF IRREGULAR BEND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.5.1 | FOR LADDER TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.5.1.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 135290.5568 | 0 | 75762.7118
(i) | Fabrication and erection complete as applicable | 250 | NO | 70% | 541.1622 | 94703.3898 | 200 | 0 | 200 | 75762.7118 | 0 | 75762.7118
(ii) | Final painting and marking of tray nos | 250 | NO | 20% | 541.1622 | 27058.1114 | 0 | 0 | 0 | 0 | 0 | 0
1.5.1.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 81174.2103 | 0 | 37881.2982
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 541.1614 | 56821.9472 | 100 | 0 | 100 | 37881.2982 | 0 | 37881.2982
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 541.1614 | 16234.8421 | 0 | 0 | 0 | 0 | 0 | 0
1.5.1.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 75668.5771 | 0 | 35312.0026
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 | 0 | 100 | 35312.0026 | 0 | 35312.0026
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 | 0 | 0 | 0 | 0 | 0
1.5.1.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 75668.5771 | 0 | 35312.0026
(i) | Fabrication and erection complete as applicable | 150 | NO | 70% | 504.4572 | 52968.0039 | 100 | 0 | 100 | 35312.0026 | 0 | 35312.0026
(ii) | Final painting and marking of tray nos | 150 | NO | 20% | 504.4572 | 15133.7154 | 0 | 0 | 0 | 0 | 0 | 0
1.5.2 | FOR PERFORRATED TYPE CABLE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.5.2.1 | IRREGULAR BEND FOR 600 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 43275.874 | 0 | 20195.4079
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 577.0117 | 30293.1118 | 50 | 0 | 50 | 20195.4079 | 0 | 20195.4079
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 577.0117 | 8655.1748 | 0 | 0 | 0 | 0 | 0 | 0
1.5.2.2 | IRREGULAR BEND FOR 450 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 72126.4567 | 0 | 0
(i) | Fabrication and erection complete as applicable | 125 | NO | 70% | 577.0117 | 50488.5197 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 125 | NO | 20% | 577.0117 | 14425.2913 | 0 | 0 | 0 | 0 | 0 | 0
1.5.2.3 | IRREGULAR BEND FOR 300 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 40587.1052 | 0 | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 | 0 | 0 | 0 | 0 | 0
1.5.2.4 | IRREGULAR BEND FOR 150 MM WIDE TRAY | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 40587.1052 | 0 | 0
(i) | Fabrication and erection complete as applicable | 75 | NO | 70% | 541.1614 | 28410.9736 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | Final painting and marking of tray nos | 75 | NO | 20% | 541.1614 | 8117.421 | 0 | 0 | 0 | 0 | 0 | 0
1.06 | SUPPLY, INSTALLATION OF DANGER PLATE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3947.4468 | 0 | 0
(i) | On completion of Supply | 25 | NO | 80% | 157.8979 | 3157.9575 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 25 | NO | 10% | 157.8979 | 394.7447 | 0 | 0 | 0 | 0 | 0 | 0
1.07 | SUPPLY, INSTALLATION OF FASTENER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8810.7459 | 0 | 0
(i) | On completion of Supply | 25 | KG | 80% | 352.4298 | 7048.5967 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 25 | KG | 10% | 352.4298 | 881.0746 | 0 | 0 | 0 | 0 | 0 | 0
1.08 | SUPPLY OF HEAVY DUTY ANCHOR FASTENERS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14809.578 | 0 | 0
(i) | On completion of Supply | 50 | SET | 80% | 296.1916 | 11847.6624 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 50 | SET | 10% | 296.1916 | 1480.9578 | 0 | 0 | 0 | 0 | 0 | 0
1.09 | INSTALLATION OF MS, CABLE GLAND ADAPTOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 13217.3565 | 0 | 0
(i) | On completion of Supply | 100 | KG | 80% | 132.1736 | 10573.8852 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 100 | KG | 10% | 132.1736 | 1321.7357 | 0 | 0 | 0 | 0 | 0 | 0
1.10 | APPLICATION OF MOISTURE SEALING COMPOUND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10579.9496 | 0 | 0
(i) | On completion of Supply | 15 | SQM | 80% | 705.33 | 8463.9597 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 15 | SQM | 10% | 705.33 | 1057.995 | 0 | 0 | 0 | 0 | 0 | 0
1.11 | MINOR CIVIL WORK | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
1.11.1 | CHIPPING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
(i) | Prorata on completion of actual work | 1 | CUM | 90% | 462.8767 | 416.589 | 0 | 0 | 0 | 0 | 0 | 0
1.11.2 | BREAKING OF CONCRETE/WALL/ FLOOR | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
(i) | Prorata on completion of actual work | 1 | CUM | 90% | 792.7072 | 713.4365 | 0 | 0 | 0 | 0 | 0 | 0
1.11.3 | EARTH EXCAVATION & BACK FILLING | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
(i) | Prorata on completion of actual work | 5 | CUM | 90% | 594.6851 | 2676.0831 | 0 | 0 | 0 | 0 | 0 | 0
2.0 | SUPLY OF MISC ITEMS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1106886.0022 | 496586.4619 | 622648.8175
2.1 | SUPPLY OF CABLE GLAND & LUG | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Supply
2.1.1 | DOUBLE COMPRESSION HEAVY DUTY CABLE GLAND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| ABOVE (MM) UP TO (MM) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.1 | -- 9 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7738.9513 | 6191.161 | 6191.161
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.2 | 09 11 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7738.9513 | 6191.161 | 6191.161
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.3 | 11 13 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7738.9513 | 6191.161 | 6191.161
(i) | On completion of Supply | 50 | Nos | 80% | 154.779 | 6191.161 | 0 | 50 | 50 | 0 | 6191.161 | 6191.161
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 154.779 | 773.8951 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.4 | 13 17 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 9379.4406 | 7503.5525 | 7503.5525
(i) | On completion of Supply | 50 | Nos | 80% | 187.5888 | 7503.5525 | 0 | 50 | 50 | 0 | 7503.5525 | 7503.5525
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 187.5888 | 937.9441 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.5 | 17 20 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12155.463 | 9724.3704 | 9724.3704
(i) | On completion of Supply | 50 | Nos | 80% | 243.1093 | 9724.3704 | 0 | 50 | 50 | 0 | 9724.3704 | 9724.3704
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 243.1093 | 1215.5463 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.6 | 20 23 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15814.5402 | 12651.6321 | 12651.6321
(i) | On completion of Supply | 50 | Nos | 80% | 316.2908 | 12651.6321 | 0 | 50 | 50 | 0 | 12651.6321 | 12651.6321
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 316.2908 | 1581.454 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.7 | 23 26 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 18674.1031 | 14939.2825 | 14939.2825
(i) | On completion of Supply | 50 | Nos | 80% | 373.4821 | 14939.2825 | 0 | 50 | 50 | 0 | 14939.2825 | 14939.2825
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 373.4821 | 1867.4103 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.8 | 26 30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 19599.8564 | 15679.8851 | 15679.8851
(i) | On completion of Supply | 50 | Nos | 80% | 391.9971 | 15679.8851 | 0 | 50 | 50 | 0 | 15679.8851 | 15679.8851
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 391.9971 | 1959.9856 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.9 | 30 33 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 27465.0468 | 21972.0374 | 21972.0374
(i) | On completion of Supply | 50 | Nos | 80% | 549.3009 | 21972.0374 | 0 | 50 | 50 | 0 | 21972.0374 | 21972.0374
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 549.3009 | 2746.5047 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.10 | 33 36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 31755.3194 | 25404.2555 | 25404.2555
(i) | On completion of Supply | 50 | Nos | 80% | 635.1064 | 25404.2555 | 0 | 50 | 50 | 0 | 25404.2555 | 25404.2555
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 635.1064 | 3175.5319 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.11 | 36 39 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 39830.2894 | 31864.2316 | 31864.2316
(i) | On completion of Supply | 50 | Nos | 80% | 796.6058 | 31864.2316 | 0 | 50 | 50 | 0 | 31864.2316 | 31864.2316
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 796.6058 | 3983.0289 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.12 | 39 42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 47064.9032 | 37651.9226 | 37651.9226
(i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50 | 0 | 37651.9226 | 37651.9226
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.13 | 42 46 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 47064.9032 | 37651.9226 | 37651.9226
(i) | On completion of Supply | 50 | Nos | 80% | 941.2981 | 37651.9226 | 0 | 50 | 50 | 0 | 37651.9226 | 37651.9226
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 941.2981 | 4706.4903 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.14 | 46 50 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 51607.0352 | 41285.6281 | 41285.6281
(i) | On completion of Supply | 50 | Nos | 80% | 1032.1407 | 41285.6281 | 0 | 50 | 50 | 0 | 41285.6281 | 41285.6281
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1032.1407 | 5160.7035 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.15 | 54 58 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 58967.888 | 47174.3104 | 47174.3104
(i) | On completion of Supply | 50 | Nos | 80% | 1179.3578 | 47174.3104 | 0 | 50 | 50 | 0 | 47174.3104 | 47174.3104
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1179.3578 | 5896.7888 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1.16 | 58 62 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 88409.4429 | 70727.5543 | 70727.5543
(i) | On completion of Supply | 50 | Nos | 80% | 1768.1889 | 70727.5543 | 0 | 50 | 50 | 0 | 70727.5543 | 70727.5543
(ii) | On laying/installation of material/item | 50 | Nos | 10% | 1768.1889 | 8840.9443 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 | AL/CU LUG (HEAVY DUTY TYPE) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.1 | 4 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 378.7173 | 302.9738 | 302.9738
(i) | On completion of Supply | 50 | NO | 80% | 7.5743 | 302.9738 | 0 | 50 | 50 | 0 | 302.9738 | 302.9738
(ii) | On laying/installation of material/item | 50 | NO | 10% | 7.5743 | 37.8717 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.2 | 6 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 462.8767 | 370.3013 | 370.3013
(i) | On completion of Supply | 50 | NO | 80% | 9.2575 | 370.3013 | 0 | 50 | 50 | 0 | 370.3013 | 370.3013
(ii) | On laying/installation of material/item | 50 | NO | 10% | 9.2575 | 46.2877 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.3 | 10 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 504.9564 | 403.9651 | 403.9651
(i) | On completion of Supply | 50 | NO | 80% | 10.0991 | 403.9651 | 0 | 50 | 50 | 0 | 403.9651 | 403.9651
(ii) | On laying/installation of material/item | 50 | NO | 10% | 10.0991 | 50.4956 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.4 | 16 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 673.2751 | 538.6201 | 538.6201
(i) | On completion of Supply | 50 | NO | 80% | 13.4655 | 538.6201 | 0 | 50 | 50 | 0 | 538.6201 | 538.6201
(ii) | On laying/installation of material/item | 50 | NO | 10% | 13.4655 | 67.3275 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.5 | 25 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1009.2939 | 807.4351 | 807.4351
(i) | On completion of Supply | 50 | NO | 80% | 20.1859 | 807.4351 | 0 | 50 | 50 | 0 | 807.4351 | 807.4351
(ii) | On laying/installation of material/item | 50 | NO | 10% | 20.1859 | 100.9294 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.6 | 35 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1345.9315 | 1076.7452 | 1076.7452
(i) | On completion of Supply | 50 | NO | 80% | 26.9186 | 1076.7452 | 0 | 50 | 50 | 0 | 1076.7452 | 1076.7452
(ii) | On laying/installation of material/item | 50 | NO | 10% | 26.9186 | 134.5931 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.7 | 50 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2187.5254 | 1750.0203 | 1750.0203
(i) | On completion of Supply | 50 | NO | 80% | 43.7505 | 1750.0203 | 0 | 50 | 50 | 0 | 1750.0203 | 1750.0203
(ii) | On laying/installation of material/item | 50 | NO | 10% | 43.7505 | 218.7525 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.8 | 70 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3238.2802 | 2590.6242 | 2590.6242
(i) | On completion of Supply | 50 | NO | 80% | 64.7656 | 2590.6242 | 0 | 50 | 50 | 0 | 2590.6242 | 2590.6242
(ii) | On laying/installation of material/item | 50 | NO | 10% | 64.7656 | 323.828 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.9 | 95 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4711.0696 | 3768.8557 | 3768.8557
(i) | On completion of Supply | 50 | NO | 80% | 94.2214 | 3768.8557 | 0 | 50 | 50 | 0 | 3768.8557 | 3768.8557
(ii) | On laying/installation of material/item | 50 | NO | 10% | 94.2214 | 471.107 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.10 | 120 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6266.7807 | 5013.4246 | 5013.4246
(i) | On completion of Supply | 50 | NO | 80% | 125.3356 | 5013.4246 | 0 | 50 | 50 | 0 | 5013.4246 | 5013.4246
(ii) | On laying/installation of material/item | 50 | NO | 10% | 125.3356 | 626.6781 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.11 | 150 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8159.7483 | 6527.7986 | 6527.7986
(i) | On completion of Supply | 50 | NO | 80% | 163.195 | 6527.7986 | 0 | 50 | 50 | 0 | 6527.7986 | 6527.7986
(ii) | On laying/installation of material/item | 50 | NO | 10% | 163.195 | 815.9748 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.12 | 185 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10683.2924 | 8546.6339 | 8546.6339
(i) | On completion of Supply | 50 | NO | 80% | 213.6658 | 8546.6339 | 0 | 50 | 50 | 0 | 8546.6339 | 8546.6339
(ii) | On laying/installation of material/item | 50 | NO | 10% | 213.6658 | 1068.3292 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.13 | 240 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16403.6559 | 13122.9247 | 13122.9247
(i) | On completion of Supply | 50 | NO | 80% | 328.0731 | 13122.9247 | 0 | 50 | 50 | 0 | 13122.9247 | 13122.9247
(ii) | On laying/installation of material/item | 50 | NO | 10% | 328.0731 | 1640.3656 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.14 | 300 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 25151.9011 | 20121.5209 | 20121.5209
(i) | On completion of Supply | 50 | NO | 80% | 503.038 | 20121.5209 | 0 | 50 | 50 | 0 | 20121.5209 | 20121.5209
(ii) | On laying/installation of material/item | 50 | NO | 10% | 503.038 | 2515.1901 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2.15 | 400 SQMM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 38905.1549 | 31124.1239 | 31124.1239
(i) | On completion of Supply | 50 | NO | 80% | 778.1031 | 31124.1239 | 0 | 50 | 50 | 0 | 31124.1239 | 31124.1239
(ii) | On laying/installation of material/item | 50 | NO | 10% | 778.1031 | 3890.5155 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | MS HEXAGONAL HEAD CABLE GLAND | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 19979.1925 | 0 | 0
(i) | On completion of Supply | 50 | KG | 80% | 399.5838 | 15983.354 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 50 | KG | 10% | 399.5838 | 1997.9192 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | GALVANISED MS CONDUIT/ PIPE WITH ACCESORIES | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.3.1 | RIGID CONDUIT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.3.2 | 20-30 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8959.8813 | 0 | 7167.9051
(i) | On completion of Supply | 250 | MTR | 80% | 35.8395 | 7167.9051 | 250 | 0 | 250 | 7167.9051 | 0 | 7167.9051
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 35.8395 | 895.9881 | 0 | 0 | 0 | 0 | 0 | 0
2.3.3 | 50 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 49515.4267 | 0 | 39612.3414
(i) | On completion of Supply | 500 | MTR | 80% | 99.0309 | 39612.3414 | 500 | 0 | 500 | 39612.3414 | 0 | 39612.3414
(ii) | On laying/installation of material/item | 500 | MTR | 10% | 99.0309 | 4951.5427 | 0 | 0 | 0 | 0 | 0 | 0
2.3.4 | 75 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 51401.5872 | 0 | 41121.2698
(i) | On completion of Supply | 250 | MTR | 80% | 205.6063 | 41121.2698 | 250 | 0 | 250 | 41121.2698 | 0 | 41121.2698
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 205.6063 | 5140.1587 | 0 | 0 | 0 | 0 | 0 | 0
2.3.5 | 100-125 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 114004.4184 | 0 | 0
(i) | On completion of Supply | 250 | MTR | 80% | 456.0177 | 91203.5348 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 456.0177 | 11400.4418 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | FLEXIBLE CONDUIT (COLD ROLLED ANNEALED) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.4.1 | 20-25 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15326.9107 | 0 | 12261.5286
(i) | On completion of Supply | 250 | MTR | 80% | 61.3076 | 12261.5286 | 250 | 0 | 250 | 12261.5286 | 0 | 12261.5286
(ii) | On laying/installation of material/item | 250 | MTR | 10% | 61.3076 | 1532.6911 | 0 | 0 | 0 | 0 | 0 | 0
2.4.2 | 40-50 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 19051.5827 | 0 | 15241.2662
(i) | On completion of Supply | 100 | MTR | 80% | 190.5158 | 15241.2662 | 100 | 0 | 100 | 15241.2662 | 0 | 15241.2662
(ii) | On laying/installation of material/item | 100 | MTR | 10% | 190.5158 | 1905.1583 | 0 | 0 | 0 | 0 | 0 | 0
2.4.3 | 75-100 MM DIAMETER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 13322.5558 | 0 | 10658.0446
(i) | On completion of Supply | 50 | MTR | 80% | 266.4511 | 10658.0446 | 50 | 0 | 50 | 10658.0446 | 0 | 10658.0446
(ii) | On laying/installation of material/item | 50 | MTR | 10% | 266.4511 | 1332.2556 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | MISCELLANEOUS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2.5.1 | MOISTURE SEALING COMPOUNDS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 99675.0441 | 0 | 0
(i) | On completion of Supply | 50 | SQM | 80% | 1993.5009 | 79740.0352 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 50 | SQM | 10% | 1993.5009 | 9967.5044 | 0 | 0 | 0 | 0 | 0 | 0
2.5.2 | DOL LOCAL STARTER PANEL (3phase,415V,3.7KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6487.0803 | 5189.6642 | 5189.6642
(i) | On completion of Supply | 4 | NO | 80% | 1621.7701 | 5189.6642 | 0 | 4 | 4 | 0 | 5189.6642 | 5189.6642
(ii) | On laying/installation of material/item | 4 | NO | 10% | 1621.7701 | 648.708 | 0 | 0 | 0 | 0 | 0 | 0
2.5.3 | DOL LOCAL STARTER PANEL (3phase,415V,5.5KW) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3158.4525 | 2526.762 | 2526.762
(i) | On completion of Supply | 2 | NO | 80% | 1579.2263 | 2526.762 | 0 | 2 | 2 | 0 | 2526.762 | 2526.762
(ii) | On laying/installation of material/item | 2 | NO | 10% | 1579.2263 | 315.8453 | 0 | 0 | 0 | 0 | 0 | 0
2.5.4 | JOINT KIT 6.6KV 1CX400AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7852.814 | 0 | 0
(i) | On completion of Supply | 2 | NO | 80% | 3926.407 | 6282.2512 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 3926.407 | 785.2814 | 0 | 0 | 0 | 0 | 0 | 0
2.5.5 | JOINT KIT 6.6KV 3CX150AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 25606.7331 | 0 | 0
(i) | On completion of Supply | 2 | NO | 80% | 12803.3666 | 20485.3865 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 12803.3666 | 2560.6733 | 0 | 0 | 0 | 0 | 0 | 0
2.5.6 | JOINT KIT 6.6KV 3CX240AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 29021.3767 | 0 | 0
(i) | On completion of Supply | 2 | NO | 80% | 14510.6884 | 23217.1014 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 14510.6884 | 2902.1377 | 0 | 0 | 0 | 0 | 0 | 0
2.5.7 | JOINT KIT 33KV 3CX120AL UNARMOURED | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 32435.4016 | 0 | 0
(i) | On completion of Supply | 2 | NO | 80% | 16217.7008 | 25948.3212 | 0 | 0 | 0 | 0 | 0 | 0
(ii) | On laying/installation of material/item | 2 | NO | 10% | 16217.7008 | 3243.5402 | 0 | 0 | 0 | 0 | 0 | 0
3.00 | COMMISSIONING SUPPORT | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 277323.7662 | 0 | 0
3.1 | SPECIALISED SKILLED TECHNICAL MANPOWER | 30 | MD | 90% | 7298.0014 | 197046.0391 | 0 | 0 | 0 | 0 | 0 | 0 | 218940.0434 | 0 | 0
3.2 | SUPPORT SERVICE BY UN-SKILLED MANPOWER | 60 | MD | 90% | 973.062 | 52545.3505 | 0 | 0 | 0 | 0 | 0 | 0 | 58383.7228 | 0 | 0
90% OF GROSS VALUE | [5 empty] | 40393437.7747 |  |  |  | 5984367.2628 | 782079.6003 | 6766446.8631 | 46878024.9952 | 782079.6003 | 6766446.8631
100% OF GROSS VALUE | [5 empty] | 44881597.5275 |  |  |  |  | 868977.3337 |  | 52086694.4392 | 868977.3337 | 7518274.2924
[14 empty] | 1.9362 | 16.7514

## Calc2 (hidden)
|  | SCOPE | PRESENT | CUM | %Present | %Cum
A | TRANSFORMERS
A1.0 | STANDBY TRANSFORMER(Rating: 37.5/30MVA) | 717482.5924 | 0 | 411823.4104 | 0 | 57.3984
A2.0 | GENERATOR TRANSFORMER(Rating: 315MVA) | 951874.9193 | 0 | 333156.2218 | 0 | 35
A3.0 | UNIT TRANSFORMER (Rating: 37.5/30MVA) | 1121134.1876 | 0 | 0 | 0 | 0
A4.0 | HV RAW WATER TRANSFORMER (Rating: 2MVA) | 98661.9135 | 0 | 0 | 0 | 0
A5.0 | LV DTT TRANFORMERS (Rating: 2000, 2500KVA) | 115381.4972 | 0 | 46152.5164 | 0 | 39.9999
A6.0 | LV DTT TRANFORMERS (Rating: <2000KVA) | 253835.7852 | 0 | 83073.3323 | 0 | 32.7272
A7.0 | GENERATOR CIRCUIT BREAKER | 36398.9377 | 0 | 0 | 0 | 0
B | ISOLATED PHASE BUS DUCT (IPBD) & ACCESSORIES | 1808227.4418 | 0 | 20191.9425 | 0 | 1.1167
C | SEGEREGATED PHASE BUS DUCT (SPBD) | 1600950.5289 | 0 | 0 | 0 | 0
D | LT BUS DUCT (DTT to LT-PMCC) | 124333.7464 | 5538.8638 | 56830.9201 | 4.4548 | 45.7084
E | DG SET (3ph, 415V AC, 750KVA) | 1947513.9609 | 0 | 0 | 0 | 0
F | HT SWITCHGEAR | 2463347.3048 | 0 | 444210.2965 | 0 | 18.0328
G | LT SWITCHGEAR | 3535213.717 | 63168.4318 | 1513997.6623 | 1.7868 | 42.8262
H1.1 | CONTROL PANELS (GRP, BTS, DAVR, DC STARTERS) | 378975.9372 | 0 | 141471.3217 | 0 | 37.3299
H1.2 | DATA CONCENTRATOR (MV AND LV System) | 43267.8294 | 0 | 0 | 0 | 0
I | ESP ELECTRICALS
I1.0 | ELECTRONIC CONTROLLERS AND HVR | 201930.0136 | 0 | 100965.0068 | 0 | 50
I2.0 | RAPPER MOTORS (CERM, EERM & GDRM) | 151821.6895 | 0 | 0 | 0 | 0
I3.0 | HOPPER HEATERS SETS | 617402.5931 | 0 | 0 | 0 | 0
I4.0 | ASH LEVEL INDICATOR | 80781.879 | 0 | 0 | 0 | 0
J | CABLE TRAY WORK | 3916995.243 | 100504.3519 | 1124201.4203 | 2.5659 | 28.7006 |  | 2.4 | 28.75
J1.0 | CABLE TRAY & SUPPORTS INSIDE POWER-HOUSE (CABLE SPREADER ROOMS) |  |  |  | 10 | 50 | 15 | 1.5 | 7.5 | 40
J1.5 | TG HALL(GROUND FLOOR, DEARATOR FLOOR, ADIOINING AREAS) |  |  |  | 5 | 20 | 15 | 0.75 | 3 | 15
J2.0 | CABLE REAY & SUPPORTS INSIDE BOILER |  |  |  | 1 | 50 | 15 | 0.15 | 7.5 | 49
J3.0 | CABLE REAY & SUPPORTS AT ESP AREA |  |  |  | 0 | 55 | 10 | 0 | 5.5 | 55
J4.0 | CABLE REAY & SUPPORTS AT FAN/MILL AREA |  |  |  | 0 | 35 | 15 | 0 | 5.25 | 35
J5.0 | CABLE REAY & SUPPORTS AT CW/CT/PTP AREA |  |  |  | 0 | 0 | 10 | 0 | 0 | 0
J6.0 | CABLE REAY & SUPPORTS AT DMPT/ETP/ADMIN-BLDG |  |  |  | 0 | 0 | 10 | 0 | 0 | 0
J7.0 | CABLE REAY & SUPPORTS AT TRF-YARD/COMPRESSOR |  |  |  | 0 | 0 | 10 | 0 | 0 | 0
K1.1 | 220V DC BATTERY SYSTEM (MAIN PLANT) | 371108.6841 | 0 | 194754.944 | 0 | 52.4792
K1.2 | 220V DC BATTERY SYSTEM (BOP AREA) | 742217.3682 | 0 | 0 | 0 | 0
L | LIGHTING SYSTEM (ATTACHED SEPERATLY)
M | VFD SYSTEM FOR ID-FAN & CEP
M1 | VFD PANEL WITH INTG-DTT FOR ID-FAN & CEP | 240313.4353 | 0 | 141184.5609 | 0 | 58.7502
M2 | 6.6KV VFD SWITCH BOARD FOR ID-FAN & CEP | 240313.4353 | 52569.6082 | 120156.7176 | 21.8754 | 50
N | HT/LT MOTORS
N1.0 | 6.6KV HT MOTORS | 181758.2996 | 0 | 0 | 0 | 0
N2.0 | 415V LT MOTORS IN MAIN PLANT AREA | 570012.1911 | 0 | 0 | 0 | 0
N3.0 | 415V LT MOTORS IN CW/CT/WATER AREA | 137253.4509 | 0 | 0 | 0 | 0
N4.0 | 415V LT MOTORS IN AC/AHU/VENTILATION SYSTEM | 244211.3766 | 0 | 0 | 0 | 0
N5.0 | LT BI-DIRECTIONAL ACTUATORS IN MAIN PLANT AREA | 519276.4532 | 0 | 0 | 0 | 0
N6.0 | LT SOOT BLOWING SYSTEM AND LRSB | 86517.713 | 0 | 0 | 0 | 0
O7.0 | SUPPLY | 1106886.0022 | 496586.4619 | 622648.8175 | 44.8634 | 56.2523
O7.1 | Commissioning Support | 277323.7662 | 0 | 0 | 0 | 0
P | Cabling | 11780283.4245 | 31284.8351 | 331804.4978 | 0.26557 | 2.8166
| Non Executable |  | 749652.5528

## F14 Part-A
MONTHLY PLAN & REVIEW WITH CONTRACTOR
| Name of Site | ROURKELA PP-II EXPANSION PROJECT (1X250 MW) | [5 empty] | Contract No |  |  | PSER:SCT:RKL-E 1903:19: (CPES-ER/02500):WO(PKG-A):7427, DATED: 21.02.2019
PS_ER | Review for the Month of | AUG-2019 | [5 empty] | Name of Contractor |  |  | M/S POWERTRONIX ENGINEERING PVT LTD
| Date of Review | 11-09-2019 | [5 empty] | Brief Scope of Work |  |  | ERECTION, TESTING AND COMMISSIONING OF MAIN PLANT ELECTRICAL SYSTEMS (PKG-A)
PART-A: PHYSICAL REVIEWOF WORK
SL NO | Description of work | Original planned quantity | Unit Rate | Planned |  | Cumulative shortfall attributable to contractor upto last month |  | Achieved in the Month of AUG-2019 |  | Shortfall attributable to BHEL w.r.t plan (as per Col. No.3 of Part-D) |  | Cumulative shortfall attributable to Contractor upto & including this month |  | Achieved upto Date AUG-2019 (Cum Phy) | REMARKS
Qty. Planned for the month as per Part-C of last month
|  | UOM | (d) | A |  | B |  | C |  | D |  | E=A+B-C-D |  | F
|  |  |  | Phy. | Financial | Phy. | Financial | Phy. | Financial | Phy. | Financial | Phy. | Financial | Phy
A | TRANSFORMERS
A1.0 | STANDBY TRANSFORMER(Rating: 37.5/30MVA) | % |  | 25 |  | 0 |  | 0 |  | 25 |  | 0 |  | 57.3984 | Radiator and Accessories Foundation not Ready, Civil work in progress
A2.0 | GENERATOR TRANSFORMER(Rating: 315MVA) | % |  | 15 |  | 0 |  | 0 |  | 15 |  | 0 |  | 35 | Radiator and Accessories Foundation not Ready, Civil work in progress
A3.0 | UNIT TRANSFORMER (Rating: 37.5/30MVA) | % |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
A4.0 | HV RAW WATER TRANSFORMER (Rating: 2MVA) | % |  | 15 |  | 0 |  | 0 |  | 15 |  | 0 |  | 0 | Raw Water Control Building not yet Ready, Civil work in Progress
A5.0 | LV DTT TRANFORMERS (Rating: 2000, 2500KVA) | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 39.9999 | Power House Floors not ready, Civil work in Progress
A6.0 | LV DTT TRANFORMERS (Rating: <2000KVA) | % |  | 15 |  | 0 |  | 0 |  | 15 |  | 0 |  | 32.7272 | ESP-CR 3.5Mtr Floor finising work in Porgress
A7.0 | GENERATOR CIRCUIT BREAKER | % |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
B | ISOLATED PHASE BUS DUCT (IPBD) & ACCESSORIES | % |  | 25 |  | 0 |  | 0 |  | 25 |  | 0 |  | 1.1167 | Support Structure Foundation Civil work not ready
C | SEGEREGATED PHASE BUS DUCT (SPBD) | % |  | 25 |  | 0 |  | 0 |  | 25 |  | 0 |  | 0 | A-Row treastle not Ready, Mechanical Erection in Progress
D | LT BUS DUCT (DTT to LT-PMCC) | % |  |  |  | 8.75 |  | 4.4548 |  | 0 |  | 4.2952 |  | 45.7084 | Agency Manpower not Adequate
E | DG SET (3ph, 415V AC, 750KVA) | % |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
F | HT SWITCHGEAR | % |  | 25 |  | 0 |  | 0 |  | 25 |  | 0 |  | 18.0328 | Power House Floors not ready, Civil work in Progress
G | LT SWITCHGEAR | % |  | 20 |  | 0 |  | 1.7868 |  | 18.21 |  | 0 |  | 42.8262 | Power House Floors not ready, Civil work in Progress
H1.1 | CONTROL PANELS (GRP, BTS, DAVR, DC STARTERS) | % |  | 10 |  | 0 |  | 0 |  | 10 |  | 0 |  | 37.3299 | Main Control Panel room not yet ready, Civil work in Progress
H1.2 | DATA CONCENTRATOR (MV AND LV System) | % |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
I | ESP ELECTRICALS |  |  |  |  | 0 |  | 0
I1.0 | ELECTRONIC CONTROLLERS AND HVR | % |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 50
I2.0 | RAPPER MOTORS (CERM, EERM & GDRM) | % |  | 15 |  | 0 |  | 0 |  | 15 |  | 0 |  | 0 | ESP Mechanical erection in Progress
I3.0 | HOPPER HEATERS SETS | % |  | 15 |  | 0 |  | 0 |  | 15 |  | 0 |  | 0 | ESP Mechanical erection in Progress
I4.0 | ASH LEVEL INDICATOR | % |  | 15 |  | 0 |  | 0 |  | 15 |  | 0 |  | 0 | ESP Mechanical erection in Progress
J | CABLE TRAY WORK |  |  |  |  | 0 |  | 2.5659 |  | 0
J1.0 | CABLE TRAY & SUPPORTS INSIDE POWER-HOUSE | % |  | 25 |  | 0 |  | 10 |  | 15 |  | 0 |  | 50 | Power House Floors not ready, Civil work in Progress
J1.5 | TG HALL(GROUND FLOOR, DEARATOR FLOOR) | % |  | 20 |  | 0 |  | 5 |  | 15 |  | 0 |  | 20 | Power House Floors not ready, Civil work in Progress
J2.0 | CABLE REAY & SUPPORTS INSIDE BOILER | % |  | 25 |  | 0 |  | 1 |  | 24 |  | 0 |  | 50 | 8/13 Boiler Floors not Ready, Mech Erection in Progress
J3.0 | CABLE REAY & SUPPORTS AT ESP AREA | % |  | 15 |  | 0 |  | 0 |  | 15 |  | 0 |  | 55 | ESP-CR Floor finising work in Porgress, Field Mechanical Erection in progress
J4.0 | CABLE REAY & SUPPORTS AT FAN/MILL AREA | % |  | 10 |  | 0 |  | 0 |  | 10 |  | 0 |  | 35 | Mechanical Erection in progress
J5.0 | CABLE REAY & SUPPORTS AT CW/CT/PTP AREA | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 0 | CW/CT/PTP AREA Building not Ready, Civil work in Progress
J6.0 | CABLE REAY & SUPPORTS AT DMPT/ETP/ADMIN-BLDG | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 0 | DMPT/ETP/ADMIN-BLDG Building not Ready, Civil work in Progress
J7.0 | CABLE REAY & SUPPORTS AT TRF-YARD/COMPRESSOR | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 0 | TRF-YARD/COMPRESSOR AREA Building not Ready, Civil work in Progress
K1.1 | 220V DC BATTERY SYSTEM (MAIN PLANT) | % |  | 30 |  | 0 |  | 0 |  | 30 |  | 0 |  | 52.4792 | Battery Room Acid proof tiling not completed by Civil
K1.2 | 220V DC BATTERY SYSTEM (BOP AREA) | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 0 | BOP Area Battery Rooms not yet ready, Civil works in Progress
L | LIGHTING SYSTEM (ATTACHED SEPERATLY) |  |  |  |  | 0 |  | 0 |  | 0
M | VFD SYSTEM FOR ID-FAN & CEP |  |  |  |  | 0 |  | 0 |  | 0
M1 | VFD PANEL WITH INTG-DTT FOR ID-FAN & CEP | % |  | 25 |  | 0 |  | 0 |  | 25 |  | 0 |  | 58.7502
M2 | 6.6KV VFD SWITCH BOARD FOR ID-FAN & CEP | % |  | 40 |  | 0 |  | 21.8754 |  | 18.12 |  | 0 |  | 50 | Switchboard items not yet received from Bhopal
N | HT/LT MOTORS |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
N1.0 | 6.6KV HT MOTORS | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 0 | Cable Route for Motors Not ready
N2.0 | 415V LT MOTORS IN MAIN PLANT AREA | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 0 | Cable Route for Motors Not ready
N3.0 | 415V LT MOTORS IN CW/CT/WATER AREA | % |  | 20 |  | 0 |  | 0 |  | 20 |  | 0 |  | 0 | Drives not yet Erected, Cable route not available
N4.0 | 415V LT MOTORS IN AC/AHU/VENTILATION SYSTEM | % |  | 10 |  | 0 |  | 0 |  | 10 |  | 0 |  | 0 | Drives not yet Erected, Cable route not available
N5.0 | LT BI-DIRECTIONAL ACTUATORS IN MAIN PLANT AREA | % |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
N6.0 | LT SOOT BLOWING SYSTEM AND LRSB | % |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| BHEL(Sign with name, designation and date) | [8 empty] | Contractor(Sign with name, designation and date)

## F14 Part-B1
MONTHLY PLAN & REVIEW WITH CONTRACTOR
| NAME OF PROJECT: ROURKELA PP-II EXPANSION PROJECT (1X250 MW) |  |  | CONTRACT NO: PSER:SCT:RKL-E 1903:19: (CPES-ER/02500):WO(PKG-A):7427, DATED: 21.02.2019
PS_ER | NAME OF WORK: ERECTION, TESTING AND COMMISSIONING OF MAIN PLANT ELECTRICAL SYSTEMS (PKG-A) |  |  |  |  | NAME OF CONTRACTOR: M/S POWERTRONIX ENGINEERING PVT.LTD
PART-B1: REVIEW OF DEPLOYMENT OF MAJOR T&PS FOR THE MONTH OF AUG-2019 | [7 empty] | DATE OF REVIEW: 11-09-2019
CONTRACTOR'S SCOPE :-
Sl. No. | PLAN |  |  |  | DEPLOYMENT STATUS
| Major T&P to be deployed as per work planned for the month | QTY / SET | Deployment period (in days) | Weightage assigned to planned T&P (in fraction such that ΣC=1) | Actual deployed Qty. | Actual deployment period(in days) | Weighted T&P deployed | REMARKS ( Works effected due to non deployment of T&Ps)
|  | A | B | C | D | E | F=(CXDXE)/(AXB)
1 | Truck/Trailor-8T/10T/12T/22T | 0 | 0 | 1 | 0 | 0 | 0
2 | Tyre mounted 12/14/16 T hydra crane | 1 | 30 | 1 | 1 | 30 | 1
3 | Steel Rope, Shackle, Jack | 1 | 30 | 1 | 1 | 30 | 1
4 | Transit Pully, Sling | 1 | 30 | 1 | 1 | 30 | 1
5 | Manual Pallet Truck | 1 | 30 | 1 | 1 | 30 | 1
6 | Oil Filtration Machine and Accessories | 0 | 0 | 1 | 0 | 0 | 0
7 | Welding Machine Set | 8 | 30 | 1 | 8 | 30 | 1
8 | Gas Cutting Machine Set | 1 | 10 | 1 | 1 | 30 | 3
9 | Grinding and Drilling Machine Set | 1 | 15 | 1 | 1 | 30 | 2
10 | Testing Equipments | 1 | 15 | 1 | 1 | 15 | 1
11 | Torque Wrench, Spanner Set | 1 | 30 | 1 | 1 | 30 | 1
12 | Measuring Equipments | 1 | 30 | 1 | 1 | 30 | 1
13 | Dewatering Set | 0 | 0 | 1 | 0 | 0 | 0
14 | Scafolding Accessories | 1 | 10 | 1 | 1 | 10 | 1
15 | Power Transformer Handling Set | 0 | 0 | 1 | 0 | 0 | 0
BHEL SCOPE :-
Sl. No. | Major T&P to be deployed as per work planned for the month | Qty. | Deployment period(in days) |  | Actual deployed Qty. | Actual deployment period (in days) | REMARKS ( Works effected due to non deployment of T&Ps)
1 | EOT Crane in TG Hall | 1 | 0
2 | 25T or Higher Capacity Crane | 1 | 0
| BHEL(Sign with name, designation and date) |  |  |  |  | Contractor(Sign with name, designation and date)

## F14 Part-B2
MONTHLY PLAN & REVIEW WITH CONTRACTOR
| NAME OF PROJECT: ROURKELA PP-II EXPANSION PROJECT (1X250 MW) |  |  |  | CONTRACT NO: PSER:SCT:RKL-E 1903:19: (CPES-ER/02500):WO(PKG-A):7427, DATED: 21.02.2019
PS_ER | NAME OF WORK: ERECTION, TESTING AND COMMISSIONING OF MAIN PLANT ELECTRICAL SYSTEMS (PKG-A) | [5 empty] | NAME OF CONTRACTOR: M/S POWERTRONIX ENGINEERING PVT.LTD
PART-B2: REVIEW OF DEPLOYMENT OF MANPOWER FOR THE MONTH OF AUG-2019 | [8 empty] | DATE OF REVIEW: 11-09-2019
CONTRACTOR'S SCOPE :-
Sl. No. | Area of Work | Category of Labour | No. of Labour required as per category | Deployment period (in days) | No. of Labour actually deployed | Actual deployment period (in days) | REMARKS (Works effected due to non availability of labour)
|  |  | A | B | C | D
1 | Engg/Supervisor Staff | Skilled | 15 | 30 | 14 | 30
2 | Skilled | Skilled | 20 | 30 | 14 | 30
3 | Un Skillefd | Un Skilled | 25 | 30 | 17 | 30
| BHEL(Sign with name, designation and date) | [6 empty] | Contractor(Sign with name, designation and date)

## F14 Part-C
MONTHLY PLAN & REVIEW WITH CONTRACTOR
| NAME OF PROJECT: ROURKELA PP-II EXPANSION PROJECT (1X250 MW) |  |  |  |  | CONTRACT NO: PSER:SCT:RKL-E 1903:19: (CPES-ER/02500):WO(PKG-A):7427, DATED: 21.02.2019
PS_ER | NAME OF WORK: ERECTION, TESTING AND COMMISSIONING OF MAIN PLANT ELECTRICAL SYSTEMS (PKG-A) |  |  |  |  | NAME OF CONTRACTOR: M/S POWERTRONIX ENGINEERING PVT.LTD
PART-C: PLAN(PHYSICAL) FOR THE NEXT MONTH | [11 empty] | DATE OF REVIEW: 11-09-2019
Sl. No. | Description of work |  | Original planned quantity | Planned qty (excluding shortfalls attributable to contractor till date) | UOM | Contractor Scope |  | BHEL Scope |  | Category of labour | No of labour required as per category | REMARKS ( reasons for difference in original planned quantity w.r.t planned quantity to be given)
|  | UOM |  |  |  | Major T&P to be deployed as per work planned for the month | Qty | Major T&P to be deployed as per work planned for the month | Qty
A | TRANSFORMERS
A1.0 | STANDBY TRANSFORMER(Rating: 37.5/30MVA) | % |  | 25 | % | Truck/Trailor-8T/10T/12T/22T | 0 | EOT Crane in TG Hall | 1 | Engg/Supervisor Staff | 15
A2.0 | GENERATOR TRANSFORMER(Rating: 315MVA) | % |  | 15 | % | Tyre mounted 12/14/16 T hydra crane | 1 | 25T or Higher Capacity Crane | 0 | Skilled | 20
A3.0 | UNIT TRANSFORMER (Rating: 37.5/30MVA) | % |  |  |  | Steel Rope, Shackle, Jack | 1 |  |  | Un Skillefd | 25
A4.0 | HV RAW WATER TRANSFORMER (Rating: 2MVA) | % |  | 10 | % | Transit Pully, Sling | 1
A5.0 | LV DTT TRANFORMERS (Rating: 2000, 2500KVA) | % |  | 15 | % | Manual Pallet Truck | 1
A6.0 | LV DTT TRANFORMERS (Rating: <2000KVA) | % |  | 10 | % | Oil Filtration Machine and Accessories | 0
A7.0 | GENERATOR CIRCUIT BREAKER | % |  | 15 | % | Welding Machine Set | 8
B | ISOLATED PHASE BUS DUCT (IPBD) & ACCESSORIES | % |  | 20 | % | Gas Cutting Machine Set | 1
C | SEGEREGATED PHASE BUS DUCT (SPBD) | % |  | 20 | % | Grinding and Drilling Machine Set | 1
D | LT BUS DUCT (DTT to LT-PMCC) | % |  |  |  | Testing Equipments | 1
E | DG SET (3ph, 415V AC, 750KVA) | % |  | 10 | % | Torque Wrench, Spanner Set | 1
F | HT SWITCHGEAR | % |  | 25 | % | Measuring Equipments | 1
G | LT SWITCHGEAR | % |  | 10 | % | Dewatering Set | 0
H1.1 | CONTROL PANELS (GRP, BTS, DAVR, DC STARTERS) | % |  | 10 | % | Scafolding Accessories | 1
H1.2 | DATA CONCENTRATOR (MV AND LV System) | % |  |  |  | Power Transformer Handling Set | 0
I | ESP ELECTRICALS
I1.0 | ELECTRONIC CONTROLLERS AND HVR | %
I2.0 | RAPPER MOTORS (CERM, EERM & GDRM) | % |  | 15 | %
I3.0 | HOPPER HEATERS SETS | % |  | 15 | %
I4.0 | ASH LEVEL INDICATOR | % |  | 50 | %
J | CABLE TRAY WORK
J1.0 | CABLE TRAY & SUPPORTS INSIDE POWER-HOUSE | % |  | 25 | %
J1.5 | TG HALL(GROUND FLOOR, DEARATOR FLOOR) | % |  | 20 | %
J2.0 | CABLE REAY & SUPPORTS INSIDE BOILER | % |  | 25 | %
J3.0 | CABLE REAY & SUPPORTS AT ESP AREA | % |  | 15 | %
J4.0 | CABLE REAY & SUPPORTS AT FAN/MILL AREA | % |  | 10 | %
J5.0 | CABLE REAY & SUPPORTS AT CW/CT/PTP AREA | % |  | 20 | %
J6.0 | CABLE REAY & SUPPORTS AT DMPT/ETP/ADMIN-BLDG | % |  | 20 | %
J7.0 | CABLE REAY & SUPPORTS AT TRF-YARD/COMPRESSOR | % |  | 20 | %
K1.1 | 220V DC BATTERY SYSTEM (MAIN PLANT) | % |  | 30 | %
K1.2 | 220V DC BATTERY SYSTEM (BOP AREA) | % |  | 20 | %
L | LIGHTING SYSTEM (ATTACHED SEPERATLY)
M | VFD SYSTEM FOR ID-FAN & CEP
M1 | VFD PANEL WITH INTG-DTT FOR ID-FAN & CEP | %
M2 | 6.6KV VFD SWITCH BOARD FOR ID-FAN & CEP | % |  | 15 | %
N | HT/LT MOTORS
N1.0 | 6.6KV HT MOTORS |  |  | 20 | %
N2.0 | 415V LT MOTORS IN MAIN PLANT AREA | % |  | 20 | %
N3.0 | 415V LT MOTORS IN CW/CT/WATER AREA | % |  | 20 | %
N4.0 | 415V LT MOTORS IN AC/AHU/VENTILATION SYSTEM | % |  | 10 | %
N5.0 | LT BI-DIRECTIONAL ACTUATORS IN MAIN PLANT AREA | % |  | 10 | %
N6.0 | LT SOOT BLOWING SYSTEM AND LRSB | %
| BHEL(Sign with name, designation and date) | [6 empty] | Contractor(Sign with name, designation and date)
| BHEL(Sign with name, designation and date) | [6 empty] | Contractor(Sign with name, designation and date)

## F14 Part-D
MONTHLY PLAN & REVIEW WITH CONTRACTOR
| NAME OF PROJECT: ROURKELA PP-II EXPANSION PROJECT (1X250 MW) |  |  | CONTRACT NO: PSER:SCT:RKL-E 1903:19: (CPES-ER/02500):WO(PKG-A):7427, DATED: 21.02.2019
PS_ER | NAME OF WORK: ERECTION, TESTING AND COMMISSIONING OF MAIN PLANT ELECTRICAL SYSTEMS (PKG-A) |  |  |  | NAME OF CONTRACTOR: M/S POWERTRONIX ENGINEERING PVT.LTD
PART-D: REASONS FOR SHORTFALL ATTRIBUTABLE TO BHEL IN RESPECT OF PLAN FOR THE MONTH OF AUG-2019 | [5 empty] | DATE OF REVIEW: 11-09-2019
Sl. No. | Description of work (from Part-A) | Quantities effected |  | Reasons for shortfall attributable to BHEL | Agency responsible for reasons for shortfall | REMARKS (Supporting documents in respect of agency responsible)
|  | Physical Qty. | UOM
1 | 2 |  | 4 | 5 | 6 | 7
A | TRANSFORMERS
A1.0 | STANDBY TRANSFORMER(Rating: 37.5/30MVA) | 25 | % | Radiator and Accessories Foundation not Ready, Civil work in progress
A2.0 | GENERATOR TRANSFORMER(Rating: 315MVA) | 15 | % | Radiator and Accessories Foundation not Ready, Civil work in progress
A3.0 | UNIT TRANSFORMER (Rating: 37.5/30MVA) | 0 | % | -
A4.0 | HV RAW WATER TRANSFORMER (Rating: 2MVA) | 15 | % | Raw Water Control Building not yet Ready, Civil work in Progress
A5.0 | LV DTT TRANFORMERS (Rating: 2000, 2500KVA) | 20 | % | Power House Floors not ready, Civil work in Progress
A6.0 | LV DTT TRANFORMERS (Rating: <2000KVA) | 15 | % | ESP-CR 3.5Mtr Floor finising work in Porgress
A7.0 | GENERATOR CIRCUIT BREAKER | 0 | % | -
B | ISOLATED PHASE BUS DUCT (IPBD) & ACCESSORIES | 25 | % | Support Structure Foundation Civil work not ready
C | SEGEREGATED PHASE BUS DUCT (SPBD) | 25 | % | A-Row treastle not Ready, Mechanical Erection in Progress
D | LT BUS DUCT (DTT to LT-PMCC) | 4.2952 | % | - | Agency Manpower not Adequate
E | DG SET (3ph, 415V AC, 750KVA) | 0 | % | -
F | HT SWITCHGEAR | 25 | % | Power House Floors not ready, Civil work in Progress
G | LT SWITCHGEAR | 18.21 | % | Power House Floors not ready, Civil work in Progress
H1.1 | CONTROL PANELS (GRP, BTS, DAVR, DC STARTERS) | 10 | % | Main Control Panel room not yet ready, Civil work in Progress
H1.2 | DATA CONCENTRATOR (MV AND LV System) | 0 | % | -
I | ESP ELECTRICALS | 0 | % | -
I1.0 | ELECTRONIC CONTROLLERS AND HVR | 0 | % | -
I2.0 | RAPPER MOTORS (CERM, EERM & GDRM) | 15 | % | ESP Mechanical erection in Progress
I3.0 | HOPPER HEATERS SETS | 15 | % | ESP Mechanical erection in Progress
I4.0 | ASH LEVEL INDICATOR | 15 | % | ESP Mechanical erection in Progress
J | CABLE TRAY WORK | 0 | % | -
J1.0 | CABLE TRAY & SUPPORTS INSIDE POWER-HOUSE | 15 | % | Power House Floors not ready, Civil work in Progress
J1.5 | TG HALL(GROUND FLOOR, DEARATOR FLOOR) | 15 | % | Power House Floors not ready, Civil work in Progress
J2.0 | CABLE REAY & SUPPORTS INSIDE BOILER | 24 | % | 8/13 Boiler Floors not Ready, Mech Erection in Progress
J3.0 | CABLE REAY & SUPPORTS AT ESP AREA | 15 | % | ESP-CR Floor finising work in Porgress, Field Mechanical Erection in progress
J4.0 | CABLE REAY & SUPPORTS AT FAN/MILL AREA | 10 | % | Mechanical Erection in progress
J5.0 | CABLE REAY & SUPPORTS AT CW/CT/PTP AREA | 20 | % | CW/CT/PTP AREA Building not Ready, Civil work in Progress
J6.0 | CABLE REAY & SUPPORTS AT DMPT/ETP/ADMIN-BLDG | 20 | % | DMPT/ETP/ADMIN-BLDG Building not Ready, Civil work in Progress
J7.0 | CABLE REAY & SUPPORTS AT TRF-YARD/COMPRESSOR | 20 | % | TRF-YARD/COMPRESSOR AREA Building not Ready, Civil work in Progress
K1.1 | 220V DC BATTERY SYSTEM (MAIN PLANT) | 30 | % | Battery Room Acid proof tiling not completed by Civil
K1.2 | 220V DC BATTERY SYSTEM (BOP AREA) | 20 | % | BOP Area Battery Rooms not yet ready, Civil works in Progress
L | LIGHTING SYSTEM (ATTACHED SEPERATLY) | 0 | % | -
M | VFD SYSTEM FOR ID-FAN & CEP | 0 | % | -
M1 | VFD PANEL WITH INTG-DTT FOR ID-FAN & CEP | 25 | % | 0
M2 | 6.6KV VFD SWITCH BOARD FOR ID-FAN & CEP | 18.12 | % | Switchboard items not yet received from Bhopal
N | HT/LT MOTORS | 0 | % | -
N1.0 | 6.6KV HT MOTORS | 20 | % | Cable Route for Motors Not ready
N2.0 | 415V LT MOTORS IN MAIN PLANT AREA | 20 | % | Cable Route for Motors Not ready
N3.0 | 415V LT MOTORS IN CW/CT/WATER AREA | 20 | % | Drives not yet Erected, Cable route not available
N4.0 | 415V LT MOTORS IN AC/AHU/VENTILATION SYSTEM | 10 | % | Drives not yet Erected, Cable route not available
N5.0 | LT BI-DIRECTIONAL ACTUATORS IN MAIN PLANT AREA | 0 | % | -
N6.0 | LT SOOT BLOWING SYSTEM AND LRSB | 0 | % | -
| BHEL(Sign with name, designation and date) |  |  |  | Contractor(Sign with name, designation and date)