## Physical quantity format
SL. NO. | AGENCY NAME (SCT NO.) & PACKAGE |  | AREAS OF WORK |  |  | PEM/ISG Drawing status |  |  |  |  | PSSR Site Completion status | [5 empty] | Balance Status | [5 empty] | 2020-04-01
[6 empty] | RFC DRG. available as on |  |  | 2020-03-31 |  | Qty Completed as on |  |  |  | 2020-03-31 |  | Balance Qty. As on |  |  |  | 2020-03-31 |  | PLAN | [5 empty] | ACTUAL | [5 empty] | Shortfall
[6 empty] | Under ground works |  |  | Above Ground works |  | Under ground works |  |  | Above ground works |  |  | Under ground works |  |  | Above ground works |  |  | Under ground works |  |  | Above ground works |  |  | Under ground works |  |  | Above ground works |  |  | Under ground works |  |  | Above ground works
[6 empty] | Piling works |  | RCC (CUM) |  | Str steel (MT) | Piling works |  | RCC (Cum) |  | Structural. Steel (MT) |  | Piling works |  | RCC (Cum) |  | Structural. Steel (MT) |  | Piling works (No) |  | RCC (Cum) |  | Structural (MT) |  | Piling works (No) |  | RCC (Cum) |  | Structural (MT) |  | Piling works (No) |  | RCC (Cum) |  | Structural (MT)
[6 empty] | GI Piles | RCC Piles | Sub Str | Super Str |  | GI Piles | RCC Piles | Sub Str | Super Str | Fabri. | Erect. | GI Piles | RCC Piles | Sub Str | Super Str | Fabri. | Erect. | GI Piles | RCC Piles | Sub Str | Super Str | Fabri. | Erect. | GI Piles | RCC Piles | Sub Str | Super Str | Fabri. | Erect. | GI Piles | RCC Piles | Sub Str | Super Str | Fabri. | Erect.
PEM SCOPE
1 | M/s RPP INFRA (SCT 1769) | [18 empty] | 0 | 0 | 0
| Main Plant Boiler & ESP fdn (U‐1) PKG. 1 |  | BOILER + Bunker fdn | Halli M V | 9449007307 |  |  | 15268 | [5 empty] | 8211 | [5 empty] | 7057 | 0 | 0
|  |  | ESP fdn | Chenna | 9739965674 |  |  | 4780 | [5 empty] | 3808 | [5 empty] | 972 | 0 | 0
| Value (Cr) | 11.98 | Mill fdns | Binesh B | 9998976096 |  |  | 1834 | [11 empty] | 1834 | 0 | 0
| Value expected (Cr) |  | CEP pit | Rupendra | 7799779152 |  |  | 450 | [11 empty] | 450 | 0 | 0
| Value completed (Cr) |  | CW pit |  |  |  |  | 650 | [11 empty] | 650 | 0 | 0
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | 2018-12-18 | [17 empty] | 0 | 0 | 0
| Duration(months) | 8 | [17 empty] | 0 | 0 | 0
| Start date | 2019-02-09 | [17 empty] | 0 | 0 | 0
| End date | 2019-10-07 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | -5.8667 | [17 empty] | 0 | 0 | 0
2 | M/s PRIYA (SCT 1769) | [18 empty] | 0 | 0 | 0
| Main Plant Boiler & ESP fdn (U‐2) PKG. 2 |  | BOILER + Bunker fdn | Halli M V | 9449007307 |  |  | 15268 | [5 empty] | 6491 | [5 empty] | 8777 | 0 | 0
|  |  | ESP fdn | Chenna | 9739965674 |  |  | 4800 | [5 empty] | 3689 | [5 empty] | 1111 | 0 | 0
| Value (Cr) | 11.98 | Mill fdns | Binesh B | 9998976096 |  |  | 1834 | [11 empty] | 1834 | 0 | 0
| Value expected (Cr) |  | CEP pit | Rupendra | 7799779152 |  |  | 450 | [11 empty] | 450 | 0 | 0
| Value completed (Cr) |  | CW pit |  |  |  |  | 650 | [11 empty] | 650 | 0 | 0
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | 2019-01-21 | [17 empty] | 0 | 0 | 0
| Duration(months) | 8 | [17 empty] | 0 | 0 | 0
| Start date | 2019-01-30 | [17 empty] | 0 | 0 | 0
| End date | 2019-09-27 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | -6.2 | [17 empty] | 0 | 0 | 0
3 | M/s RPP INFRA (SCT 1770) | [18 empty] | 0 | 0 | 0
| BTG packages –Struct Work‐TG hall U‐1, partly mill & bunker bldg & CCR A TO C PKG.A |  | Str work MPH U1+CCR A to C | Halli M V | 9449007307 |  |  |  |  | 5805 |  |  |  |  | 767 |  |  |  |  | 0 | 5038 | 5805
|  |  | PH & CCR Main Column | Navneethakrishnan | [5 empty] | 3820 | [9 empty] | 0 | 3820 | 3820
|  |  | PH Floors - Structural | Vijay Raghavan | 9585529829 |  |  |  |  | 2187 | [9 empty] | 0 | 2187 | 2187
| Value (Cr) | 40.25 | PH Aux. Column | [6 empty] | 440 | [9 empty] | 0 | 440 | 440
| Value expected (Cr) |  | PH Staircase - Structural | [6 empty] | 60 | [9 empty] | 0 | 60 | 60
| Value completed (Cr) |  | PH Roof Truss - Structural | [6 empty] | 635 | [9 empty] | 0 | 635 | 635
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | 2019-01-28 | [17 empty] | 0 | 0 | 0
| Duration(months) | 24 | [17 empty] | 0 | 0 | 0
| Start date | 2019-06-24 | [17 empty] | 0 | 0 | 0
| End date | 2021-06-13 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 1478.6667 | [17 empty] | 0 | 0 | 0
4 | M/s GDCL (SCT 1864) | [18 empty] | 0 | 0 | 0
| Main plant structs‐(TG hall U‐2 & CCR, partly mill bunker bldg & CCR C TO H) & BTG super struct‐ (U-1 & 2) |  | Str work MPH U2, CCR CtoH | [6 empty] | 3927 | [9 empty] | 0 | 3927 | 3927
|  |  | Pipe & cable Rack –U 2 | [16 empty] | 0 | 0 | 0
|  |  | Transformer yard | [16 empty] | 0 | 0 | 0
|  |  | ESP control bldg |  |  |  |  | 303 | 323 | [10 empty] | 626 | 0 | 0
| Value (Cr) | 258.9 | Service bldg | [16 empty] | 0 | 0 | 0
| Value expected (Cr) |  | FD/ID/PA /seal air fan fdns |  |  |  |  | 9140 | [11 empty] | 9140 | 0 | 0
| Value completed (Cr) |  | ID duct fdns |  |  |  |  | 2400 | [11 empty] | 2400 | 0 | 0
| Value Left (Cr) |  | DG bldg | [16 empty] | 0 | 0 | 0
| LOI Date | 2020-01-22 | Air compressor bldg | [16 empty] | 0 | 0 | 0
| Duration(months) | 22 | Air washer bldg | [16 empty] | 0 | 0 | 0
| Start date | Not started | PH & Bunker Floors - RCC | [16 empty] | 0 | 0 | 0
| End date | #VALUE! | Boiler & ESP grade slab | [16 empty] | 0 | 0 | 0
| 1st Time Extn |  | DG set bldg, Gate House | [16 empty] | 0 | 0 | 0
| 2nd Time Extn |  | Chlori chamber & Septic tanks | [16 empty] | 0 | 0 | 0
| Duration left(months) | #VALUE! | Watch towers |  |  |  |  | 774 | [11 empty] | 774 | 0 | 0
5 | THROUGH EXISTING AGENCIES | [18 empty] | 0 | 0 | 0
| POWER HOUSE FDNS work through B&B builders under SCT 1815 |  | MPH fdns, TG - U 1& 2 (part) |  |  |  |  | 10832 | [5 empty] | 487 | [5 empty] | 10345 | 0 | 0
|  |  | CCR fdns |  |  |  |  | 4611 | [11 empty] | 4611 | 0 | 0
|  |  | TG raft Unit #1&2 |  |  |  |  | 4056 | [11 empty] | 4056 | 0 | 0
6 | M/s BYGGING (SCT 1736) | [18 empty] | 0 | 0 | 0
| RCC chimney |  | Chimney - RAFT | R B Meshram | 9422166879 |  |  | 7267 | [5 empty] | 7267 | [5 empty] | 0 | 0 | 0
|  |  | Chimney - Shell | [5 empty] | 13700 |  |  |  |  | 275 | [5 empty] | 13425 | 0 | 0
| Value (Cr) | 34.81 | Platforms, Staircase - Strl | [6 empty] | 1000 | [9 empty] | 0 | 1000 | 1000
| Value expected (Cr) |  | Flue can - Structural | R K Panigrahi | 9886234857 |  |  |  |  | 1200 | [9 empty] | 0 | 1200 | 1200
| Value completed (Cr) |  | Chimney SS Liner | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | Grade and roof slab | [16 empty] | 0 | 0 | 0
| LOI Date | 2018-10-08 | Gas sampl &liner exp joints | [16 empty] | 0 | 0 | 0
| Duration(months) | 26 | [17 empty] | 0 | 0 | 0
| Start date | 2018-12-17 | [17 empty] | 0 | 0 | 0
| End date | 2021-02-04 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 10.3333 | [17 empty] | 0 | 0 | 0
7 | M/s B&B VELLORE (SCT 1805) | [18 empty] | 0 | 0 | 0
| Non plant bldg –Part‐1 |  | CW PH & Feed Pool | R B Meshram | 9422166879 |  |  | 1830 | [11 empty] | 1830 | 0 | 0
|  |  | CW channel | R K Panigrahi | 9886234857 |  |  | 1950 | [11 empty] | 1950 | 0 | 0
| Value (Cr) | 50.8 | CWduct pipe encas+ stator |  |  |  |  | 4000 | [11 empty] | 4000 | 0 | 0
| Value expected (Cr) |  | CW electrical annexe | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | CWPH - floors, gantry | [16 empty] | 0 | 0 | 0
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | 2019-06-04 | [17 empty] | 0 | 0 | 0
| Duration(months) | 24 | [17 empty] | 0 | 0 | 0
| Start date | 2019-06-20 | [17 empty] | 0 | 0 | 0
| End date | 2021-06-09 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 14.5 | [17 empty] | 0 | 0 | 0
8 | M/s SREE SARAVANA (SCT 1823) | [18 empty] | 0 | 0 | 0
| Non plant bldg –Part‐2 |  | Aux boiler fdn & FD Fan fdn | R B Meshram | 9422166879 |  |  | 156 | [11 empty] | 156 | 0 | 0
|  |  | Permanent store |  |  |  |  | 1427 |  | 644 | [9 empty] | 1427 | 644 | 644
| Value (Cr) | 51 | Hydrogen gas cylinder | P K Sahoo | 9632558977 | [14 empty] | 0 | 0 | 0
| Value expected (Cr) |  | Weigh bridge | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | Chemical lab |  |  |  |  | 85 | 127 | [10 empty] | 212 | 0 | 0
| Value Left (Cr) |  | CST tank & PH |  |  |  |  | 295 | [11 empty] | 295 | 0 | 0
| LOI Date | 2019-07-06 | Aux boiler stack fdn | [16 empty] | 0 | 0 | 0
| Duration(months) | 24 | Workshop bldg floor & roof | [16 empty] | 0 | 0 | 0
| Start date | 2019-11-13 | [17 empty] | 0 | 0 | 0
| End date | 2021-11-02 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 19.3667 | [17 empty] | 0 | 0 | 0
9 | M/s RPP INFRA (SCT 1821) | [18 empty] | 0 | 0 | 0
| Non plant bldg –Part‐3 |  | FO system, HFO & HSD tank | R B Meshram | 9422166879 |  |  | 375 | [11 empty] | 375 | 0 | 0
|  |  | DM tank & PH |  |  |  |  | 340 | [11 empty] | 340 | 0 | 0
| Value (Cr) | 65.4 | CPU regeneration bld. | P K Sahoo | 9632558977 | [14 empty] | 0 | 0 | 0
| Value expected (Cr) |  | Diesel bunk & storage tank | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | Desalination tank & PH | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | FO Dyke Floor & Oil Seperator | [16 empty] | 0 | 0 | 0
| LOI Date | 2019-07-25 | FO Pump House | [16 empty] | 0 | 0 | 0
| Duration(months) | 24 | [17 empty] | 0 | 0 | 0
| Start date | 2019-11-13 | [17 empty] | 0 | 0 | 0
| End date | 2021-11-02 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 19.3667 | [17 empty] | 0 | 0 | 0
10 | M/s B&B VELLORE (SCT 1815) | [18 empty] | 0 | 0 | 0
| Non plant bldg –Part‐4 |  | Sea water intake/outfall PH | R B Meshram | 9422166879 | [14 empty] | 0 | 0 | 0
|  |  | Fire station Building |  |  |  |  | 145 | 198 |  |  |  |  | 53 | [5 empty] | 290 | 0 | 0
| Value (Cr) | 75.7 | Canteen‐near fire station | R K Panigrahi | 9886234857 |  |  | 377 | [5 empty] | 53 | [5 empty] | 324 | 0 | 0
| Value expected (Cr) |  | Admin bldg | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | Dispensary |  |  |  |  | 107 | 147 |  |  |  |  | 32 | [5 empty] | 222 | 0 | 0
| Value Left (Cr) |  | Bank & post office bldg | [16 empty] | 0 | 0 | 0
| LOI Date | 2019-06-04 | Canteen cum Dormitory | [16 empty] | 0 | 0 | 0
| Duration(months) | 24 | [18 empty] | 0 | 0
| Start date | 2019-06-20 | GRPpiping - SWIPH to CWPH | [16 empty] | 0 | 0 | 0
| End date | 2021-06-09 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 14.5 | [17 empty] | 0 | 0 | 0
11 | M/s VRP (SCT 1718) | [18 empty] | 0 | 0 | 0
| Boundary wall package‐ 1 |  | Boundary wall -1 | Gangai Konda | 9942492221
|  |  | RCC |  |  |  |  | 7100 | [5 empty] | 4604 | [5 empty] | 2496 | 0 | 0
| Value (Cr) | 11.49 | [18 empty] | 0 | 0
| Value expected (Cr) | [18 empty] | 0 | 0 | 0
| Value completed (Cr) | [18 empty] | 0 | 0 | 0
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | 2018-03-31 | [17 empty] | 0 | 0 | 0
| Duration(months) | 8 | [17 empty] | 0 | 0 | 0
| Start date | 2018-09-26 | [17 empty] | 0 | 0 | 0
| End date | 2019-05-24 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | -10.4 | [17 empty] | 0 | 0 | 0
12 | M/s PRIYA (SCT 1771) | [18 empty] | 0 | 0 | 0
| Boundary wall packages- 2 |  | Boundary wall -2 | Gangai Konda | 9942492221 | [14 empty] | 0 | 0 | 0
|  |  | RCC |  |  |  |  | 7400 | [5 empty] | 2715 | [5 empty] | 4685 | 0 | 0
| Value (Cr) | 21.26 | [18 empty] | 0 | 0
| Value expected (Cr) | [18 empty] | 0 | 0 | 0
| Value completed (Cr) | [18 empty] | 0 | 0 | 0
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | 2018-12-10 | [17 empty] | 0 | 0 | 0
| Duration(months) | 8 | [17 empty] | 0 | 0 | 0
| Start date | 2019-01-30 | [17 empty] | 0 | 0 | 0
| End date | 2019-09-27 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | -6.2 | [17 empty] | 0 | 0 | 0
13 | INCLUDED IN RESPECTIVE PACKAGES |  | Roads & drains incl. Patrol road commom for all packages (PEM) |  |  |  |  | 31930 | [11 empty] | 31930 | 0 | 0
PEM QTY | [5 empty] | 0 | 0 | 142884 | 14495 | 19718 |  |  |  | 37685 | 767 | 0 |  |  |  | 119694 | 18951 | 19718 | [5 empty] | 0 |  |  |  | 0 | 0 | 0
ISG SCOPE
14 | M/s GAMMON (SCT 1869) | [18 empty] | 0 | 0 | 0
| NDCT (Cooling Tower)‐ 1 &2 |  | NDCT ‐ 1 Shell Foundation | Halli M V | 9449007307 |  |  | 7750 | [11 empty] | 7750 | 0 | 0
|  |  | NDCT ‐ 2 Shell Foundation | Chenna | 9739965674 |  |  | 7750 | [11 empty] | 7750 | 0 | 0
| Value (Cr) | 165.95 | NDCT - 1&2 - Shell | Binesh B | 9998976096 |  |  |  | 35000 | [10 empty] | 35000 | 0 | 0
| Value expected (Cr) |  | NDCT - 1&2 - Basin Floor | Rupendra | 7799779152 |  |  | 10000 | [11 empty] | 10000 | 0 | 0
| Value completed (Cr) | [18 empty] | 0 | 0 | 0
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | 2019-12-26 | [17 empty] | 0 | 0 | 0
| Duration(months) | 24 | [17 empty] | 0 | 0 | 0
| Start date | 2020-02-06 | [17 empty] | 0 | 0 | 0
| End date | 2022-01-26 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 22.2 | [17 empty] | 0 | 0 | 0
15 | M/s ANNAI INFRA (SCT 1811 P-1) | [18 empty] | 0 | 0 | 0
| CHP Civil fdns+ super structural works Pkg-1 |  | Coal shed 1 | R B Meshram | 9422166879 | [14 empty] | 0 | 0 | 0
|  |  | Stock Pile - 2 Nos | [16 empty] | 0 | 0 | 0
| Value (Cr) | 66.84 | SCR 1 |  |  |  |  | 3370 | [11 empty] | 3370 | 0 | 0
| Value expected (Cr) |  | Yard, Retain. Wall for SCR 1 | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | Barricading – SCR 1 | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | Crusher House | [16 empty] | 0 | 0 | 0
| LOI Date | 2019-07-15 | BCs - 2A, 2B | [16 empty] | 0 | 0 | 0
| Duration(months) | 26 | BC 4 | [16 empty] | 0 | 0 | 0
| Start date | 2019-10-04 | BC 6A, 6B | [16 empty] | 0 | 0 | 0
| End date | 2021-11-22 | BC 7A, 7B (Bet JNT5 & 6) | [16 empty] | 0 | 0 | 0
| 1st Time Extn |  | BC 9 A, 9B | [16 empty] | 0 | 0 | 0
| 2nd Time Extn |  | BC 10A, 10B | [16 empty] | 0 | 0 | 0
| Duration left(months) | 20.0333 | BC 11A, 11B | [16 empty] | 0 | 0 | 0
|  |  | BC 12A, 12B |  |  |  |  | 380 | [11 empty] | 380 | 0 | 0
|  |  | BC 13A, 13B |  |  |  |  | 380 | [11 empty] | 380 | 0 | 0
|  |  | JT – 5 | [16 empty] | 0 | 0 | 0
|  |  | JT – 6 | [16 empty] | 0 | 0 | 0
|  |  | JT – 7 | [16 empty] | 0 | 0 | 0
|  |  | JT – 8 | [16 empty] | 0 | 0 | 0
|  |  | JT – 9 |  |  |  |  | 864 | [11 empty] | 864 | 0 | 0
|  |  | JT – 10 |  |  |  |  | 825 | [11 empty] | 825 | 0 | 0
|  |  | CHP MCC 1 | [16 empty] | 0 | 0 | 0
|  |  | Cable Rack (resp part) | [16 empty] | 0 | 0 | 0
16 | M/s GEO FDNS (SCT-1811 P-2) | [18 empty] | 0 | 0 | 0
| CHP Civil fdns+ super structural works Pkg-2 |  | Coal shed 2 | R B Meshram | 9422166879 | [14 empty] | 0 | 0 | 0
|  |  | Stock Pile - 2 Nos | [16 empty] | 0 | 0 | 0
| Value (Cr) | 66.84 | SCR 2 |  |  |  |  | 3370 | [11 empty] | 3370 | 0 | 0
| Value expected (Cr) |  | Yard, Retain. Wall for SCR 2 | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | Barricading - SCR 2 | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | ERH | [16 empty] | 0 | 0 | 0
| LOI Date | 2019-07-15 | ERH Tunnel | [16 empty] | 0 | 0 | 0
| Duration(months) | 26 | Pent House | [16 empty] | 0 | 0 | 0
| Start date | 2019-12-06 | JT – 2 |  |  |  |  | 350 | [5 empty] | 22 | [5 empty] | 328 | 0 | 0
| End date | 2022-01-24 | JT – 3 |  |  |  |  | 350 | [11 empty] | 350 | 0 | 0
| 1st Time Extn |  | JT – 4 |  |  |  |  | 280 | [11 empty] | 280 | 0 | 0
| 2nd Time Extn |  | JT – 11 |  |  |  |  | 879 | [11 empty] | 879 | 0 | 0
| Duration left(months) | 22.1333 | JT – 12 |  |  |  |  | 825 | [11 empty] | 825 | 0 | 0
|  |  | BC 1A, 1B | [16 empty] | 0 | 0 | 0
|  |  | BC 3 A, 3B | [16 empty] | 0 | 0 | 0
|  |  | BC 5 | [16 empty] | 0
|  |  | BC 7A,7B(JNT 4 to JNT 5) | [16 empty] | 0 | 0 | 0
|  |  | BC 8 | [16 empty] | 0 | 0 | 0
|  |  | BC 14A, 14B | [16 empty] | 0 | 0 | 0
|  |  | BC 15A, 15B |  |  |  |  | 380 | [11 empty] | 380 | 0 | 0
|  |  | BC 16A, 16B |  |  |  |  | 380 | [11 empty] | 380 | 0 | 0
|  |  | CHP MCC 2 | [16 empty] | 0 | 0 | 0
|  |  | CHP MCC 3 | [16 empty] | 0 | 0 | 0
|  |  | Dozer shed | [16 empty] | 0 | 0 | 0
|  |  | Coal settling Pond | [16 empty] | 0 | 0 | 0
|  |  | Dust supp. PH & water tank | [16 empty] | 0 | 0 | 0
|  |  | Cable Rack (resp part) | [16 empty] | 0 | 0 | 0
17 | M/s RPP INFRA (SCT 1820) | [18 empty] | 0 | 0 | 0
| AHP Civil fdns+ super structural work |  | Bottom Ash Hopper fdn | R B Meshram | 9422166879 |  |  | 634 | [5 empty] | 443.8 | [5 empty] | 190.2 | 0 | 0
|  |  | Bottom ash Overflow Tank | [16 empty] | 0 | 0 | 0
| Value (Cr) | 20.67 | AWPH | [16 empty] | 0 | 0 | 0
| Value expected (Cr) |  | AWRS Sump and PH | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | BA S & WPH | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | FASPH & FASS | [16 empty] | 0 | 0 | 0
| LOI Date | 10.06.19 | Chemical House | [16 empty] | 0 | 0 | 0
| Duration(months) | 24 | Cable Rack - AHP | [16 empty] | 0 | 0 | 0
| Start date | 2019-10-12 | AHP MCC | [16 empty] | 0 | 0 | 0
| End date | 2021-10-01 | Garlanding pedestal | [16 empty] | 0 | 0 | 0
| 1st Time Extn |  | FAE Towers | [16 empty] | 0 | 0 | 0
| 2nd Time Extn |  | Tube Settler, Clarifier | [16 empty] | 0 | 0 | 0
| Duration left(months) | 18.3 | Compressor House |  |  |  |  | 400 | [11 empty] | 400 | 0 | 0
|  |  | Vacc PH, other struct of AHP |  |  |  |  | 800 | [11 empty] | 800 | 0 | 0
|  |  | Pipe Rack | [16 empty] | 0 | 0 | 0
18 | M/s RPP INFRA (SCT 1809 P-1 ) | [18 empty] | 0 | 0 | 0
| CHP, AHP & Non Plant bldgs - Structural Works Pkg-1 |  | Barricading – SCR 1 | R B Meshram | 9422166879 | [14 empty] | 0 | 0 | 0
|  |  | Crusher House | [16 empty] | 0 | 0 | 0
| Value (Cr) | 47.2 | BC 2 A/B | [6 empty] | 400 | [9 empty] | 0 | 400 | 400
| Value expected (Cr) |  | BC 4 | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | BC 6A/B | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | BC 7A/B (Bet JNT 5 & 6) | [16 empty] | 0 | 0 | 0
| LOI Date | 2019-06-04 | BC 9 A/B | [16 empty] | 0 | 0 | 0
| Duration(months) | 24 | BC 10 A/B | [16 empty] | 0 | 0 | 0
| Start date | Not started | BC 11 A/B | [6 empty] | 600 | [9 empty] | 0 | 600 | 600
| End date | #VALUE! | BC 12 A/B | [6 empty] | 300 | [9 empty] | 0 | 300 | 300
| 1st Time Extn |  | BC 13 A/B | [6 empty] | 300 | [9 empty] | 0 | 300 | 300
| 2nd Time Extn |  | JT – 5 | [16 empty] | 0 | 0 | 0
| Duration left(months) | #VALUE! | JT – 6 | [16 empty] | 0 | 0 | 0
|  |  | JT – 7 | [16 empty] | 0 | 0 | 0
|  |  | JT – 8 | [16 empty] | 0 | 0 | 0
|  |  | JT – 9 | [6 empty] | 1200 | [9 empty] | 0 | 1200 | 1200
|  |  | JT – 10 | [6 empty] | 1200 | [9 empty] | 0 | 1200 | 1200
| Not awarded (SCT 1866 ) |  | Barricading - SCR2 | [16 empty] | 0 | 0 | 0
| CHP, AHP & Non Plant bldgs - Structural Works Pkg-2 |  | ERH | [16 empty] | 0 | 0 | 0
|  |  | BC 1A/B | [16 empty] | 0 | 0 | 0
| Value (Cr) |  | BC 3A/B | [16 empty] | 0 | 0 | 0
| Value expected (Cr) |  | BC 5 | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | BC 7A/B (Bet JNT 4 & 5) | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | BC 8 | [16 empty] | 0 | 0 | 0
| LOI Date |  | BC 14 A/B | [16 empty] | 0 | 0 | 0
| Duration(months) |  | BC 15 A/B | [6 empty] | 310 | [9 empty] | 0 | 310 | 310
| Start date |  | BC 16 A/B | [6 empty] | 340 | [9 empty] | 0 | 340 | 340
| End date |  | Tunnel & Pent House | [16 empty] | 0 | 0 | 0
| 1st Time Extn |  | JT – 2 | [6 empty] | 296 | [9 empty] | 0 | 296 | 296
| 2nd Time Extn |  | JT – 3 | [6 empty] | 300 | [9 empty] | 0 | 300 | 300
| Duration left(months) | -1464.0333 | JT – 4 | [6 empty] | 300 | [9 empty] | 0 | 300 | 300
|  |  | JT – 11 | [6 empty] | 1200 | [9 empty] | 0 | 1200 | 1200
|  |  | JT – 12 | [6 empty] | 1200 | [9 empty] | 0 | 1200 | 1200
|  |  | Cable racks | [16 empty] | 0 | 0 | 0
|  |  | Dozer shed | [16 empty] | 0 | 0 | 0
|  |  | Pipe rack | [16 empty] | 0 | 0 | 0
21 | Not awarded (SCT-1858) | [18 empty] | 0 | 0 | 0
| Silos & Overhead tank |  | RCC silo |  |  |  |  | 2000 | 1500 | 250 | [9 empty] | 3500 | 250 | 250
|  |  | RCC Overhead tank | [16 empty] | 0 | 0 | 0
| Value (Cr) | [18 empty] | 0 | 0 | 0
| Value expected (Cr) | [18 empty] | 0 | 0 | 0
| Value completed (Cr) | [18 empty] | 0 | 0 | 0
| Value Left (Cr) | [18 empty] | 0 | 0 | 0
| LOI Date | [18 empty] | 0 | 0 | 0
| Duration(months) | [18 empty] | 0 | 0 | 0
| Start date | [18 empty] | 0 | 0 | 0
| End date | 0 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | -1464.0333 | [17 empty] | 0 | 0 | 0
22 | INCLUDED IN RESPECTIVE PACKAGES |  | Roads & drains incl. Patrol road commom for all packages (ISG) | [16 empty] | 0 | 0 | 0
21 | Included in respective packages |  | Bought out items supply in terms of value (Rs.) shall be planned. items invloves major value shall be provided. | [16 empty] | 0 | 0 | 0
a | Deck sheets | [18 empty] | 0 | 0 | 0
b | Side sladding sheets | [18 empty] | 0 | 0 | 0
c | Gratings | [18 empty] | 0 | 0 | 0
16 | Brick work (Cum) | [18 empty] | 0 | 0 | 0
17 | Plastering (SQM) | [18 empty] | 0 | 0 | 0
18 | Finishing works (Rs) | [18 empty] | 0 | 0 | 0
ISG QTY | [7 empty] | 16467 | 1500 | 8196 |  |  |  | 465.8 | 0 | 0 |  |  |  | 17501.2 | 8196 | 8196 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
TOTAL QTY (PEM+ISG) | [7 empty] | 159351 | 15995 | 27914 |  |  |  | 38150.8 | 767 | 0 |  |  |  | 137195.2 | 27147 | 27914 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Total value of Value of work (PEM+ISG) (Cr) | [7 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[23 empty] | PLAN | [5 empty] | ACTUAL | [5 empty] | SHORTFALL
23 | M/s COMACO (SCT-1765) | [6 empty] | Scope | [5 empty] | Completed | [5 empty] | Balance Qty. As on
| Sea Water Intake & Outfall system | [18 empty] | 0
[20 empty] | 0 | 0 | 0
| Value (Cr) | 293.47 | [18 empty] | 0 | 0
| Value expected (Cr) | [19 empty] | 0 | 0
| Value completed (Cr) |  | Supply of HDPE Pipes |  |  |  |  | 5090 RM | [5 empty] | 1212 RM | [6 empty] | 0 | 0
| Value Left (Cr) |  | Design & Engineering | [16 empty] | 0 | 0 | 0
| LOI Date | 2019-05-09 | Onshore works | [16 empty] | 0 | 0 | 0
| Duration(months) | 24 | Offshore works | [16 empty] | 0 | 0 | 0
| Start date | 2019-12-20 | [17 empty] | 0 | 0 | 0
| End date | 2021-12-09 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 20.6 | [17 empty] | 0 | 0 | 0
|  |  | Value of work (Cr) for SWIO | [10 empty] | 7.88 | [11 empty] | 0 |  | 0
19 | M/s SREE SARAVANA (SCT-1772) | [18 empty] | 0 | 0 | 0
| Ash Dyke | [18 empty] | 0 | 0 | 0
[20 empty] | 0 | 0 | 0
| Value (Cr) | 63 | Excavation | [16 empty] | 0 | 0 | 0
| Value expected (Cr) |  | Filling embankment | [16 empty] | 0 | 0 | 0
| Value completed (Cr) |  | HDPE film - Supply | [16 empty] | 0 | 0 | 0
| Value Left (Cr) |  | HDPE film - installation | [16 empty] | 0 | 0 | 0
| LOI Date | 2019-01-21 | Flyash Brick- Supply | [16 empty] | 0 | 0 | 0
| Duration(months) | 20 | Flyash Brick- Laying | [16 empty] | 0 | 0 | 0
| Start date | 2019-06-26 | [17 empty] | 0 | 0 | 0
| End date | 2021-02-15 | [17 empty] | 0 | 0 | 0
| 1st Time Extn | [18 empty] | 0 | 0 | 0
| 2nd Time Extn | [18 empty] | 0 | 0 | 0
| Duration left(months) | 10.7 | [17 empty] | 0 | 0 | 0
Value of work (Cr) for ash bond
Month wise Value of all work (Cr) | [25 empty] | 0 | [5 empty] | 0
Required Turnover target (Cr)

## PEM (hidden)
Sl. No | Drawing/Document No | Title | Purpose | Schedule | Current Approval Cat | Current Rev No | Re Sub. Required | Pending With
41 | PE-DC-435-620-C002 | CHIMNEY-Design of foundation | A | 30-Aug-18 | 1 | 2 | N | Approved
42 | PE-DC-435-616-C004 | BUNKERSBAY - ANALYSIS AND DES. OF COAL SILOS | A | 14-Feb-19 | 2 | 4 | Y | Re Submission Pending
43 | PE-DC-435-653-C002 | CW PUMP HOUSE - LOAD CALCULATION | A | 07-Feb-19 | 1 | 2 | N | Approved
44 | PE-DG-435-611-C045 | PH BUILDING ARCHITECTURAL PLAN AT (+)17.00M (CCR BUILDING) | I | 25-Apr-19 | 3 | 1 | Y | Re Submission Pending
45 | PE-DC-435-674-C001 | DESIGN OF SEWAGE SYSTEM | A | 09-Apr-20 |  |  | Y | Submission Not Due
46 | PE-DG-435-611-C060 | PH BLDG.- TOILET DETAILS | I | 12-Sep-19 |  |  | Y | First Submission Due
47 | PE-DG-435-611-C062 | PH BLDG- CONTROL ROOM - FALSE CEILING CONNECTION DETAILS | I | 12-Sep-19 |  |  | Y | First Submission Due
48 | PE-DG-435-618-C006 | F.D. FAN - RC DETAILS OF FOUNDATION | I | 03-Jan-19 | 2 | 3 | Y | Re Submission Pending
49 | PE-DG-435-648-C009 | AIR WASHER BLDG. -GA FLOOR PLAN AT EL 8.50M | I | 12-Sep-19 |  |  | Y | First Submission Due
50 | PE-DG-435-648-C007 | AIR WASHER BLDG- WALL BEAM DETAILS | I | 11-Jul-19 |  |  | Y | First Submission Due
51 | PE-DG-435-641-C027 | GATE HOUSE - LAYOUT & RC DETAILS OF PLINTH & LINTEL BEAMS | I | 28-Mar-19 |  |  | Y | First Submission Due
52 | PE-DG-435-653-C007 | CW PH - RC DETAIL OF SUMP SH-1 | I | 21-Feb-19 | 2 | 1 | Y | Re Submission Pending
53 | PE-DG-435-648-C008 | AIR WASHER BLDG- LAYOUT AND RC DETLS. OF SLAB & BEAMS AT EL16.850M | I | 11-Jul-19 |  |  | Y | First Submission Due
54 | PE-DG-435-619-C001 | ESP CONTROL BLDG.-ARCHITECTURAL PLANS-SH-1 | A | 16-May-19 | 2 | 2 | Y | Re Submission Pending
55 | PE-DG-435-651-C003 | CW DUCTS - GA OF PIPE ENCASEMENT NEAR PH | I | 21-Mar-19 | 2 | 2 | Y | Re Submission Pending
56 | PE-DG-435-651-C002 | CW PIPING-RC DETAILS OF CW PIPING | I | 21-Mar-19 | 2 | 3 | Y | Re Submission Pending
57 | PE-DG-435-645-C006 | WORK SHOP BLDG ROOF SLAB & BEAM DETAILS | I | 26-Sep-19 |  |  | Y | First Submission Due
58 | PE-DG-435-651-C004 | CW DUCTS - RC DETAILS OF PIPE ENCASEMENT NEAR PH | I | 28-Mar-19 | 2 | 3 | Y | Re Submission Pending
59 | PE-DG-435-645-C007 | WORKSHOP BLDG - GA & RC DETAILS OF FLOOR PLAN AT EL 0.000 | I | 24-Oct-19 |  |  | Y | First Submission Due
60 | PE-DG-435-619-C002 | ESP CONTROL BLDG.-ARCHITECTURAL PLANS SH-2 | A | 30-May-19 | 2 | 2 | Y | Re Submission Pending
61 | PE-DC-435-612-C030 | PH BLDG.-DESIGN OF STRUCTURE SUPPORTING STAIRCASE | A | 20-Dec-18 |  |  | Y | First Submission Due
62 | PE-DC-435-612-C031 | PH BLDG-DESIGN OF CRITICAL PIPE SUPPORTING STR (CD BAY) (UNIT-1 & 2) | A | 31-Jan-19 | 3 | 0 | Y | Re Submission Pending
63 | PE-DG-435-651-C005 | CW PIPE-LAYOUT OF DETAILS OF PIPE ENCASEMENT,ROAD CROSSINGS & UFM PIT | I | 11-Apr-19 | 2 | 3 | Y | Re Submission Pending
64 | PE-DG-435-620-C020 | Chimney Liner Details- Can type A | I | 13-Dec-18 | 2 | 3 | Y | Re Submission Pending
65 | PE-DC-435-612-C009 | P.H. BLDG.-DES. OF A ROW CLADDING SUPPORTS AND WALL BEAMS (CCR) | A | 13-Sep-18 |  |  | Y | First Submission Due
66 | PE-DG-435-617-C008 | ESP AREA G.A. & R.C. DETAILS OF GRADE SLAB @(-) 0.200M | I | 20-Jun-19 |  |  | Y | First Submission Due
67 | PE-DC-435-608-C002 | PERMT STORE - DESIGN OF FOUNDATION | A | 19-Jul-18 | 2 | 1 | Y | Re Submission Pending
68 | PE-DG-435-620-C021 | Chimney Liner Details- Can type D | I | 20-Dec-18 | 2 | 3 | Y | Re Submission Pending
69 | PE-DG-435-617-C009 | CHIMNEY AREA G.A. & R.C. DETAILS OF GRADE SLAB @ (-) 0.200M | I | 15-Aug-19 |  |  | Y | First Submission Due
70 | PE-DC-435-612-C010 | P.H. BLDG.-DES. OF B ROW COLUMN, BASE PLATE, BRACINGS & BC BAY TRANS GIRDERS (Unit-1 & 2) | A | 27-Sep-18 | 2 | 0 | Y | Re Submission Pending
71 | PE-DG-435-619-C012 | ESP CONT ROOM- GA & RC DETAILS OF LIFT MACHINE ROOM | I | 04-Jul-19 |  |  | Y | First Submission Due
72 | PE-DG-435-641-C011 | ADMN BLDG. - WINDOWS DETAILS | I | 15-Aug-19 |  |  | Y | First Submission Due
73 | PE-DG-435-613-C007 | T.G FDN.-DETAILS OF EMBEDMENTS ON DECK | A | 04-Oct-18 | 3 | 0 | Y | Re Submission Pending
74 | PE-DG-435-608-C002 | PERMT STORE& OFFICE- SECTIONAL ELEVATION | A | 05-Jul-18 | 2 | 1 | Y | Re Submission Pending
75 | PE-DG-435-647-C006 | COMP BLDG -GA & RC DETAILS OF PLINTH BEAM | I | 14-Nov-19 |  |  | Y | First Submission Due
76 | PE-DG-435-608-C003 | PERMT STORE& OFFICE- FRONT & REAR ELEVATION | A | 05-Jul-18 | 2 | 1 | Y | Re Submission Pending
77 | PE-DG-435-641-C010 | ADMN BLDG. - SOUTH ELEVATION | A | 08-Aug-19 |  |  | Y | First Submission Due
78 | PE-DG-435-619-C016 | ESP CONT ROOM-DTLS OF STAIRCASE | I | 23-May-19 | 2 | 0 | Y | Re Submission Pending
79 | PE-DG-435-653-C010 | CW PH - RC DETAIL AT MEZANINE FLOOR | I | 27-Jun-19 |  |  | Y | First Submission Due
80 | PE-DG-435-612-C007 | PH BUILDING GA AND DETAILS OF GANTRY GIRDERS (2-SHEETS) | I | 16-Aug-18 | 2 | 0 | Y | Re Submission Pending
81 | PE-DG-435-647-C001 | COMP BLDG - ARCHITECTURAL PLANS | A | 12-Sep-19 |  |  | Y | First Submission Due
82 | PE-DG-435-648-C006 | AIR WASHER BLDG- FRAMING PLAN AT EL 8.460M | I | 04-Jul-19 |  |  | Y | First Submission Due
83 | PE-DG-435-602-C001 | GEOTECHNICAL INVESTIGATION DETAILS | A | 15-Feb-18 | 4 | 4 | N | Approved
84 | PE-DG-435-608-C001 | PERMT STORE & OFFICE - GROUND FLOOR PLAN | A | 16-Aug-18 | 2 | 1 | Y | Re Submission Pending
85 | PE-DG-435-613-C008 | T.G DECK-REINFORCEMENT DETAILS OF CROSS-BEAM-1(SHEETS 1 & 2) | I | 04-Oct-18 | 3 | 0 | Y | Re Submission Pending
86 | PE-DG-435-614-C002 | RC OF MDBFP DECK | I | 03-Jan-19 | 2 | 1 | Y | Re Submission Pending
87 | PE-DG-435-675-C001 | PIPE RACK PR-1 - FOUNDATION LAYOUT & DETAILS | I | 19-Sep-19 |  |  | Y | First Submission Due
88 | PE-DG-435-612-C008 | PH BLDG. -PURLIN DETAILS (UNIT#1 & UNIT#2) (2-SHEETS) | I | 02-Aug-18 | 4 | 2 | N | Approved
89 | PE-DG-435-620-C002 | G.A. of foundation & detail of starter bars | A | 30-Aug-18 | 1 | 3 | N | Approved
90 | PE-DG-435-620-C003 | Reinforcement details of foundation | I | 20-Sep-18 | 1 | 1 | N | Approved
91 | PE-DG-435-639-C007 | CPU REGENERATION BLDG- GA & RC DETAILS OF TIE BEAM | I | 27-Feb-20 |  |  | Y | Submission Not Due
92 | PE-DG-435-650-C003 | FIRE STATION -FOUNDATION & COLUMN DETAILS | I | 05-Dec-19 | 2 | 3 | Y | Re Submission Pending
93 | PE-DG-435-674-C003 | SEPTIC TANK,UPFLOW FILTER AND CHLORINATION CHAMBER(UP TO 25 USERS) - GA & MASONARY DETAILS | I | 09-Apr-20 |  |  | Y | Submission Not Due
94 | PE-DC-435-635-C001 | DM Tank-Design of Foundation | A | 11-Apr-19 | 1 | 1 | N | Approved
95 | PE-DG-435-634-C010 | FO dyke area-ga & rc details of fencing | I | 15-Aug-19 | 3 | 0 | Y | Re Submission Pending
96 | PE-DC-435-638-C004 | COND TRF PH -DESIGN OF SUPERSTRUCTURE | A | 31-Oct-19 | 2 | 0 | Y | Re Submission Pending
97 | PE-DC-435-639-C001 | CPU REGENERATION BLDG-LOAD CALCULATIONS | A | 16-Jan-20 |  |  | Y | First Submission Due
98 | PE-DG-435-674-C004 | SEPTIC TANK,UPFLOW FILTER AND CHLORINATION CHAMBER(UP TO 25 USERS) - REINFORCEMENT DETAILS | I | 23-Apr-20 |  |  | Y | Submission Not Due
99 | PE-DG-435-653-C008 | CW PH - RC DETAILS OF SUMP SH-2 | I | 07-Mar-19 | 2 | 1 | Y | Re Submission Pending
100 | PE-DG-435-641-C005 | ADMN BLDG WEST SIDE ELEVATION | A | 11-Jul-19 |  |  | Y | First Submission Due
101 | PE-DG-435-611-C020 | PH BLDG.(BCDEFG BAY-CR)- GA & R.C. DTLS OF FLOOR AT EL 17M | I | 17-Oct-19 |  |  | Y | First Submission Due
102 | PE-DG-435-634-C020 | F.O. PR PH ROOF SLAB AND BEAM LAYOUT& R.C. DTLS | I | 27-Jun-19 |  |  | Y | First Submission Due
103 | PE-DG-435-640-C003 | SERVICE BLDG-ARCH GA AT SECONDLEVEL | A | 30-Aug-18 | 2 | 2 | Y | Re Submission Pending
104 | PE-DG-435-641-C006 | ADMN BLDG SECTION 1-1 | A | 18-Jul-19 |  |  | Y | First Submission Due
105 | PE-DG-435-611-C063 | PH BLDG- MISCELLENOUS ARCHITECTURAL DETAILS | I | 01-Aug-19 |  |  | Y | First Submission Due
106 | PE-DG-435-612-C014 | PH BLDG- CLADDING FRAMING OF GABLE END (UNIT#1 & UNIT#2) (2-SHEETS) | I | 23-May-19 |  |  | Y | First Submission Due
107 | PE-DC-435-675-C001 | PIPE RACK PR1 - DESIGN OF FOUNDATION | A | 19-Sep-19 |  |  | Y | First Submission Due
108 | PE-DG-435-612-C025 | PH BLDG.(AB BAY-TG) - FRAMING PLAN AT EL +17.0M FFL (UNIT#1 & UNIT#2) (2-SHEETS) | I | 29-Nov-18 | 2 | 1 | Y | Re Submission Pending
109 | PE-DG-435-653-C020 | ELEC ANN - GA & RC DETAILS OF FOUNDATION, COLUMN & PLINTH BEAMS | I | 22-Aug-19 | 3 | 0 | Y | Re Submission Pending
110 | PE-DG-435-610-C009 | CANTEEN BLDG WITH DORMITORY (NEAR ADMIN) - LAYOUT & RC DETAILS OF GRADE & PLINTH BEAMS | I | 17-Oct-19 |  |  | Y | First Submission Due
111 | PE-DG-435-603-C002 | PLANT ROADS LAYOUT | A | 16-Aug-18 | 2 | 3 | Y | Re Submission Pending
112 | PE-DG-435-674-C002 | SEPTIC TANK,UPFLOW FILTER AND CHLORINATION CHAMBER(UP TO 100 USERS) - REINFORCEMENT DETAILS | I | 02-Apr-20 |  |  | Y | Submission Not Due
113 | PE-DG-435-675-C007 | PIPE RACK PR-4 - FOUNDATION LAYOUT & DETAILS | I | 31-Oct-19 |  |  | Y | First Submission Due
114 | PE-DG-435-612-C026 | PH BLDG.(AB BAY) - FRAMING PLAN AT EL+ 17.0M FFL (CCR BUIILDING) | I | 27-Dec-18 | 2 | 1 | Y | Re Submission Pending
115 | PE-DC-435-606-C001 | BOUNDARY WALL - DESIGN | A | 07-Jun-18 | 2 | 2 | Y | Re Submission Pending
116 | PE-DG-435-653-C024 | ELEC ANN - GA & RC DETAILS OF GROUND FLOOR | I | 05-Dec-19 |  |  | Y | First Submission Due
117 | PE-DG-435-653-C023 | ELEC ANN - GA & RC DETAILS OF ROOF | I | 31-Oct-19 |  |  | Y | First Submission Due
118 | PE-DC-435-606-C002 | WATCH TOWER : DESIGN | A | 19-Jul-18 | 2 | 1 | Y | Re Submission Pending
119 | PE-DG-435-600-C002 | GENERAL NOTES FOR STRUCTURAL STEEL WORKS. | A | 07-Jun-18 | 2 | 0 | Y | Re Submission Pending
120 | PE-DG-435-603-C003 | PLANT ROADS CROSS SECTION AND DETAILS | I | 13-Sep-18 | 2 | 3 | Y | Re Submission Pending
121 | PE-DG-435-653-C025 | ELEC ANN - GA & RC DETAILS OF STAIRCASE | I | 19-Mar-20 |  |  | Y | Submission Not Due
122 | PE-DC-435-610-C001 | CANTEEN BLDG (NEAR FIRE STATION)- LOAD CALCULATION ,DESIGN OF COL-FDN,PLINTH BEAMS | A | 12-Sep-19 | 1 | 0 | N | Approved
123 | PE-DG-435-611-C010 | PH BLDG.(AB BAY-TG)- GA & R.C. DTLS OF FLOOR AT EL +8.5M (UNIT#1 & UNIT#2) (2-SHEETS) | I | 04-Jul-19 |  |  | Y | First Submission Due
124 | PE-DG-435-641-C007 | ADMN BLDG. - EAST ELEVATION | A | 25-Jul-19 |  |  | Y | First Submission Due
125 | PE-DG-435-640-C022 | SERVICE BLDG - GA & RC DETAILS OF BEAMS & SLAB AT SECOND FLOOR LEVEL-SH1 | I | 13-Dec-18 |  |  | Y | First Submission Due
126 | PE-DC-435-612-C028 | PH BLDG.-DESIGN OF BC/CD/DE BAY SECONDARY BEAMS @24.0M , 25.5M (UNIT-1 & 2) | A | 28-Mar-19 | 2 | 0 | Y | Re Submission Pending
127 | PE-DC-435-675-C003 | PIPE RACK PR2 - DESIGN OF FOUNDATION | A | 03-Oct-19 |  |  | Y | First Submission Due
128 | PE-DC-435-675-C004 | PIPE RACK PR2 - DESIGN OF SUPERSTRUCTURE | A | 19-Sep-19 |  |  | Y | First Submission Due
129 | PE-DG-435-620-C028 | Chimney paintings | I | 14-Mar-19 | 4 | 1 | N | Approved
130 | PE-DG-435-653-C009 | CW PH - GA DETAIL AT MEZANINE FLOOR | I | 06-Jun-19 |  |  | Y | First Submission Due
131 | PE-DG-435-620-C017 | Chimney Liner Details- Can type SS1 & SS2 | I | 29-Nov-18 | 2 | 3 | Y | Re Submission Pending
132 | PE-DG-435-611-C047 | PH BLDG. -GA & R.C. DTLS OF FLOOR AT EL + 0.0M (CCR BUILDING) (SHEET 6 OF 7) | I | 16-May-19 |  |  | Y | First Submission Due
133 | PE-DG-435-650-C004 | FIRE STATION -PLINTH BEAM LAYOUT & DEATAILS | I | 19-Dec-19 | 2 | 3 | Y | Re Submission Pending
134 | PE-DG-435-611-C050 | PH BLDG.(CDEFG BAY-CR) - ARCH PLAN AT EL + 27.0M | I | 20-Jun-19 | 3 | 1 | Y | Re Submission Pending
135 | PE-DG-435-639-C008 | CPU REGENERATION BLDG- ROOF SLAB & BEAM LAYOUT & RC DETAILS | I | 05-Mar-20 |  |  | Y | Submission Not Due
136 | PE-DG-435-612-C038 | PH BLDG. - (BC-BAY) FRAMING PLAN AT EL+37.50M FFL (UNIT#1 & UNIT#2) | I | 14-Feb-19 |  |  | Y | First Submission Due
137 | PE-DG-435-612-C039 | PH BLDG. -VENTILLATION AND BUS DUCT SUPPORTING STRUCTURE ALONG AXIS-A | I | 10-Oct-19 |  | 0 | Y | Pending for Approval
138 | PE-DG-435-611-C017 | PH BLDG.(BCDEFGH BAY-CR)- GA & R.C. DTLS OF FLOOR AT EL +8.5M | I | 24-Oct-19 |  |  | Y | First Submission Due
139 | PE-DG-435-620-C023 | Chimney Liner Details- Can type G | I | 03-Jan-19 | 2 | 3 | Y | Re Submission Pending
140 | PE-DG-435-620-C024 | Chimney Liner Details- Can type B | I | 03-Jan-19 | 2 | 3 | Y | Re Submission Pending
141 | PE-DG-435-611-C051 | PH BLDG.(BCDEFG BAY-CR) - ARCH PLAN AT EL + 32.50M | I | 27-Jun-19 | 3 | 0 | Y | Re Submission Pending
142 | PE-DG-435-648-C003 | AIR WASHER BLDG - GA AND RC DETAILS OF FOUNDATION & PEDESTAL | I | 16-May-19 |  |  | Y | First Submission Due
143 | PE-DG-435-645-C004 | WORK SHOP BLDG. -PLINTH BEAM DETAILS | I | 05-Sep-19 | 3 | 0 | Y | Re Submission Pending
144 | PE-DG-435-612-C001 | PH BLDG. - STRUCTURAL FRAMING ALONG A ROW | I | 13-Sep-18 | 2 | 3 | Y | Re Submission Pending
145 | PE-DG-435-612-C002 | PH BLDG. - STRUCTURAL FRAMING ALONG B ROW | I | 27-Sep-18 | 2 | 2 | Y | Re Submission Pending
146 | PE-DG-435-611-C018 | PH BLDG.(CDEFGH BAY-CR)- GA & R.C. DTLS OF FLOOR AT EL 13.5M | I | 31-Oct-19 |  |  | Y | First Submission Due
147 | PE-DG-435-622-C004 | TRANSFORMER YARD - LAYOUT DETAILS SH-1 & RAIL TRACK DETAILS | I | 23-May-19 |  |  | Y | First Submission Due
148 | PE-DG-435-613-C011 | T.G DECK-REINFORCEMENT DETAILS OF CROSS-BEAM-4(SHEETS 1 & 2) | A | 11-Oct-18 | 3 | 0 | Y | Re Submission Pending
149 | PE-DC-435-608-C001 | PERMT STORE - LOAD CALCULATION | A | 05-Jul-18 | 1 | 1 | N | Approved
150 | PE-DG-435-675-C002 | PIPE RACK PR-1 - STRUCTURAL STEEL DETAILS | I | 29-Aug-19 |  |  | Y | First Submission Due
151 | PE-DG-435-640-C007 | SERVICE BLDG WEST SIDE ELEVATION | A | 20-Sep-18 |  |  | Y | First Submission Due
152 | PE-DG-435-620-C010 | Details of Liner restraint | I | 22-Nov-18 | 4 | 1 | N | Approved
153 | PE-DG-435-641-C023 | ADMN BLDG. -GA & RC DETAILS OF LIFT PIT | I | 06-Aug-20 |  |  | Y | Submission Not Due
154 | PE-DC-435-653-C003 | CW PUMP HOUSE - DESIGN OF FOUNDATIONS | A | 21-Feb-19 | 2 | 0 | Y | Re Submission Pending
155 | PE-DG-435-616-C006 | BUNKER`S BAY - R.C.C. DTLS OF ROOF. | I | 25-Apr-19 | 3 | 0 | Y | Re Submission Pending
156 | PE-DG-435-653-C021 | ELEC ANN - GA & RC DETAILS OF LINTEL BEAMS | I | 31-Oct-19 |  |  | Y | First Submission Due
157 | PE-DG-435-622-C015 | TRANSFORMER YARD - FENCING DTLS | I | 16-May-19 |  |  | Y | First Submission Due
158 | PE-DG-435-612-C023 | PH BLDG. -(AB BAY) FRAMING PLAN AT EL 8.5M FFL (CCR BUILDING) | I | 03-Jan-19 | 2 | 1 | Y | Re Submission Pending
159 | PE-DG-435-675-C009 | PIPE RACK PR-5 - FOUNDATION LAYOUT & DETAILS | I | 14-Nov-19 |  |  | Y | First Submission Due
160 | PE-DG-435-610-C002 | CANTEEN BLDG - ARCHITECTURAL ELEVATIONS | A | 28-Nov-19 | 2 | 2 | Y | Re Submission Pending
161 | PE-DC-435-620-C001 | CHIMNEY-Shell analysis | A | 04-Oct-18 | 1 | 2 | N | Approved
162 | PE-DG-435-644-C002 | ARCHITECTURAL ELEVATION | I | 31-Oct-19 |  |  | Y | First Submission Due
163 | PE-DG-435-612-C005 | PH BLDG. - STRUCTURAL FRAMING ALONG D` TO H` ROW (CCR BUILDING) | I | 25-Oct-18 | 2 | 2 | Y | Re Submission Pending
164 | PE-DG-435-612-C024 | PH BLDG.(AB BAY-TG) FRAMING PLAN AT EL +12M FFL (CCR BUILDING) | I | 25-Apr-19 | 2 | 0 | Y | Re Submission Pending
165 | PE-DG-435-611-C037 | PH BUILDING ARCHITECTURAL PLAN AT EL.(±)0.00M(FFL) (UNIT#2) (SHEET 3 OF 3) | I | 31-Jan-19 | 2 | 1 | Y | Re Submission Pending
166 | PE-DG-435-608-C006 | PERMT STORE - SUPER STRUCTURE | I | 16-Aug-18 | 1 | 1 | N | Approved
167 | PE-DG-435-675-C006 | PIPE RACK PR-3 - STRUCTURAL STEEL DETAILS | I | 10-Oct-19 |  |  | Y | First Submission Due
168 | PE-DG-435-640-C024 | SERVICE BLDG - GA & RC DETAILS OF BEAMS & SLAB AT THIRD FLOOR LEVEL-SH1 | I | 27-Dec-18 |  |  | Y | First Submission Due
169 | PE-DC-435-612-C012 | P.H. BLDG.-DES. OF C ROW COLUMN, BASE PLATE, BRACINGS (Unit-1 & 2) | A | 11-Oct-18 | 2 | 0 | Y | Re Submission Pending
170 | PE-DG-435-611-C038 | PH BLDG. -GA & R.C. DTLS OF FLOOR AT EL + 0.0M (SHEET 5 OF 7) | I | 14-Feb-19 |  |  | Y | First Submission Due
171 | PE-DC-435-612-C032 | PH BLDG.-DESIGN OF GABLE END CLADDING SUPPORTS (UNIT-1 & 2) | A | 23-May-19 |  |  | Y | First Submission Due
172 | PE-DG-435-612-C020 | PH BLDG. -OIL CANAL FRAMING PLAN. | I | 20-Dec-18 | 2 | 1 | Y | Re Submission Pending
173 | PE-DG-435-612-C041 | PH BLDG. -MISC. DETAILS | I | 17-Jan-19 |  |  | Y | First Submission Due
174 | PE-DC-435-642-C001 | D.G. SET BLDG. - LOAD CALCULATION | A | 23-May-19 |  |  | Y | First Submission Due
175 | PE-DG-435-620-C011 | Details of Gas Sampling Ports | I | 07-Mar-19 |  |  | Y | First Submission Due
176 | PE-DC-435-642-C002 | D.G. SET BLDG. - DESIGN OF FOUNDATIONS | A | 23-May-19 |  |  | Y | First Submission Due
177 | PE-DG-435-641-C025 | GATE HOUSE - ARCHITECTURAL ELEVATIONS & SECTIONS | A | 15-Nov-18 | 3 | 0 | Y | Re Submission Pending
178 | PE-DG-435-644-C003 | FOUNDATION & PLINTH BEAM | I | 31-Oct-19 |  |  | Y | First Submission Due
179 | PE-DC-435-620-C005 | CHIMNEY-Roof Paltform-Framing Design | A | 24-Jan-19 |  |  | Y | First Submission Due
180 | PE-DC-435-620-C007 | CHIMNEY -Design of STAIRCASE | A | 29-Nov-18 | 2 | 1 | Y | Re Submission Pending
181 | PE-DG-435-634-C002 | GA & RC DETAILS OF DYKE | I | 12-Sep-19 | 3 | 0 | Y | Re Submission Pending
182 | PE-DC-435-617-C003 | ID SYSTEM FOUNDATIONS(DESIGN OF ID SYS FDN BETWEEN BOILER & ESP ) | A | 03-Jan-19 | 2 | 2 | Y | Re Submission Pending
183 | PE-DG-435-608-C004 | PERMT STORE - GA & RC OF FOUNDATION & COLUMN | I | 02-Aug-18 | 2 | 1 | Y | Re Submission Pending
184 | PE-DC-435-613-C002 | DYNAMIC ANALYSIS-TG FOUNDATION | A | 04-Oct-18 | 1 | 2 | N | Approved
185 | PE-DG-435-611-C032 | PH BLDG.- FRONT ELEVATION (UNIT#1 & UNIT#2) | A | 15-Nov-18 | 3 | 0 | Y | Re Submission Pending
186 | PE-DG-435-612-C035 | PH BLDG. - (C TO G`-BAY) FRAMING PLAN AT EL+27.0M FFL (CCR BUILDING) | I | 28-Mar-19 | 3 | 1 | Y | Re Submission Pending
187 | PE-DC-435-640-C002 | SERVICE BLDG-DESIGN OF FOUNDATIONS | A | 01-Nov-18 |  | 0 | Y | Pending for Approval
188 | PE-DG-435-610-C010 | CANTEEN BLDG(NEAR FIRE STATION) - RC DETAILS OF ROOF SLAB BEAMS & SLAB AT EL 3.2M,4.500M,8.7M LVL | I | 24-Oct-19 | 2 | 2 | Y | Re Submission Pending
189 | PE-DG-435-601-C001 | TOPOGRAPHICAL SURVEY OF PLANT AREA | A | 15-Feb-18 | 4 | 2 | N | Approved
190 | PE-DG-435-613-C014 | T.G DECK-REINFORCEMENT DETAILS OF LONGITUDINAL BEAM-7(SHEETS 1 TO 6) | I | 18-Oct-18 |  | 0 | Y | Pending for Approval
191 | PE-DC-435-613-C003 | STATIC ANALYSIS-TG DECK | A | 11-Oct-18 | 3 | 0 | Y | Re Submission Pending
192 | PE-DG-435-645-C003 | WORK SHOPBLDG. - G.A. AND R.C. DTLS OF COLUMN | I | 29-Aug-19 |  |  | Y | First Submission Due
193 | PE-DG-435-611-C061 | CONTROL TOWER - CONTROL ROOM ARCH DETAILS | A | 15-Aug-19 |  |  | Y | First Submission Due
194 | PE-DG-435-611-C019 | PH BLDG.(BC BAY-TG)- GA & R.C. DTLS OF FLOOR AT EL 17.0M (UNIT#1 & UNIT#2) (2-SHEETS) | I | 29-Aug-19 |  | 0 | Y | Pending for Approval
195 | PE-DG-435-651-C001 | GA & RC DETAILS OF STATOR LIFTING GANTRY CRANE FDN | I | 14-Feb-19 | 2 | 0 | Y | Re Submission Pending
196 | PE-DG-435-638-C002 | COND TRANSFER PH- FOUNDATION & COL DETAILS | A | 12-Sep-19 | 2 | 1 | Y | Re Submission Pending
197 | PE-DG-435-634-C014 | F.O. PR PH -ARCHITECTURAL ELEVATIONS | A | 20-Jun-19 | 3 | 2 | Y | Pending for Approval
198 | PE-DG-435-620-C012 | Details of manholes in flues | I | 21-Feb-19 | 2 | 0 | Y | Re Submission Pending
199 | PE-DG-435-620-C013 | Details of grade slab | I | 28-Feb-19 | 2 | 1 | Y | Re Submission Pending
200 | PE-DG-435-610-C008 | CANTEEN BLDG WITH DORMITORY (NEAR ADMIN) - LAYOUT & RC DETAILS OF COL,FOUNDATIONS | I | 10-Oct-19 | 2 | 1 | Y | Re Submission Pending
201 | PE-DG-435-620-C018 | Details of steel staircase | I | 07-Feb-19 | 2 | 1 | Y | Re Submission Pending
202 | PE-DG-435-620-C014 | G.A. & R.C.C. details of roof slab | I | 07-Mar-19 | 3 | 0 | Y | Re Submission Pending
203 | PE-DG-435-638-C003 | COND STORAGE TANK-GA & RC DETAILS OF FOUNDATION | I | 26-Sep-19 | 2 | 1 | Y | Re Submission Pending
204 | PE-DG-435-612-C004 | PH BLDG. - STRUCTURAL FRAMING ALONG D & E`A ROW | I | 25-Oct-18 | 2 | 3 | Y | Re Submission Pending
205 | PE-DG-435-618-C002 | I.D. FAN - R.C. DETAILS OF FOUNDATION | I | 17-Jan-19 | 2 | 1 | Y | Re Submission Pending
206 | PE-DG-435-675-C010 | PIPE RACK PR-5 - STRUCTURAL STEEL DETAILS | I | 28-Nov-19 |  |  | Y | First Submission Due
207 | PE-DG-435-619-C014 | ESP CONT ROOM- GA & RC DTLS OF GROUND FLOOR | I | 18-Jul-19 |  |  | Y | First Submission Due
208 | PE-DG-435-635-C006 | DM MAKEUP PUMP HOUSE - ARCH. PLANS, SECTIONSAND ELEVATIONS | A | 21-Feb-19 | 2 | 1 | Y | Re Submission Pending
209 | PE-DG-435-653-C019 | FEED POOL - RC DETAIL | I | 31-Jan-19 | 1 | 3 | N | Approved
210 | PE-DC-435-616-C007 | MILL & BUNKER BAY-DESIGN OF TRIPPER ROOF | A | 14-Feb-19 | 3 | 0 | Y | Re Submission Pending
211 | PE-DG-435-611-C015 | PH BLDG.(BC BAY-TG)-GA & RCC DETAILS AT EL. +5.10 M | I | 18-Jul-19 |  |  | Y | First Submission Due
212 | PE-DC-435-616-C005 | MILL & BUNKER BAY-DESIGN OF FEEDER FLOOR | A | 21-Feb-19 | 2 | 2 | Y | Re Submission Pending
213 | PE-DG-435-644-C005 | GROUND DETAILS | I | 26-Mar-20 |  |  | Y | Submission Not Due
214 | PE-DC-435-612-C013 | P.H. BLDG.-DES. OF C ROW WALL BEAMS | A | 11-Oct-18 |  |  | Y | First Submission Due
215 | PE-DC-435-616-C006 | MILL & BUNKER BAY-DESIGN OF TRIPPER FLOOR | A | 09-May-19 | 3 | 3 | Y | Re Submission Pending
216 | PE-DG-435-612-C036 | PH BLDG. - (B TO G`-BAY) FRAMING PLAN AT EL+32.50M FFL (CCR BUILDING) | I | 28-Feb-19 | 3 | 1 | Y | Re Submission Pending
217 | PE-DG-435-641-C024 | GATE HOUSE - ARCHITECTURAL PLANS | A | 18-Oct-18 | 2 | 1 | Y | Re Submission Pending
218 | PE-DC-435-640-C003 | SERVICE BLDG-DESIGN OF SUPERSTRUCTURE | A | 15-Nov-18 |  | 0 | Y | Pending for Approval
219 | PE-DG-435-614-C005 | RC OF TDBFP DECK (PART 1 OF 6) | I | 04-Apr-19 |  | 0 | Y | Pending for Approval
220 | PE-DC-435-642-C003 | D.G. SET BLDG. - DESIGN OFSUPERSTRUCTURE | A | 06-Jun-19 |  |  | Y | First Submission Due
221 | PE-DC-435-620-C004 | CHIMNEY-Internal Platform Framing Design | A | 08-Nov-18 | 2 | 1 | Y | Re Submission Pending
222 | PE-DG-435-644-C004 | TIE BEAMS & ROOF | I | 31-Oct-19 |  |  | Y | First Submission Due
223 | PE-DC-435-644-C001 | HYD. GEN.PLANT - LOAD CALCULATION | A | 31-Oct-19 |  |  | Y | First Submission Due
224 | PE-DG-435-641-C008 | ADMN BLDG. SECTION 2-2 | A | 01-Aug-19 |  |  | Y | First Submission Due
225 | PE-DG-435-611-C009 | PH BLDG.(AB BAY)- GA & R.C. DTLS OF FL @EL +3.5M | I | 18-Jul-19 |  |  | Y | First Submission Due
226 | PE-DG-435-610-C001 | CANTEEN BLDG - ARCHITECTURAL PLAN AT EL 4.5 & SECTION | A | 14-Nov-19 | 2 | 3 | Y | Re Submission Pending
227 | PE-DC-435-622-C001 | GT-DESIGN OF FOUNDATION & FIRE BARRIER WALL | A | 07-Feb-19 |  | 0 | Y | Pending for Approval
228 | PE-DG-435-615-C002 | BOWL MILLS - FOUNDATION RC DETAILS | I | 08-Nov-18 | 2 | 5 | Y | Re Submission Pending
229 | PE-DG-435-612-C018 | PH BLDG.-AB BAY-DETAILS OF STAIRCASE MKD. SC-04 | I | 17-Jan-19 | 2 | 1 | Y | Re Submission Pending
230 | PE-DG-435-641-C022 | ADMN BLDG. -DETAILS OF STAIRCASE | I | 02-Jul-20 |  |  | Y | Submission Not Due
231 | PE-DC-435-640-C004 | SERVICE BLDG(INTER-CONNECTING GALLERY TO POWER HOUSE)-ANALYSIS & DESIGN OF GALLERY | A | 11-Apr-19 |  |  | Y | First Submission Due
232 | PE-DG-435-638-C004 | COND TRANSFER PH- PLINTH, LINTEL & ROOF LAYOUT & DETAILS | I | 31-Oct-19 | 2 | 0 | Y | Re Submission Pending
233 | PE-DG-435-622-C005 | TRANSFORMER YARD - LAYOUT DETAILS SH-2 & RAIL TRACK DETAILS | I | 20-Jun-19 |  |  | Y | First Submission Due
234 | PE-DG-435-616-C010 | BUNKER BAY - FRAMING PLAN OF FEEDER FLOOR | I | 21-Feb-19 | 2 | 2 | Y | Re Submission Pending
235 | PE-DG-435-619-C009 | ESP CONT ROOM- GA & RC DTLS OF TIE/LNTEL BEAMS | I | 08-Aug-19 |  |  | Y | First Submission Due
236 | PE-DC-435-620-C006 | CHIMNEY -Liner Design | A | 15-Nov-18 | 1 | 0 | N | Approved
237 | PE-DG-435-619-C010 | ESP CONT ROOM- GA & RC DTLS OF FL @ ROOF LEVEL | I | 08-Aug-19 |  |  | Y | First Submission Due
238 | PE-DG-435-674-C001 | SEPTIC TANK,UPFLOW FILTER AND CHLORINATION CHAMBER(100 USERS) - GA & MASONARY DETAILS | I | 19-Mar-20 |  |  | Y | Submission Not Due
239 | PE-DG-435-640-C004 | SERVICE BLDG-ARCH GA AT SECOND & THIRD FLOOR LEVEL | A | 06-Sep-18 | 2 | 2 | Y | Re Submission Pending
240 | PE-DC-435-641-C001 | Admin Building – Load Calculation, Analysis and Design of Foundation | A | 28-Nov-19 | 2 | 1 | Y | Re Submission Pending
241 | PE-DC-435-650-C001 | FIRE STATION -LOAD CALCULATION | A | 05-Dec-19 | 2 | 3 | Y | Re Submission Pending
242 | PE-DG-435-622-C012 | TRANSFORMER YARD - 220KV STATION TFR-CONCRETE OUTLINE DETAILS | A | 11-Apr-19 |  |  | Y | First Submission Due
243 | PE-DG-435-613-C001 | T.G. FDN -GA OF SUB-STRUCTURE RAFT | A | 16-Aug-18 | 2 | 2 | Y | Re Submission Pending
244 | PE-DG-435-612-C028 | PH BLDG. - (BC-BAY-TG) FRAMING PLAN 8.5M FFL (UNIT#1 & UNIT#2) (2-SHEETS) | I | 20-Dec-18 | 2 | 0 | Y | Re Submission Pending
245 | PE-DC-435-612-C033 | PH BLDG - DESIGN OF VENTILATION DUCT ALONG AXIS C (UNIT-1 & 2 & CCR) | A | 17-Oct-19 |  |  | Y | First Submission Due
246 | PE-DG-435-640-C002 | SERVICE BLDG-ARCH GA ATFIRST FLOOR LEVEL | A | 30-Aug-18 | 2 | 2 | Y | Re Submission Pending
247 | PE-DC-435-639-C003 | CPU REGENERATION BLDG-DESIGN OF SUPERSTRUCTURE | A | 30-Jan-20 |  |  | Y | First Submission Due
248 | PE-DG-435-618-C001 | ID FAN-GA OF FOUNDATION | A | 03-Jan-19 | 2 | 1 | Y | Re Submission Pending
249 | PE-DG-435-611-C048 | PH BLDG.(BC BAY-TG)- ARCH PLAN AT EL+ 24M/25.5 (UNIT#1 & UNIT#2) | I | 30-May-19 | 2 | 1 | Y | Re Submission Pending
250 | PE-DC-435-675-C002 | PIPE RACK PR1 - DESIGN OF SUPERSTRUCTURE | A | 29-Aug-19 |  |  | Y | First Submission Due
251 | PE-DC-435-639-C004 | CPU REGENERATION - DESIGN OF TANKS | A | 13-Feb-20 |  |  | Y | First Submission Due
252 | PE-DG-435-634-C001 | HFO & LDO TANKS-G.A. & R.C. DTLS OF FOUNDNS. | I | 15-Aug-19 | 4 | 1 | N | Approved
253 | PE-DG-435-653-C006 | CW PH - GA DETAILS OF SUMP (SECTION) | I | 14-Feb-19 | 2 | 2 | Y | Re Submission Pending
254 | PE-DG-435-611-C029 | PH BLDG.-GA & R.C DETAILS OF CEP PIT (UNIT#1 & UNIT#2) (2-SHEETS) | I | 08-Nov-18 | 2 | 2 | Y | Re Submission Pending
255 | PE-DG-435-611-C030 | PH BLDG. - GA & RC DETAILS OF OIL CANAL | I | 28-Feb-19 | 2 | 1 | Y | Re Submission Pending
256 | PE-DG-435-611-C056 | PH BLDG. -GA & R.C. DTLS OF FLOOR AT EL + 0.0M (CCR BUILDING) (SHEET 7 OF 7) | I | 22-Aug-19 |  |  | Y | First Submission Due
257 | PE-DG-435-642-C001 | D.G. HOUSE -ARCH PLAN, ELEVATIONS AND SECTIONS. | A | 04-Jul-19 |  | 0 | Y | Pending for Approval
258 | PE-DG-435-611-C033 | PH BLDG.- REAR ELEVATION (UNIT#1 & UNIT#2) | A | 29-Nov-18 | 3 | 0 | Y | Re Submission Pending
259 | PE-DG-435-675-C008 | PIPE RACK PR-4 - STRUCTURAL STEEL DETAILS | I | 07-Nov-19 |  |  | Y | First Submission Due
260 | PE-DC-435-675-C009 | PIPE RACK PR5 - DESIGN OF FOUNDATION | A | 14-Nov-19 |  |  | Y | First Submission Due
261 | PE-DG-435-634-C019 | F.O. PR PH LINTEL LEVEL BEAM LAYOUT& R.C. DTLS | I | 20-Jun-19 |  |  | Y | First Submission Due
262 | PE-DG-435-613-C013 | T.G DECK-REINFORCEMENT DETAILS OF CROSS-BEAM-6(SHEETS 1 TO 3) | I | 18-Oct-18 |  | 0 | Y | Pending for Approval
263 | PE-DC-435-675-C010 | PIPE RACK PR5 - DESIGN OF SUPERSTRUCTURE | A | 28-Nov-19 |  |  | Y | First Submission Due
264 | PE-DC-435-600-C001 | DESIGN CRITERION FOR CIVIL, STRUCTURAL & ARCHITECHTURAL WORKS | A | 05-Jul-18 | 2 | 1 | Y | Re Submission Pending
265 | PE-DG-435-635-C008 | DM MAKEUP PUMP HOUSE -GA & RC DETAILS OF ROOF BEAM & SLAB | I | 16-May-19 | 2 | 1 | Y | Re Submission Pending
266 | PE-DG-435-603-C005 | PLANT DRAINS DETAILS | I | 11-Oct-18 | 2 | 2 | Y | Re Submission Pending
267 | PE-DG-435-606-C001 | LAYOUT OF BOUNDARY WALL | A | 07-Jun-18 | 1 | 5 | N | Approved
268 | PE-DC-435-608-C003 | PERMT STORE - DESIGN OF SUPERSTRUCTURE | A | 02-Aug-18 | 1 | 1 | N | Approved
269 | PE-DG-435-611-C058 | PH BLDG.- WINDOWS SCHEDULE. | I | 18-Jul-19 |  |  | Y | First Submission Due
270 | PE-DG-435-622-C013 | TRANSFORMER YARD - 220KV STATION TFR-RC DETAILS | I | 25-Apr-19 |  |  | Y | First Submission Due
271 | PE-DG-435-612-C017 | PH BLDG.-AB BAY-DETAILS OF STAIRCASE MKD. SC-03 | I | 03-Jan-19 | 2 | 1 | Y | Re Submission Pending
272 | PE-DG-435-641-C033 | DISPENSARY - ARCH PLAN | A | 20-Jun-19 | 1 | 2 | N | Approved
273 | PE-DG-435-612-C021 | PH BLDG. -(AB BAY) FRAMING PLAN AT EL 3.5M FFL (CCR BUILDING) | I | 28-Mar-19 | 2 | 1 | Y | Re Submission Pending
274 | PE-DG-435-611-C002 | POWER HOUSE BUILDING -GA AND RC OF COLUMN FOUNDATION ON A ROW TO C ROW (UNIT#2) SH-1 and 2 | I | 13-Sep-18 | 2 | 1 | Y | Re Submission Pending
275 | PE-DG-435-621-C002 | AUXILIARY BOILER – GA & RC DETAILS OF AUX BFP FOUNDATION | I | 06-Dec-18 | 3 | 0 | Y | Re Submission Pending
276 | PE-DG-435-648-C002 | AIR WASHER BLDG-ARCHITECTURAL SECTIONS | A | 10-Oct-19 | 1 | 1 | N | Approved
277 | PE-DG-435-611-C003 | PH BUILDING- GA & R.C DTLS OF INTERMEDIATE COLS. FDN (UNIT#1) | A | 27-Sep-18 | 2 | 0 | Y | Re Submission Pending
278 | PE-DC-435-615-C001 | BOWL MILL FOUNDATION-(DESIGN CALCULATION) | A | 11-Oct-18 | 2 | 5 | Y | Re Submission Pending
279 | PE-DG-435-613-C018 | T.G DECK-REINFORCEMENT DETAILS OF LONGITUDINAL BEAMS-11 & 12 | I | 25-Oct-18 |  |  | Y | First Submission Due
280 | PE-DC-435-645-C002 | WORK SHOP BLDG - DESIGN OF FOUNDATIONS | A | 15-Aug-19 | 2 | 1 | Y | Re Submission Pending
281 | PE-DG-435-639-C005 | CPU REGN BLDG- COLUMN LAYOUT & RC DETAILS | I | 30-Jan-20 |  |  | Y | First Submission Due
282 | PE-DG-435-613-C019 | T.G DECK-REINFORCEMENT DETAILS OF LONGITUDINAL BEAMS-13 & 14 | I | 25-Oct-18 |  |  | Y | First Submission Due
283 | PE-DC-435-622-C005 | OIL WATER SEPARATOR PIT DESIGN | A | 02-May-19 |  |  | Y | First Submission Due
284 | PE-DG-435-611-C011 | PH BLDG.(AB BAY-CR)- GA & R.C. DTLS OF FL @EL +8.5M | I | 10-Oct-19 |  |  | Y | First Submission Due
285 | PE-DG-435-620-C015 | External Platform Details | I | 24-Jan-19 | 4 | 1 | N | Approved
286 | PE-DG-435-638-C001 | COND TRANSFER PH- ARCHITECTURAL PLANS, ELEVATION AND SECTIONS | A | 31-Oct-19 | 2 | 2 | Y | Re Submission Pending
287 | PE-DG-435-603-C004 | PLANT DRAIN LAYOUT | A | 13-Sep-18 | 2 | 3 | Y | Pending for Approval
288 | PE-DG-435-611-C023 | PH BLDG.(BC BAY-CR) - GA & R.C. DTLS OF FLOOR AT EL + 27.50M | I | 19-Sep-19 |  |  | Y | First Submission Due
289 | PE-DG-435-611-C031 | PH BLDG. - GEN. NOTES & STD. DETAILS FOR ARCH. WORKS | I | 08-Nov-18 | 2 | 1 | Y | Re Submission Pending
290 | PE-DC-435-645-C003 | WORK SHOP BLDG. - DESIGN OFSUPERSTRUCTURE | A | 29-Aug-19 |  |  | Y | First Submission Due
291 | PE-DG-435-644-C001 | ARCHITECTURAL PLAN | I | 26-Sep-19 |  |  | Y | First Submission Due
292 | PE-DG-435-617-C001 | G.A. OF BOILER FOUNDATION. | A | 24-May-18 | 2 | 2 | Y | Re Submission Pending
293 | PE-DC-435-613-C005 | TG FOUNDATION - DESIGN OF SUBSTRUCTURE BEAMS | A | 15-Nov-18 |  |  | Y | First Submission Due
294 | PE-DG-435-617-C002 | R.C. DTLS OF BOILER FDN. | I | 07-Jun-18 | 4 | 4 | N | Approved
295 | PE-DG-435-611-C059 | PH BLDG.-DOORS SCHEDULE. | I | 15-Aug-19 | 4 | 0 | N | Approved
296 | PE-DC-435-614-C001 | DESIGN OF MDBFP DECK (STATIC & DYNAMIC) | A | 20-Dec-18 | 1 | 1 | N | Approved
297 | PE-DC-435-613-C001 | TG FOUNDATION- ANALYSIS & DESIGN OF RAFT, COLUMN | A | 16-Aug-18 | 2 | 2 | Y | Re Submission Pending
298 | PE-DC-435-641-C006 | GATE HOUSE - DESIGN OF SUPERSTRUCTURE | A | 28-Mar-19 |  |  | Y | First Submission Due
299 | PE-DG-435-620-C016 | TYPICAL DETAILS OF STEEL DOORS & ROLLING SHUTTER | I | 31-Jan-19 | 4 | 0 | N | Approved
300 | PE-DG-435-612-C015 | PH BLDG. -AB-BAY DETAILS OF MISC. PLATEFORMS & STAIRS | I | 13-Jun-19 |  |  | Y | First Submission Due
301 | PE-DC-435-634-C003 | F.O. PR PH -DESIGNOF FOUNDATIONS | A | 11-Jul-19 | 3 | 0 | Y | Re Submission Pending
302 | PE-DC-435-640-C001 | SERVICE BLDG- LOAD CALCULATION AND ANALYSIS | A | 01-Nov-18 |  | 0 | Y | Pending for Approval
303 | PE-DC-435-622-C002 | ST-DESIGN OF FOUNDATION & FIRE BARRIER WALL | A | 11-Apr-19 |  |  | Y | First Submission Due
304 | PE-DG-435-618-C007 | SEAL AIR FAN -GA & RC DETAILS OF FDN. | I | 03-Jan-19 | 2 | 1 | Y | Re Submission Pending
305 | PE-DG-435-608-C012 | PERMT STORE - DETAILS OF PURLIN & TOP CHORD | I | 13-Sep-18 | 2 | 0 | Y | Re Submission Pending
306 | PE-DG-435-640-C006 | SERVICE BLDG-ARCH GA AT ROOF LEVEL | A | 13-Sep-18 | 2 | 2 | Y | Re Submission Pending
307 | PE-DC-435-622-C003 | UAT-DESIGN OF FOUNDATION & FIRE BARRIER WALL | A | 28-Feb-19 |  |  | Y | First Submission Due
308 | PE-DG-435-612-C030 | PH BLDG. - (B TO H`-BAY) FRAMING PLAN AT EL+13.5M FFL (CCR BUILDING) | I | 14-Feb-19 |  |  | Y | First Submission Due
309 | PE-DG-435-610-C003 | CANTEEN BLDG WITH DORMITORY (NEAR ADMIN) - ARCHITECTURAL PLAN AT EL 0 & 4.5 | I | 12-Dec-19 | 2 | 1 | Y | Re Submission Pending
310 | PE-DC-435-617-C002 | ESP FOUNDATION(DESIGN OF ESP FOUNDATION) | A | 21-Jun-18 | 2 | 2 | Y | Re Submission Pending
311 | PE-DG-435-619-C008 | ESP CONT ROOM- GA & RC DTLS OF FL @ FIRST FLOOR | I | 18-Jul-19 |  | 0 | Y | Pending for Approval
312 | PE-DG-435-614-C006 | RC OF TDBFP DECK (PART 2 OF 6) | I | 11-Apr-19 |  | 0 | Y | Pending for Approval
313 | PE-DG-435-620-C009 | Details of Liner support beams | I | 15-Nov-18 | 4 | 1 | N | Approved
314 | PE-DC-435-641-C003 | ADMN BLDG-DESIGN OF SUPERSTRUCTURE | A | 06-Feb-20 |  |  | Y | First Submission Due
315 | PE-DG-435-620-C027 | Fixing details of Liner insulation | I | 14-Feb-19 | 2 | 1 | Y | Pending for Approval
316 | PE-DC-435-675-C005 | PIPE RACK PR3 - DESIGN OF FOUNDATION | A | 17-Oct-19 |  |  | Y | First Submission Due
317 | PE-DG-435-646-C002 | CHEMICAL LAB. BLDG. - LAYOUT AND R.C. DTLS OF FDN & COLUMNS | I | 18-Jul-19 | 2 | 1 | Y | Re Submission Pending
318 | PE-DC-435-622-C006 | TRANSFOREMR YARD PAVING : MISC DESIGN | A | 28-Feb-19 |  |  | Y | First Submission Due
319 | PE-DG-435-610-C007 | CANTEEN BLDG(NEAR FIRE STATION) - LAYOUT & RC DETAILS OF GRADE & PLINTH BEAMS | I | 26-Sep-19 | 1 | 0 | N | Approved
320 | PE-DC-435-617-C001 | BOILER & MILL BUNKER FOUNDATION (DESIGN OF BOILER & MILL BUNKER FOUNDATION) | A | 24-May-18 | 2 | 2 | Y | Re Submission Pending
321 | PE-DG-435-646-C003 | CHEMICAL LAB. BLDG. - G.A. AND R.C. DTLS OF COLUMN OF GRADE BEAM AND PLINTH BEAMS | I | 22-Aug-19 | 2 | 1 | Y | Re Submission Pending
322 | PE-DC-435-612-C018 | P.H. BLDG.-DES. OF OIL CANAL (Unit-1 & 2) | A | 20-Dec-18 | 2 | 1 | Y | Re Submission Pending
323 | PE-DG-435-614-C004 | GA OF TDBFP DECK | A | 28-Mar-19 | 3 | 1 | Y | Pending for Approval
324 | PE-DG-435-639-C009 | CPU REGN - G.A. AND R.C. DTLS OF GROUND FLOOR, EP AT BOTTOM OF ROOF SLAB/BEAMS | I | 09-Apr-20 |  |  | Y | Submission Not Due
325 | PE-DG-435-603-C001 | SITE LEVELLING AND GRADING | A | 21-Jun-18 | 4 | 1 | N | Approved
326 | PE-DG-435-622-C011 | TRANSFORMER YARD - UT R.C. DETAILS | I | 04-Apr-19 |  |  | Y | First Submission Due
327 | PE-DC-435-634-C002 | F.O.PR PH -LOAD CALCULATION | A | 16-May-19 | 3 | 0 | Y | Re Submission Pending
328 | PE-DG-435-641-C009 | ADMN BLDG. - NORTH ELEVATION | A | 01-Aug-19 |  |  | Y | First Submission Due
329 | PE-DG-435-653-C004 | CW PH - ARCHITECTURAL SECTIONS | I | 16-May-19 | 2 | 0 | Y | Re Submission Pending
330 | PE-DG-435-606-C003 | ARCH DETAILS OF WATCH TOWERS | A | 05-Jul-18 | 2 | 1 | Y | Re Submission Pending
331 | PE-DG-435-642-C006 | D.G. BLDG ROOF SLAB & BEAM DETAILS | I | 04-Jul-19 |  |  | Y | First Submission Due
332 | PE-DC-435-612-C007 | P.H. BLDG.-DES. OF ROOF TRUSS SYSTEM | A | 06-Sep-18 | 2 | 1 | Y | Re Submission Pending
333 | PE-DG-435-638-C005 | COND TRANSFER PH- GA AND RC DETAILS OF GROUND FLOOR | I | 31-Oct-19 |  | 0 | Y | Pending for Approval
334 | PE-DC-435-612-C011 | P.H. BLDG.-DES. OF B ROW CLADDING SUPPORTS AND WALL BEAMS | A | 27-Sep-18 |  |  | Y | First Submission Due
335 | PE-DG-435-606-C004 | GA & RC DETAILS OF WATCH TOWERS | I | 19-Jul-18 | 2 | 1 | Y | Re Submission Pending
336 | PE-DG-435-611-C049 | PH BLDG.(BCDEFG BAY-CR)- ARCH PLAN AT EL+24M | I | 06-Jun-19 | 3 | 1 | Y | Re Submission Pending
337 | PE-DG-435-613-C003 | T.G FDN-REINFORCEMENT DETAILS OF SUBSTRUCTURE UP TO( + -) 0.0 M | I | 06-Sep-18 | 2 | 2 | Y | Re Submission Pending
338 | PE-DG-435-612-C003 | PH BLDG. - STRUCTURAL FRAMING ALONG C ROW | I | 11-Oct-18 | 2 | 2 | Y | Re Submission Pending
339 | PE-DG-435-640-C001 | SERVICE BLDG-ARCH GA AT GROUND LEVEL | A | 23-Aug-18 | 2 | 2 | Y | Re Submission Pending
340 | PE-DC-435-644-C002 | HYD. GEN.PLANT - DESIGN OF FOUNDATIONS | A | 31-Oct-19 |  |  | Y | First Submission Due
341 | PE-DG-435-642-C007 | GA AND RC DETAILS OF DG FOUNDATION | I | 01-Aug-19 |  |  | Y | First Submission Due
342 | PE-DC-435-641-C004 | GATE HOUSE - LOAD CALCULATION | A | 14-Mar-19 |  |  | Y | First Submission Due
343 | PE-DG-435-612-C105 | PH BLDG - WALL BEAM FRAMING ON AXIS B | I | 13-Dec-18 |  |  | Y | First Submission Due
344 | PE-DG-435-608-C005 | PERMT STORE AND OFFICE- DETAIL OF GUARD ROOM, OFFICE AND FENCING | I | 16-Aug-18 | 2 | 2 | Y | Re Submission Pending
345 | PE-DG-435-612-C019 | PH BLDG.-AB BAY-DETAILS OF STAIRCASE MKD. SC-05 | I | 31-Jan-19 | 3 | 0 | Y | Re Submission Pending
346 | PE-DG-435-613-C004 | T.G FDN.-GA OF DECK: TOP PLAN | I | 13-Sep-18 | 3 | 0 | Y | Re Submission Pending
347 | PE-DG-435-611-C012 | PH BLDG. (AB BAY-CR)- GA & R.C. DTLS OF FL @ EL 12M | I | 12-Sep-19 |  |  | Y | First Submission Due
348 | PE-DG-435-640-C019 | SERVICE BLDG - GA & RC DETAILS OF GRADE BEAMS & PLINTH BEAMS | I | 22-Nov-18 |  | 0 | Y | Pending for Approval
349 | PE-DG-435-653-C018 | FEED POOL -GENERAL ARRANGEMENT | A | 10-Jan-19 | 1 | 3 | N | Approved
350 | PE-DG-435-617-C006 | G.A. & R.C. DETAILS OF ID DUCT FOUNDATIONS( ESP TO CHIMNEY)PART 1 | I | 14-Feb-19 | 2 | 2 | Y | Re Submission Pending
351 | PE-DC-435-612-C014 | P.H. BLDG.-DES. OF D, E, F, G & H ROW COLUMN, BASE PLATE BRACINGS & DE, EF,FG,GH BAY TRANS GIRDERS (CCR) | A | 25-Oct-18 | 3 | 1 | Y | Re Submission Pending
352 | PE-DC-435-644-C003 | HYD. GEN.PLANT - DESIGN OFSUPERSTRUCTURE | A | 14-Nov-19 |  |  | Y | First Submission Due
353 | PE-DG-435-640-C020 | SERVICE BLDG - GA & RC DETAILS OF BEAMS & SLAB AT FIRST FLOOR LEVEL-SH1 | I | 29-Nov-18 |  |  | Y | First Submission Due
354 | PE-DG-435-616-C003 | BUNKER`S BAY - R.C.C. DTLS OF GROUND FL. | I | 18-Jul-19 |  |  | Y | First Submission Due
355 | PE-DC-435-612-C015 | P.H. BLDG.-DES. OF D & E ROW WALL BEAMS (CCR) | A | 25-Oct-18 |  |  | Y | First Submission Due
356 | PE-DC-435-650-C002 | FIRE STATION -DESIGN OF FOUNDATIONS | A | 05-Dec-19 | 1 | 2 | N | Approved
357 | PE-DG-435-611-C040 | PH BUILDING ARCHITECTURAL PLAN AT EL.(+)8.50M (UNIT#1) | I | 07-Mar-19 | 3 | 1 | Y | Re Submission Pending
358 | PE-DG-435-641-C003 | ADMN BLDG ARCHITECTURAL PLAN AT EL 8.500 | A | 04-Jul-19 | 2 | 1 | Y | Re Submission Pending
359 | PE-DC-435-612-C004 | PH BLDG. - 3D ANALYSIS - CCR | A | 27-Sep-18 | 2 | 3 | Y | Re Submission Pending
360 | PE-DG-435-651-C006 | CW DUCTS - LAYOUT OF DUCT FROM COOLING TOWER TO FEED POOL | I | 14-Mar-19 | 2 | 4 | Y | Re Submission Pending
361 | PE-DG-435-613-C010 | T.G DECK-REINFORCEMENT DETAILS OF CROSS-BEAM-3(SHEETS 1 & 2) | I | 11-Oct-18 | 3 | 0 | Y | Re Submission Pending
362 | PE-DC-435-612-C017 | P.H. BLDG.-DES. OF GABLE END (Unit-1 & 2) | A | 23-May-19 | 2 | 0 | Y | Re Submission Pending
363 | PE-DG-435-611-C041 | PH BUILDING ARCHITECTURAL PLAN AT (+)8.50M (CCR BUILDING) | I | 14-Mar-19 | 3 | 1 | Y | Re Submission Pending
364 | PE-DG-435-611-C008 | PH BLDG. -GA & R.C. DTLS OF FL @ EL + 0.0M (SHEET 4 OF 7) | I | 17-Oct-19 |  |  | Y | First Submission Due
365 | PE-DG-435-653-C011 | CW PH - GA DETAIL AT OPERATING FLOOR | I | 18-Jul-19 |  |  | Y | First Submission Due
366 | PE-DC-435-612-C006 | P.H. BLDG.-DES. OF CRANE GIRDER IN BC BAY | A | 13-Sep-18 | 2 | 0 | Y | Re Submission Pending
367 | PE-DG-435-611-C042 | PH BUILDING ARCHITECTURAL PLAN AT (+)8.50M (UNIT#2) | I | 28-Mar-19 | 3 | 1 | Y | Re Submission Pending
368 | PE-DG-435-620-C004 | Shuttering & R.C. details of chimney shell | I | 18-Oct-18 | 2 | 0 | Y | Re Submission Pending
369 | PE-DG-435-611-C043 | PH BLDG. (AB BAY-CR)- ARCH PLAN EL @ EL 12M | I | 04-Apr-19 | 3 | 1 | Y | Re Submission Pending
370 | PE-DG-435-620-C022 | Chimney Liner Details- Can type F | I | 27-Dec-18 | 2 | 3 | Y | Re Submission Pending
371 | PE-DG-435-618-C005 | F.D. FAN - G.A. OF FOUNDATION | A | 20-Dec-18 | 2 | 3 | Y | Re Submission Pending
372 | PE-DG-435-645-C001 | WORK SHOP HOUSE -ARCH PLAN, ELEVATIONS AND SECTIONS. | A | 25-Jul-19 | 2 | 1 | Y | Re Submission Pending
373 | PE-DG-435-634-C015 | F.O. PR PH - ARCH. SECTIONS & DETAILS | I | 27-Jun-19 | 3 | 2 | Y | Pending for Approval
374 | PE-DG-435-639-C004 | CPU REGN BLDG- FOUNDATION LAYOUT & RC DETAILS | I | 16-Jan-20 |  |  | Y | First Submission Due
375 | PE-DG-435-650-C006 | FIRE STATION - REINFORCEMENT DETAILS OF ROOF SLAB & BEAMS | I | 09-Jan-20 | 1 | 2 | N | Approved
376 | PE-DG-435-611-C044 | PH BUILDING ARCHITECTURAL PLAN AT EL.(+)17.00M (UNIT#1) | I | 18-Apr-19 | 3 | 1 | Y | Re Submission Pending
377 | PE-DG-435-635-C009 | DM MAKE UP PUMP HOUSE-GA& RC DETAILS OF 0.00M FLOOR | I | 22-Aug-19 |  |  | Y | First Submission Due
378 | PE-DC-435-622-C004 | UT-DESIGN OF FOUNDATION & FIRE BARRIER WALL | A | 21-Mar-19 |  |  | Y | First Submission Due
379 | PE-DG-435-610-C011 | CANTEEN BLDG WITH DORMITORY (NEAR ADMIN) - RC DETAILS OF ROOF SLAB BEAMS & SLAB | I | 31-Oct-19 |  |  | Y | First Submission Due
380 | PE-DG-435-611-C028 | PH BLDG.-C.W. PIT - RC DETAIL (UNIT#1 & UNIT#2) | I | 25-Apr-19 | 3 | 0 | Y | Re Submission Pending
381 | PE-DG-435-614-C007 | RC OF TDBFP DECK (PART 3 OF 6) | I | 18-Apr-19 |  | 0 | Y | Pending for Approval
382 | PE-DG-435-610-C012 | CANTEEN (NEAR FIRE STATION)- GA & RC DETAILS OF FLOOR PLAN AND MISC. EQUIIPMENT FOUNDATIONS AT EL 0.000 | I | 05-Dec-19 |  |  | Y | First Submission Due
383 | PE-DC-435-619-C001 | ESP CONTROL BLDG.-LOAD CALCULATION | A | 28-Mar-19 | 2 | 1 | Y | Re Submission Pending
384 | PE-DG-435-616-C004 | BUNKER`S BAY - R.C.C. DTLS OF FEEDER FLOOR | I | 11-Apr-19 | 2 | 0 | Y | Re Submission Pending
385 | PE-DG-435-617-C003 | G.A. OF ESP FOUNDATION | A | 21-Jun-18 | 2 | 2 | Y | Re Submission Pending
386 | PE-DC-435-653-C005 | CW PUMP HOUSE - DESIGN OF FLOORS | A | 07-Mar-19 |  |  | Y | First Submission Due
387 | PE-DC-435-653-C006 | CW PUMP HOUSE - DESIGN OF SUMP | A | 07-Feb-19 | 1 | 2 | N | Approved
388 | PE-DG-435-675-C012 | PIPE RACK PR-6 - STRUCTURAL STEEL DETAILS | I | 19-Dec-19 |  |  | Y | First Submission Due
389 | PE-DG-435-617-C004 | R.C. DTLS OF ESP FDN. | I | 05-Jul-18 | 2 | 2 | Y | Re Submission Pending
390 | PE-DG-435-611-C046 | PH BUILDING ARCHITECTURAL PLAN AT EL.(+)17.00M (UNIT#1) | I | 09-May-19 | 3 | 1 | Y | Re Submission Pending
391 | PE-DC-435-634-C004 | F.O. PR PH -DESIGN OF SUBSTRUCTURE | A | 11-Jul-19 |  |  | Y | First Submission Due
392 | PE-DG-435-634-C013 | F.O. PR PH -ARCHITECTURAL PLANS | A | 06-Jun-19 | 3 | 2 | Y | Pending for Approval
393 | PE-DG-435-646-C001 | CHEMICAL LAB.HOUSE -ARCH PLAN, ELEVATIONS AND SECTIONS. | A | 09-Jan-20 | 2 | 1 | Y | Re Submission Pending
394 | PE-DG-435-622-C006 | TRANSFORMER YARD - GENERATOR TRANSFORMER CONCRETE OUTLINE DETAILS | A | 07-Feb-19 |  | 0 | Y | Pending for Approval
395 | PE-DG-435-650-C007 | FIRE STATION - DETAILS OF GROUND FLOOR | I | 19-Mar-20 |  |  | Y | Submission Not Due
396 | PE-DG-435-653-C003 | CW PH - ARCITECTURAL ELEVATIONS | A | 25-Apr-19 | 2 | 0 | Y | Re Submission Pending
397 | PE-DG-435-641-C017 | ADMN BLDG. - GA & RC DETAILS OF LINTEL BEAMS | I | 23-Jan-20 |  |  | Y | First Submission Due
398 | PE-DG-435-612-C037 | PH BLDG. - (BC-BAY) FRAMING PLAN AT EL+32.50M FFL (UNIT#1 & UNIT#2) | I | 07-Feb-19 |  |  | Y | First Submission Due
399 | PE-DG-435-634-C003 | GA & RC DETAILS OF DYKE FLOOR | I | 03-Oct-19 | 3 | 0 | Y | Re Submission Pending
400 | PE-DG-435-640-C017 | SERVICE BLDG - GA & RC DETAILS OF COLUMNS | I | 08-Nov-18 |  | 0 | Y | Pending for Approval
401 | PE-DG-435-648-C004 | AIR WASHER BLDG -LAYOUT & RC DETAILS OF PLINTH BEAM | I | 20-Jun-19 |  |  | Y | First Submission Due
402 | PE-DC-435-653-C007 | ELEC ANNEXE - LOAD CALCULATION | A | 22-Aug-19 | 3 | 0 | Y | Re Submission Pending
403 | PE-DG-435-620-C026 | Details of Liner expansion joints | I | 17-Jan-19 | 2 | 1 | Y | Re Submission Pending
404 | PE-DG-435-617-C011 | BOILER AREA - GA & RC DETAILS OF LIFT COLUMN FOUNDATIONS & M/C ROOM DETAILSLIFT PIT | I | 15-Aug-19 |  |  | Y | First Submission Due
405 | PE-DC-435-647-C003 | COMPRESSOR BUILDING - DESIGN OF SLABS AND CRANE GIRDER | A | 08-Aug-19 |  |  | Y | First Submission Due
406 | PE-DG-435-639-C003 | CPU REGENERATION BLDG- ARCHITECTURAL ELEVATIONS | I | 05-Mar-20 |  |  | Y | Submission Not Due
407 | PE-DG-435-617-C012 | BOILER AREA - GA & RC DETAILS OF LIFT M/C ROOM FLOOR AND ROOF | A | 29-Aug-19 |  |  | Y | First Submission Due
408 | PE-DC-435-675-C006 | PIPE RACK PR3 - DESIGN OF SUPERSTRUCTURE | A | 10-Oct-19 |  |  | Y | First Submission Due
409 | PE-DC-435-610-C003 | CANTEEN WITH DORMITORY BLDG (NEAR ADMIN)- LOAD CALCULATION ,DESIGN OF COL-FDN,PLINTH BEAMS,TIE,ROOF BEAMS & SLAB | A | 24-Oct-19 | 2 | 1 | Y | Re Submission Pending
410 | PE-DC-435-653-C008 | ELEC ANNEXE - DESIGN OF FOUNDATIONS | A | 22-Aug-19 | 2 | 0 | Y | Re Submission Pending
411 | PE-DC-435-675-C007 | PIPE RACK PR4 - DESIGN OF FOUNDATION | A | 31-Oct-19 |  |  | Y | First Submission Due
412 | PE-DC-435-653-C009 | ELEC ANNEXE - DESIGN OF SUPERSTRUCTURE | A | 05-Sep-19 | 3 | 0 | Y | Re Submission Pending
413 | PE-DC-435-610-C002 | CANTEEN BLDG (NEAR FIRE STATION)- LOAD CALCULATION ,DESIGN OF SUPERSTR | A | 12-Sep-19 | 2 | 1 | Y | Re Submission Pending
414 | PE-DG-435-671-C003 | DRINKING & SERVICE WATER TANK-GA & RC DETAILS OF FOUNDATION | I | 05-Sep-19 |  |  | Y | First Submission Due
415 | PE-DG-435-617-C005 | G.A. & R.C. DETAILS OF ID DUCT FOUNDATIONS( BOILER TO ESP ) | I | 03-Jan-19 | 2 | 2 | Y | Re Submission Pending
416 | PE-DG-435-634-C018 | F.O. PR PH PLINTH BEAM LAYOUT& R.C. DTLS | I | 06-Jun-19 | 3 | 0 | Y | Re Submission Pending
417 | PE-DC-435-646-C001 | CHEMICAL LAB BUILDING - LOAD CALCULATION | A | 18-Jul-19 | 2 | 1 | Y | Re Submission Pending
418 | PE-DC-435-671-C004 | DESIGN OF SERVICE WATER OVERHEAD TANK | A | 03-Oct-19 |  |  | Y | First Submission Due
419 | PE-DG-435-640-C011 | SERVICE BLDG. - NORTH ELEVATION | A | 04-Oct-18 |  |  | Y | First Submission Due
420 | PE-DG-435-653-C015 | CW PH - GA & RC DETAILS OF GROUND FLOOR | I | 25-Apr-19 |  |  | Y | First Submission Due
421 | PE-DG-435-611-C022 | PH BLDG.(BCDEFG BAY-CR)- GA & R.C. DTLS OF FLOOR AT EL+ 24M | I | 24-Oct-19 |  |  | Y | First Submission Due
422 | PE-DG-435-641-C001 | ADMN BLDG ARCHITECTURAL PLAN AT EL 0.0 | A | 20-Jun-19 | 2 | 1 | Y | Re Submission Pending
423 | PE-DC-435-650-C003 | FIRE STATION -DESIGN OF SUPERSTRUCTURE | A | 19-Dec-19 | 2 | 3 | Y | Re Submission Pending
424 | PE-DG-435-641-C002 | ADMN BLDG ARCHITECTURAL PLAN AT EL 4.50 | A | 27-Jun-19 | 2 | 1 | Y | Re Submission Pending
425 | PE-DG-435-653-C016 | CW PH - SUPERSTRUCTURE FRAMING ELEVATION | I | 25-Apr-19 | 2 | 2 | Y | Re Submission Pending
426 | PE-DC-435-675-C008 | PIPE RACK PR4 - DESIGN OF SUPERSTRUCTURE | A | 07-Nov-19 |  |  | Y | First Submission Due
427 | PE-DG-435-648-C005 | AIR WASHER BLDG- DETAILS OF COLUMNS, BRACINGS AND BASE PLATE | I | 27-Jun-19 |  |  | Y | First Submission Due
428 | PE-DG-435-634-C016 | F.O. PR PH FOUNDATION LAYOUT & R.C DTLS | I | 16-May-19 | 3 | 0 | Y | Re Submission Pending
429 | PE-DG-435-616-C016 | BUNKER`S BAY - ARCH ELEVATIONS (SH-1) | A | 06-Jun-19 |  |  | Y | First Submission Due
430 | PE-DG-435-640-C033 | SERVICE BLDG(INTER-CONNECTING GALLERY TO PH)-GA & STRUCTURAL DETAILS | I | 11-Apr-19 |  |  | Y | First Submission Due
431 | PE-DG-435-641-C034 | DISPENSARY - ARCH ELEVATION AND SECTIONS | I | 27-Jun-19 | 4 | 2 | N | Approved
432 | PE-DC-435-612-C005 | P.H. BLDG.-DES. OF CRANE GIRDER | A | 16-Aug-18 | 2 | 0 | Y | Re Submission Pending
433 | PE-DG-435-646-C006 | CHEMICAL LAB. BLDG ROOF SLAB & BEAM DETAILS | I | 22-Aug-19 | 2 | 1 | Y | Re Submission Pending
434 | PE-DG-435-634-C017 | F.O. PR PH COLUMN LAYOUT& R.C. DTLS | I | 30-May-19 | 3 | 0 | Y | Re Submission Pending
435 | PE-DC-435-618-C002 | PA FAN-DESIGN OF FOUNDATION SUB-STRUCTURE | A | 08-Nov-18 | 1 | 2 | N | Approved
436 | PE-DG-435-675-C011 | PIPE RACK PR-6 - FOUNDATION LAYOUT & DETAILS | I | 28-Nov-19 |  |  | Y | First Submission Due
437 | PE-DG-435-635-C007 | DM MAKEUP PUMP HOUSE -GA & RC DETAILS OF COLUMNS, FOUNDATION. & PLINTH BEAMS | I | 02-May-19 | 1 | 1 | N | Approved
438 | PE-DG-435-618-C003 | P.A. FAN - G.A. OF FOUNDATION | A | 08-Nov-18 | 1 | 2 | N | Approved
439 | PE-DG-435-674-C006 | SEPTIC TANK,UPFLOW FILTER AND CHLORINATION CHAMBER(UP TO 15 USERS) - REINFORCEMENT DETAILS | I | 14-May-20 |  |  | Y | Submission Not Due
440 | PE-DG-435-640-C008 | SERVICE BLDG SECTION 1-1 | A | 20-Sep-18 |  |  | Y | First Submission Due
441 | PE-DC-435-634-C001 | F.O. STORAGE TANK(DESIGN OF FOUNDATION) | A | 15-Aug-19 | 1 | 1 | N | Approved
442 | PE-DC-435-618-C003 | FD FAN-DESIGN OF FOUNDATION SUB-STRUCTURE | A | 20-Dec-18 | 2 | 3 | Y | Re Submission Pending
443 | PE-DG-435-613-C009 | T.G DECK-REINFORCEMENT DETAILS OF CROSS-BEAM-2(SHEETS 1 TO 3) | I | 11-Oct-18 | 3 | 0 | Y | Re Submission Pending
444 | PE-DG-435-639-C001 | CPU REGENERATION BLDG- ARCHITECTURAL PLANS | A | 13-Feb-20 |  |  | Y | First Submission Due
445 | PE-DC-435-675-C013 | PIPE RACK PR7 - DESIGN OF FOUNDATION | A | 05-Dec-19 |  |  | Y | First Submission Due
446 | PE-DG-435-640-C015 | SERVICE BLDG. - TOILET DETAILS | I | 18-Oct-18 |  |  | Y | First Submission Due
447 | PE-DG-435-651-C007 | CW DUCTS - RC DETAIL OF DUCT FROM COOLING TOWER TO FEED POOL | I | 11-Apr-19 | 2 | 4 | Y | Re Submission Pending
448 | PE-DC-435-617-C005 | MISC. FOUNDATION IN BOILER AREA - DESIGN | A | 02-Jan-20 |  |  | Y | First Submission Due
449 | PE-DG-435-634-C022 | FO PR PUMP HOUSE -GA & RC DETAILS OF GROUND FLOOR & EQUIPMENT FOUNDATIONS | I | 15-Aug-19 |  |  | Y | First Submission Due
450 | PE-DG-435-641-C036 | DISPENSARY –GA & RC DETAILS OF PLINTH AND TIE BEAMS | I | 11-Jul-19 | 2 | 2 | Y | Re Submission Pending
451 | PE-DG-435-639-C002 | CPU REGENERATION BLDG- ARCH. SECTIONS & DETAILS. | A | 27-Feb-20 |  |  | Y | Submission Not Due
452 | PE-DG-435-641-C035 | DISPENSARY –GA & RC DETAILS OF FOUNDATION AND COLUMN | I | 11-Jul-19 | 4 | 2 | N | Approved
453 | PE-DC-435-641-C007 | DISPENSARY - LOAD CALCULATION, DESIGN OF FOUNDATIONS & SUPERSTRUCTURE | A | 11-Jul-19 | 1 | 2 | N | Approved
454 | PE-DG-435-640-C016 | SERVICE BLDG - GA & RC DETAILS OF FOUNDATIONS | I | 01-Nov-18 |  | 0 | Y | Pending for Approval
455 | PE-DG-435-651-C008 | CW PIPE-LAYOUT OF PIPE ENCASEMENT NEAR CWPH | I | 25-Apr-19 | 2 | 3 | Y | Re Submission Pending
456 | PE-DC-435-638-C001 | CONDENSATE STORAGE TANK-DESIGN OF FOUNDATION | A | 26-Sep-19 | 1 | 1 | N | Approved
457 | PE-DG-435-611-C054 | PH BLDG.(BC BAY-TG) - ARCH PLAN EL +27.0M (UNIT#1 & UNIT#2) | I | 01-Aug-19 |  |  | Y | First Submission Due
458 | PE-DG-435-612-C016 | PH BLDG.- DETAILS OF STAIRCASE A-B BAY. MKD. SC-01 & SC-2 | I | 13-Jun-19 | 4 | 1 | N | Approved
459 | PE-DG-435-675-C004 | PIPE RACK PR-2 - STRUCTURAL STEEL DETAILS | I | 19-Sep-19 |  |  | Y | First Submission Due
460 | PE-DG-435-612-C108 | PH BLDG - CRITICAL PIPE SUPPORT B/W CD BAY | I | 31-Jan-19 | 3 | 0 | Y | Re Submission Pending
461 | PE-DG-435-675-C013 | PIPE RACK PR-7 - FOUNDATION LAYOUT & DETAILS | I | 05-Dec-19 |  |  | Y | First Submission Due
462 | PE-DG-435-612-C034 | PH BLDG. - (B TO H`-BAY) FRAMING PLAN +24.0M FFL (CCR BUILDING) | I | 04-Apr-19 |  |  | Y | First Submission Due
463 | PE-DC-435-612-C020 | P.H. BLDG.-DES. OF FLOOR BEAMS @ EL +3.5M (AB BAY) CCR | A | 28-Mar-19 | 2 | 1 | Y | Re Submission Pending
464 | PE-DG-435-622-C007 | TRANSFORMER YARD - GENERATOR TRANSFORMER R.C. DETAILS | I | 21-Feb-19 |  | 0 | Y | Pending for Approval
465 | PE-DC-435-646-C002 | CHEMICAL LAB BUILDING - DESIGN OF FOUNDATIONS, COLUMNS, PLINTH BEAMS | A | 18-Jul-19 | 2 | 1 | Y | Re Submission Pending
466 | PE-DG-435-675-C014 | PIPE RACK PR-7 - STRUCTURAL STEEL DETAILS | I | 09-Jan-20 |  |  | Y | First Submission Due
467 | PE-DG-435-622-C008 | TRANSFORMER YARD - UAT CONCRETE OUTLINE DETAILS | I | 28-Feb-19 |  |  | Y | First Submission Due
468 | PE-DC-435-612-C021 | P.H. BLDG.-DES. OF FLOOR BEAMS @ EL +8.5M (AB BAY) (UNIT-1 & 2) | A | 20-Dec-18 |  | 0 | Y | Pending for Approval
469 | PE-DG-435-675-C005 | PIPE RACK PR-3 - FOUNDATION LAYOUT & DETAILS | I | 17-Oct-19 |  |  | Y | First Submission Due
470 | PE-DG-435-653-C014 | CW PH - FOUNDATION LAYOUT & RC DETAILS | I | 21-Feb-19 | 2 | 0 | Y | Re Submission Pending
471 | PE-DC-435-612-C003 | PH BLDG. - 3D ANALYSIS | A | 20-Sep-18 | 2 | 2 | Y | Re Submission Pending
472 | PE-DC-435-612-C025 | PH BLDG.-DESIGN OF BUS DUCT & CABLE RACK AT AXIS A (UNIT-1 & 2 & CCR) | A | 10-Oct-19 |  |  | Y | First Submission Due
473 | PE-DG-435-612-C029 | PH BLDG. - (BC-BAY) FRAMING PLAN 8.5M FFL (CCR BUILDING) | I | 25-Apr-19 |  |  | Y | First Submission Due
474 | PE-DG-435-675-C003 | PIPE RACK PR-2 - FOUNDATION LAYOUT & DETAILS | I | 03-Oct-19 |  |  | Y | First Submission Due
475 | PE-DC-435-646-C003 | CHEMICAL LAB BUILDING - DESIGN OF SUPERSTRUCTURE | A | 01-Aug-19 | 2 | 1 | Y | Re Submission Pending
476 | PE-DC-435-675-C014 | PIPE RACK PR7 - DESIGN OF SUPERSTRUCTURE | A | 09-Jan-20 |  |  | Y | First Submission Due
477 | PE-DG-435-640-C009 | SERVICE BLDG. - EAST ELEVATION | A | 27-Sep-18 |  |  | Y | First Submission Due
478 | PE-DG-435-612-C013 | PH BLDG. - FRAMING ARRGT. FOR AUXILIARY STRUCTURES IN AB BAY (UNIT#1 & UNIT#2) | I | 20-Jun-19 |  |  | Y | First Submission Due
479 | PE-DG-435-640-C010 | SERVICE BLDG. SECTION 2-2 | A | 27-Sep-18 |  |  | Y | First Submission Due
480 | PE-DG-435-612-C031 | PH BLDG. - (BC-BAY-TG) FRAMING PLAN AT EL+17M FFL (UNIT#1 & UNIT#2) (2-SHEETS) | I | 27-Dec-18 | 2 | 0 | Y | Re Submission Pending
481 | PE-DC-435-612-C016 | P.H. BLDG.-DES. OF AUXILLIARY COLUMNS (Unit-1 & 2) | A | 18-Oct-18 | 2 | 0 | Y | Re Submission Pending
482 | PE-DG-435-653-C005 | CW PH - GA DETAILS OF SUMP (PLANS) | A | 07-Feb-19 | 2 | 2 | Y | Re Submission Pending
483 | PE-DG-435-611-C016 | PH BLDG.(BC BAY-TG)-GA & R.C. DTLS OF FLOOR AT EL +8.5M (UNIT#1 & UNIT#2) (2-SHEETS) | I | 15-Aug-19 |  |  | Y | First Submission Due
484 | PE-DG-435-645-C002 | WORK SHOP BLDG. - LAYOUT AND R.C. DTLS OF FDN | I | 15-Aug-19 | 2 | 1 | Y | Re Submission Pending
485 | PE-DG-435-611-C055 | PH BLDG.(BC BAY-TG) - ARCH PLAN AT EL + 37.50M | I | 08-Aug-19 |  |  | Y | First Submission Due
486 | PE-DG-435-640-C012 | SERVICE BLDG. - SOUTH ELEVATION | A | 04-Oct-18 |  |  | Y | First Submission Due
487 | PE-DG-435-653-C012 | CW PH - RC DETAIL AT OPERATING FLOOR | I | 08-Aug-19 |  |  | Y | First Submission Due
488 | PE-DG-435-640-C013 | SERVICE BLDG. - WINDOWS DETAILS | I | 11-Oct-18 |  |  | Y | First Submission Due
489 | PE-DG-435-600-C001 | PH BLDG. - GEN. NOTES & STD. DETAILS FOR CIVIL WORKS | A | 21-Jun-18 | 2 | 0 | Y | Re Submission Pending
490 | PE-DG-435-640-C029 | SERVICE BLDG - GA & RC DETAILS OF BEAMS & SLAB AT ROOF LEVEL-SH2 | I | 31-Jan-19 |  |  | Y | First Submission Due
491 | PE-DC-435-611-C002 | PH BLDG. - DES. OF FDN FOR A TO C ROW COLS. (CCR) | A | 27-Sep-18 | 2 | 1 | Y | Re Submission Pending
492 | PE-DG-435-653-C013 | CW PH - GA & RC SHEET DETAIL OF ROOF | I | 22-Aug-19 |  |  | Y | First Submission Due
493 | PE-DG-435-641-C013 | ADMN BLDG. - TOILET DETAILS | I | 22-Aug-19 |  |  | Y | First Submission Due
494 | PE-DC-435-612-C019 | P.H. BLDG.-DES. OF STAIR CASE | A | 23-May-19 | 1 | 1 | N | Approved
495 | PE-DG-435-641-C014 | ADMN BLDG. - GA & RC DETAIL OF FOUNDATIONS & COLUMNS | I | 28-Nov-19 | 2 | 1 | Y | Re Submission Pending
496 | PE-DC-435-616-C008 | BUNKERSBAY - DES. OF CLADDING RUNNERS | A | 27-Jun-19 |  |  | Y | First Submission Due
497 | PE-DG-435-641-C030 | LAYOUT AND DETAILS OF PARKING SHED | A | 21-Nov-19 |  |  | Y | First Submission Due
498 | PE-DG-435-611-C027 | PH BLDG.-C.W. PIT - G.A. (UNIT#1 & UNIT#2) | I | 11-Apr-19 | 2 | 1 | Y | Re Submission Pending
499 | PE-DG-435-617-C007 | G.A. & R.C. DETAILS OF ID DUCT FOUNDATIONS( ESP TO CHIMNEY)PART 2 | I | 28-Feb-19 | 2 | 1 | Y | Re Submission Pending
500 | PE-DG-435-611-C004 | PH BLDG (AB BAY)- G.A. & RCC DETAILS OF METAL DECK ROOF | I | 18-Jul-19 |  |  | Y | First Submission Due
501 | PE-DC-435-675-C011 | PIPE RACK PR6 - DESIGN OF FOUNDATION | A | 28-Nov-19 |  |  | Y | First Submission Due
502 | PE-DC-435-641-C002 | Admin Building – Design of Columns and Beams | A | 28-Nov-19 | 2 | 1 | Y | Re Submission Pending
503 | PE-DG-435-642-C003 | D.G. SET BLDG. - G.A. AND R.C. DTLS OF COLUMN | I | 06-Jun-19 |  |  | Y | First Submission Due
504 | PE-DG-435-612-C033 | PH BLDG. - (BC-BAY-TG) FRAMING PLAN AT EL+24.0M FFL (UNIT#1 & UNIT#2) (2-SHEETS) | I | 28-Feb-19 | 2 | 0 | Y | Re Submission Pending
505 | PE-DG-435-642-C002 | D.G. SET BLDG. - LAYOUT AND R.C. DTLS OF FDN | I | 23-May-19 |  | 0 | Y | Pending for Approval
506 | PE-DC-435-675-C012 | PIPE RACK PR6 - DESIGN OF SUPERSTRUCTURE | A | 19-Dec-19 |  |  | Y | First Submission Due
507 | PE-DG-435-611-C005 | PH BLDG. -GA & R.C. DTLS OF FLOOR AT EL + 0.0M (SHEET 1 OF 7) | I | 26-Sep-19 |  |  | Y | First Submission Due
508 | PE-DG-435-642-C004 | D.G. SET BLDG. -PLINTH BEAM DETAILS | I | 13-Jun-19 |  |  | Y | First Submission Due
509 | PE-DC-435-651-C002 | CW DUCT - DESIGN OF DUCT | A | 21-Mar-19 | 2 | 2 | Y | Re Submission Pending
510 | PE-DC-435-612-C026 | PH BLDG.-DESIGN OF PURLIN (UNIT-1 & 2 & CCR) | A | 02-Aug-18 | 1 | 2 | N | Approved
511 | PE-DG-435-645-C005 | WORK SHOP BLDG. -TIE BEAM DETAILS | I | 19-Sep-19 |  |  | Y | First Submission Due
512 | PE-DG-435-613-C002 | T.G. FDN -G.A. OF SUB-STRUCTURE RAFT SECTION | A | 23-Aug-18 | 2 | 2 | Y | Re Submission Pending
513 | PE-DC-435-653-C001 | CW PUMP HOUSE-DESIGN OF FEED POOL | A | 10-Jan-19 | 1 | 3 | N | Approved
514 | PE-DG-435-612-C032 | PH BLDG. - (BC-BAY) FRAMING PLAN AT EL +17M FFL (CCR BUIILDING) | I | 09-May-19 | 2 | 2 | Y | Re Submission Pending
515 | PE-DG-435-611-C014 | PH BLDG. (AB BAY-CR)- GA & R.C. DTLS OF FL @ EL 17.0M | I | 04-Jul-19 |  |  | Y | First Submission Due
516 | PE-DC-435-612-C027 | P.H. BLDG.-DES. OF A, B and C ROW COLUMN & BASE PLATE (CCR BUILDING) | A | 25-Apr-19 | 2 | 2 | Y | Re Submission Pending
517 | PE-DG-435-647-C002 | COMP BLDG - ARCHITECTURAL ELEVATIONS | A | 17-Oct-19 |  |  | Y | First Submission Due
518 | PE-DG-435-618-C004 | P.A. FAN - R.C. DETAILS OF FOUNDATION | I | 22-Nov-18 | 4 | 2 | N | Approved
519 | PE-DC-435-665-C001 | WEIGH BRIDGE : DESIGN OF PIT | A | 26-Dec-19 |  |  | Y | First Submission Due
520 | PE-DG-435-648-C010 | AIR WASHER BLDG. - STAIRCASE DETAILS | I | 10-Oct-19 |  |  | Y | First Submission Due
521 | PE-DG-435-611-C006 | PH BLDG. -GA & R.C. DTLS OF FL @ EL + 0.0M (SHEET 2 OF 7) | I | 03-Oct-19 |  |  | Y | First Submission Due
522 | PE-DC-435-619-C002 | ESP CONTROL BLDG.-DESIGN OF FOUNDATIONS & COLUMNS | A | 28-Mar-19 | 2 | 1 | Y | Re Submission Pending
523 | PE-DG-435-640-C014 | SERVICE BLDG. - DOOR & PARTITIONS DETAILS | I | 18-Oct-18 |  |  | Y | First Submission Due
524 | PE-DG-435-621-C001 | AUXILIARY BOILER : GA & RC DETAILS | A | 22-Nov-18 | 2 | 1 | Y | Re Submission Pending
525 | PE-DG-435-622-C003 | TRANSFORMER YARD - LAYOUT SH-3(UNIT 1) | I | 25-Apr-19 |  |  | Y | First Submission Due
526 | PE-DC-435-619-C003 | ESP CONTROL BLDG.-DESIGN OF SUPERSTRUCTURE | A | 09-May-19 |  |  | Y | First Submission Due
527 | PE-DG-435-611-C034 | PH BLDG.- ELEVATION OF GABLE END (UNIT#1 & UNIT#2) | A | 06-Dec-18 | 3 | 0 | Y | Re Submission Pending
528 | PE-DG-435-622-C014 | TRANSFORMER YARD - OIL WATER PIT CONCRETE OUTLINE AND RC DETAILS | I | 02-May-19 |  |  | Y | First Submission Due
529 | PE-DC-435-614-C002 | DESIGN OF TDFBFP DECK (STATIC & DYNAMIC) | A | 28-Mar-19 | 3 | 1 | Y | Pending for Approval
530 | PE-DC-435-619-C004 | ESP CONT ROOM- DESIGN OF SEC BEAMS AT MISC FLOORS | A | 18-Jul-19 |  |  | Y | First Submission Due
531 | PE-DG-435-611-C007 | PH BLDG. -GA & R.C. DTLS OF FL @ EL + 0.0M (SHEET 3 OF 7) | I | 10-Oct-19 |  |  | Y | First Submission Due
532 | PE-DG-435-640-C031 | SERVICE BLDG. -DETAILS OF STAIRCASE SH 1 | I | 03-Jan-19 |  |  | Y | First Submission Due
533 | PE-DG-435-641-C015 | ADMN BLDG. - GA & RC DETAIL OF GRADE BEAM @ EL(-)3.50M & PLINTH BEAM @ EL(-)0.50M SH1 | I | 19-Dec-19 | 2 | 1 | Y | Re Submission Pending
534 | PE-DC-435-641-C005 | GATE HOUSE - DESIGN OF FOUNDATIONS | A | 14-Mar-19 |  |  | Y | First Submission Due
535 | PE-DG-435-613-C006 | T.G FDN.-DETAILS OF SECTION OF DECK | I | 04-Oct-18 | 3 | 0 | Y | Re Submission Pending
536 | PE-DG-435-611-C024 | PH BLDG.(BC BAY-CR) - GA & R.C. DTLS OF FLOOR AT EL + 32.50M | I | 03-Oct-19 |  |  | Y | First Submission Due
537 | PE-DG-435-611-C025 | PH BUILDING GA & R.C DTLS OF INTERMEDIATE COLS. FDN (UNIT#2) | I | 25-Jul-19 | 2 | 0 | Y | Re Submission Pending
538 | PE-DC-435-634-C008 | DYKE AREA : DESIGN OF DYKE WALL & PEDESTALS | A | 12-Sep-19 | 3 | 1 | Y | Pending for Approval
539 | PE-DG-435-620-C001 | General arrangement - Chimney | A | 04-Oct-18 | 1 | 2 | N | Approved
540 | PE-DC-435-639-C002 | CPU REGENERATION BLDG- DESIGNOF FOUNDATIONS | A | 16-Jan-20 |  |  | Y | First Submission Due
541 | PE-DG-435-642-C005 | D.G. SET BLDG. -TIE BEAM DETAILS | I | 27-Jun-19 |  |  | Y | First Submission Due
542 | PE-DG-435-611-C026 | PH BUILDING GA & RC DTLS OF COLUMN. FDN (CCR BUILDING) | I | 08-Aug-19 | 2 | 1 | Y | Re Submission Pending
543 | PE-DG-435-620-C019 | Liner general arrangement | I | 06-Dec-18 | 2 | 3 | Y | Re Submission Pending
544 | PE-DC-435-611-C003 | PH BLDG. - DES. OF R.C SLABS FOR FLOORS | A | 04-Jul-19 |  |  | Y | First Submission Due
545 | PE-DG-435-648-C001 | AIR WASHER BLDG-ARCHITECTURAL PLANS & ELEVATIONS | A | 12-Sep-19 | 1 | 1 | N | Approved
546 | PE-DC-435-653-C004 | CW PUMP HOUSE - DESIGN OF SUPERSTRUCTURE | A | 07-Mar-19 | 2 | 1 | Y | Re Submission Pending
547 | PE-DC-435-618-C001 | ID FAN-DESIGN OF FOUNDATION SUB-STRUCTURE | A | 03-Jan-19 | 2 | 1 | Y | Re Submission Pending
548 | PE-DC-435-612-C008 | P.H. BLDG.-DES. OF A ROW COLUMN & BASE PLATE | A | 13-Sep-18 | 2 | 1 | Y | Re Submission Pending
549 | PE-DG-435-648-C011 | AIR WASHER BUILDING -MISC. EQUIIPMENT FOUNDATIONS AT EL 0.000 | I | 17-Oct-19 |  |  | Y | First Submission Due
550 | PE-DC-435-613-C004 | MISALIGNMENT CALCULATIONS OF TG DECK | A | 18-Oct-18 | 3 | 0 | Y | Re Submission Pending
551 | PE-DC-435-612-C029 | PH BLDG.-DESIGN OF BC/CD/DE BAY SECONDARY BEAMS @ 32.5M & 33.4M EL (UNIT-1 & 2) | A | 07-Feb-19 |  |  | Y | First Submission Due
552 | PE-DG-435-650-C005 | FIRE STATION - LINTEL BEAM LAYOUT & DEATAILS | I | 02-Jan-20 | 1 | 3 | N | Approved
553 | PE-DG-435-613-C005 | T.G FDN.-GA OF DECK: BOTTOM PLAN | I | 20-Sep-18 | 3 | 0 | Y | Re Submission Pending
554 | PE-DG-435-653-C002 | CW PH - ARCITECTURAL PLANS | A | 07-Mar-19 | 4 | 0 | N | Approved
555 | PE-DG-435-647-C005 | COMP BLDG -GA & RC DETAILS OF FOUNDATION & PEDESTALS | I | 15-Aug-19 |  |  | Y | First Submission Due
556 | PE-DG-435-653-C017 | CW PH - GANTRY GIRDER | I | 25-Apr-19 | 2 | 1 | Y | Re Submission Pending
557 | PE-DG-435-613-C020 | T.G FDN.-DETAILS OF TG PLATFORMS/SUBSTRUCTURE BEAMS (SHEETS 1 & 2) | I | 25-Oct-18 |  |  | Y | First Submission Due
558 | PE-DG-435-612-C027 | PH BLDG. -(BC-BAY) FRAMING PLAN +5.1 M FFL | I | 03-Jan-19 |  |  | Y | First Submission Due
559 | PE-DC-435-612-C002 | PH BLDG. - LOAD CALCULATION FOR ANALYSIS - CCR | A | 27-Sep-18 | 2 | 3 | Y | Re Submission Pending
560 | PE-DG-435-611-C052 | PH BUILDING ARCHITECTURAL PLAN AT EL.(+)37.5 | I | 11-Jul-19 | 3 | 0 | Y | Re Submission Pending
561 | PE-DG-435-612-C012 | PH BLDG- DETAILS OF GABLE END COLUMNS (UNIT#1 & UNIT#2) (2-SHEETS) | I | 15-Nov-18 | 2 | 0 | Y | Re Submission Pending
562 | PE-DG-435-612-C107 | PH BLDG - BC BAY GANTRY GIRDER | I | 20-Dec-18 | 2 | 1 | Y | Re Submission Pending
563 | PE-DG-435-665-C001 | WEIGH BRIDGE CONTROL ROOM-GA & RC DETAIL | I | 05-Dec-19 |  |  | Y | First Submission Due
564 | PE-DG-435-647-C003 | COMP BLDG -GA & RC DETAILS OF COL. FOUNDATION& COLUMNS | I | 25-Jul-19 |  |  | Y | First Submission Due
565 | PE-DC-435-645-C001 | WORK SHOP BLDG. - LOAD CALCULATION | A | 15-Aug-19 | 2 | 1 | Y | Re Submission Pending
566 | PE-DG-435-641-C026 | GATE HOUSE - GA & RC OF FOUNDATIONS | I | 14-Mar-19 |  |  | Y | First Submission Due
567 | PE-DG-435-619-C004 | ESP CONTROL BLDG.-ARCHITECTURAL SECTIONS | A | 13-Jun-19 | 2 | 2 | Y | Re Submission Pending
568 | PE-DG-435-641-C018 | ADMN BLDG. - LAYOUT & RC DETAILS OF BEAM & SLAB AT EL 4.5 M (FIRST FLOOR) | I | 06-Feb-20 |  |  | Y | First Submission Due
569 | PE-DG-435-641-C019 | ADMN BLDG. - LAYOUT & RC DETAILS OF BEAM & SLAB AT EL 8.50 M (ROOF FLOOR) | I | 20-Feb-20 |  |  | Y | Submission Not Due
570 | PE-DG-435-619-C005 | ESP CONTROL ROOM LAYOUT, RC DETAILS OF FOUNDATION | I | 28-Mar-19 | 2 | 1 | Y | Re Submission Pending
571 | PE-DC-435-650-C004 | FIRE STATION - DRILL TOWER DESIGN | A | 02-Jan-20 |  |  | Y | First Submission Due
572 | PE-DG-435-611-C013 | PH BLDG. (AB BAY-TG)- GA & R.C. DTLS OF FLOOR AT EL 17.0M (UNIT#1 & UNIT#2) (2-SHEETS) | I | 18-Jul-19 |  |  | Y | First Submission Due
573 | PE-DG-435-622-C009 | TRANSFORMER YARD - UAT R.C. DETAILS | I | 14-Mar-19 |  |  | Y | First Submission Due
574 | PE-DC-435-651-C001 | STATOR LIFT & JACK PAD(DESIGN OF FOUNDATION) | A | 21-Mar-19 | 1 | 0 | N | Approved
575 | PE-DG-435-613-C017 | T.G DECK-REINFORCEMENT DETAILS OF LONGITUDINAL BEAM-10(SHEETS 1 TO 6) | I | 25-Oct-18 |  |  | Y | First Submission Due
576 | PE-DG-435-622-C010 | TRANSFORMER YARD - UT CONCRETE OUTLINE DETAILS | I | 21-Mar-19 |  |  | Y | First Submission Due
577 | PE-DG-435-611-C035 | PH BUILDING ARCHITECTURAL PLAN AT EL.(±)0.00M(FFL) (UNIT#1) (SHEET 1 OF 3) | I | 10-Jan-19 | 2 | 1 | Y | Re Submission Pending
578 | PE-DG-435-634-C006 | FO Dyke area-GA & rc details of tanker unloading platform | A | 22-Aug-19 | 3 | 0 | Y | Re Submission Pending
579 | PE-DG-435-611-C036 | PH BUILDING ARCHITECTURAL PLAN AT EL.(±)0.00M(FFL) (CCR BUILDING) (SHEET 2 OF 3) | I | 24-Jan-19 | 3 | 1 | Y | Re Submission Pending
580 | PE-DG-435-613-C015 | T.G DECK-REINFORCEMENT DETAILS OF LONGITUDINAL BEAM-8(SHEETS 1 TO 6) | I | 18-Oct-18 |  | 0 | Y | Pending for Approval
581 | PE-DG-435-620-C025 | Chimney Liner Details- Can type E | I | 10-Jan-19 | 2 | 3 | Y | Re Submission Pending
582 | PE-DG-435-650-C002 | FIRE STATION - ARCH. ELEVATION & SECTION. | A | 19-Mar-20 | 1 | 2 | N | Approved
583 | PE-DG-435-615-C001 | BOWL MILL FOUNDATION-GA & CONCRETE OUTLINE DETAILS | A | 11-Oct-18 | 2 | 5 | Y | Re Submission Pending
584 | PE-DG-435-674-C005 | SEPTIC TANK,UPFLOW FILTER AND CHLORINATION CHAMBER(UP TO 15 USERS) - GA & MASONARY DETAILS | I | 07-May-20 |  |  | Y | Submission Not Due
585 | PE-DG-435-613-C016 | T.G DECK-REINFORCEMENT DETAILS OF LONGITUDINAL BEAM-9(SHEETS 1 TO 6) | I | 18-Oct-18 |  |  | Y | First Submission Due
586 | PE-DC-435-611-C001 | PH BLDG. - DES. OF FDN FOR A TO C ROW COLS. (UNIT-1 & 2) | A | 30-Aug-18 | 2 | 1 | Y | Re Submission Pending
587 | PE-DG-435-616-C017 | BUNKER`S BAY - ARCH. ELEVATIONS (SH-2) | A | 20-Jun-19 |  |  | Y | First Submission Due
588 | PE-DG-435-620-C005 | Details of Shell openings | I | 25-Oct-18 | 2 | 0 | Y | Re Submission Pending
589 | PE-DG-435-612-C006 | PH BUILDING DETAILS OF ROOF TRUSS (UNIT#1 & UNIT#2) (2-SHEETS) | I | 06-Sep-18 | 2 | 2 | Y | Re Submission Pending
590 | PE-DG-435-616-C005 | BUNKER`S BAY - R.C.C. DTLS OF TRIPPER FLOOR | I | 13-Jun-19 | 2 | 0 | Y | Re Submission Pending
591 | PE-DG-435-620-C006 | Details of Extra Reinforcement around openings | I | 01-Nov-18 | 2 | 1 | Y | Re Submission Pending
592 | PE-DG-435-612-C022 | PH BLDG. -(AB BAY-TG) FRAMING PLAN AT EL 8.5M FFL (UNIT#1 & UNIT#2) (3-SHEETS) | I | 20-Dec-18 | 3 | 0 | Y | Re Submission Pending
593 | PE-DG-435-616-C013 | BUNKER`S BAY - CLADDING AND MIS.DETAILS | I | 27-Jun-19 | 3 | 0 | Y | Re Submission Pending
594 | PE-DG-435-614-C001 | GA OF MDBFP DECK | A | 20-Dec-18 | 2 | 1 | Y | Re Submission Pending
595 | PE-DG-435-616-C014 | BUNKER BAY - G.A. OF BUNKERS & SUPPORTING DETAILS | A | 14-Feb-19 | 3 | 6 | Y | Re Submission Pending
596 | PE-DG-435-622-C001 | TRANSFORMER YARD - LAYOUT SH-1(UNIT 1) | A | 28-Feb-19 |  |  | Y | First Submission Due
597 | PE-DG-435-640-C028 | SERVICE BLDG - GA & RC DETAILS OF BEAMS & SLAB AT ROOF LEVEL -SH1 | I | 24-Jan-19 |  |  | Y | First Submission Due
598 | PE-DG-435-610-C004 | CANTEEN BLDG WITH DORMITORY (NEAR ADMIN) - ARCHITECTURAL ELEVATIONS & SECTIONS | I | 26-Dec-19 | 2 | 0 | Y | Re Submission Pending
599 | PE-DG-435-619-C006 | GA & RC DETAILS OF COLUMNS | I | 01-Aug-19 | 2 | 1 | Y | Re Submission Pending
600 | PE-DC-435-617-C004 | ID SYSTEM FOUNDATIONS(DESIGN OF ID SYS FDN BETWEEN ESP & CHIMNEY) | A | 14-Feb-19 | 2 | 2 | Y | Re Submission Pending
601 | PE-DG-435-622-C002 | TRANSFORMER YARD - LAYOUT SH-2(UNIT 1) | A | 28-Mar-19 |  |  | Y | First Submission Due
602 | PE-DG-435-619-C007 | GA & RC DETAILS OF GRADE BEAMS,PLINTH BEAMS & LIFT PIT | I | 01-Aug-19 | 3 | 1 | Y | Re Submission Pending
603 | PE-DG-435-610-C005 | CANTEEN BLDG - DOOR & WINDOW DETAILS (sht1 & 2) | I | 09-Jan-20 |  |  | Y | First Submission Due
604 | PE-DG-435-641-C012 | ADMN BLDG. - DOOR & PARTITIONS DETAILS | I | 22-Aug-19 |  |  | Y | First Submission Due
605 | PE-DG-435-612-C009 | PH BLDG.-DETAILS OF INTERMEDIATE COLUMNS (UNIT#1 & UNIT#2) (2-SHEETS) | I | 18-Oct-18 | 4 | 1 | N | Approved
606 | PE-DG-435-608-C009 | PERMT STORE - DETAILS OF CLADDING RUNNER | I | 13-Sep-18 | 2 | 0 | Y | Re Submission Pending
607 | PE-DG-435-612-C010 | PH BLDG-CLADDING FRAMING ELEVATION ON AXIS A (UNIT#1 & UNIT#2) (2-SHEETS) | I | 28-Mar-19 |  |  | Y | First Submission Due
608 | PE-DG-435-620-C007 | Internal platform details SH1 | I | 08-Nov-18 | 2 | 2 | Y | Re Submission Pending
609 | PE-DG-435-620-C008 | Internal platform details SH2 | I | 08-Nov-18 | 2 | 2 | Y | Re Submission Pending
610 | PE-DG-435-634-C004 | GA & RC DETAILS OF OIL WATER SEPERATOR | I | 24-Oct-19 | 3 | 1 | Y | Pending for Approval
611 | PE-DG-435-611-C001 | POWER HOUSE BUILDING -GA AND RC OF COLUMN FOUNDATION ON A ROW TO C ROW (UNIT#1) SH-1 and 2 | A | 30-Aug-18 | 2 | 1 | Y | Re Submission Pending
612 | PE-DC-435-603-C001 | DESIGN OF DRAINS | A | 11-Oct-18 | 2 | 2 | Y | Re Submission Pending
613 | PE-DC-435-603-C002 | DESIGN OF ROAD | A | 13-Sep-18 | 2 | 1 | Y | Re Submission Pending
614 | PE-DG-435-650-C001 | FIRE STATION -GEN ARCH. PLAN ELEVATION & SECTION. | A | 13-Feb-20 | 1 | 2 | N | Approved
615 | PE-DC-435-638-C002 | COND TRF PH -LOAD CALCULATION | A | 31-Oct-19 | 2 | 1 | Y | Re Submission Pending
616 | PE-DC-435-638-C003 | COND TRF PH -DESIGNOF FOUNDATIONS | A | 31-Oct-19 | 2 | 1 | Y | Re Submission Pending
617 | PE-DG-435-611-C021 | PH BLDG.(BC BAY-TG)- GA & R.C. DTLS OF FLOOR AT EL+ 24M (UNIT#1 & UNIT#2) (2-SHEETS) | I | 10-Oct-19 |  |  | Y | First Submission Due
618 | PE-DC-435-611-C006 | PH BLDG. - DESIGN OF AB BAY ROOF | A | 18-Jul-19 |  |  | Y | First Submission Due
619 | PE-DG-435-634-C005 | FO Dyke area-ga & rc Details of foundations | A | 15-Aug-19 | 3 | 0 | Y | Re Submission Pending
620 | PE-DG-435-611-C039 | PH BLDG. (ABC BAY)- ARCH PLAN AT EL +3.5M (CCR BUILDING) | I | 21-Feb-19 | 2 | 1 | Y | Re Submission Pending
621 | PE-DC-435-602-C001 | GEOTECHNICAL INVESTIGATION REPORT | A | 19-Apr-18 | 1 | 1 | N | Approved
622 | PE-DC-435-612-C001 | PH BLDG. - LOAD CALCULATION FOR ANALYSIS | A | 13-Sep-18 | 2 | 2 | Y | Re Submission Pending
623 | PE-DC-435-611-C005 | PH BLDG.- DESIGN OF CEP PIT | A | 08-Nov-18 | 2 | 2 | Y | Re Submission Pending
624 | PE-DC-435-647-C001 | COMPRESSOR BUILDING - LOAD CALCULATIONS, ANALYSIS AND DESIGN OF FOUNDATION | A | 25-Jul-19 |  |  | Y | First Submission Due
625 | PE-DC-435-647-C002 | COMPRESSOR BUILDING - DESIGN OF COLUMNS AND BEAMS | A | 25-Jul-19 |  |  | Y | First Submission Due
626 | PE-DC-435-612-C023 | P.H. BLDG.-DES. OF FLOOR BEAMS @ EL +17.0M (AB BAY) (UNIT-1 & 2) | A | 29-Nov-18 | 2 | 1 | Y | Re Submission Pending
627 | PE-DC-435-612-C024 | PH BLDG.-DESIGN OF PIPE & CABLE RACK AT AXIS C (UNIT-1 & 2 & CCR) | A | 17-Oct-19 |  |  | Y | First Submission Due
628 | PE-DG-435-647-C004 | COMP BLDG -G.A & R.C. DETAILS OF PLINTH BEAMS & LINTEL BEAMS | I | 01-Aug-19 |  |  | Y | First Submission Due
629 | PE-DG-435-612-C040 | PH BLDG. -PIPE AND CABLE SUPPORTING STRUCTURE ALONG AXIS-C | I | 17-Oct-19 |  |  | Y | First Submission Due
630 | PE-DG-435-613-C012 | T.G DECK-REINFORCEMENT DETAILS OF CROSS-BEAM-5(SHEETS 1 & 2) | I | 11-Oct-18 | 3 | 0 | Y | Re Submission Pending
631 | PE-DG-435-665-C002 | WEIGH BRIDGE -GA & RC DETAIL OF PIT | I | 26-Dec-19 |  |  | Y | First Submission Due
632 | PE-DG-435-641-C038 | DISPENSARY –GA & RC DETAILS OF ROOF BEAM & SLAB | A | 11-Jul-19 | 2 | 2 | Y | Re Submission Pending
633 | PE-DG-435-641-C040 | DISPENSARY –GA & RC DETAILS OF STAIR | A | 25-Jul-19 | 2 | 1 | Y | Re Submission Pending
634 | PE-DC-435-611-C004 | P.H. BLDG.-DESIGN OF C.W. PIT | A | 11-Apr-19 |  |  | Y | First Submission Due
635 | PE-DG-435-617-C013 | BOILER AREA - GA & RC DETAILS OF GRADE SLAB / PAVING | A | 05-Dec-19 |  |  | Y | First Submission Due
636 | PE-DG-435-611-C053 | PH BLDG.- ARCH PLAN AT EL+17M (INDICATING FLOORING PATTERN) (UNIT#1, UNIT#2 & CCR BUILDING) (3-SHEETS) | I | 18-Jul-19 |  |  | Y | First Submission Due
637 | PE-DG-435-619-C003 | ESP CONTROL BLDG.-ARCHITECTURAL DETAILS-SH-3 (ELEVATIONS) | A | 13-Jun-19 | 2 | 2 | Y | Re Submission Pending
638 | PE-DG-435-641-C029 | GATE HOUSE - DETAILS OF GATE STRUCTURE | I | 18-Apr-19 |  |  | Y | First Submission Due
639 | PE-DC-435-612-C022 | P.H. BLDG.-DES. OF FLOOR BEAMS +12.0 M (AB BAY) CCR | A | 25-Apr-19 | 2 | 1 | Y | Re Submission Pending
640 | PE-DG-435-610-C006 | CANTEEN BLDG(NEAR FIRE STATION) - LAYOUT & RC DETAILS OF COL,FOUNDATIONS | I | 12-Sep-19 | 2 | 1 | Y | Re Submission Pending
641 | PE-DG-435-611-C057 | PH BLDG.(CDEFG BAY-CR) - ARCH PLAN AT EL + 27.0M | I | 29-Aug-19 |  |  | Y | First Submission Due
642 | PE-DG-435-612-C011 | PH BLDG-CLADDING FRAMING ELEVATION ON AXIS C (UNIT#1 & UNIT#2) (2-SHEETS) | I | 25-Apr-19 |  |  | Y | First Submission Due
643 | PE-DC-435-618-C004 | SEAL AIR FAN -DESIGN OF FAN FDN | A | 03-Jan-19 | 2 | 1 | Y | Re Submission Pending
644 | PE-DG-435-616-C012 | BUNKER BAY - FRAMING PLAN OF BUNKER ROOF. | A | 14-Feb-19 | 3 | 0 | Y | Re Submission Pending
645 | PE-DG-435-617-C019 | INTERFPLANT CABLE TRENCHES-GA & RC DETAILS | A | 02-Jun-20 |  |  | Y | Submission Not Due
646 | PE-DG-435-617-C020 | GA & RC DETAILS OF MRS TRENCH | A | 15-Jul-20 |  |  | Y | Submission Not Due
647 | PE-DG-435-621-C006 | AUXILIARY BOILER-FD FAN & BFP FOUNDATION-GA DETAILS | A | 06-May-19 | 2 | 2 | Y | Re Submission Pending
648 | PE-DG-435-621-C007 | AUXILIARY BOILER-FD FAN & BFP FOUNDATION-RC DETAILS | A | 16-May-19 | 2 | 2 | Y | Re Submission Pending
649 | PE-DG-435-621-C008 | AUXILIARY BOILER-STACK FOUNDATION-GA DETAILS | A | 20-May-19 | 2 | 1 | Y | Pending for Approval
650 | PE-DG-435-621-C009 | AUXILIARY BOILER-STACK FOUNDATION-RC DETAILS | A | 30-May-19 | 3 | 1 | Y | Pending for Approval
651 | PE-DG-435-622-C020SHT1 | TRANSFORMER YARD - SAT -CONCRETE OUTLINE & GA DETAILS | A | 05-Mar-19 |  |  | Y | First Submission Due
652 | PE-DG-435-622-C020 SHT2 | TRANSFORMER YARD - SAT -FBWALL & RC DETAILS | A | 15-Mar-19 |  |  | Y | First Submission Due
653 | PE-DG-435-622-C021 | TRANSFORMER YARD - STANDBY MAINTENANCE TRF -CONCRETE OUTLINE & GA DETAILS | A | 25-Mar-19 |  |  | Y | First Submission Due
654 | PE-DG-435-622-C022 | TRANSFORMER YARD - STANDBY MAINTENANCE TRF -CONCRETE OUTLINE & RC DETAILS | A | 05-May-19 |  |  | Y | First Submission Due
655 | PE-DG-435-622-C023 | TRANSFORMER YARD - GA & RC DETAILS OFAUX TRANSFORMERS FOR AHP,CHP,SWIPH | A | 15-May-19 |  |  | Y | First Submission Due
656 | PE-DG-435-622-C024 | TRANSFORMER YARD - GA & RC DETAILS OF TRF OIL FILTER PLANT SHED | A | 25-May-19 |  |  | Y | First Submission Due
657 | PE-DG-435-627-C001 | H2,CO2 GAS CYLINDER SHED-GA,RC & SUPERSTRUCTURE DETAILS OF SHED | A | 15-Nov-20 |  |  | Y | Submission Not Due
658 | PE-DG-435-640-C034 | BANK EXTENSION COUNTER-GA & RC DETAILS OF FDNS ,COLUMNS,PLINTH BEAM | A | 25-Sep-20 |  |  | Y | Submission Not Due
659 | PE-DG-435-640-C035 | BANK EXTENSION COUNTER-GA & RC DETAILS OF TIE,ROOF BEAMS & ROOF SLAB | A | 25-Oct-20 |  |  | Y | Submission Not Due
660 | PE-DG-435-640-C036 | BANK EXTENSION COUNTER-GA & RC DETAILS OF GROUND FLOOR | A | 25-Nov-20 |  |  | Y | Submission Not Due
661 | PE-DG-435-667-C001 | SWIPH - EXCAVATION DETAILS | A | 21-Dec-18 |  |  | Y | First Submission Due
662 | PE-DG-435-667-C002 | SWIPH - ARCITECTURAL PLANS | A | 21-Mar-19 |  |  | Y | First Submission Due
663 | PE-DG-435-667-C003 | SWIPH - ARCITECTURAL ELEVATIONS | A | 25-Mar-19 |  |  | Y | First Submission Due
664 | PE-DG-435-667-C004 | SWIPH- ARCHITECTURAL SECTIONS | A | 30-Mar-19 |  |  | Y | First Submission Due
665 | PE-DG-435-667-C005 | SWIPH - GA DETAILS OF SUMP (PLANS) | A | 10-May-19 |  |  | Y | First Submission Due
666 | PE-DG-435-667-C006 | SWIPH - GA DETAILS OF SUMP (SECTION) | A | 15-May-19 |  |  | Y | First Submission Due
667 | PE-DG-435-667-C007 | SWIPH - RC DETAIL OF SUMP SH-1 | A | 21-May-19 |  |  | Y | First Submission Due
668 | PE-DG-435-667-C008 | SWIPH - RC DETAILS OF SUMP SH-2 | A | 30-May-19 |  |  | Y | First Submission Due
669 | PE-DG-435-667-C009 | SWIPH - GA DETAIL AT MEZANINE FLOOR | A | 29-Sep-19 |  |  | Y | First Submission Due
670 | PE-DG-435-667-C010 | SWIPH - RC DETAIL AT MEZANINE FLOOR | A | 29-Sep-19 |  |  | Y | First Submission Due
671 | PE-DG-435-667-C011 | SWIPH- GA DETAIL AT OPERATING FLOOR | A | 29-Nov-19 |  |  | Y | First Submission Due
672 | PE-DG-435-667-C012 | SWIPH - RC DETAIL AT OPERATING FLOOR | A | 29-Nov-19 |  |  | Y | First Submission Due
673 | PE-DG-435-667-C013 | SWIPH - GA & RC SHEET DETAIL OF ROOF | A | 29-Dec-19 |  |  | Y | First Submission Due
674 | PE-DG-435-667-C014 | SWIPH - FOUNDATION LAYOUT & RC DETAILS | A | 29-Dec-19 |  |  | Y | First Submission Due
675 | PE-DG-435-667-C015 | SWIPH - GA & RC DETAILS OF GROUND FLOOR | A | 04-May-20 |  |  | Y | Submission Not Due
676 | PE-DG-435-667-C016 | SWIPH - SUPERSTRUCTURE FRAMING ELEVATION | A | 25-Jan-20 |  |  | Y | First Submission Due
677 | PE-DG-435-667-C017 | SWIPH - GANTRY GIRDER | A | 16-Jan-20 |  |  | Y | First Submission Due
678 | PE-DG-435-667-C018 | SWIPH-GA DETAILS OF FOREBAY | A | 16-Mar-20 |  | 0 | Y | Pending for Approval
679 | PE-DG-435-667-C019 | SWIPH-RC DETAILS OF FOREBAY | A | 26-Mar-20 |  | 0 | Y | Pending for Approval
680 | PE-DG-435-667-C020 | ELEC ANN - GA & RC DETAILS OF SUBSTRUCTURE | A | 16-May-20 |  |  | Y | Submission Not Due
681 | PE-DG-435-667-C021 | ELEC ANN - GA & RC DETAILS OF SUPERSTRUCTURE | A | 26-May-20 |  |  | Y | Submission Not Due
682 | PE-DG-435-667-C022 | BRINE WATERTANKS- GA & RC DETAILS OF BRINE TANKS | A | 11-Jul-20 |  |  | Y | Submission Not Due
683 | PE-DG-435-667-C023 | ELEC ANN - GA & RC DETAILS OF GROUND FLOOR | A | 12-Aug-20 |  |  | Y | Submission Not Due
684 | PE-DG-435-667-C024 | ELEC ANN - GA & RC DETAILS OF STAIRCASE | A | 13-Sep-20 |  |  | Y | Submission Not Due
685 | PE-DG-435-668-C001 | SWO PH- EXCAVATION DETAILS | A | 15-Jan-19 |  |  | Y | First Submission Due
686 | PE-DG-435-668-C002 | SWO PH- ARCITECTURAL PLANS | A | 15-Mar-20 | 2 | 1 | Y | Re Submission Pending
687 | PE-DG-435-668-C003 | SWO PH - ARCITECTURAL ELEVATIONS | A | 20-Mar-20 | 2 | 1 | Y | Re Submission Pending
688 | PE-DG-435-668-C004 | SWO PH- ARCHITECTURAL SECTIONS | A | 25-Mar-20 | 2 | 1 | Y | Re Submission Pending
689 | PE-DG-435-668-C005 | SWO PH- GA DETAILS OF SUMP (PLANS) | A | 18-May-20 |  |  | Y | Submission Not Due
690 | PE-DG-435-668-C006 | SWO PH - GA DETAILS OF SUMP (SECTION) | A | 18-May-20 |  |  | Y | Submission Not Due
691 | PE-DG-435-668-C007 | SWO PH - RC DETAIL OF SUMP SH-1 | A | 28-May-20 |  |  | Y | Submission Not Due
692 | PE-DG-435-668-C008 | SWO PH- RC DETAILS OF SUMP SH-2 | A | 28-May-20 |  |  | Y | Submission Not Due
693 | PE-DG-435-668-C009 | SWO PH - GA DETAIL AT MEZANINE FLOOR | A | 08-Jun-20 |  |  | Y | Submission Not Due
694 | PE-DG-435-668-C010 | SWO PH- RC DETAIL AT MEZANINE FLOOR | A | 18-Jun-20 |  |  | Y | Submission Not Due
695 | PE-DG-435-668-C011 | SWO PH- GA DETAIL AT OPERATING FLOOR | A | 28-Jun-20 |  |  | Y | Submission Not Due
696 | PE-DG-435-668-C012 | SWO PH - RC DETAIL AT OPERATING FLOOR | A | 05-Jul-20 |  |  | Y | Submission Not Due
697 | PE-DG-435-668-C013 | SWO PH - GA & RC DETAIL OF ROOF BEAM AND SLAB | A | 15-Jul-20 |  |  | Y | Submission Not Due
698 | PE-DG-435-668-C014 | SWO PH- GA AND RC DETAIL OF FOUNDATION COLUMN & PLINTH BEAMS | A | 25-Jul-20 |  |  | Y | Submission Not Due
699 | PE-DG-435-668-C015 | SWO PH- GA & RC DETAILS OF GROUND FLOOR | A | 08-Aug-20 |  |  | Y | Submission Not Due
700 | PE-DG-435-668-C016 | SWO PH- GA AND RC DETAIL OF LINTEL AND TIE BEAMS | A | 28-Aug-20 |  |  | Y | Submission Not Due
701 | PE-DG-435-668-C017 | SWO PH- GANTRY GIRDER AND CORBEL | A | 18-Sep-20 |  |  | Y | Submission Not Due
702 | PE-DG-435-669-C001 | DIESEL BUNK-ARCH PLAN,ELEV,SECTIONS | A | 02-Nov-20 |  |  | Y | Submission Not Due
703 | PE-DG-435-669-C002 | DIESEL BUNK-GA & RC DETAILS OF FDN | A | 22-Nov-20 |  |  | Y | Submission Not Due
704 | PE-DG-435-669-C003 | DIESEL BUNK-MISC FDN DETAILS | A | 28-Nov-20 |  |  | Y | Submission Not Due
705 | PE-DG-435-671-C007 | SERVICE & POTABLE WATER OVERHEAD TANK-SH1 | A | 03-Nov-19 |  |  | Y | First Submission Due
706 | PE-DG-435-671-C008 | SERVICE & POTABLE WATER OVERHEAD TANK-SH2 | A | 13-Nov-19 |  |  | Y | First Submission Due
707 | PE-DG-435-671-C009 | SERVICE & POTABLE WATER OVERHEAD TANK-SH3 | A | 23-Nov-19 |  |  | Y | First Submission Due
708 | PE-DG-435-671-C010 | SERVICE & POTABLE WATER OVERHEAD TANK-SH4 | A | 06-Mar-20 |  |  | Y | Submission Not Due
709 | PE-DG-435-671-C011 | SERVICE & POTABLE WATER OVERHEAD TANK-SH5 | A | 17-Mar-20 |  |  | Y | Submission Not Due
710 | PE-DC-435-617-C007 | INTERRPLANT CABLE TRENCH-DESIGN | A | 02-Jun-20 |  |  | Y | Submission Not Due
711 | PE-DC-435-617-C008 | DESIGN OF MRS TRENCH | A | 15-Jul-20 |  |  | Y | Submission Not Due
712 | PE-DC-435-621-C001 | AUX BOILER-DESIGN OF FOUNDATIONS | A | 14-Mar-19 | 2 | 1 | Y | Re Submission Pending
713 | PE-DC-435-621-C002 | AUX BOILER-DESIGN OF STACK FOUNDATION | A | 24-Mar-19 | 2 | 0 | Y | Re Submission Pending
714 | PE-DC-435-621-C005 | AUX BOILER-DESIGN OF FD & BFP FOUNDATION | A | 28-May-19 | 2 | 2 | Y | Re Submission Pending
715 | PE-DC-435-622-C007 | TRANSFORMER YARD -DESIGN OF STANDBY TRANSFORMER FOUNDATION,FBWALL | A | 05-Mar-19 |  |  | Y | First Submission Due
716 | PE-DC-435-622-C008 | TRANSFORMER YARD -DESIGN OF IPBD & SPBD FOUNDATIONS | A | 25-Mar-19 |  |  | Y | First Submission Due
717 | PE-DC-435-622-C009 | TRANSFORMER YARD -DESIGN OF TRF OIL FILTER PLANT | A | 15-May-19 |  |  | Y | First Submission Due
718 | PE-DC-435-627-C001 | DESIGN OF H2 CO2 SHED FDNS & SUPERSTUCTURE | A | 15-Nov-20 |  |  | Y | Submission Not Due
719 | PE-DC-435-640-C005 | BANK EXTENSION COUNTER-LOAD CALC & DESIGN | A | 25-Sep-20 |  |  | Y | Submission Not Due
720 | PE-DC-435-665-C002 | WEIGHBRIDGE CONTROL ROOM-DESIGN OF FOUNDATIONS & SUPERSTRUCTURE | A | 20-Nov-19 |  |  | Y | First Submission Due
721 | PE-DC-435-665-C003 | DIESEL BUNK-DESIGN OF MISC FOUNDATIONS | A | 02-Nov-20 |  |  | Y | Submission Not Due
722 | PE-DC-435-667-C001 | SWI PUMP HOUSE - LOAD CALCULATION | A | 18-May-20 |  |  | Y | Submission Not Due
723 | PE-DC-435-667-C002 | SWI PUMP HOUSE - DESIGN OF FOUNDATIONS | A | 18-May-20 |  |  | Y | Submission Not Due
724 | PE-DC-435-667-C003 | SWI PUMP HOUSE - DESIGN OF SUPERSTRUCTURE | A | 28-May-20 |  |  | Y | Submission Not Due
725 | PE-DC-435-667-C004 | SWI PUMP HOUSE - DESIGN OF FLOORS | A | 15-Jul-20 |  |  | Y | Submission Not Due
726 | PE-DC-435-667-C005 | SWI PUMP HOUSE - DESIGN OF SUMP | A | 25-Jul-20 |  |  | Y | Submission Not Due
727 | PE-DC-435-667-C006 | SWI ELEC ANNEXE - LOAD CALCULATION | A | 26-May-20 |  |  | Y | Submission Not Due
728 | PE-DC-435-668-C001 | SWO PH - LOAD CALCULATION | A | 28-May-20 |  |  | Y | Submission Not Due
729 | PE-DC-435-668-C002 | SWO PH - DESIGN OF FOUNDATIONS, COLUMN AND PLINTH BEAMS | A | 15-Jul-20 |  |  | Y | Submission Not Due
730 | PE-DC-435-668-C003 | SWO PH - DESIGN OF LINTEL AND TIE BEAMS | A | 25-Jul-20 |  |  | Y | Submission Not Due
731 | PE-DC-435-668-C004 | SWO PH - DESIGN OF FLOORS | A | 18-Jun-20 |  |  | Y | Submission Not Due
732 | PE-DC-435-668-C005 | SWO PH - DESIGN OF SUMP | A | 18-May-20 |  |  | Y | Submission Not Due
733 | PE-DC-435-668-C006 | SWO PH - DESIGN OF ROOF BEAMS AND ROOF SLAB | A | 26-May-20 |  |  | Y | Submission Not Due
734 | PE-DC-435-669-C001 | DIESEL BUNK-DESIGN OF MISC FDNS | A | 02-Nov-20 |  |  | Y | Submission Not Due
1421 | PE-DC-435-602-C002 | GEOTECHNICAL INVESTIGATION REPORT-PART-2 | A | 19-Apr-18 | 1 | 1 | N | Approved
1422 | PE-DG-435-612-C042 | PH BLDG. - STRUCTURAL FRAMING ALONG B ROW (CCR BUILDING) | A | 17-Nov-18 | 2 | 2 | Y | Re Submission Pending
1423 | PE-DG-435-612-C043 | PH BLDG. - STRUCTURAL FRAMING ALONG C ROW (CCR BUILDING) | A | 28-Nov-18 | 2 | 2 | Y | Re Submission Pending
1424 | PE-DG-435-612-C044 | PH BLDG.-AB BAY-DETAILS OF STAIRCASE MKD. SC-06 & 07 | A | 17-May-19 |  |  | Y | First Submission Due
1425 | PE-DG-435-612-C045 | PH BLDG.-AB BAY-DETAILS OF STAIRCASE MKD. SC-08 | A | 17-Jun-19 |  |  | Y | First Submission Due
1426 | PE-DG-435-612-C046 | PH BUILDING DETAILS OF ROOF TRUSS ( CCR BUILDING) | A | 25-Nov-18 | 2 | 0 | Y | Re Submission Pending
1427 | PE-DG-435-612-C047 | PH BLDG. -PURLIN DETAILS (CCR BUILDING) | A | 25-Dec-18 | 1 | 1 | N | Approved
1428 | PE-DG-435-612-C048 | PH BLDG.-DETAILS OF INTERMEDIATE COLUMNS (CCR BUILDING) | A | 28-Apr-19 | 2 | 0 | Y | Re Submission Pending
1429 | PE-DG-435-612-C049 | PH BLDG-CLADDING FRAMING ELEVATION ON AXIS A (CCR BUILDING) | A | 28-Jun-19 |  |  | Y | First Submission Due
1430 | PE-DG-435-612-C050 | PH BLDG-CLADDING FRAMING ELEVATION ON AXIS C (CCR BUILDING) | A | 18-Jul-19 |  |  | Y | First Submission Due
1536 | PE-DG-435-635-C001 | PE-DG-435-635-C001-DM TANK-GA & RC DETAILS OF FOUNDATION | A | 26-Sep-19 | 2 | 1 | Y | Re Submission Pending
1537 | PE-DC-435-612-C035 | P.H. BLDG.-DES. OF FLOOR BEAMS @ EL +8.5M (AB BAY) (CCR) | A | 04-Aug-19 | 2 | 0 | Y | Re Submission Pending
1538 | PE-DC-435-612-C036 | P.H. BLDG.-DES. OF FLOOR BEAMS @ EL +17.0M (AB BAY) (CCR) | A | 20-May-19 | 1 | 1 | N | Approved
1539 | PE-DC-435-612-C037 | PH BLDG.-DESIGN OF BC/CD/DE/EF/FG/GH BAY SECONDARY BEAMS @8.5M (CCR) | A | 30-Jun-19 |  |  | Y | First Submission Due
1540 | PE-DC-435-612-C038 | PH BLDG.-DESIGN OF BC/CD/DE/EF/FG/GH BAY SECONDARY BEAMS @12.5M/13.5M (CCR) | A | 23-May-19 |  |  | Y | First Submission Due
1541 | PE-DC-435-612-C039 | PH BLDG.-DESIGN OF BC/CD/DE/EF/FG/GH BAY SECONDARY BEAMS @17M (CCR) | A | 17-Jun-19 | 1 | 1 | N | Approved
1542 | PE-DC-435-612-C040 | PH BLDG.-DESIGN OF BC/CD/DE/EF/FG/GH BAY SECONDARY BEAMS @27.5M (CCR) | A | 07-Aug-19 | 3 | 1 | Y | Pending for Approval
1543 | PE-DC-435-612-C041 | PH BLDG.-DESIGN OF BC/CD/DE/EF/FG/GH BAY SECONDARY BEAMS @32.5M (CCR) | A | 20-Dec-19 |  | 0 | Y | Pending for Approval
1544 | PE-DC-435-612-C042 | PH BLDG.-DESIGN OF MISC. STRUCTURES | A | 31-Jan-19 |  |  | Y | First Submission Due
1545 | PE-DC-435-611-C007 | PH BLDG. DESIGN OF MISC FOUNDATIONS AND TRENCHES | A | 17-Oct-19 |  |  | Y | First Submission Due
1546 | PE-DC-435-612-C034 | P. H. BLDG. - DES. OF AUXILIARY COLUMNS (CCR) | A | 28-Feb-19 | 2 | 0 | Y | Re Submission Pending
1558 | PE-DC-435-651-C003 | CW ENCASEMENT-DESIGN | A | 21-Apr-19 | 2 | 3 | Y | Re Submission Pending
1560 | PE-DC-435-635-C002 | Dm pumphouse-load calculations-design of substr & supstr | A | 11-Apr-19 | 2 | 1 | Y | Re Submission Pending
1561 | PE-DC-435-635-C003 | DM pumphouse-design of ground floor | A | 11-Apr-19 |  |  | Y | First Submission Due
1562 | PE-DC-435-620-C008 | Chimney Wind tunnel study reports | I | 07-May-19 | 4 | 1 | N | Approved
1586 | PE-DG-435-616-C011 | Mill & Bunker Bay – steel framing details of Tripper floor | A | 12-Jul-19 | 3 | 3 | Y | Re Submission Pending
1593 | PE-DC-435-612-C041 | PH BLDG.-DESIGN OF BC/CD/DE/EF/FG/GH BAY SECONDARY BEAMS @32.5M (CCR) | A | 29-Aug-19 |  |  | Y | First Submission Due
1594 | PE-DC-435-612-C040 | PH BLDG.-DESIGN OF BC/CD/DE/EF/FG/GH BAY SECONDARY BEAMS @24M (CCR) | A | 29-Aug-19 |  |  | Y | First Submission Due
1642 | PE-DC-435-619-C005 | ESP CONTROL BLDG.-DESIGN OF SUBSTRUCTURE | A | 12-Sep-19 | 3 | 0 | Y | Re Submission Pending
1643 | PE-DC-435-619-C006 | ESP CONTROL BLDG.-DESIGN OF STAIRCASE | A | 22-Sep-19 | 2 | 0 | Y | Re Submission Pending
1648 | PE-DC-435-621-C003 | AUXILIARY BOILER-DESIGN OF AUX BFP FOUNDATION | A | 21-Sep-19 | 3 | 0 | Y | Re Submission Pending
1649 | PE-DG-435-636-C001 | DESALINATED WATER PUMP HOUSE-ARCH PLAN AT EL (±)0.00M, TERRACE PLAN, AND FINISH SCHEDULE | A | 21-Sep-19 | 3 | 1 | Y | Pending for Approval
1650 | PE-DG-435-636-C002 | DESALINATED WATER PUMP HOUSE-ARCHITECTURAL ELEVATIONS & SECTIONS | A | 21-Sep-19 | 3 | 1 | Y | Pending for Approval
1651 | PE-DG-435-636-C001 | DESALINATED WATER PUMPHOUSE-ARCH PLAN AT EL (�) 0.0M, TERRACE PLAN, AND FINISH SCHEDULE | I | 30-Oct-19 |  |  | Y | First Submission Due
1652 | PE-DG-435-636-C002 | DESALINATED WATER PUMPHOUSE-ARCH ELEVATIONS�& SECTIONS | I | 30-Oct-19 |  |  | Y | First Submission Due
1653 | PE-DG-435-636-C003 | DESALINATED WATER PUMPHOUSE- DETAILS OF FOUNDATIONS, COLUMNS | I | 30-Nov-19 |  |  | Y | First Submission Due
1654 | PE-DG-435-636-C004 | DESALINATED WATER PUMPHOUSE- LAYOUT AND DETAILS OF GRADE BEAMS & PLINTH BEAMS | I | 30-Nov-19 |  |  | Y | First Submission Due
1655 | PE-DG-435-636-C005 | DESALINATED WATER PUMPHOUSE- LAYOUT AND DETAILS OF TIE BEAMS, ROOF SLAB AND BEAMS | I | 30-Nov-19 |  |  | Y | First Submission Due
1656 | PE-DG-435-636-C006 | DESALINATED WATER PUMPHOUSE-LAYOUT AND DETAILS OF GROUND FLOOR AND PUMP FOUNDATIONS | I | 30-Dec-19 |  |  | Y | First Submission Due
1657 | PE-DG-435-636-C007 | DESALINATED WATER PUMPHOUSE-MISC DETAILS | I | 28-Feb-20 |  |  | Y | Submission Not Due
1658 | PE-DG-435-636-C008 (SHEET 1 OF 3) | DESALINATED AND FIRE WATER TANK - GA & SECTION OF TANK | I | 30-Nov-19 | 2 | 2 | Y | Re Submission Pending
1659 | PE-DG-435-636-C008 (SHEET 2 OF 3) | DESALINATED AND FIRE WATER TANK - GA & SECTION OF TANK | I | 30-Nov-19 | 2 | 2 | Y | Re Submission Pending
1660 | PE-DG-435-636-C008 (SHEET 3 OF 3) | DESALINATED AND FIRE WATER TANK - GA & SECTION OF TANK | I | 30-Nov-19 | 2 | 3 | Y | Re Submission Pending
1661 | PE-DG-435-636-C009 (SHEET 1 OF 3) | DESALINATED AND FIRE WATER TANK - RC DETAIL OF TANK | I | 30-Nov-19 | 2 | 3 | Y | Re Submission Pending
1662 | PE-DG-435-636-C009 (SHEET 2 OF 3) | DESALINATED AND FIRE WATER TANK - GA & SECTION OF TANK | I | 30-Nov-19 | 2 | 3 | Y | Re Submission Pending
1663 | PE-DG-435-636-C009 (SHEET 3 OF 3) | DESALINATED AND FIRE WATER TANK - GA & SECTION OF TANK | I | 30-Nov-19 | 2 | 3 | Y | Re Submission Pending
1664 | PE-DC-435-636-C001 | DESALINATED WATER PUMPHOUSE- LOAD CALCULATIONS | I | 30-Nov-19 |  |  | Y | First Submission Due
1665 | PE-DC-435-636-C002 | DESALINATED WATER PUMPHOUSE- DESIGN OF FOUNDATIONS & COLUMNS | I | 30-Nov-19 |  |  | Y | First Submission Due
1666 | PE-DC-435-636-C003 | DESALINATED WATER PUMPHOUSE- DESIGN OF PLINTH & TIE BEAMS | I | 30-Nov-19 |  |  | Y | First Submission Due
1667 | PE-DC-435-636-C004 | DESALINATED WATER PUMPHOUSE- DESIGN OF ROOF BEAMS & ROOF SLAB | I | 30-Nov-19 |  |  | Y | First Submission Due
1668 | PE-DC-435-636-C005 | DESALINATED WATER PUMPHOUSE-DESIGN OF GROUND FLOOR SLAB & PUMP FOUNDATIONS | I | 30-Dec-19 |  |  | Y | First Submission Due
1669 | PE-DC-435-636-C006 | DESALINATED WATER TANK-LOAD CALCULATIONS & ANALYSIS | I | 30-Nov-19 | 2 | 3 | Y | Re Submission Pending
1670 | PE-DC-435-636-C007 | DESALINATED WATER TANK-DESIGN OF FOUNDATIONS | I | 30-Nov-19 | 2 | 3 | Y | Re Submission Pending
1671 | PE-DC-435-636-C008 | DESALINATED WATER TANK-DESIGN OF BEAMS & COLUMNS | I | 30-Nov-19 | 2 | 3 | Y | Re Submission Pending
1672 | PE-DC-435-636-C009 | DESALINATED WATER TANK-DESIGN OF MISC FDNS | I | 28-Feb-20 |  |  | Y | Submission Not Due
1700 | PE-DC-435-667-C007 | SWI ELEC ANNEXE - DESIGN OF FOUNDATIONS | I | 20-Feb-20 |  |  | Y | Submission Not Due
1701 | PE-DC-435-667-C008 | SWI ELEC ANNEXE - DESIGN OF BEMAS AND SLAB | I | 22-Feb-20 |  |  | Y | Submission Not Due
1702 | PE-DC-435-667-C009 | SWI ELEC ANNEXE - DESIGN OF FLOORS AND TRENCHES | I | 20-Feb-20 |  |  | Y | Submission Not Due
1703 | PE-DC-435-667-C010 | SWI ELEC ANNEXE - DESIGN OF MISC STRUCTURE | I | 22-Feb-20 |  |  | Y | Submission Not Due
1704 | PE-DC-435-667-C011 | SWI ELEC ANNEXE - DESIGN OF TRNASFORMER FDN AND FB WALL | I | 20-Feb-20 |  |  | Y | Submission Not Due
1705 | PE-DC-435-667-C012 | SWI PUMP HOUSE - DESIGN OF FORE BAY | I | 22-Feb-20 |  | 0 | Y | Pending for Approval
1706 | PE-DC-435-667-C013 | SWI PUMP HOUSE - DESIGN OF GANTRY GIRDER | I | 25-Feb-20 |  |  | Y | Submission Not Due
1707 | PE-DC-435-667-C014 | SWI PUMP HOUSE - DESIGN OF CHANNEL | I | 20-Feb-20 |  |  | Y | Submission Not Due
1708 | PE-DG-435-667-C025 | SWIPH-ELEC ANN - GA & RC DETAILS OF FB WALL AND TRANSFORMER FOUNDATION DETAIL | I | 20-Feb-20 |  |  | Y | Submission Not Due
1709 | PE-DG-435-667-C026 | SWIPH-ELEC ANN - GA & RC DETAILS OF FLOOR | I | 22-Feb-20 |  |  | Y | Submission Not Due
1710 | PE-DG-435-667-C027 | SWIPH-GA DETAILS OF CHNNEL | I | 20-Feb-20 |  |  | Y | Submission Not Due
1711 | PE-DG-435-667-C028 | SWIPH-RC DETAILS OF CHNNEL | I | 22-Feb-20 |  |  | Y | Submission Not Due
1712 | PE-DC-435-648-C001 | AIR WASHER BLDG -LOAD CALCULATIONS | I | 15-Feb-20 |  |  | Y | First Submission Due
1713 | PE-DC-435-648-C002 | AIR WASHER BLDG - DESIGN OF FOUNDATIONS | I | 20-Feb-20 |  |  | Y | Submission Not Due
1714 | PE-DC-435-648-C003 | AIR WASHER BLDG -DESIGN OF COLUMN, BRACINGS AND BASE PLATE | I | 22-Feb-20 |  |  | Y | Submission Not Due
1715 | PE-DC-435-648-C004 | AIR WASHER BLDG -DESIGN OF W BEAMS | I | 20-Feb-20 |  |  | Y | Submission Not Due
1716 | PE-DC-435-648-C005 | AIR WASHER BLDG - DESIGN OF ROOF BEAMS | I | 15-Feb-20 |  |  | Y | First Submission Due
1734 | PE-DC-435-634-C005 | F.O. PR PH -DESIGN OF GROUND FLOOR | A | 12-Mar-20 |  |  | Y | Submission Not Due
1735 | PE-DC-435-647-C004 | COMPRESSOR BUILDING - DESIGN OF STAIRCASE AND EQUIPEMENT FOUNDATION AT EL(±)0.00M | A | 08-Nov-20 |  |  | Y | Submission Not Due
1736 | PE-DG-435-647-C009 | COMP BLDG -FRAMING DETAILS OF CRANE GIRDER | I | 25-Jul-20 |  |  | Y | Submission Not Due
1737 | PE-DG-435-647-C010 | COMP BLDG -DETAILS OF WALL BEAM & CLADDING | I | 25-Jul-20 |  |  | Y | Submission Not Due
1738 | PE-DG-435-647-C011 | COMP BLDG -GA & RC DETAILS AT ROOF LEVEL | I | 25-Aug-20 |  |  | Y | Submission Not Due
1739 | PE-DG-435-647-C012 | COMP BLDG -G.A & R.C. DETAILS OF GRADE SLABS & MISC FOUNDTIONS | I | 25-Nov-20 |  |  | Y | Submission Not Due
1740 | PE-DG-435-647-C003 | COMP BLDG - ARCHITECTURAL SECTIONS & DETAILS | A | 25-Mar-20 |  |  | Y | Submission Not Due
1741 | PE-DG-435-647-C004 | COMP BLDG - ARCHITECTURAL TOILET DETAILS | A | 25-Nov-20 |  |  | Y | Submission Not Due
1742 | PE-DG-435-641-C016 | ADMN BLDG. - GA & RC DETAILS OF GRADE SLAB AT EL(�)0.00M | I | 23-Oct-20 |  |  | Y | Submission Not Due
1743 | PE-DG-435-640-C018 | SERVICE BLDG - GA & RC DETAILS OF GRADE SLAB AT EL(�)0.00M |  | 08-Nov-20 |  |  | Y | Submission Not Due
1744 | PE-DG-435-640-C030 | SERVICE BLDG - GA & RC DETAILS LIFT PIT | I | 22-Mar-20 |  |  | Y | Submission Not Due
1745 | PE-DG-435-647-C008 | COMP BLDG -FRAMING AT ROOF LEVEL | I | 14-Nov-19 |  |  | Y | First Submission Due
1746 | PE-DG-435-647-C007 | COMP BLDG -STRUCTURAL FRAMING AND BASEPLATE FRAMING | I | 14-Aug-19 |  |  | Y | First Submission Due
1747 | PE-DC-435-634-C006 | F.O. AYKE AREA -DESIGN OF TANKER UNLOADING PLATFORM | I | 15-Feb-20 |  |  | Y | First Submission Due
1748 | PE-DC-435-634-C007 | F.O. DYKE AREA -DESIGN OF MISC FOUNDATIONS | I | 15-Feb-20 |  |  | Y | First Submission Due
1752 | PE-DG-435-641-C031 | POST OFFICE & BANK EXTENSION-ARCH PLAN ELEV SECTIONS | I | 01-Mar-20 |  |  | Y | Submission Not Due
1753 | PE-DG-435-641-C032 | POST OFFICE & BANK EXTENSION-ARCH- ELEV SECTIONS | I | 01-Mar-20 |  |  | Y | Submission Not Due
1754 | PE-DG-435-641-C033 | POST OFFICE & BANK EXTENSION- GA & RC DETAILS OF SUBSTR | I | 01-Mar-20 |  |  | Y | Submission Not Due
1755 | PE-DG-435-641-C034 | POST OFFICE & BANK EXTENSION- GA & RC DETAILS OF SUPSTR | I | 01-Mar-20 |  |  | Y | Submission Not Due
1756 | PE-DG-435-641-C035 | POST OFFICE & BANK EXTENSION- GA & RC DETAILS OF GR FLOOR | I | 01-Mar-20 |  |  | Y | Submission Not Due
1757 | PE-DC-435-641-C007-A | POST OFFICE & BANK EXTENSION- DESIGN OF SUBSTR | I | 01-Mar-20 |  |  | Y | Submission Not Due
1758 | PE-DC-435-641-C008-A | POST OFFICE & BANK EXTENSION- DESIGN OF SUPSTR | I | 01-Mar-20 |  |  | Y | Submission Not Due
1759 | PE-DG-435-668-C020 | SWO PH - GA OF OUTFALL TANK | I | 01-Mar-20 |  |  | Y | Submission Not Due
1760 | PE-DG-435-668-C021 | SWO PH - RC DETAIL OF OUTFALL TANK | I | 05-Mar-20 |  |  | Y | Submission Not Due
1761 | PE-DC-435-668-C007 | SWO PH - DESIGN OF OUTFALL TANK | I | 10-Mar-20 |  |  | Y | Submission Not Due
1762 | PE-DG-435-668-C022 | SWO PH - GA OF FEED POOL | I | 15-Mar-20 |  |  | Y | Submission Not Due
1763 | PE-DG-435-668-C023 | SWO PH - RC DETAIL OF FEED POOL | I | 20-Mar-20 |  |  | Y | Submission Not Due
1764 | PE-DC-435-668-C008 | SWO PH - DESIGN OF FEED POOL | I | 25-Mar-20 |  |  | Y | Submission Not Due

## Composite Rate
Calculation for Composite rate of RCC - Sub structure
Ref.No. | Description | Unit | L | B | D | Qty | SCT 1769 Rate | Amount
-- | 100 EARTH WORK | --
101 | Earth work in excavation | --
a | Depth from ground level but not exceeding 2 m | CUM |  |  |  | 0 |  | 0
b | Depth exceeding 2 m but not exceeding 4 m | CUM |  |  |  | 0 |  | 0
107 | Back filling | --
a | Back filling | CUM |  |  |  | 18 |  | 0
109 | carriage of excavated earth/selected materials for every 500m or part thereof beyond an initial lead of 500m. | CUM |  |  |  | 0 |  | 0
| 200 CONCRETE WORKS | --
201 | PCC- grade M7.5 | CUM |  |  |  | 0 |  | 0
205 | RCC-Below Ground level | --
a | M30 Grade | CUM
-- | 300 FORM WORKS | --
301 | Fairface form work - below finished ground floor level | SQM |  |  |  | 4 |  | 0
402 | 400 REINFORCEMENT | MT |  |  |  | 0.1 |  | 0
511 | Bitumen coating | SQM |  |  |  | 4 |  | 0
|  |  |  | TOTAL(excl cement) |  |  |  | 0
|  |  | Qty per cum of RCC |  |  |  | RC rate
| Rate for cement per cum of RCC | [6 empty] | 0
|  |  |  | TOTAL(incl cement) |  |  |  | 0
Calculation for Composite rate of RCC - Super structure
Ref.No. | Description | Unit | L | B | D | Qty | SCT 1815 Rate | Amount
-- | 100 EARTH WORK | --
101 | Earth work in excavation | --
a | Depth from ground level but not exceeding 2 m | CUM
b | Depth exceeding 2 m but not exceeding 4 m | CUM
107 | Back filling | --
a | Back filling | CUM
109 | carriage of excavated earth/selected materials for every 1 km or part thereof beyond an initial lead of 500m. | CUM
| 200 CONCRETE WORKS | --
201 | PCC- grade M7.5 | CUM
205 | RCC-Below Ground level | --
a | M25 Grade | CUM
206 | RCC-Super structure | --
a | M25 Grade | CUM | [5 empty] | 0
-- | 300 FORM WORKS | --
301 | Fairface form work - below finished ground floor level | SQM
302 | Fairface form work - above finished ground floor level | SQM |  |  |  | 4 |  | 0
A405 | 401 REINFORCEMENT | MT |  |  |  | 0.1 |  | 0
A509 | Bitumen coating | SQM
|  |  |  | TOTAL(excl cement) |  |  |  | 0
|  |  | Qty per cum of RCC |  |  |  | RC rate
| Rate for cement per cum of RCC | [6 empty] | 0
|  |  |  | TOTAL(incl cement) |  |  |  | 0
| average rate per cum of RCC | [6 empty] | 0
Calculation for Composite rate of Fabrication & Erection
Ref.No. | Description | Unit | SCT 1770 Rate
2301 | transportation, fabrication, erection, alignment | MT
| Fabrication(60%) | MT
2302 | Blast cleaning | MT
| Composite rate for Fabrication (incl. blast cleaning) | MT | 0
| Erection(40%) | MT | 0

## Uniq fields
Project details | Contract details | Contract Extn details | Composite Rate
Project Name | Agency Name | Contract Key(Contract details) | Ref.No.
| SCT No | Extn Date | Description
| Scope | Extn Duration | Unit
| Value |  | L
| LOI Date | Contract Execution details | B
| Duration(months) | Value expected (Cr) | D
| Start date | Value completed (Cr) | Qty
| End date | for month | Contract Key(Contract details)
Description 1 (Under/ Above ground works)
Drawing No | Drawing No Details | Completion Details | Description 2 (Piling/ RCC/ Str steel)
Description 3 (GI / RCC Piles, Sub/Super Str, Fabri/Erect)
PEM/ISG | Drawing No Key(Drawing No ) | Drawing No Details Key (Drawing No Details)
Drawing No | Description 1 (Under/ Above ground works) | for month
Issue date | Description 2 (Piling/ RCC/ Str steel) | Qty Plan for month
| Description 3 (GI / RCC Piles, Sub/Super Str, Fabri/Erect) | Qty completed for month
Area
Design Qty

## Sheet1 (hidden)
1 | Not awarded
NDCT (Cooling Tower)‐ 1 &2
2 | M/s RPP INFRA (SCT 1769)
Main Plant Boiler & ESP Foundation (Unit‐1) PKG. 1
3 | M/s PRIYA (SCT 1769)
Main Plant Boiler & ESP Foundation (Unit‐2) PKG. 2
4 | M/s RPP infra. (SCT 1770)
BTG packages –structural Work‐Main plant structures‐(TG hall unit‐1, partly mill & bunker building excluding Trichy scope) & CCR A TO C PKG.1
5 | Not awarded
Main plant structures‐(TG hall Unit‐2 & CCR and partly mill & bunker building excluding Trichy scope) & CCR C TO H‐ PKG‐2
6 | through exsisting agencies
Power house foundations including TG raft for both units
7 | Not awarded.
BTG super structure‐ (Unit-1 & 2 both)
8 | M/s BYGGING (SCT 1776)
RCC chimney Package.
9 | M/s B&B, Vellore(SCT 1804)
Non plant building –Part‐1
10 | M/s SREE SARAVANA(SCT 1823)
Non plant building –Part‐2
11 | M/s RPP Infra(SCT 1821)
Non plant building –Part‐3
12 | M/s B&B Vellore(SCT 1815)
Non plant building –Part‐4
13 | i. M/s VRP (SCT 1718) Pkg-1
ii. M/s PRIYA (SCT 1771) Pkg-2
Boundary wall packages‐ 1 & 2
14 | M/s Annai Infra (SCT 1811 Pkg-1)
CHP Civil foundations+ super structural works Pkg-1
15 | Not awarded
CHP Civil foundations+ super structural works Pkg-2
16 | M/s RPP Infra(SCT 1820)
AHP Civil foundations+ super structural work
17 | M/s RPP Infra (SCT 1809 Pkg-1 )
CHP, AHP & Non Plant Buildings - Structural Works Pkg-1
18 | Not awarded (SCT 1809 Pkg-2 )
CHP, AHP & Non Plant Buildings - Structural Works Pkg-2
19 | Not awarded
Silos & Overhead tank