## Doc Schedule-R00
MASTER DOCUMENT LIST
PROJECT |  | RINL VIZAG ESP R&M
CLIENT |  | M/S RINL
MAIN CONTRACTOR |  | M/S BHEL
SUB-CONTRACTOR
PACKAGE |  | VENTILATION SYSTEM
BHEL P.O. DETAILS
PESD/VENT/15/199-Rev01
S.NO | DRG./DOC.NO | EXPECTED SUBMISSION DATE | DRG/DOC | CAT | SUBMISSION DATE OF BHEL STATUS | [7 empty] | STATUS | REMARKS
|  |  | NUMBER | A/I | REV.00 |  | REV.01 |  | REV.02 |  | REV.03
[5 empty] | SUB. DATE | OBS. DATE | SUB. DATE | APP. DATE | SUB. DATE | APP. DATE | SUB. DATE | APP. DATE
1 | Master Documnt List | Within 1 week from PO |  | A
2 | List of special tools & tackles | Within 1 week from PO |  | I
3 | List of recommended spares | Within 1 week from PO |  | I
4 | Erection Procedure | Within 1 week from PO |  | I
5 | Commissioning Procedure | Within 1 week from PO |  | I
6 | PG Test Procedure for Ventilation system | Within 1 week from PO |  | I
7 | Equipment storage procedure at site | Within 1 week from PO |  | I
8 | Consolidated BOQ | Within 4 week from PO |  | I
9 | BBU - Supply | Within 1 week from PO |  | A
10 | AS-Built Drawing |  |  | I
11 | O & M Manual | Within 4 week from PO |  | A
12 | Location Lay out wall Opening Details of Ventilation Fans for Cable Cellar (at EL +6.0M) in New ECR Bldg | Within 3 week from PO |  | A
13 | Location Lay out & Opening Details of ventilatioin fans for Transformer Room-1 (at EL +0.0) in New ECR Bldg | Within 3 week from PO |  | A
14 | Location Lay out & Opening Details of ventilatioin fans for Transformer Room-2 (at EL +0.0) in New ECR Bldg | Within 3 week from PO |  | A
15 | Location Lay out & wall Opening Details of exhaust fans and louvers for Toilet (at El + 108.28) in New ECR Bldg | Within 3 week from PO |  | A
16 | Location Lay out & wall Opening Details of exhaust fans and louvers for STORE ROOM | Within 3 week from PO |  | A
17 | TDS & GAD of Propellar Fan | Within 2 week from PO |  | A
18 | TDS & GAD of Tube Axial Exhaust Fan | Within 2 week from PO |  | A
19 | TDS & GAD for Tube Axial SUPPLY fan | Within 2 week from PO |  | A
20 | Technical Data Sheet & Performance Curve For Induction Motor ( All fans) | Within 2 week from PO |  | A
21 | TDS & Gad of Air Intake Louver | Within 2 week from PO |  | A
22 | Consolidated Power& Control Cable schedule | Within 2 week from PO |  | A
23 | Electrical Load List | Within 2 week from PO |  | A
24 | Item Categorization Plan/Master Index | Within 1 week from PO |  | A
25 | QAP for Ventilation System | Within 4 week from PO |  | A
26 | Field Quality Plan | Within 1 week from PO |  | A
A- Approval Catagory I - Information Category

## Summary
Summary of Document Submission
Package | Review date | Total No. of Document | No. of Docs Submitted by AVPL | Number of documents overdue for first submission | Number of drawings / Documents approved by BHEL ( Code -1 / Code -4) | Number of drawings/Doc pending with BHEL | Number of Drawings pending with AVPL for revised submission
Ventilation System | 2020-12-03 | 26 | 0 | 0 | 0 | 0 | 0
QAPs are not included here.
Overdue for first submission
Approved
Pending with BHEL
Pending with AVPL