GENERAL INFORMATION: TENDER FOR PORT CLEARANCE & INLAND TRANSPORTATION FOR SULAYMANIAH  PROJECT.

REF No. BHEL:IOD:SUL:TRANS-001

( To be read along with the Techno-Commercial Bid Document)

SCOPE OF WORK

BHEL is executing a turkey contract for setting up a 4xFr9E Gas Turbine based simple cycle power project at Sulaymaniyah, Kurdistan, Iraq. BHEL shall be delivering materials for the project at the Iskenderun/Mersin port. Details of weights and dimension of the materials are mentioned in the list enclosed (Annexure-1).Equipments will be dispatched from India and some third countries as well, mainly by Ocean freight. Some small items will be sent by Air to Erbil /Sulaymaniyah air port. Contractor is required to perform the following major activities:

1.Arrangement of coordination and unloading from ships, receipt of material on trucks / trailers at Iskenderun/Mersin seaport/Sulaymaniyah airport. Arrangement custom/Port clearance, Clearing & forwarding (Interaction with shipping Agent for delivery order, locating the cargo, identification of cargo, planning for loading & arrange for loading, tally & supervision, arrange survey if required, to obtain short landing reports, administration of cargo charges removal order). Arrange customs/ port documentation and Inland transportation for delivery to Sulaymaniah site at Sulaymaniah, Kurdistan, Iraq.

2.	Contractor to confirm that there will be no restriction for all boxes as per details in

ANNEX-1 for transportation through Iskendrun / Mersin Port to Sulaymaniah site.

- Notice shall be issued for every shipment within 3 days after ship sails from port of despatch.

The works referred above shall include but not limited to the following:

- Receipts, customs/ Port clearance, loading/ unloading of estimated shipment of approximately 5385MT/ 18227 CBM gross weight including 9 (nine) heavy lifts (One Gas Turbine of approximate weight 0f 230MT, Two Accessory Bases of approximate weight 60MT each, Two Generators of approximate weight of 210MT each and four Generator Transformers of 125 MT each). A variation of 15% is possible in actual dimensions and weights of heavy lifts as well as break bulk equipments. Shipment of equipments will be done progressively from end February 2008. Shipments is likely to be completed by Dec2008, Some small items may be delivered after December 2008 also, which cannot be anticipated now.

  - Arrangements of heavy lift hydraulic axles; trailers of required capacity for heavy lift cargo for safe inland transportation.

  - Trucks and trailers for Break bulk cargo & container cargo.

- Contractor to intimate along with offer, list of documents required for port clearance for BHEL to review. All the agreed documents for port clearance & inland transportation will be provided by BHEL.  Contractor to satisfy that all the documents are in order for customs/Port clearance and road transportation. No claims of any kind by the contractor shall be admissible on BHEL due to missing / insufficient information or documentation.

- Payment of statutory levies and other costs for inland transportation, with no cost implication on BHEL.

- Customs duties, port charges and other local taxes, if any, as per laws of Turkey/Kurdistan payable directly to Port Authorities on BHEL supplied material, shall be reimbursed by BHEL at actual on furnishing original supporting documents along with the final Bill.

- Making transportation arrangements including suitable hydraulic trailers, Low bed Trailers/Trucks & transportation of cargo from Port of discharge to Sulaymaniyah site, Kurdistan, Iraq.

- Contractor shall conduct Road and Route Survey at his own Cost as per the Rules and Regulation of Turkey / Kurdistan & the Countries of Transit and take the approval from the required authorities under intimation to BHEL.

- The scope shall include obtaining all the lease, licenses, permits and clearances (paper/physical), bridge/culvert crossing permissions, police / environment / traffic / road-authorities / overhead-wires, (telephone / electrical), statutory requirements, etc. in Turkey and Kurdistan, Iraq.

It will be the responsibility of the Contractor to study the terrain for arranging the land transportation for delivery to Sulaymaniyah.  Actual site conditions are to be ascertained by the Contractor .The company shall not be liable for any additional claims on this account.

- BHEL shall not bear any cost towards detention / demurrage at Sea port / Air port and Road permits, levies etc. for the transit countries and Kurdistan/Iraq. Towards this, Contractor shall collect all required documents within good time, and proper coordination with the shipping agents and other agencies is to be ensured by the Contractor.

- Insurance up to site shall be arranged by BHEL.

- Contractor should handle sophisticated Electrical & Instrument items with care specially during inland transportation on graded roads.

- Contractor should submit within 2 (Two) weeks of issue of Fax-of-Intent, details of Road survey for heavy lift cargo in Turkey / Kurdistan and transit countries with road map and critical bridges, capacity etc., bridges to be propped up / strengthening required and subways/sideways to be prepared, if required.

12) Financial Bids of only those parties shall be opened which are found Techno-commercially compliant.

DOCUMENTS TO BE SUBMITTED ALONG WITH THE OFFER FOR PRE-QUALIFICATION :

- Details of past experience along with value of contracts.

- List of hydraulic trailers owned by the company / associates.

- Drawings / Details along with the copy of registration certificates of the trailers proposed to be deployed for this work.

- Bankers certificate indicating credit worthiness and financial capability.

- Certificates from port authorities in Turkey for local registration to perform as clearing agent.