BHARAT   HEAVY ELECTRICALS LIMITED

IVP GOINDWAL -143422

CIVIL ENGINEERING DEPARTMENT (FACTORY)

# PREAMBLE

01.	The scope of work includes Extension of shop floors, and other infrastructure works under Valves Capacity Augmentation in IVP complex, BHEL, GOINDWAL Punjab involving all Civil, Structural steel, Water supply, Drainage, Approach road and other allied works.

02.	Time is the essence of the contract.  Being a time bound expansion scheme with capital expenditure, the contractor should make all efforts to complete the work in time.  Eventhough the overall completion period is indicated as 07 months, the shop floor and other works shall be completed progressively and handed over as per agreed split up  schedule.

03. 	Usually, working hours are limited to day time only.  In emergency cases to carryout works during nights, it may be done so with the specific prior permission of BHEL. In such case, it is to be carried out in the presence of BHEL officials or their authorized persons.

04.	The tenderers are advised to visit BHEL Factory at Goindwal and get themselves acquainted with the site conditions before submitting the offer.

05.	The following eligibility criteria shall be complied to fulfill the Qualification Bid:-

- Contractor should have separate Registration Code No. for EPF & ESI.

- Average annual financial turnover of similar works in the last three years should be 30% value of respective work.

- During last seven years should have successfully completed works either i)Three similar works each not less than 40% value of respective work or ii)Two similar works each not less than 50% value of respective work or iii)One similar work not less than 80% value of respective work.

- Value of structural steel works completed in the last three years should be atleast 30% value of the minimum required annual turn over as given in criterion 05b..

- Solvency shall be produced for atleast 40% value of respective work.

06. 	The norms for qualification with prescribed score is attached in the Qualification Bid Document. Evaluation will be done accordingly. Minimum score required for qualification is 60.

07.	The value of turnover and the value of similar works mentioned above excludes cost of cement, reinforcement steel and structural steel. However if the turnover value furnished by the tenderer includes the above materials, then the tenderer has to furnish the cost of the same separately. If it is not furnished, the materials cost will be presumed as follows: -

Civil & structural works combined                                        -  50 %

Civil works alone                                                                  -  35 %

Structural works including cloaking items                            -  70 %

Other minor maintenance works                                          -  20 %

CONTRACTOR								ACCEPTING OFFICER

08. 	The works executed in the own name of the tenderer only will be considered for eligibility criteria.

09. 	Dissimilar / irrelevant works will not be considered for eligibility criteria.

10. 	Documentary evidences (Xerox copies - attested) for turnover, works experience, P.F, ESI registration etc., all as indicated & required in the tender document should be furnished without which it will not be taken into account.

11. 	The tender value excludes cost of cement, reinforcement steel & structural steel which will be supplied by BHEL at Stores at free of cost. Other free issue materials by BHEL are indicated in Schedule B of the Price bid document.

12.	Tender Value is only approximate and liable for variation without entitling the tenderer to any compensation, till the total value of contract vary by more than 20% (twenty percentage).

13.	Quoted rate shall be firm throughout the contract period  of 07 months and extended  contract period also and  no  cost escalation is allowed on any account.

14.	The work shall be carried out as per drawings released then and there, Civil Engineering Department Work & Safety procedure, AWS / BIS specifications, standard code of practice and as per the instructions of Engineer-in-charge.  The brief description of items of work is given in the bill of quantities provided in the Price Bid. Tenderer has to quote rates both in figures and in words for all the items given in the Bill of Quantities provided in the Price Bid. (From page No.24 to62).

15. 	The item rate offered is for finished item of works and shall provide for the complete cost towards fuel, tools, tackles, plant & machinery, temporary works, labour, materials, levies, taxes, transport, lay-out, repairs, rectifications, maintenance till handing over, supervision, labour colonies, establishment, services, roads, revenue expenses, overheads, profits & all other incidentals etc., complete.  However if the service tax is applicable for this contract, the same will be reimbursed on production of valid document proof for having paid service tax by the tenderer.

16. 	For any item of work not covered in Bill of Quantities, the rate will be arrived at based on the conditions given in BHEL General Conditions of Contract.

17. 	After award of work the contractor has to furnish the security deposit, as per Clause 13 of Tender Notice, attached in the Price Bid.  Also it is to be noted that after award of work the contractor has to furnish 50 % of security deposit before the commencement of work.

18.	The contractor should bring the construction earth moving machineries like Poclain,  Paver, Road Roller, JCB etc., as and when required for the work without any delay.  Also required number of the following tools & Plants / instruments shall be made available always at site for the works.

a)	Precise Leveling instruments and theodolite.

b)	Full load mixture machine / mini batching

c)	Petrol / Kerosene driven vibrator/ mechanical vibrat

d)	Cube moulds

e)	Inter carting vehicle (tractor, hand trolley etc)

f)	Hydra cranes

g)	Power operated winches

h)	Mobile / Hydraulic crane

- Welding machine etc.

CONTRACTOR								ACCEPTING OFFICER

19.	The contractor has to arrange sufficient number of lorries to collect & transport the surplus earth, construction debris generated, etc. at site. Otherwise BHEL would clear the debris at the contractor’s risk and cost.

20. 	The contractor has to execute any item of work irrespective of the quantity without any reservation.

21. 	The contractor has to carryout the work in production shops without affecting the production by planning such work on holidays / obtaining proper shut down.

22. 	The decision of Engineer-in-charge shall be final and binding on the contractor regarding clarification of items in this tender schedule.

23. 	The contractor shall strictly adhere to various labour laws in force.

24. 	The contractor shall follow norms of BHEL security system for movement of men & materials within the complex.

25.	Since the responsibility for the quality, workmanship and accuracy of any work being carried out under this contract lies with the contractor, the contractor should ensure that no work is done without the presence of contractor’s representative at the work spot.

26.	The contractor has to submit the organization chart of their set up for the  works and any change thereafter in the organization set up shall have the prior approval of BHEL.

27.   	Statement of completed works with detailed measurements along with material reconciliation statements shall be submitted by the contractor in the last week of every month for processing bill.

28. 	The contractor should establish his own site office, fabrication yard, handling facility, storage facility to stock about 300 MT of cement etc., for which vacant land will be allotted on specific request for which the rent  will not be collected.

29.	The contractor is required to carry out construction activities as directed by the department officials.  It is required to engage certain minimum strength of staff for effective supervision of works as indicated below:

Site in-charge / Construction Manager 				-	1 No.

Planning Engineer and co-ordinator				-	1 No.

Qualified Surveyor						-	1 No.

Civil Engineer (Graduate in Civil Engineering)	          	 	-	2 Nos.

Structural Engineer (Graduate in Mechanical / Civil Engg.)	- 	2 Nos.

Supervisor/Engineer (Diploma Holder)              			-           4 Nos.

Level-II NDT Inspector						-	1 Nos.

In addition to the above, Quantity surveyors have to be engaged to prepare measurements and submit    the bills.

30.	Adequate number of Quality Engineer and qualified Safety Engineer should be deployed at site. Experienced  Engineers / Supervisors are  to be engaged in Railway and water supply works.

CONTRACTOR								ACCEPTING OFFICER

31. 	To safeguard the persons working at height in roof, wall etc., sufficient number of Industrial Safety nets shall be provided at tenderer’s cost in appropriate level and locations.  The working hand including Supervisors, Engineers should wear the personal protective items and safety measures such as helmets, safety belts, shoes, etc., before entering into working place.

32.	The tenderer has to deploy adequate labour of required categories such as Unskilled, Skilled, Mason, Carpenter, Plumber, Welder, Fitter, Mistry, Technically experienced, etc. so as to execute the works simultaneously in all areas of work.   The Technical persons with experience shall have to produce valid certificate for verification.

33.	Expertised labour only to be engaged for specialized items of work like laying of ceramic tiles, marbles, cuddapah slabs, granite slabs and false ceiling, partition, wall paneling, architectural finishing etc. and work experienced persons shall be engaged for fabrication, water supply, railway track laying and aligning works, sewerage system work, etc.

34.	Exclusive Stores personnel should be engaged who would co ordinate with department official for clearance and collection of BHEL supplied materials required for works.

35.	Separate non-technical persons should be engaged for arranging daily gate passes for labours and vehicles entry in all the gates of Factory Complex.

36. 	The tenderer shall carry out health performance test at his cost for all the workmen engaged  in the work through a registered medical practitioner and produce certificate on demand.

37. 	It shall be the responsibility of the contractor to see that the workmen do not utilize the departmental canteen facilities.  Contractor has to make his own arrangements to provide refreshment for the workmen.

38.	All the works shall be executed as per the standard specifications as provided in CPWD / BIS.

39.	The works contract to be entered into with the successful tenderer will be governed by the BHEL Revised General Conditions of Contract in force.

40.	Some changes are likely in the quantities furnished as well as in the layout, design and specifications of the work.  The rates quoted shall be deemed to be inclusive of all such contingencies.

41.	All the materials to be used in the work and the nature of work shall conform to the respective CPWD & BIS and National Building Organisation, Standard Specifications forming part of "ALL INDIA STANDARD SCHEDULE OF RATES" specifications and shall be got approved by the Engineer-in-charge before actual incorporation in the work.

42.	The contractor should maintain proper accounts for cement, reinforcement steel and structural steel sections and other materials if any supplied by this organisation and these should be available at the site of work for verification and check by the Officials of this Organisation at any time.

43.	All materials brought by the Contractor for incorporation in the work shall be got inspected and approved by the Engineer-in-charge before they are incorporated in the work.

All the structural works including fabrication, erection etc., are subjected to inspection and clearance by BHEL 	 ENGINEER –IN-CHARGE..

CONTRACTOR								ACCEPTING OFFICER

44.	All tools and plants including jack hammer with silencer  & bits, rock drilling machine, etc., required for all the works covered under this contract will have to be brought by the contractor.  Compressed air alone will be provided at viable locations at free of cost by BHEL. From that point the contractor has to provide further arrangements for site works.

45.	The contractor should be in a position to make his own arrangement for compressed air without any extra claim for the uninterrupted operation of jackhammer with silencer wherever BHEL is not in a position to supply compressed air.

46.	All safety measures are to be followed during execution of work, particularly during blasting and only licensed blaster should be engaged for this purpose.  Sufficient care shall be taken by the contractor during excavation to avoid damages to the buried pipe lines, cables and other infrastructure like railway lines if any etc. Controlled blasting including muffling can be carried out with prior permission from safety department.

47.	The contractor should use only the materials of brand and quality as approved by BHEL.

48.	The contractor should submit the programme for the completion of work and the list of machineries and site personnel to be deployed for the work along with tender.

49.	All materials and consumables brought by the contractor should have manufacturer’s certificate.

50.	The contractor should use only weigh batch for all reinforced cement concrete  works (controlled concrete).  The tenderer is advised to install concrete mini batching plant at site considering the quantum of concrete work involved.

51.	Contractor’s materials and tools & plants shall have to be brought inside factory with proper invoice / voucher and make necessary entry in the security gate.  They should maintain proper record for tools and plats, materials, etc., brought inside the factory complex.

52.	The contractor should submit the mix design for RCC for different mix of concrete for different grade of cement at his cost through reputed institution.

53.	The contractor should extend fullest co-operation with the third party agencies engaged, if any by BHEL to adhere the Quality Control Procedures ensuring quality.

54.	The contractor should extend full co-operation to the other contractors who may be doing other works in the same areas to enable them to execute their portions of work without any delay or difficulty.

55.	With regard to specifications not covered by the General and Special Conditions of Contract, those contained in the CPWD Specifications or other specifications approved by Bharat Heavy Electricals Limited, shall apply.

CONTRACTOR								ACCEPTING OFFICER

56	Water required for the work may be provided by this organization at only one point at the     site of the work at free of cost. In case of failure of water supply, the Contractor will have to make his own arrangements for water without any extra claims until supply is restored. BHEL does not accept any liability whatsoever for non-supply or delay in the supply of water under any circumstances. The contractor shall ensure that there is no wastage of water otherwise supply of water is liable to be stopped at contractor’s risk and cost.

57.	Electrical energy required for the work may be given  by this organization at any one point at the site of work at free of cost. BHEL does not accept any liability whatsoever for non-supply, delay in supply or failure of supply of electrical energy.  Contractor shall ensure that there is no wastage of electrical energy otherwise supply is  liable to be stopped at contractor’s risk and cost.  The contractor shall make leak proof / fire proof shed and provide control panel board of required capacity and lay the required cables at their own cost for further distribution.

58.	Purchase preference policy will be extended to CPSE bidders subject to other terms & conditions as provided in the office memorandum issued by DPE.

59.	No advance / mobilization advance will be given.

60.	For the agencies who had already been qualified and enlisted by BHEL under various money category, price bid document for the eligible value of work  can be obtained after paying  the cost of tender document.  They already enlisted and eligible agencies may submit document duly signed in all pages and no Technical evaluation is applicable for item.

61.	LD / Penalty clause is applicable as per General Conditions of Contract.

- BHEL reserves its right to reject a tender  due to unsatisfactory past performance in the execution of  a contract at another project/unit awarded against a different enquiry.

63. 	BHEL reserves its right to accept/reject any or all the tenders and to award the work in full or split to more than one agency without assigning any reasons.

CONTRACTOR								ACCEPTING OFFICER

BHARAT HEAVY ELECTRICALS LIMITED

(A Government of India Undertaking )

Unit : IVP GOINDWAL

# CIVIL ENGINEERING DEPARTMENT

### NOTICE INVITING TENDER

### 01.	Name of work 			:	Extension of shop floors,

### and other infrastructure works under Valves Capacity Augmentation in IVP complex, BHEL, GOINDWAL.

02.	Estimated Cost 			:	Rs.253.00 Lakh

03.	Earnest Money Deposit		:	Rs.2.00 Lakh

04.	Completion Time		:	Seven  (07) MONTHS

(From the date of commencement of  work which will be   reckoned  from the date of the  site, handed  over  to the   Contractor )

05.	Cost of Tender Document	:	Rs.500/- ( including Sales Tax )

This amount will not be refunded  under any 							circumstances

06.  	Last Date for Receipt of

Tenders 			:          13/12/2008

07. 	Date of Qualification Bid opening  :       13/12/2008

08. 	Date of Price Bid opening	:	will be intimated to those who are qualified

separately.

09.	Maintenance Period 		:	6  (Six)  Months  from  the  date  of   actual

completion of the entire work and handed over to BHEL.

This document contains Qualification Bid  pages, Price Bid 67 pages  including Bill of Quantities , and   Drawing etc.,

Issued to Messrs / Thiru			:	…………………………………………………

…………………………………………………

…………………………………………………

…………………………………………………

CONTRCTOR 						ISSUING OFFICER

### INSTRUCTIONS TO TENDERERS

- The tender is open to all Contractors. The Contractors  not borne on the approved list of contractors of this Organisation must submit the following testimonials simultaneously with their tenders.

  - A Certificate to establish that the tenderer is an independent contractor working on his own

  - Atleast two certificates from responsible Officers of Government of Firms of repute, regarding the tenderer’s capacity to undertake and to carryout the work tendered  for or similar work satisfactorily

NOTE :

- Copies of testimonials unless attested a Gazetted Officer will not be accepted

- Non – Submission of the above testimonials simultaneously with the tenders may result in the tender being rejected

- The tenders should be accompanied by a list of contracts already held by the contractor at the time of submitting the tender and giving the following particulars

- Value of  each contract

- The balance value of work  to be done on the same

- The tenderer is advised to obtain the tender documents in person  or by a messenger duly authorized to do so. The BHARAT HEAVY ELECTRICALS LIMITED will not under any circumstances accept responsibility for the non – receipt of delay in the receipt of the tender documents by the tender.

- Rate for each item of the tender schedule should  be quoted in FIGURES and in WORDS. In case of any difference in the rates quoted in figures and in words, the lower of the two rates will be taken as the tendered rate.     Unit rate quoted  shall be the basis for arriving the total value of the tender.  The total amount for every item shall be arrived by multiplying the unit rate with the quantity indicated for that item.  In case of any arithmatic deviation is noticed in the total amount, the same will be corrected and evaluated by taking unit rate as basis and multiplying with the quantity indicated.

- Rate quoted shall include all royalties, terminal taxes, Octroi duties, Central or Provincial Excise Tax, Sales Tax  and any other taxes leviable under the State or Central Government rules. The Bharat Heavy Electricals Ltd., will not entertain any claim whatever in this respect.  However if the service tax is applicable for this contract, the same will be reimbursed on production of valid  document proof for having paid service tax by the tenderer.

- Should a tender find discrepancies or omissions in the drawings or any of the tender documents or should be in doubt  as to their meaning,  he should at once address the authority inviting the tender for clarification. Every endeavour is made to avoid any error which can materially affect the basis of the tender but the successful tenderer shall  take upon himself to provide for the risk of any error which may be subsequently discovered and shall make no subsequent claim on account thereof.

CONTRACTOR							ACCEPTING OFFICER

- Tenders submitted by post should be through “Registered Post with Acknowledgement due” and should be posted with due allowance for any delay in postal delivery. Tenders received after the due date and time of opening, tenders are liable  for rejection.

- Where the tender called for covers only the building work and excludes internal services such as sanitary and water supply installations, electrification etc., the building contractor will have to leave pockets, holes, etc., as required for other works  and will have to phase  his work to ensure smooth progress of the work of the other agencies also as directed by the Engineer – in – charge.

- Where the tender schedule contains special items of work such special floor finishes, foam concrete for insulation, special water proofing treatment to roofs etc., it will be entirely at the discretion of the Project Authorities to allot these items of work to other contractors specialized in these works. In such cases, the main building Contractor will have  to tender all necessary co-operation to the agencies involved so as to ensure the smooth progress of all work.

- The contractor’s  responsibility under this  shall commence form the  date of  receipt  of the order of acceptance of his tender. The scheduled period of completion for this work will be as mentioned in page No. 07, and the Contractor will have to plan his work accordingly.

- Generally, the maintenance period  for any work under BHEL Organisation will be  SIX (6) MONTHS .

12. 	Earnest Money Deposit:

Earnest Money is to be paid by each tenderer to ensure that the tenderer does not refuse to execute the work after it is awarded to him.   EMD  shall  be furnished only in the  form Pay Order or Demand Draft in favour of BHEL.  EMD  in any other form will not be accepted.    The rate of earnest money deposit shall be as under:

Works costing upto Rs. 1 lakh 					NIL

Works costing more than Rs.1 lakh and upto Rs. 5 lakhs	     	Rs. 10000/-

Works costing more than Rs.5 lakhs and upto Rs.10 lakhs	Rs.  25000/-

Works costing more than Rs.10 lakhs and upto Rs.50 lakhs	Rs. 100000/-

Works costing more than Rs.50 lakhs and upto Rs.100 lakhs        Rs. 150000/-

Works costing more than Rs.100 lakhs 			     	Rs. 200000/-

No interest shall be allowed on the Earnest Money Deposit.

- Should a tenderer or a contractor on the list of approved Contractors  have a relative, or in case or a firm or Company of contractors any of its share holders or shareholder’s relative, employed in a gazetted capacity in the Engineering Department of the Bharat Heavy Electricals Limited, the authority inviting tenders shall be informed of this fact at the time of submission of the tender, failing which tender may be disqualified or if such fact subsequently comes to light, the contract may be rescinded in accordance with the relevant provisions in the General Conditions of Contract.

- If tenderer expires after the submission of his tender or after the acceptance of his tender, BHEL may at their discretion, cancels such tender. If a partner of a firm expires after submission of tender or after the acceptance of the Tender, BHEL may cancel such Tender at their discretion unless the firm retain its character.

CONTRACTOR							ACCEPTING OFFICER

- The Bharat Heavy Electricals Limited will not be bound by any power of attorney granted by the tenderer or by changes in the composition of firm made subsequent to the execution of the  contract. They may however recognise such power of attorney and  changes after obtaining proper legal advice the cost of which  will be chargeable to the contract concerned.

- lf the tenderer deliberately gives  wrong  information  in his tender or creates conditions favourable for the acceptance of  his tender, the Bharat  heavy  Electricals Limited, reserves the right to reject  such tender at any stage.

- Words  importing the singular number shall also be deemed to include the plural number and vice  versa where the context  so requires.

- The expenses  for completing and stamping the agreement shall be paid by the contractor.

19.	The General and special  conditions are complementary  to each other and where they  are conflict  the Special Conditions shall prevail. In regard to matters not covered by the General and Special Conditions of Contract, those contained in the CPWD or other  specifications approved by the Bharat Heavy Electricals Limited, Shall apply.

20. 	Tenderers  shall not increase their quoted rates in case the Bharat Heavy Electricals Limited,	 negotiates for reduction of rates. Such negotiation shall not amount to cancellation or withdrawal of the original offer and the rates originally quoted shall be binding on the tenderes for a period of three months from the date of opening of tenders.

21.	Canvassing in any form in connection with tenders  is strictly prohibited and the tenders submitted by  the contractors who resort to canvassing will be liable for rejection.

22. 	All contractors will have to produce Income tax Clearance Certificate from the Income Tax– Officer concerned along with their tenders. Those Contractors whose income is not  taxable will be required to give an affidavit of their income on the prescribed form. If the successful tenderer fails to produce the Income – tax clearance certificate within the stated  period the Earnest Money Deposit and Security Deposit  of the tenderer may be forfeited and the contract terminated.

CONTRACTOR							ACCEPTING OFFICER

### TENDER NOTICE

### NAME OF WORK : 	Extension of shop floors,  and other infrastructure works under Valves Capacity Augmentation in IVP complex, BHEL, GOINDAWAL

#### ESTIMATED COST : Rs. 253 Lakh

- SEALED TENDERS for the above noted work are hereby invited from contractor experienced  in works of similar kind and magnitude. Tenders will be received by  SENIOR MANAGER / CIVIL / PLANNING Bharat Heavy Electricals Limited, GOINDAWAL . upto 14.30 Hrs. on and  the  Qualification Bid  alone will  be opened on the same day at 15.00 Hrs. at the Office of the SENIOR MANAGER/ CIVIL / PLANNING in the presence  of such of those tenderers. Or their agents who may choose to attend.

- TENDER FORMS and other particulars regarding the proposed work can be  obtained on any working day from 8.00 A.M. to 3:00 P.M. upto 13/12/08 on payment of the prescribed sum of Rs.500/ - per set ( including Sales Tax ).  This amount will not be refunded under any circumstances.

- TENDERS must be submitted in sealed covers and should be addressed to Sr. MANAGER/CIVIL/PLANNING (FACTORY) with full name and address of the tenderer and the name of work being noted on the cover.

- All entries in the tender documents should be in one ink. Erasers and overwritings are not permitted. All cancellations and insertions should be duly signed by the tenderer concerned.

- TENDERERS should fill in all the required particulars in the blank  spaces provided for  this purpose in the tender documents and also  sign each and every  page of Tender Documents including the drawings attached there to before submitting their tender.

- UNIT rate  should be quoted in figures as well as in words with reference to each  item and for all the items shown in the attached schedule. These rates shall be for the finished work in site.  Amount of each item and the total page by page and also the grand total amount of the whole contract should be filled in by the tenderers.  Unit rate quoted  shall be the basis for arriving the total value of the tender.  The total amount for every item shall be arrived by multiplying the unit rate with the quantity indicated for that item.  In case of any arithmatic deviation is noticed in the total amount, the same will be corrected and evaluated by taking unit rate as basis and multiplying with the quantity indicated.

- QUANTITIES  shown in the attached  schedule are  only approximate and are liable for variation without entitling the Contractors to any compensation, provided the total value of the Contract does not vary by more than 20% (twenty percent )

- In quoting their rates, the tenderers are advised to take into account all factors including any fluctuations in the market rates etc. No claim will be entertained on this account after acceptance of the tender  or during the currency of the contract.

- Before tendering, the tenderers are advised to inspect the site of work and its environments and be well acquainted with  the actual working and other prevalent conditions, position of materials and labour, General and Special Conditions of Contract. Instructions to tenderers, drawings and Specifications and all other documents which form part of the agreement to be entered into.

- The rates quoted in the tender shall remain valid for a period THREE MONTHS  from the date of opening of tenders.

CONTRACTOR							ACCEPTING OFFICER

- In the event of tender being submitted by firm the tender must be signed separately and legibly by each  partner or member of the firm or in their absence, by the person  holding the power of attorney on behalf  of the firm concerned  in the latter case a copy for the power of attorney  duly attested by a Gazetted Officer must accompany the tender.

- Every tender must be accompanied with EMD for the amount as specified in Page No. 09 in any of the form mentioned in Para 12 of the “Instruction to Tenderers”. This Earnest  Money will be refunded to the unsuccessful tenderers within fifteen days of finalisation of the award of work. In case of the successful tenderer, the Earnest Money will be retained as part of the Security Deposit for satisfactory completion of the work in accordance with Clause 16 of the General Conditions of Contract

NOTE :	Cheques, Currency Notes and  Money Orders will not be accepted in lieu of the deposit receipt referred to above

13.	Security Deposit

13.1	Security Deposit should be collected from the successful tenderer .  The rate of Security   Deposit will be  as below:

Upto Rs. 10 lakhs				10%

Above Rs. 10 lakhs  upto Rs.50 lakhs		1 lakh + 7.5% of the amount  exceeding

Rs. 10 lakhs.

Above Rs. 50 lakhs				Rs.4 lakhs + 5% of the amount

exceeding   Rs. 50 lakhs.

Atleast 50% of the security Deposit should be furnished before start of the work by the contractor.

  - Security Deposit may be furnished in any one of the following forms

- i)	Cash (as permissible under the Income Tax Act)

- ii) 	Pay Order, Demand Draft in favour of BHEL.

- iii)	Local cheques of scheduled banks, subject to realization.

iv) 	Securities available from Post Offices such as National Savings Certificates, Kisan Vikas Patras etc.

- (Certificates should be held in the  name of Contractor furnishing the security and duly    pledged in  favour of BHEL and discharged on the back).

v)	Bank Guarantee from  Scheduled Banks /  Public Financial Institutions as defined in the Companies Act subject to a maximum of 50% of the total security deposit value.  The balance 50% has to be remitted either by cash or in the other form of  security. The Bank Guarantee format should have the approval of BHEL.

vi)	Fixed Deposit Receipt issued by  Scheduled Banks /  Public Financial Institutions  as defined in the Companies Act . The FDR should be in the name of the contractor,  A/C BHEL, duly discharged on the back.

vii)	Security deposit can also be recovered at the rate of 10% from the running bills. However in such cases at least 50% of the Security Deposit should be collected before start of the work and the balance 50% may be recovered from the running bills.

CONTRACTOR							ACCEPTING OFFICER

viii)  	EMD of the successful tenderer  shall be converted and adjusted against the security deposit.

ix)  	The security deposit shall not carry any interest.

NOTE:	Acceptance of Security Deposit against Sl. No. (iv) and (vi) above will be subject to hypothecation or endorsement on the documents in favour of BHEL. However, BHEL will not be liable or responsible in any manner for the collection of interest or renewal of the documents or in any other matter connected therewith.

- Unless the contractor whose tender is accepted signs the Contract Agreements and makes the necessary  security deposit specified in Para 13 above within Seven days of the date of the order directing him to do so the amount of Earnest Money Deposit already deposited by him will be forfeited and acceptance of his tender withdrawn.

- After tender opening if tenderer revokes his tender or increases his earlier quoted rates or after acceptance of his tender does not commence the work in accordance with the instructions of the Engineer-in-charge, the Earnest Money deposited by him will be forfeited and acceptance of his tender withdrawn. If only a part of the work included in the tender had been awarded to the tenderer, the amount of Earnest Money to be forfeited will be based on the value of the contract so awarded.

- The Bharat Heavy Electricals  Limited reserved the right to reject any or all the received or accept any tender  or part there of without assigning any reason thereof. In the case acceptance of part of tender, time for completion may also be reduced to the extent considered appropriate by the Accepting Authority.

- Conditional and Unwitnessed tenders, tender containing absurd rates and amounts tenders which are incomplete or otherwise considered defective and tenders not in accordance with the tender conditions laid down by the Accepting Officer are liable for rejection.

- Tenders not submitted on the prescribed form are liable for rejection.

- The work must be completed within a period  as mentioned in page no.07.

- The Chairman / General Manger / Deputy General Manager / Deputy Manager / Senior Engineer  shall be Accepting Officer, herein after referred to as such for the purpose of this contract.

- This tender notice shall be deemed to form an integral part of the contract to be entered into for this work.

- The tenderers are advised to go through the condition stipulated in Tender document & code of conduct for ‘Health & Safety of Contract Labourer’ in details. Any violation thereof  will invite  punitive action being taken against them. While quoting the rate all the above factors are to be taken into account.

ISSUING OFFICER

CONTRACTOR							ACCEPTING OFFICER

##### GENERAL SAFETY PRECAUTIONS TO BE FOLLOWED AT WORK SITE DURING EXECUTION

The following safety measures should be strictly  adhered to during execution of works at sites.

1. 	Providing the working platform with toe board  and handrail for continuous working at heights.

2. 	Providing safety belt and life line at all times for men working at heights.

3. 	Providing dust or fume respirator in places where dust and fume concentration exists.

4. 	Providing goggles and welding screens.

5. 	Providing acid and alkali  proof rubber gloves for handling acid and alkali and chemical which are corrosive.

6.	 Providing rubber gloves for working on electrical works.

7. 	Ensuring proper  lashing of the components while being transported in vehicles.

8. 	The vehicles must have side supports or have body to support the materials conveyed.

9. 	The materials should not  be allowed to extend or overflow the sides of the vehicles.

10.	Materials should not be allowed to overhang from the rear edge of the body of the vehicle.

11.	Driver of the vehicle must possess license.

12.	Vehicle must not be overloaded  prescribed limits.

13.	Red flags and lights for parts projecting from the body of vehicle must be provided.

14.	The speed restrictions within the factory premises must  be strictly adhered to.

15.	The gas cylinders must be always handled on trolleys or kept tied down not in use. They should never be rolled as Roller for conveying.

16.	Cylinders should not be used without regulators.

17.	All excavations must be barricaded and red lamps  must be provided.

18.	All electrical connections must be properly earthed.

19.	No work should be taken up for execution inside shop floor, without obtaining necessary work permit.

20.	Providing helmet, full body safety belt, etc., for high level work and sufficient number of Industrial Safety nets at appropriate level to safeguard the persons working at high level particularly in trusses, girders, roofing etc., of industrial and high roof buildings.

21.	The contractor should maintain a register regarding the driver license particulars.

22.	All personal  protective equipment conform with standard specification as per the details given in the code of conduct.

Contractor including their sub contractors, agents and labour engaged on the work  are required to scrupulously adhere to the safety regulations, safety precautions and measurers. Any violation thereof will invite punitive action being taken against them. Also contractors with frequent violations of safety regulations will not be entrusted with further  work in this organization.

CONTRACTOR							ACCEPTING OFFICER

##### SAFETY PRECAUTIONS TO BE OBSERVED WHILE TRANSPORTING MATERIALS

I.  VEHICLE

- Vehicles carrying material should have proper registration documents and must  be produced on demand by our Security Staff.

- The light on right side, i.e., over the drivers cabin shall be in working  condition.

- Both  the head lights as well as park lamps must be in working conditions.

##### II. MOVEMENT OF VEHICLE

- The vehicle should not travel at more than 20 km.ph in our premises.

- The Driver of the vehicle must possess heavy duty licence and produce  on demand by the Security Staff.

- Vehicles carrying inflammable liquids in the tank containers should have grounding chain or the tank should be coated with insulating material also to avoid Static Electricity.

- In road junctions, speed breakers and railway crossing, the speed should be lowered and vehicle should proceed cautiously.

- The driving should ‘KEEP TO THE LEFT’ at all places.

- The vehicle should not be parked in road which could obstruct the vehicular traffic.

- No person other than driver should be allowed to sit or stand on the prime mover or trailer.

- The vehicle should pass only through the approved routes. Short cuts should be forbidden.

- There must be a safe distance behind another moving truck.

- The driver should avoid making quick starts, jerky stops or quick turns at excessive speed.

CONTRACTOR							ACCEPTING OFFICER

##### III SHIPPING

- Strong side supports should be  provided on both  sides of  the trailer.   The side supports  should  be fixed  in such a way that  it cannot be removed even temporarily.

- Adequate  packing must be given for  easy slinging operation. The packing materials should  be good enough to withstand the load.

- The stacking of loads in the truck should be evenly placed. The load should not be heaped together or dumped over the  chassis.

- The loaded materials should be fastened tightly with ‘WIRE ROPE’.   Manila rope or coir rope should not at all be used. There must be side packing such as gunny or rubber tyre between the sharp edge of the job and wire rope in order to avoid  cut in the wire rope.

- There must be minimum two fastenings and  it should be more in case of lengthier loads.

- The wire rope  should be in sound conditions i.e, there should not be links, knots or bristles etc.,

- The wire rope ends should  be clamped with ‘U’ clamps.

- The load on the truck should not be beyond its standard capacity. The carrying capacity must be clearly marked on the trailer also.

- The loose pieces should be bundled before loading on the truck.

- There must be red flags or red lamps for the lengthy loads which extend beyond chassis.

- The load should  not be over  hanging more than 3 ft. from the end of the body.

- The materials should not be stacked too high to avoid hitting against live electric lines.

- While transporting the scraps, there must be wire knitting cover to prevent falling of scrap.

##### IV GENERAL

The vehicles should not be moved directly inside the production building in case the materials are to be unloaded there. But the vehicle should be parked outside the building and the driver should ascertain the passage as well as the unloading points with the help of shop officials. This will avoid  the congestion of blocking of traffic in the gangway.

CONTRACTOR							ACCEPTING OFFICER

GENERAL AND SPECIAL CONDITIONS OF CONTRACT

#### GENERAL CONDITIONS

- No night work  will be permitted without the written permission of the Engineer – in – charge.

- Bulkage test on the sand to be used on the work should be conducted  periodically to arrive at the correct quantity of sand to be mixed for the different  proportions as and when required.

- Items of work other than those mentioned in the Bill of Quantities (Tender Schedule) attached hereto will be carried out at the rates to be fixed by this organization as per relevant clauses of the General Conditions of Contract.

- (a) Water required for the  work may be provided by this organization at only one point at the site of the work at free of cost. In case of failure of water supply, the Contractor will have to make his own arrangements for water without any extra claims until supply is restored. BHEL does not accept any liability whatsoever for non supply or delay in the supply of water under any circumstances. The contractor shall ensure  that there is no wastage of water otherwise supply of water, is liable to be stopped at contractor’s risk and cost.

(b) Electrical energy required for the work may be provided by this organization at any one point at the site of work at free of cost. BHEL does not accept any liability whatsoever for non-supply, delay in supply or failure of supply of electrical energy.  Contractor shall ensure that there is no wastage of electrical energy otherwise supply is  liable to be stopped at contractor’s risk and cost.

- Permission  for erection of temporary work sheds etc., at site will have to be obtained from BHEL  in writing in advance.

- The works contract to be entered into with the successful tenderer will be governed by the BHEL revised General Conditions of Contract in force.

- The successful tenderer / Contractor shall observe all safety regulations and take necessary safety precaution as called for under the “BHEL General Conditions of Contract and Safety Precautions” enclosed herewith.

- In all matters of dispute, the decision of the AGM, Bharat Heavy Electricals Ltd., GOINDWAL – 22. shall be final and binding on the tenderer / contractor.

- Some changes are likely in the quantities furnished as well as in the layout, design and specifications of the work. The rate quoted  shall be deemed to be inclusive of all such contingencies.

CONTRACTOR							ACCEPTING OFFICER

- All the materials to be used in the work and nature of work shall conform to respective IS and National Buildings Organisation Standard Specifications and shall be got approved by the Engineer – in – charge before actual incorporation in the work

- All surplus raw steel remaining with the contractor shall be returned to BHEL stores at his own cost after completion of fabrication, in the form of full lengths, useful cut bits and scrap. The following yardstick will be adopted for the purpose  of classification of scrap.

| (a) Mild steel and alloy Steel plates and sheets | 1000X500mm and above | Useful cut bit |
| --- | --- | --- |
| (b) Mild steel and alloy Steel plates and sheets | Less than 1000 X 500 mm | Scrap |
| (c) Structurals | One metre and above in length | Useful cut bits |
| (d) Structurals | Less than one metre in length | Scrap |

The invisible (Non-returnable) wastage should not exceed a maximum of 2% by weight of fabricated steel work and returnable wastage generated by way of scrap or useful cutbits  shall be returned at “Actuals”.  Maximum permissible limit for scrap without recovery  shall be 5% of actual fabricated  quantity.  However every care should be taken to see that raw steel is  utilised  most economically by preparing necessary cutting lists to restrict the scrap within the permissible limit.

Should the quantum of invisible  wastage exceed the 2% permissible limit, RECOVERY AT TWO TIMES OF THE VALUE OF the extra tonnage involved  (which will be evaluated  on an average cost per tonne basis considering the total raw steel materials issued ) will be effected from the contractor for the excess quantity involved ( 2 times x  Rs. 40,290 = Rs.80,580 / MT + applicable taxes at the time of recovery).  This rate is only indicative and BHEL issue rate on date of actual issue will be applied.

The Contractor shall submit a material tallying statement on completion of the work indicating the details of quantities of each material (section by section) received quantities used for fabrication as per DOD lists. Quantity returned in full length, useful cut bits and scrap and the quantity reckoned as invisible wastage.

a)	Single recovery rate for the non returned scrap	: 	Rs. 40,290/- per M.T

upto 5% of actual consumption				  + applicable taxes at

the  time of recovery

- The punitive recovery rate for  steel qty. not  	: 	Rs. 80,580/- per M.T.

###### accounted and  extra  scrap generated beyond		 + applicable taxes at

5% of actual consumption					  the time of recovery

CONTRACTOR							ACCEPTING OFFICER

### SPECIAL CONDITIONS OF CONTRACT

- Unless otherwise indicated in the Bill of Quantities cement, structural steel sections, reinforcement steel (MS rods, CTD bars etc.,) and other items ( as mentioned in Schedule B ) will  be issued at BHEL Stores at free of cost. The Contractor’s quoted rates shall therefore be inclusive of the cost of conveyance of these items  from BHEL Stores to site of work  including, loading, unloading and other incidental costs etc.  The quantities of each items to the extent required for  actual incorporation of the work will be treated as ISSUED FREE OF COST.

- All surplus reinforcement rod with the contractor shall be returned to BHEL Stores at his own cost in the form of full lengths, useful cut bits and scrap. The invisible (non-returnable) wastage should not exceed a maximum of 0.5% of the actual quantity consumed in the work.

- The contractor shall return all the scrap to the disposal stores  at his own cost. Bent rods  will also be taken as scrap only, irrespective of their length. The maximum permissible limit of scrap without recovery  is 5% of actual consumption.  The recovery details for the materials are as follows:

a)	Single recovery rate for the non returned scrap	: 	Rs.36,030/- per M.T

upto 5% of actual consumption				+ applicable taxes at

the  time of recovery

- The punitive recovery rate for  steel qty.  not  	: 	Rs.72,060/- per M.T.

###### accounted and  extra  scrap generated beyond		+ applicable taxes at

5% of actual consumption					the time of recovery

The above  rates are only indicative and BHEL issue rate on date of actual issue will be applied.

Excess consumption of cement over and above the theoretical requirement as per BHEL Data upto a limit of 5% will be charged  at the  rate of Rs.3,815/per M.T. + applicable taxes at the time of recovery.  Consumption beyond 5% will be charged at the punitive recovery rate of   Rs.7,630/per M.T.. + applicable taxes at the time of recovery.

The above  rates are only indicative and BHEL issue rate on date of actual issue will be applied

- Gunny bags or Polythene Bags or Paper Bags in which cement is issued from BHEL Stores, need not be returned by Contractor to BHEL. The cost for each empty cement  bag will be recovered from the Contractor’s bills at the following rates.

i.  	Empty cement gunny bag		Rs.1.25 + ST and SC / each

ii  	Empty Polythene bag			Rs. 0.50 + ST and SC / each

iii 	Empty paper bag			Rs. 0.25+ST and SC / each.

CONTRACTOR							ACCEPTING OFFICER

- The Contractor should maintain proper accounts of cement, MS rods / CTD bars, structural steel sections and other materials if any supplied by this organization and these should be available at the site of the work for verification and check by the official of this organization at any time.

- All materials brought by the Contractor for incorporation in the work shall be got inspected and approved by the Engineer-in-charge  before they are incorporated in the work

- The Manager / Civil or his duly authorized representative shall have all reasonable times access to Contractor’s premises of work and shall have the power at all the reasonable times to inspect  and test any portion of the work or examine the materials and workmanship of the structures during their manufacture and test. The contractor shall give due notice in writing to the Inspecting Engineer of BHEL when the materials supplied  to be incorporated in the work are ready for Inspection and test. No material shall be incorporated in the work until the inspecting Engineer certified in writing that such materials have been inspected and approved by him.

- The Contractor shall closely scrutinize all the drawings issued in connection with the work by this organization and bring to the notice of the Engineer-in-charge if any discrepancies, omissions in the drawings before undertaking the actual work pertaining thereto.

- The contractor should submit in advance every fortnight a detailed programme of work to be undertaken from time to time strictly in conformities  with the “Time and Progress Chart” covering the entire  constructed work and reschedule them wherever necessary during the progress of the work so as to achieve the target set.  Periodical progress  reports of every fortnight should also  be furnished by the Contractor regarding the collection of materials issued and to be issued from BHEL Stores and other relevant information as asked for by the Engineer-in-charge and other BHEL Officers-in-charge of the work.

- The contractor should extend full co-operation to the other contractors who may be doing other works in the same areas to enable them to execute their portions of work without any delay or difficulty.

SCHEDULE ‘A’

###### LIST OF WORKS AND PRICES

DETAILS & QUANTITIES of each item of work shown in the BILL OF QUANTITIES  are only approximate. They are given as a guide for the purpose  of tendering only and are liable to variation  and alteration of the Competent Authority. The work  under each item as executed  shall be measured and priced at the  corresponding rate quoted  by the contractor in the BILL OF QUANTITIES

| Sl.No. | Description of work / supplied | Total amount of work / supplies (in figures and words) Rs. Ps. | Period of contract |
| --- | --- | --- | --- |
| 1. | Extension of shop floors, and other infrastructure works under Valves Capacity Augmentation in IVP complex, BHEL, GOINDWAL. | 253,00,000/- | TEN (10) MONTHS |

##### BILL OF QUANTITIES

| Sl. No. | Appx. Qty. | Description of work | TNBP No. | Rate (Both in Unit fig & Words | Amount Rs. Ps. |
| --- | --- | --- | --- | --- | --- |
| AS PER SEPARATE SHEETS ATTACHED CONTAINING 39 PAGES FROM SERIAL No. 24 to 62 |  |  |  |  |  |

##### SCHEDULE ‘B’

- The following materials will be issued FREE of cost to contractor at BHEL Stores / Stock yard.

| Sl.No. | DESCRIPTION | PLACE OF ISSUE |
| --- | --- | --- |
| 1 | Cement | BHEL STORES or Stock yard |
| 2 | M.S Rounds, C.T.D Bars & Structural Steel, rails and all railway materials | BHEL STORES or Stock yard |

- It will be the responsibility  of the Contractor to submit his demands for the above stores in writing atleast seven days in advance of the actual requirement.

- Issue of Stores is subject of the availability at the place of issue cited above, items of stores to be issued  by BHEL which are not available at the time of indenting by the contractor may be supplied by BHEL after necessary procurement. The contractor shall not be entitled to any claim of compensation for delay in the supply of stores by BHEL under any circumstances.

- The materials will be issued only during the working hours of the BHEL Stores Department ( 8.00 a.m. to 4.30 p.m. ). Contractor shall have to transport them to the site  of work at his own cost as soon as they are issued to him.

- The steel  materials if issued will be in random lengths and sizes as stocked by the BHEL and the cost  of all cutting, conversion, substitution and fabrication as well as wastage shall have to be borne  by the Contractor.

- The contractor shall from time to time render proper account of all materials issued to him by BHEL. If he fails to do so, no further issue of materials will be made to him and he will be held responsible  for any delay in the execution of the work which may occur on this account.

- Where  A.C. Sheets and accessories, Doors, Windows, Sanitary fittings, Special glasses or other items are issued free of cost to the contractor, the contractor will have to make good at his own cost  any loss or damage to any part or whole of the items issued to him as above. All wastage  within the premises  limits as fixed by BHEL will be charged for at the prescribed issued rates of BHEL. Excess  wastage will be charged for at punitive rates which will be 100% higher than the issue rates.

- All surplus materials in good condition which are not returned to the BHEL  Stores as also quantities of materials consumed in excess of the max.  permissible limit as fixed by BHEL shall be charged for at punitive rates.

The decision of the Senior Engineer / Dy. Manager / Manager/Engineer-in-charge as to the extent to which materials have been rendered  surplus or consumed in excess of the actual requirements shall be final and conclusive and binding  on the contractor.

SCHEDULE ‘C’

###### ISSUE OF TOOLS AND PLANTS TO CONTRACTORS

| Sl.No. | Qty. | Particulars | Details of BHEL Crew Supplied | Hire Charges Per unit Per Day | Place of Issue | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| ……………………………..Nil………………………………. |  |  |  |  |  |  |

  - Machineries shall not be operated over time without the written permission of the            Sr. Engineer / Dy. Manager / Manager.

  - All Coolies, Watermen etc., required  in addition to BHEL crew mentioned above shall be  arranged by the contractor at his own expense.

##### SCHEDULE ‘D’

NOTE : All Drawings are to be signed by the Contractor as well as the officer entering into contract.

| SL.No. | DRAWING NUMBER | DESCRIPTION |
| --- | --- | --- |
| 1. | BHE-CP-01-323/08 | Proposed extension of workshop |
| 2. | BHE-CP-01-324/08 | Details of foundation and other civil works |
| 3. | BHE-CP-00-325/08 | Proposed Construction shot blasting shed |
| 4. | BHE-CP-00-326/08 | Details of DSL foundation |
| 5. | BHE-CP-02-316/08 | Details of DG set bulding |
| 6. | BHE:CP:01:01/08 | Proposed construction of road |

SCHEDULE ‘E’

LEAD STATEMENT

| Sl.No. | Name of Material | Name of Source | Lead Particulars both for Factory and Township |
| --- | --- | --- | --- |
| 1 | Cement | BHEL Stores | 1 kilometre |
| 2 | M.S Rounds, C.T.D Bars & Structural Steel, rails and all railway materials | BHEL Stores | 1 kilometre |

C.A……………………………………..Date …………………………………………………………

(To be used in conjunction with BHE Ltd., General Conditions of Contract )

##### AUTHORITY TO TENDER

Tender Notice No.	02/08-09	Office of the

SR.  MANAGER /CIVIL/ PLANNING ( FACTORY)

BHARAT HEAVY ELECTRICALS LIMITED

GOINDWAL -22.

Tender Schedule No.	03/08-09

### Item rate tender for work required in  “Extension of shop floors,  and other infrastructure works under Valves Capacity Augmentation in IVP complex, BHEL, Goindwal .”

Messrs / Mr. …………………………….………….…………………….………………………………

……………………of………………………………………………………………………………………….

are / is hereby authorized to tender for the above work. The Tender is to be delivered at the Office of the SR. MANAGER / CIVIL / PLANNING / (FACTORY)  Bharat  Heavy Electricals  Limited Unit, GOINDWAL, upto hrs. on addressed to the Sr. Manager / Civil / Planning (Factory), BHEL. GOINDWAL-22  super scribing the name of work as mentioned above.

Any correspondence concerning this tender should be addressed as indicated above quoting  the Tender Notice,   Schedule No. and other relevant particulars.

BHARAT HEAVY ELECTRICALS LIMITED DO NOT BIND THEMSELVES TO ACCEPT THE LOWEST OR ANY  TENDER.

Issuing Officer with

Designation

Contract Agreement No………………………………………………………………………………….

TENDER

To

The Sr. Manager/Civil/Factory

Bharat Heavy Electricals Limited

GOINDWAL-22

PUNJAB.

### I / We hereby offer to carryout the work of  “Extension of shop floors,  and other infrastructure works under Valves Capacity Augmentation in IVP complex, BHEL, GOINDWAL.”

I / We hereby carefully perused the following documents connected with the above noted work and agree to obide by  the same.

1.Specifications (General & Particular )

2.Drawings

3.Schedule ‘A’, ‘B’, ‘C’, ‘D’ & ‘E’

4.Schedule of Rates

5.BHE Ltd., General & Special Conditions of Contract, Tender Notice and Instructions to Tenders attached hereto.

I / We forward herewith the sum of Rs……………………………………….as Earnest Money, which shall be  refunded should  this tender be rejected. I / We further  agree to deposit such sum which along with the sum of Rs…………………………mentioned above shall make up 50% of the fully Security Deposit  for this work as provided for under conditions of the BHARAT HEAVY ELECTRICALS LIMITED General Conditions of Contract.

I / We further agree to execute all the work referred to in the said documents upon the terms & conditions contained or referred therein and as detailed in Schedule ‘A’ and Bill of Quantities annexure  thereto and to carry out such deviations as may be ordered, vide conditions 6 of the BHEL Ltd., General Conditions  of Contract upto a maximum of 20% of the tendered amount of Rs…………………………………………………….

I / We further agree to refer all disputes, as required by condition 62 of the General conditions of Contract to the sole arbitration of an Officer, to be appointed by the General Manager, B.H.E Ltd., in his sold discretion  whose decision shall be final and binding.

WITNESS						                  Signature of the Contractor

Date :

- ………………………………….

- ………………………………….

GENERAL SUMMARY

1. 	(a) Net Cost of works or building etc., from Schedule ‘A’		Rs.

2.  	Provisional sum							Rs.

……………………….

Total 				Rs.

….……………………

Rupees………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………Shri…………………………………………………………………………………………………………………………………………..…. in the capacity of ……………………………………………………………………………………………… has been duly authorized by me / us  to sign the tender for and on behalf of ………………………………………………………………………………………………………………………………………………

( in block letters )

Date : 							          SIGNATURE OF CONTRACTOR

Witness : 						                 Postal Address :

1………………………………….				                Telephone No.

Address

2. …………………………………

Address

……………………………………………………………………………………………………………………

alterations have been made in the Tender Document and as evidence that these alterations were made before the execution of contract agreement, they have been initialed by the Contractor and the representatives of BHEL one  from Planning section  of  Civil  Engineering Department & one from Works  Finance section of  Accounts Department.

……………………………………………… CIVIL / FACTORY the said officer is hereby authorized to sign and initial on my behalf  the documents forming part of this contract (Number of alternation in figures and words to be given here)

The above tender is accepted by me on behalf  of the Bharat Heavy Electricals  Limited, Unit: GOINDWAL-22. for a sum of Rs…………………………………… ……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………… at the percentage  rates as indicated in  Schedule ‘A’.

Signature ……………………………………….Date…………………………………………..

Designation ………………………………………………………………………………………

BHEL APPROVED BRANDS FOR THE FOLLOWING MATERIALS / ITEMS

| Sl.No. | Material | Manufacturing Co. | Brand |
| --- | --- | --- | --- |
| 1. | Synthetic Enamel Paint | Asian Berger ICI | Apcolite Luxol Dulux gloss |
| 2. | Aluminium Paint | Berger / J & N | Berger Aluminium / J & N |
| 3. | Interior Emulsion | Asian Berger ICI | Royale Luxol Silk Supercote |
| 4. | Exterior Emulsion | Asian ICI | ACE Supercote |
| 5. | Distemper | Asian Berger ICI | Tractor Bison Maxilite |
| 6. | Cement Paint | Snowcem Agsarcem | Snowcem Agsarcem |
| 7. | A.C. Sheets | Everest India Ltd. Hyderabad India Ltd. Visaka Industries Ltd. Ramco | Everest I Charminar Visaka Ramco |
| 8. | G.I. Pipes | TATA Zenith TNT | TATA Zenith TNT |
| 9. | PVC Pipes | Avonplast Finolex Truebore Vignesh | Avonplast Finolex Truebore Vignesh |
| 10. | Ceramic Tiles | Johnson / Nitco / Naveen / Kajaria / Orient | Johnson / Nitco / Naveen / Kajaria / Orient |