ANNEXURE- PEC : T7D1T33620

PACKAGE EXECUTION SCHEDULE

Applicable Documents:

- Datasheet: Approval by NTPC & BHEL

- Type test reports: Approval by NTPC & BHEL

- QAP: Approval by NTPC & BHEL

| Sl. No. | Event | Schedule |
| --- | --- | --- |
| 1 | Datasheet, Type test reports and QAP submission by vendor | Within 1 week from P.O. date |
| 2 | BHEL Comments | Within 21 working days from receipt of the “Drawings/docs/datasheet/ QAP in line with Specification” |
| 3 | Revised Documents submission by vendor | Within 1 week from BHEL’s comments date |
| 4 | BHEL Comments / Approval for Manufacture Clearance | Within 14 working days from receipt of the revised Drawings/datasheet/QAP/doc |

- Submission of documents i.e., Datasheets and Type test reports within 1 weeks of placement of P.O (for approval by BHEL and / or BHEL’s customer in 4 sets)

- All vendor documents shall be submitted to End user for approval. Any comments furnished by End user/BHEL shall be taken care by vendor.

- Further BHEL will provide comments on vendor submitted document within 21 working days for revision & resubmission. Vendor shall follow up with BHEL for non-receipt of comments/approvals.

- Revised drawings / Documents shall be submitted by Bidder in 1 week of receipt of comments / observations from BHEL.Vendor shall strictly incorporate all the comments; partial incorporation of comments is not acceptable. BHEL shall revert within 14 days on receipt of these revised documents / drawings from vendor for approvals.

- All the approvals required for manufacturing shall be completed with 2 months from P.O to meet the P.O delivery schedule. Accordingly, vendor shall ensure the submission of approval category documents (which are required for manufacturing) and obtain their approvals.

- Vendor shall obtain final approvals on all technical + quality aspect documents before inspection dates.

- It is vendor’s responsibility to obtain approvals from BHEL as earliest as possible to meet PO delivery schedules. Accordingly, vendor to plan and execute the supplies in time.

- Inspection and MDCC is in scope of NTPC.