ANNEXURE-1

PACKAGE EXECUTION SCHEDULE

| Sl. No. | Event | Schedule |
| --- | --- | --- |
|  |  | Vendor Drawings |
| 1 | Drawings/Datasheet submission | Within 1 week from P.O. date |
| 2 | BHEL Comments | Within 1 week from receipt of the “Drawings in line with Specification” |
| 3 | Revised Drawings submission | Within 1 week from BHEL’s comments date |
| 4 | BHEL Comments / Approval for Manufacture Clearance | Within 1 week from receipt of the revised Drawings |

However, it’s vendor responsibility to ensure the cycle time reduction for the submission of drawing.