## MDL
ANNEXURE - 2
2X660 MW MAITREE SUPER THERMAL POWER PROJECT- COAL STOCK PILE FIRE DETECTION SYSTEM - BIDDER DWGS/DOCS SCHEDULE
1 | LIST OF SUPERCIDED DRAWINGS / DOCUMENTS |  |  |  | S | TO INDEX PAGE |  | NO COMMENTS |  |  |  | 1
2 | LIST OF ACTIVE DRAWINGS / DOCUMENTS |  |  |  | A | TODAY'S DATE |  | COMMENTS AS MARKED CLEARED FOR MANUFACTURE |  |  |  | 2
3 | LIST OF DRAWINGS/DOCUMENTS UNDER PREPARATION |  |  |  | UP | 2019-06-28 |  | NOT APPROVED & COMMENTS AS MARKED |  |  |  | 3
4 | LIST OF BHEL APPROVED DRAWINGS |  |  |  | ADS |  |  | RETAINED FOR INFORMATION |  |  |  | 4
[9 empty] | A |  | 1
1 | Drawings & Documents Pending with BIDDER | [7 empty] | A | P-BIDDER | 2
2 | Drawings & Documents Pending with BHEL | [7 empty] | A | P-BHEL | 3
3 | Drawings & Documents Approved by BHEL | [7 empty] | A | ADS | 4
4 | Supercided Drawings. | [7 empty] | A | S
S. NO | DRAWING/ DOCUMENTS | DWG. NO. | APPR (A/I) | SCHEDULE OF SUBMISSION | REV | SENT BY BIDDER (SOFT COPY) | HARD COPY RECEIVED FROM BIDDER | COMMENTS SEND TO BIDDER | STS | PEND | BHEL APP STATUS | REMARKS
A | MECHANICAL
A.01 | Schematic of Coal Stock Pile Fire Detection System |  | A | 14 days from P.O Placement | 0 |  |  |  | UP | P-BIDDER
A.02 | Design Philosphy & Write-up |  | A | 14 days from P.O Placement | 0 |  |  |  | UP | P-BIDDER
A.03 | Layout of Thermal Cameras |  | A | 30 days from P.O Placement | 0 |  |  |  | UP | P-BIDDER
B | DATASHEETS
B.01 | Thermal Imaging Cameras |  | A | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
B.02 | PC, Printer & UPS |  | A | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
B.03 | Cables |  | A | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
B.04 | G.A of Junction Box |  | A | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
C | QUALITY
C.01 | Quality Assurance Plan |  | A | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
D | D) PROCEDURE
D.01 | System Write-Up |  | I | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
D.02 | Bill of Materials |  | A | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
D.03 | Testing & Commisioning Procedure |  | A | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
D.04 | Pre-Commissioning Procedure |  | I | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
D.05 | Job Procedure / Installation Procedure |  | I | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
E.01 | E) OTHERS
E.01 | Flow calculations |  | I | 14 days from placement of P.O | 0 |  |  |  | UP | P-BIDDER
F | INTERFACE DRAWINGS
F.01 | Interface between DCS and Coal Stock Pile Fire Detection System |  | I | 30 days from P.O Placement | 0 |  |  |  | UP | P-BIDDER