## MDL
MASTER DOCUMENT LIST FOR KOD
PROJECT:
PO NO.
S.No. | Category | Drg./ Doc. Name | BHEL DOC. No. | Vendor Doc. No. | SCHEDULE DATE OF SUBMISSION | Rev.0 |  | Rev.1 | Rev.3 | Rev.2 | Rev.3
| Category |  |  |  |  | vendor submission | BHEL reply | vendor submission | BHEL reply | vendor submission | BHEL reply | Status | Remarks
1.0 Mechanical
GENERAL:
1 | A | P&I Diagram of KOD |  |  | Within 2 weeks of placement of Purchase Order.
2 | A | GA Drawing of KOD |  |  | Within 2 weeks of placement of Purchase Order.
3 | A | Technical Datasheet of KOD |  |  | Within 2 weeks of placement of Purchase Order.
4 | I | Foundation Details of KOD |  |  | Within 2 weeks of placement of Purchase Order.
5 | A | Technical Datasheet of Pressure Safety Valve |  |  | Within 2 weeks of placement of Purchase Order.
6 | A | GAD of Pressure Safety Valve |  |  | Within 2 weeks of placement of Purchase Order.
7 | A | BOM of KOD |  |  | Within 6 weeks of placement of Purchase Order.
8 | A | Painting Specification |  |  | Within 6 weeks of placement of Purchase Order.
9 | I | List of Commissioning spares |  |  | Within 8 weeks of placement of Purchase Order.
10 | I | Recommended List of 2 Yrs spares |  |  | Within 8 weeks of placement of Purchase Order.
11 | A | List of Mandatory spares |  |  | Within 8 weeks of placement of Purchase Order.
12 | I | Sub vendor list |  |  | Within 4 weeks of placement of Purchase Order.
2.0 Quality
1 | A | QAP of KOD | LATER |  | Within 6 weeks of placement of Purchase Order.
3.0 Erection Documents
1 | I | Erection Documents | LATER
2 | I | Storage & preservation procedures
4.0 Dispatch Documentation
1 | A | Packing List | LATER
2 | I | Quality Plan,Inspection Agency Report,Test Certificate As Identified In Approved Quality Plan | LATER
5.0 Final Documentation
1 | I | Draft Of O& M Manual for Engg. Review | LATER
2 | A | Final O&M Manuals(17 Hard Copies as per Tender Spec) | LATER
3 | I | Final O&M Manuals(In Cd 04 Nos) | LATER
NOTE: Purchase to note that dispatch clearence shall not be given untill Billing break-up is approved.
Status of Documents
Pending With vendor
Pending With BHEL
Approved/Retain for Information
1. A=INDICATES THE DRAWING/DOCUMENTS SHALL BE SUBMITTED FOR BHEL APPROVAL
2. I=INDICATES THE DRAWINGS / DOCUMENTS TO BE SUBMITTED FOR INFORMATION PURPOSE
3. E= INDICATES THE DRAWINGS / DOCUMENTS TO BE SUBMITTED FOR AS ERECTION DOCUMENTS ALSO.
4. All approval category items to be submitted within two week of reciept of LOI/PO.
5. As valves & Instruments are long lead items, datasheets for vavles & Instruments to be submitted within six week of reciept of PO/LOI.