## DOC. SCHEDULE
ANNEXURE - 3 : FIRE PROTECTION SYSTEM - DWGS/DOCS SCHEDULE
1 | LIST OF SUPERCIDED DRAWINGS / DOCUMENTS |  |  |  | S | TO INDEX PAGE |  |  |  | APPROVED |  |  | A
2 | LIST OF ACTIVE DRAWINGS / DOCUMENTS |  |  |  | A | TODAY'S DATE |  |  |  | APPROVED WITH COMMENTS |  |  | B
3 | LIST OF DRAWINGS/DOCUMENTS UNDER PREPARATION |  |  |  | UP |  | 2020-01-24 |  |  | NOT APPROVED |  |  | C
4 | LIST OF STEAG APPROVED DRAWINGS |  |  |  | ADS |  |  |  |  | INFORMATION CATEGORY |  |  | D
[10 empty] | RECORD PURPOSE |  |  | R
|  | DRAWING NOT FOR APPROVAL, ONLY FOR INFORMATION. INFORMATION FURNISHED IN THE DRAWING IS NOTED | [10 empty] | H
[10 empty] | A |  | A
1 | Drawings & Documents Pending with BIDDER | [8 empty] | A | P-BHEL | B
2 | Drawings & Documents Pending with PURCHASER | [8 empty] | A | P-BIDDER | C
3 | Drawings & Documents Approved by PURCHASER | [8 empty] | A | ADS | D
4 | Supercided Drawings. | [8 empty] | A | S | R
H
S. NO | DRAWING/ DOCUMENTS | DWG. NO. | APPR (A/I) | SCHEDULE OF SUBMISSION | REV | SENT BY BIDDER (SOFT COPY) | HARD COPY RECEIVED BY BHEL | COMMENTS SEND TO BIDDER BY BHEL | REVISED DWG. / DOC. RECEIVED FROM BIDDER | STS | PEND | STEAG APP STATUS | REMARKS
DOCUMENTS
1 | CO2 type Fire Extinguishers-4.5 kg |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
1 | 9 Lit. Pressurized water type |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
2 | 5kg CO2 type Fire Extinguisher |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
3 | 30kg CO2 type Fire Extinguisher |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
4 | 6kg DCP type Fire Extinguisher |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
5 | 75kg DCP type Fire Extinguisher |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
6 | 10 Lit. Mechanical Foam type Fire Extinguisher |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
7 | 130 Lit. Mechanical Foam type Fire Extinguisher |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
8 | Quality Assurance Plan |  | A | Within 14 days after placement of P.O | 0 |  |  |  |  | UP
9 | List of Consumables |  | I | Within 30 days after placement of P.O | 0 |  |  |  |  | UP
10 | List of Shelf life items |  | I | Within 30 days after placement of P.O | 0 |  |  |  |  | UP
11 | Non destructive testing procedure |  | I | Within 30 days after placement of P.O | 0 |  |  |  |  | UP
12 | Procedure for storage of Shelf life items (if any) |  | I | Within 30 days after placement of P.O | 0 |  |  |  |  | UP
13 | Inspection Reports |  | A | Within 30 days after placement of P.O | 0 |  |  |  |  | UP
14 | Packing List |  | I | Within 30 days after placement of P.O | 0 |  |  |  |  | UP
15 | O & M Manuals |  | I | Within 30 days after placement of P.O | 0 |  |  |  |  | UP
Notes:
1 | List of any other drawing / document required for completion of engineering & supply of the system other than above mentioned list, shall be furnished by bidder within 14 days after Placement of P.O