## Sheet1
Enq No. 06Q2100095- dated 30/05/2020, Project- IOCL Panipat (FCL)
SL.NO. | ACTIVITY | ACTIVITY TIME IN Days | Remarks
| (A) | (B) | (I)
| PO / Input receipt from BHEL | 0
1 | Submission of document necessary for getting manufacturing clerance like drawing, data sheet | 21
2 | Re-submission of documents after BHEL/Customer comment | 15
3 | Manufacturing Time after CAT-A approval & Manufacturing clerance
4 | BHEL/Customer Inspection & Dispatch Clearnace | 14
5 | Dispatch | 14
64
*Delay/Preponement if any, shall be adjusted in delivery time.

## Sheet2
S No | Action taken | Dated | Remarks
1 | PO receipt on | 10th Dec2018
2 | 1st Drawing submission | 17th Dec2018 | Which is well within the time frame as per tender/PO terms.
3 | 1st comments received on drawing from BHEL | 18th Dec2018
4 | Meeting held at BHEL office for drawings discussion as per BHEL requirement on | 23rd Dec2018
5 | 2nd time Comments received on drawings by BHEL on… | 5th Jan2019
6 | R2 revised drawings submission was on | 15th Jan2019 and 17th Jan2019 | Which is well within the time frame as per tender/PO terms.
7 | Again meeting required by BHEL for drawings discussion
8 | 2nd time Meeting held at BHEL office for drawings discussion on | 25th Jan2019
9 | Revised (R2) drawings submitted on | 28th Jan2019
10 | Comments received from BHEL on submitted revised drawings on | 29th Jan2019
11 | Final drawings submitted for approval on | 29th Jan2019
12 | Final drawings approval received on | 5th March2019 | i.e. after 35days of final drawings submission. As per tender/ PO terms and condition, approval was to be given by BHEL to BCH within 7 days of drawing submission.